## Cover Sheet
MDE
Maintenance Duration Estimator
|  | EuroFusion UID: | 2NBXBQ
|  | Date | 29 Sept. 2017
|  | Deliverable-ID(s) | RM-2-T002 D003
|  | Work Package | WPRM-2-T002
|  | Project Leader | Dan Wolff
|  | TS Title(s) | Assessment of plant architecture
|  | TS Ref. No.(s) | AWP2017-RM-2-T002
|  | Task Owner(s) | Dan Wolff
|  | RU(s) | RACE
Report Review & Approval
|  | IDM role | Name(s)
|  | Author/Editor | Iain Farquhar
Co-author(s)
|  | Reviewer(s) | Dan Wolff
|  | PMU Reviewer | Greg Keech
|  | Approver | Antony Loving

## Reactor Design Inputs
Section | INPUTS | Shortname | Value | Unit | Comments
| Tokamak Segments | Tokamak_Segmts | 18 | Segments
Port Lengths | Length of the Upper Port | Upper_Port_Length | 6 | m | Used to calculate the deployment time of certain pieces of RM equipment
| Length of the Lower Port | Lower_Port_Length | 12 | m | Used to calculate the deployment time of certain pieces of RM equipment
Layout of IVC
| Out-Board Blankets per segment | OB_blankets_per_segmt | 3 | OB blankets | These variables currently impact welding and failure calculations but in order to correctly update the model the critical path(s) will need to be updated take into account any changes in the number of blankets or divertor cassettes
| In-Board Blankets per segment | IB_blankets_per_segmt | 2 | IB blankets
| Total Blankets per segment | Blankets_per_segmt | 5 | blankets
| Total Divertor cassettes per segment | Cassettes_per_segmt | 3 | cassettes
Blanket Pipework
| Diamter of Blanket Coolant Pipes | Blanket_coolant_diameter | 193.68 | mm ID | Inner diameter of the blanket coolant pipework
| Circumference of blanket coolant pipe | Blanket_coolant_circumference | 608.4637 | mm | The circumerence of the inner surface of the pipework
| Thickness of blanket coolant pipe | Blanket_coolant_thickness | 12.7 | mm | and the pipe wall thickness
| Diamter of Blanket LiPb Pipes | Blanket_LiPb_diameter | 77.93 | mm ID
| Circumference of blanket LiPb pipe | Blanket_LiPb_circumference | 244.8243 | mm
| Thickness of Blanket LiPb pipe | Blanket_LiPb_thickness | 5.49 | mm
| Diamter of Blanket Drain Pipes | Blanket_Drain_diameter | 77.93 | mm ID
| Circumference of blanket drain pipe | Blanket_drain_circumference | 244.8243 | mm
| Thickness of Blanket Drain pipe | Blanket_drain_Thickness | 5.49 | mm
Divertor Pipework
| Diamter of Divertor Coolant Pipes | Divertor_Coolant_diameter | 193.68 | mm ID
| Circumference of divertor drain pipe | divertor_coolant_circumference | 608.4637 | mm
| Thickness of Divertor coolant pipe | divertor_coolant_thickness | 12.7 | mm
| Diamter of Divertor LiPb Pipes | Divertor_LiPb_diameter | 77.93 | mm ID
| Circumference of Divertor LiPb pipe | Divertor_LiPb_circumference | 244.8243 | mm
| Thickness of divertor LiPb pipe | Divertor_LiPb_thickness | 5.49 | mm
| Diamter of Divertor Drain Pipes | Divertor_Drain_diameter | 20 | mm ID
| Circumference of blanket drain pipe | divertor_drain_circumference | 62.8319 | mm
| Thickness of Divertor Drain pipe | divertor_drain_thickness | 5 | mm
Pipe Module Design
Upper Blanket Pipe Module Design
| Number of blanket cooling pipes in the Upper Port | vertical_blanket_cooling_pipes | 4 | pipes
| Number of blanket LiPb pipes in the Upper Port | vertical_blanket_LiPb_pipes | 2 | pipes
| Number of blanket drain pipes in the Upper Port | vertical_blanket_drain_pipes | 0 | pipes
| Total Blanket Pipework in the Upper Port | Vertical_port_pipes_per_blanket | 6 | pipes
Lower Blankent Pipe Module Design | Number of blanket cooling pipes in the Lower Port | divertor_blanket_cooling_pipes | 2 | pipes
| Number of blanket LiPb pipes in the Lower Port | divertor_blanket_LiPb_pipes | 0 | pipes
| Number of blanket drain pipes in the Lower Port | divertor_blanket_drain_pipes | 1 | pipes
| Total Blanket Pipework in the Lower Port | Divertor_port_pipes_per_blanket | 3 | pipes
Divertor Pipe Module Design | Number of Divertor cooling pipes | divertor_module_cooling_pipes | 4 | pipes
| Number of Divertor LiPb pipes | divertor_module_LiPb_pipes | 0 | pipes
| Number of Divertor drain pipes in the Lower Port | divertor_module_drain_pipes | 0 | pipes
| Total Divertor Pipework per cassette | pipes_per_cassette | 4 | pipes
Pipe cutting operations
| Cutting tool linear speed in m/min |  | 1 | m/min | This defines the linear speed of the cutting head of the SJS system
| Cutting tool linear speed in mm/sec | cutting_speed | 16.6667 | mm/sec | This takes the linear speed in m/min and converts it into mm/sec
| Cutting system penetration depth | cutting_depth | 12.7 | mm per pass | The maximum cutting depth achievable by the SJS is defined here
Blanket Pipe cutting timings:
| Number of passes taken to cut a blanket cooling pipe | Blanket_Cooling_Cutting_Passes | 1 | Passes | This calculates the number of passes required for the defined SJS to completely cut through the defined pipe wall
| Time taken to cut a single Blanket coolant pipe joint | Blanket_Cooling_Cut_Time | 0.010141 | Hours | Or ~36.5 Seconds per pipe
| Number of passes taken to cut a blanket LiPb pipe | Blanket_LiPb_Cutting_Passes | 1 | Passes
| Time taken to cut a single Blanket LiPb pipe joint | Blanket_LiPb_Cut_Time | 0.0040804 | Hours | Or ~14.7 Seconds per pipe
| Number of passes taken to cut a blanket drain pipe | Blanket_Drain_Cutting_Passes | 1 | Passes
| Time taken to cut a single Blanket drain pipe joint | Blanket_Drain_Cut_Time | 0.0040804 | Hours | Or ~14.7 Seconds per pipe
Divertor Pipe cutting timings:
| Number of passes taken to cut a Divertor cooling pipe | Divertor_Cooling_Cutting_Passes | 1 | Passes
| Time taken to cut a single Divertor coolant pipe joint | Divertor_Coolant_Cut_Time | 0.010141 | Hours | Or ~36.5 Seconds per pipe
| Number of passes taken to cut a Divertor LiPb pipe | Divertor_LiPb_Cutting_Passes | 1 | Passes
| Time taken to cut a single Divertor LiPb pipe joint | Divertor_LiPb_Cut_Time | 0.0040804 | Hours | Or ~14.7 Seconds per pipe
| Number of passes taken to cut a Divertor Drain pipe | Divertor_Drain_Cutting_Passes | 1 | Passes
| Time taken to cut a single Divertor drain pipe joint | Divertor_Drain_Cut_Time | 0.0010472 | Hours | Or ~3.8 Seconds per pipe
Pipe welding operations | Welding tool linear speed |  | 4.5 | m/min | Linear speed of the welding head of the SJS system
| Welding tool linear speed in mm/sec | welding_speed | 75 | mm/sec | This takes the linear speed in m/min and converts it into mm/sec
| Welding system penetration depth | weld_depth | 12.7 | mm | The maximum weld penitration depth achievable by the SJS is defined here
Pipe welding timings:
| Number of passes taken to weld a blanket cooling pipe | Blanket_Cooling_Weld_Passes | 1 | Passes
| Time taken to weld a single Blanket coolant pipe joint | Blanket_Cooling_Weld_Time | 0.0022536 | Hours | Or ~8.1 Seconds per pipe
| Number of passes taken to weld a blanket LiPb pipe | Blanket_LiPb_Weld_Passes | 1 | Passes
| Time taken to weld a single Blanket LiPb pipe joint | Blanket_LiPb_Weld_Time | 0.00090676 | Hours | Or ~3.3 Seconds per pipe
| Number of passes taken to weld a blanket drain pipe | Blanket_Drain_Weld_Passes | 1 | Passes
| Time taken to weld a single Blanket drain pipe joint | Blanket_Drain_Weld_Time | 0.00090676 | Hours | Or ~3.3 Seconds per pipe
| Number of passes taken to weld a Divertor cooling pipe | Divertor_Coolant_Weld_Passes | 1 | Passes
| Time taken to weld a single Divertor coolant pipe joint | Divertor_Coolant_Weld_Time | 0.0022536 | Hours | Or ~8.1 Seconds per pipe
| Number of passes taken to weld a Divertor LiPb pipe | Divertor_LiPb_Weld_Passes | 1 | Passes
| Time taken to weld a single Divertor LiPb pipe joint | Divertor_LiPb_Weld_Time | 0.00090676 | Hours | Or ~3.3 Seconds per pipe
| Number of passes taken to weld a divertor drain pipe | Divertor_Drain_Weld_Passes | 1 | Passes
| Time taken to weld a single Divertor drain pipe joint | Divertor_Drain_Weld_Time | 0.00023271 | Hours | Or ~0.8 Seconds per pipe
Welding Processes | Generate inert atmosphere | SJS_inserting_welding_gas | 0.0027778 | hours | ~10 seconds
| Post weld heat treatment time | PWHT_time | 1.5 | hours | comment from Tristan Tremethic: 25min @900°C + 1h @700°C, to be refined. Cooldown happens as tooling is removed from port
| Pipe cooldown time following heat treatment | Pipe_Cooldown_time | 0 | hours | Cooldown happens as tooling is removed from port rather than as a defined maintenance phase
| SJS Tool Change time | SJS_Tool_Change | 0.5 | hours
NDT Testing processes | Visual Inspection | SJS_visual_check | 0.083333 | hours | ~5 minutes
| Volumetric inspection | SJS_volumetric_testing | 0.083333 | hours | ~5 minutes
| Helium leak test time per pipe | He_Leak_test | 1 | hours | Guess but will be refined as concept is tested
| Post weld NDT time per pipe | NDT_Testing_time | 1.1667 | hours | Sum of the visual, volumetric and leak testing tasks
SJS tasks / operations | Clamp to pipe | SJS_pipe_clamp | 0.0013889 | hours | ~5 seconds
| Tension pipes | SJS_tension_pipe | 0.0013889 | hours | ~5 seconds
| Unclamp and release pipe | SJS_unclamp_pipe | 0.0013889 | hours | ~5 seconds
Operational Variables
| Two-shift productivity ratio (8hr/ea) | two_shift_productivity_ratio | 0.66667
| Automatic Operations Productivity Factor | Auto_Operations_Productivity_Factor | 0.9 |  | Not currently referenced in the model
| Man-in-the-loop Operations Productivity Factor | Manual_Operations_Productivity_Factor | 0.7 |  | Not currently referenced in the model
| Time to verify tool or part is in the position/state it is expected to be in | Check_time | 0.1 | hours | Not currently referenced in the model
| Time to confirm Blanket segement or cask lift path | Lift_check | 0.1 | hours | Not currently referenced in the model
Specific In Port Hardware
Vacuum Pumping system
| Number of electrical service connections | pumping_power_connections | 5 | Connections
| Time taken to disconnect a single service connection | pumping_power_disconnection | 0.83 | hours
| Time taken to connect a single service connection | pumping_power_connection | 0.6 | hours
| Vacuum pumping pipework connections | pumping_pipework_connections | 4 | mechanical flanges
| Time taken to disconnect a single pumping pipe connection | pumping_pipe_disconnection_time | 0.6 | hours
| Time taken to connect a single pumping pipe connection | pumping_pipe_connection_time | 0.6 | hours
| Connecting vacuum pump transport assembly | vacuum_transport_connection_time | 0.5 | hours
| Releasing transport twistlocks | vacuum_transport_release_time | 0.5 | hours
ECH System
ECH Cooling Pipework | Number of cooling pipes | ECH_cooling_pipes | 4 | pipes
| Time taken to disconnect ECH piepwork | ECH_cooling_disconnection_time | 0.2 | hours per pipe
| Time taken to connect ECH piepwork | ECH_cooling_connection_time | 0.4 | hours per pipe
Number of ECH mechanical systems | Number of ECH RM system operating in parallel | ECH_fixation_systems | 1 | systems | This defines the number of bolt runners that are deployed into the port to remove the ECH
| Number of ECH Fixactions | ECH_fixation_bolts | 20 | Connections | This is the number of bolts, clamp, etc that is used to secure the ECH
ECH disconnection operations | Number of phases of the disconnection operations | ECH_fixation_disconnection_ops | 1 | phases | This is to allow for any mechanical fixation to be released in stages, rather than a single operation
| Time taken to remove an ECH fixation | ECH_fixations_disconnection_time | 0.083 | Hours
| Recover fixation timings | ECH_fixation_recovery | 0.1 | hours | Time taken to remove and store the removed fixation
ECH Connection Operations | Number of phases of the tightening operations | ECH_fixation_tightening_ops | 1 | phases | This is to allow for any mechanical fixation to be tightened in stages, rather than a single operation
| Deploy new fixations timings | ECH_fixation_deployment | 0.3 | hours | The time taken to collect a new fixation and place it ready for installation
| Pretensioning timings | ECH_pretensioning_duration | 0.167 | Hours
| Time taken to install an ECH fixation | ECH_fixations_connection_time | 0.167 | Hours
Port Closure Plate
Number of Port Closure Plate RM Systems | Number of PCP RM systems operating in parallel | PCP_fixations_RM_systems | 1 | systems | This defines the number of bolt runners that are deployed into the port to remove the port closure plate
| Number of Port Closure Plate mechanical Connections | PCP_fixation_bolts | 60 | bolts | This is the number of bolts, clamp, etc that is used to secure the port closure plate
PCP Disconnection Operations | Number of phases of the PCP disconnection operations | PCP_fixation_disconnection_ops | 1 | phases | This is to allow for any mechanical fixation to be released in stages, rather than a single operation
| Time taken to remove an PCP fixation | PCP_fixations_disconnection_time | 0.083 | Hours
| Recover PCP fixation timings | PCP_fixation_recovery | 0.1 | hours | Time taken to remove and store the removed fixation
PCP Connections Operations | Number of phases of the PCP tightening operations | PCP_fixation_tightening_ops | 1 | phases | This is to allow for any mechanical fixation to be tightened in stages, rather than a single operation
| Deploy new PCP fixations timings | PCP_fixation_deployment | 0.3 | hours | The time taken to collect a new fixation and place it ready for installation
| PCP Fixations pretensioning timings | PCP_pretensioning_duration | 0.167 | Hours
| Time taken to install an PCP fixation | PCP_fixations_connection_time | 0.167 | Hours
Shield Plug Pipe
| Number of shield plug RM systems | Plug_RM_systems | 1 | RM System | This defines the number of bolt runners that are deployed into the port to remove the shield plug
| Number of mechanical fixations | Plug_fixation_bolts | 15 | bolts | This is the number of bolts, clamp, etc that is used to secure the port plug
Shield plug mechanical flange | Number of flange bolts | Plug_flange_bolts | 10 | bolts | This is the number of bolts, clamp, etc that is used to secure the shield plug
Shield Plug Disconnection Operations | Number of phases of the Plug disconnection operations | Plug_fixation_disconnection_ops | 1 | phases
| Time taken to remove an Plug fixation | Plug_fixations_disconnection_time | 0.083 | Hours
| Recover Plug fixation timings | Plug_fixation_recovery | 0.1 | hours
Shield Plug Connections Operations | Number of phases of the Plug tightening operations | Plug_fixation_tightening_ops | 1 | phases
| Deploy new Plug fixations timings | Plug_fixation_deployment | 0.3 | hours
| Plug Fixations pretensioning timings | Plug_pretensioning_duration | 0.167 | Hours
| Time taken to install an Plug fixation | Plug_fixations_connection_time | 0.167 | Hours
Equipment Inputs
Movements:
| Cask Movement Speed | Cask_move_spd | 0.02 | m/s | guess
| Average Cask Movement Distance | Av._cask_displacement | 36 | m | guess
| In-Vessel Component Movement Speed | Part_movement_spd | 0.01 | m/s | Not currently referenced in the model
| In-Vessel Component Rotational Speed | Part_rotational_spd | 0.5 | deg/s | Not currently referenced in the model
| Fine location time | Fine_location_time | 0.2 | hours | Not currently referenced in the model
| In-vessel Tool Movement Speed (includes in-bore movements) | Tool_movement_spd | 0.025 | m/s | Not currently referenced in the model
| In-vessel Tool Rotational Speed | Tool_rotation_spd | 5 | deg/s | Not currently referenced in the model
| IVM arm speed | IVM_arm_spd | 0.1 | m/s | Not currently referenced in the model
Overhead Crane Speeds | Loaded crane speed | loaded_crane_spd | 0.02 | m/s | Informed guess based on nuclear crane speeds
| unloaded crane speed | unloaded_crane_spd | 0.2 | m/s | Informed guess based on nuclear crane speeds
| crane recovery speed | crane_recovery_spd | 0.01 | m/s | Guess
Hot Cell Hardware Transporter Speeds | Hardware Transporter (loaded) | loaded_hardware_transporter_spd | 0.02 | m/sec | Informed guess based on nuclear crane speeds
| hardware transporter (No load) | unloaded_hardware_transporter_spd | 0.2 | m/sec | Informed guess based on nuclear crane speeds
| hardware transporter (Empty stillage) | empty_hardware_transporter_spd | 0.06 | m/sec | Informed guess based on nuclear crane speeds
Cask Transporter Movement Speeds | Unloaded Cask Transporter speeds | loaded_cask_transporter_spd | 0.02 | m/sec | Informed guess based on nuclear crane speeds
| Loaded Cask Transporter speeds | unloaded_cask_transporter_spd | 0.2 | m/sec | Informed guess based on nuclear crane speeds
| Empty Cask Transport speed | empty_cask_transporter_spd | 0.06 | m/sec | Informed guess based on nuclear crane speeds
Multifunction Manipulator Deployment Speeds | MFM Deployment speed | MFM_deployment_spd | 0.02 | m/sec | Informed guess based on nuclear crane speeds
| MFM Fine movement speeds | MFM_fine_mvmt_spd | 0.01 | m/sec | Informed guess based on nuclear crane speeds
| MFM Recovery speeds | MFM_recovery_spd | 0.05 | m/sec | Not currently referenced in the model
Divertor Port In-port Deployer Speeds | Movement speed of IPD when loaded | loaded_IPD_speed | 0.01 | m/sec | Guess
| Movement speed of IPD when unloaded | unloaded_IPD_speed | 0.2 | m/sec | Guess
| IPD Recovery speeds | IPD_recovery_speed | 0.01 | m/sec | Not currently referenced in the model
Vertical Port Vertical Deployer System Speeds | Movement speed of VDS when loaded | loaded_VDS_speed | 0.01 | m/sec | Guess
| Movement speed of VDS when unloaded | unloaded_VDS_speed | 0.2 | m/sec | Guess
| VDS Recovery speeds | VDS_recovery_speed | 0.01 | m/sec | Not currently referenced in the model
SJS Deployer speeds | SJS deployment speed | SJS_deployment_spd | 0.042 | m/sec | Based on Inuktun NanoMag crawller system moving at 2.5m/min
| SJS Recovery speed | SJS_recovery_spd | 0.008 | m/sec | Not currently referenced in the model
Blanket Transporter System Speeds | Blanket Module lifting time | blanket_lift_duration | 1 | Hours | Early guess which will be informed by future design work
| Blanket Module manuvering duration | blanket_kinamatic_duration | 1 | Hours | Early guess which will be informed by future design work
| Total Blanket Lift Time | total_blanket_lift_time | 2 | Hours | Early guess which will be informed by future design work
RM Equipment Failure Rates
| Weld Failure Rate | Weld_Failure_Rate | 0.1% | %/hr
| Tool Failure Rate | Tool_Failure_Rate | 1% | %/hr | non-recoverable tool failures only e.g. no redundant tools in cask.
| VMC Failure Rate | VMC_Failure_Rate | 0.2% | %/hr
| IVM Failure Rate | IVM_Failure_Rate | 0.2% | %/hr
Cask Failure Rates | CCD seal failure | Cask_CCD_Seal_failure | 0.003% | %/hr
| Cask Control System Failure | Cask_Controller_Failure | 0.003% | %/hr
| Cask Interface Hardware Failure | BT_fixations_failure | 0.003% | %/hr
| Total Cask Failure Rate | Total_Cask_Failure_Rate | 0.009% | %/hr | Early guess which will be informed by future design work
Blanket Transporter Failure | Blanket Transporter Drive Failure | BT_drive_failure | 2% | %/hr
| Failure of fine positioning system | BT_fine_positioning_failure | 1% | %/hr
| Fixation System Failures | BT_fixations_failure | 2% | %/hr
| Total Blanket Transporter Failure | total_BT_failure | 5% | %/hr | Early guess which will be informed by future design work
Multifunction manipulator failures | Actuator assembly failure | mfm_actuator_failure | 1% | %/hr
| Failure of fine positioning system | mfm_fine_positioning_failure | 1% | %/hr
| Total Multifunction Manipulator failure | total_mfm_failure | 2% | %/hr | Early guess which will be informed by future design work
Overhead crane failures | Overhead crane hoist failure | Overhead_hoist_failure | 0.075% | %/hr
| Overhead crane gantry failure | Overhead_gantry_failure | 0.025% | %/hr
| Total Overhead crane failure | overhead_crane_failure | 0.1% | %/hr | Early guess which will be informed by future design work
Service Joint System Welding Failure | Rotational drive failure | SJS_drive_failure | 0.05% | %/hr
| NDT Sensor failure | SJS_NDT_failure | 0.75% | %/hr
| Failure of the clamping system | SJS_Clamp_failure | 0.2% | %/hr
| Total SJS Weld Failure | SJS_welder_failure | 1% | %/hr | Early guess which will be informed by future design work
Hardware Transporter Failures | Drive unit failure | hardware_transport_drive_failure | 0.001% | %/hr
| Control hardware failure | hardware_transport_controller_failure | 0.0001% | %/hr
| payload handling system failure | hardware_transport_pl_handling_failure | 0.01% | %/hr
| Total Hardware Transporter Failure | Hardware_transport_failure | 0.0111% | %/hr | Early guess which will be informed by future design work
Divertor Cassette Handling System | mechanical fixation system failure | cassette_handling_mechanical_fixation_failure | 0.001% | %/hr
| Cassette deployment system failure | cassette_deployment_system_failure | 0.05% | %/hr
| Fine positioning sensors | cassette_handling_location_sensor | 0.01% | %/hr
| Camera system failure | cassette_handling_camera_failure | 0.44% | %/hr
| Total Divertor Cassette Handling System Failure | Total_Cassette_Handling_Failure | 0.501% | %/hr | Early guess which will be informed by future design work
DEMO Lifecycle |  |  |  |  | Values taken from J. Anthony, “Operational Concept Document for DEMO,” https://idm.euro-fusion.org/?uid=2M6ALV&version=v1.2&action=get_document, 2016.
Operational durations | DEMO Post-operation cooldown period | RM_cooldown_period |  | days
| Duration of Operational Sequence | power_generation_period |  | days
| Duration of short maintenance periods | interim_maintenace_period |  | days
| Total duration of an operational sequence in calandar days | sequence_duration |  | days
| Number of sequences per starting campaign | campaign_duration |  | sequences
| Number of sequences per longer campaign | long_campaign_duration |  | sequences
| length of a campaign in fpy | campaign_fpy |  | fpy
| duration of shorter campaigns | warmup_campaigns |  | campaigns
| Duration of minor maintenance interval | minor_maintenance_duration |  | days
| Duration of Minor maintenance in sequences | maintenance_sequence |  | sequences
| Period Between Minor Maintenance Outages | minor_maintenance_intervals |  | fpy
| DEMO pumpdown and conditioning duration | demo_pumpdown |  | days

## BLUEPRINT_output
Full divertor maintenance (days) | Hot Cell | Cask
1 system | 240.0042 | 311.6693
2 system | 135.1309 | 165.6791
3 system | 90.0873 | 110.4527
4 system | 75.0727 | 92.0439
6 system | 45.0436 | 55.2264
Full blanket and divertor maintenance (days) | Hot Cell | Cask
1 system | 665.102 | 691.8507
2 system | 436.1446 | 436.1446
3 system | 238.7161 | 238.7161
4 system | 184.7436 | 192.1807
6 system | 110.8503 | 115.3084
Single divertor port maintenance (days) | Hot Cell | Cask
1 system | 48.4605 | 49.1356
Single sector maintenance (days) | Hot Cell | Cask
1 system | 48.4605 | 48.4605

## Generic Vertical Port Tasks (hidden)
Operations Required
Operation | Subtask | Time (hrs)
Blanket Removal Required | Blanket Removal Required | 0
Open Bioshield | Attach crane to plug | 0.2
| Lift plug | 0.16667
| Health Physics check | 0.2
| Open Bioshield | 0.56667
Open Contamination Control Door | Connect double lidded door and frame | 0.3
| Disconnect door | 0.3
| Open Contamination Control Door | 0.6
Perform Health Physics Checks | Position tool at work site | 0.8
| Monitor work site | 2
| Collect samples | 0.5
| Reposition inspection system | 0.3
| Monitor work site | 2
| Collect samples | 0.5
| Retract tool | 0.67222
| Perform Health Physics Checks | 6.7722
Perform engineering checks | Position tool at work site | 0.8
| Perform photogramity survey of site 1 | 2
| Reposition inspection system | 0.3
| Perform photogramity survey of site 2 | 2
| Retract tool | 0.67222
| Perform engineering checks | 5.7722
Install Contamination Control System | Insert CCS into the area near the port | 0.3
| Connect mechancial fixations | 0.2
| Install Contamination Control System | 0.5
Commission Contamination Control System | Connect Services and supplies | 0.2
| Comission and test system | 2
| Commission Contamination Control System | 2.2
Disconnect ECH | Position tool at work site | 0.8
| Disconnet ECH cooling services | 0.8
| Reposition tool at retaining arm fasteners | 0.325
| Pretensions studs prior to removal | 3.34
| Unfasten nuts | 1.66
| Recovery ECH Fixations and Lift ECH clamps | 2
| Retract tool | 0.5
| Disconnect ECH | 9.425
Extract ECH | Deploy tool | 0.0083333
| Connect to ECH | 2
| Lift ECH plug | 0.16667
| Extract ECH | 2.175
Disconnect Port Closure Plate | Position tool at work site | 0.16667
| Place remote control cars | 2
| Pretensions studs prior to removal | 10.02
| Unfasten nuts | 4.98
| Release studs | 6
| Collect tools | 6
| Retract tool | 0.16667
| Disconnect Port Closure Plate | 29.3333
Extract Port Closure Plate | Extend VMS | 0.0083333
| Clamp to plate | 0.2
| VMS plate lift | 0.16667
| Extract Port Closure Plate | 0.375
Disconnect Shield Plug Pipe Flange | Position tool at work site | 0.16667
| Pretensions studs prior to removal | 1.67
| Release permanent service flange fastenings | 0.83
| Recovery fixations | 1
| Retract Tool | 0.16667
| Disconnect Shield Plug Pipe Flange | 3.8333
Disconnect & extract Shield Plug and Fixations | Extend Tools | 0.0083333
| Apply pre-load | 2.505
| Disconnect mechanical fixations | 1.245
| Lift shield plug | 0.16667
| Disconnect & extract Shield Plug and Fixations | 3.925
Disconnect Multipipe Flange & Access Lid | Position tool at work site | 0.83
| Undo multi pipe flange fasteners | 3
| Undo module lid fasteners | 2
| Collect Lid and retract Tool | 1
| Disconnect Multipipe Flange & Access Lid | 6.83
Disconnect Vertical Port Pipework | Deploy bore cutting tool to cut position | 0.2381
| Clamp to pipe | 0.0083333
| Tension pipes | 0.0083333
| Cut Upper Port Pipe Joints near to blanket manifold | 0.048725
| Camera inspection of cut | 0.5
| Release pipe/unclamp | 0.0083333
| Remove cutting tool from the pipe | 0.2381
| Disconnect Vertical Port Pipework | 1.0499
Extract Pipe Module | Extend VMS | 0.0083333
| Connect to pipe module | 0.3
| Disconnect cassette vacuum vessel attachment points | 0.25
| Lift pipe module | 0.16667
| Extract Pipe Module | 0.725
Extract Blanket Segment | Lower transporter to docking location | 0.6
| Secure transporter plate to dock | 1
| Transporter commissioning checks | 0.5
| Move transporter arm to segment lifting point | 0.14
| Connect transporter to lift point | 1
| Manoeuvre blanket to lifting position | 1
| Lift blanket segment | 1
| Release transporter from dock | 0.5
| Extract Blanket Segment | 5.74
Blanket Installation Required | Blanket Installation Required | 0
Install Blanket Segment | Lower transporter to docking location | 0.57
| Secure transporter plate to dock | 1
| Manoeuvre blanket into the vessel | 1.5
| Position Blanket into final position | 0.56
| Release Blanket segment from Transport | 0.2
| Retract Transporter | 0.5
| Install Blanket Segment | 4.33
Install Pipe Module | Deploy tooling | 0.16667
| Position pipework | 2.67
| Secure pipework | 1.25
| Retract tool | 0.0083333
| Install Pipe Module | 4.095
Connect Vertical Port Pipework | Deploy SJS - welding system | 0.2381
| Clamp to pipe | 0.0083333
| Tension pipes | 0.0083333
| Inspect weld fit up | 0.5
| Fill with inert gas | 0.016667
| Weld Upper Port Pipe Joints near to blanket manifold | 0.010828
| Inspect weld | 0.0083333
| Release pipe/unclamp | 0.0083333
| Recovery welding system | 0.2381
| Change end effector | 3
| Deploy SJS_post weld heat treatment system | 0.2381
| Clamp SJS tool to pipe | 0.0083333
| Perform post weld heat treatment | 9
| Release pipe/unclamp | 0.0083333
| Recovery SJS - PWHT system | 0.2381
| Change SJS end effector | 3
| Deploy SJS - NDT System | 0.2381
| Clamp to pipe | 0.0083333
| Visual inspection | 0.5
| Volumetric inspection | 0.5
| He leaktest | 6
| Release SJS clamps | 0.0083333
| Retract tool | 0.2381
| Connect Vertical Port Pipework | 24.0227
Connect Multipipe Flange & Access Lid | Position tool and access lid at work site | 0.83
| Apply multi pipe flange fasteners | 4
| Apply module lid fasteners | 2.5
| Retract Tool | 0.5
| Connect Multipipe Flange & Access Lid | 7.83
Insert and Connect Shield Plug and Fixations | Insert shield plug | 0.16667
| Position shield plug within port | 0.5
| Apply pre-load | 2
| Turn twist locks | 0.02
| Release pre-load | 1
| Retract tool | 0.0083333
| Insert and Connect Shield Plug and Fixations | 3.695
Connect Shield Plug Pipe Flange | Position tool at work site | 0.8
| Apply permanent service flange fastenings | 2.505
| Retract Tool | 0.8
| Connect Shield Plug Pipe Flange | 4.105
Insert Port Closure Plate | Insert Plate | 0.16667
| Release plate | 0.2
| Retract tool | 0.0083333
| Insert Port Closure Plate | 0.375
Connect Port Closure Plate | Position tool at work site | 0.8
| fasten studs | 18
| Tension studs | 10.02
| Collect and recovery tools from the port | 0.5
| Test seal | 5
| Connect Port Closure Plate | 34.32
Insert ECH | Insert ECH | 0.16667
| Release ECH | 2
| Retract tool | 0.0083333
| Insert ECH | 2.175
Connect ECH | Position tool at work site | 0.8
| Apply retaining arm lock fasteners | 2
| Reposition tool at ech fasteners | 6
| apply ECH fasteners | 3.34
| Reposition tool at cooling services connection | 0.325
| connect ECH cooling services | 1.6
| Retract tooling | 0.5
| Connect ECH | 14.565
Disconnect CCS Services | Deploy multifunction Manipulator | 0.083333
| Disconnect Services and supplies | 0.2
| Remove mechanical fixations | 0.5
| Recover multifunction manipulator | 0.083333
| Disconnect CCS Services | 0.86667
Close Contamination Control Door | Insert doubled lidded door and frame | 0.3
| Connect door | 0.3
| Test seal | 5
| Close Contamination Control Door | 5.6
Seal Bioshield | Lower plug | 0.5
| Remove crane | 0.2
| Retract tool | 0.2
| Health Physics check | 0.2
| Seal Bioshield | 1.1
Inspect the Port | Deploy inspection hardware to inspection site | 0.75
| Inspect the vacuum vessel | 5
| Inspect IVC mounting hardware | 2
| Retract sensors | 0.75
| Inspect the Port | 8.5
Clean/re-condition port hardware | Deploy hardware into the port | 0.75
| Re-condition IVC mounting points | 4
| Clean port | 3
| Retract hardware | 0.75
| Clean/re-condition port hardware | 8.5
Hardware Recovery Required | Hardware Recovery Required | 0
Equipment Recovery Required | Equipment Recovery Required | 0
Man-in-loop recovery work | Man-in-loop recovery work | 12

## Generic Divertor Port Tasks (hidden)
Operations Required
Operation | Subtask | Time (hrs)
Cassette Removal Required | Cassette Removal Required | 0
Open Lower Port Plug | Attach crane to the plug | 0.5
| Remove the plug | 0.2
| Health Physics check | 0.2
| Open Lower Port Plug | 0.9
Install Contamination Control System | Insert CCS into the area near the port | 0.3
| Connect mechancial fixations | 0.2
| Install Contamination Control System | 0.5
Commission Contamination Control System | Connect Services and supplies | 0.2
| Comission and test system | 2
| Commission Contamination Control System | 2.2
Open Contamination Control Door | Connect double lidded door and frame | 0.3
| Disconnect door | 0.3
| Open Contamination Control Door | 0.6
Perform Health Physics Checks | Position tool at work site | 0.8
| Monitor work site | 2
| Collect samples | 0.5
| Reposition inspection system | 0.3
| Monitor work site | 2
| Collect samples | 0.5
| Retract tool | 0.67222
| Perform Health Physics Checks | 6.7722
Perform engineering checks | Position tool at work site | 0.8
| Perform photogramity survey of site 1 | 2
| Reposition inspection system | 0.3
| Perform photogramity survey of site 2 | 2
| Retract tool | 0.67222
| Perform engineering checks | 5.7722
Install Threshold Rails | Position tool at work site | 0.79722
| Attach mechanical fixations | 5
| Reposition manipulators | 0.3
| Connect service connetions | 4
| Retract Tool | 0.79722
| Install Threshold Rails | 10.8944
Disconnect Diagnostic services | Position tool at work site | 0.016667
| Disconnect power services | 0.069167
| Disconnect pipework connections | 0.04
| Retract Tool | 0.33333
| Disconnect Diagnostic services | 0.45917
Disconnect shielding modules | Position tool at work site | 0.016667
| Disconnect mechanical fixations | 2
| remove shielding module and place in storage stillage | 1
| Retract Tooling | 0.33333
| Disconnect shielding modules | 3.35
Remove Lower Port Pipework Access Lid | Position tool at work site | 0.83
| Undo module lid fasteners | 2
| Collect Lid and retract Tool | 1
| Remove Lower Port Pipework Access Lid | 3.83
Disconnect vacuum pumping system | Position tool at work site | 0.79722
| Disconnect power services | 4.15
| Disconnect pipework connections | 2.4
| Retract Tool | 0.79722
| Disconnect vacuum pumping system | 8.1444
Lift pumping assembly from port | Connect pumping system interface equipment | 0.5
| Release brakes/flixations holding pumping system in place | 0.2
| Remove pumping system from the port | 3
| Lift pumping assembly from port | 3.7
Disconnect Divertor Pipe module | Deploy bore cutting tool to cut position | 0.31746
| Clamp to pipe | 0.0055556
| Tension pipes | 0.0055556
| Cut Upper Port Pipe Joints near manifold | 0.040564
| Camera inspection of cut | 0.33333
| Release pipe/unclamp | 0.0055556
| Remove cutting tool from the pipe | 0.31746
| Disconnect Divertor Pipe module | 1.0255
Disconnect Blanket Pipe Module | Deploy bore cutting tool to cut position | 0.2381
| Clamp to pipe | 0.0041667
| Tension pipes | 0.0041667
| Cut Upper Port Pipe Joints near to blanket manifold | 0.021329
| Camera inspection of cut | 0.25
| Release pipe/unclamp | 0.0041667
| Remove cutting tool from the pipe | 0.2381
| Disconnect Blanket Pipe Module | 0.76002
Disconnect Inner Port Pipe Module | Cut welded joints near blanket mainifold | 0.76002
| Reposition welding tool | 0.252
| Cut second welded joint | 0.76002
| Disconnect Inner Port Pipe Module | 1.772
Remove Vacuum Closure Plate | Tensions studs | 10.02
| Unfasten nuts | 4.98
| Release studs | 6
| Retract port plate and pipes into cask | 0.5
| Remove Vacuum Closure Plate | 21.5
Remove Central Divertor Cassette | Deploy cassette handling system | 0.016667
| Attach to central cassette to transporter | 0.2
| Disconnect central cassette cassette from VV | 0.3
| Retract central cassette | 0.33333
| Remove Central Divertor Cassette | 0.85
Remove Peripheral Divertor Cassette | Deploy cassette handling system | 0.016667
| Attach to left or right cassette to transporter | 0.2
| Disconnect left or right cassette from VV | 0.3
| Retract left or right cassette | 0.33333
| Remove Peripheral Divertor Cassette | 0.85
Cassette Installation Required | Cassette Installation Required | 0
Inspect the Port | Deploy inspection hardware to inspection site | 0.33333
| Inspect the vacuum vessel | 5
| Inspect IVC mounting hardware | 2
| Retract sensors | 0.33333
| Inspect the Port | 7.6667
Clean/re-condition port hardware | Deploy hardware into the port | 0.33333
| Re-condition IVC mounting points | 4
| Clean port | 3
| Retract hardware | 0.33333
| Clean/re-condition port hardware | 7.6667
Install Peripheral Divertor Cassette | Insert Peripheral Divertor cassette | 0.33333
| Connect left or right cassette to VV | 0.3
| Detach left or right cassette | 0.3
| Recovery hardware transporter from port | 0.016667
| Install Peripheral Divertor Cassette | 0.95
Install Central Divertor Cassette | Insert Peripheral Divertor cassette | 0.33333
| Connect left or right cassette to VV | 0.3
| Detach left or right cassette | 0.3
| Recovery hardware transporter from port | 0.016667
| Install Central Divertor Cassette | 0.95
Install Lower Port Pipework Access Lid | Position tool and access lid at work site | 0.83
| Apply module lid fasteners | 2.5
| Leak Testing | 1
| Retract Tool | 0.83
| Install Lower Port Pipework Access Lid | 5.16
Connect shielding modules | Position tool at work site | 0.33333
| Export shielding module and install in port | 2
| Connect mechanical fixations | 2
| Retract Tooling | 0.016667
| Connect shielding modules | 4.35
Lift pumping assembly into port | Lift pumping hardware into the port | 4
| Engage brakes/flixations holding pumping system in place | 0.5
| Release pumping assembly hardware from transporter | 0.5
| Retract Tooling | 0.016667
| Lift pumping assembly into port | 4.5
Connect vacuum pumping system | Position tool at work site | 0.79722
| Connect pipework service joints | 3
| Connect service connetions | 2.4
| Retract Tool | 0.79722
| Connect vacuum pumping system | 6.9944
Connect Diagnostic services | Position tool at work site | 0.79722
| Connect mechanical fixations | 6
| connect power services | 2
| Retract Tooling | 0.016667
| Connect Diagnostic services | 8.8139
Remove Threshold Rails | Position tool at work site | 0.79722
| Disconnect service connections | 4
| Reposition manipulators | 0.3
| Remove mechanical fixations | 3
| Retract Tooling | 0.016667
| Remove Threshold Rails | 8.1139
Insert Vacuum Closure Plate | Insert Plate | 1
| Release plate | 0.2
| Retract Tooling | 0.016667
| Insert Vacuum Closure Plate | 1.2167
Install Vacuum Closure Plate | Position Port Plate & Pipes | 0.55
| Tension studs | 6
| Tension nuts | 1.5
| Retract Tooling | 0.016667
| Install Vacuum Closure Plate | 8.0667
Connect Divertor Pipe module | Deploy SJS - welding system | 0.31746
| Clamp to pipe | 0.0055556
| Tension pipes | 0.0055556
| Inspect weld fit up | 0.33333
| Fill with inert gas | 0.011111
| Weld Divertor Port Pipe Joints near manifold | 0.0047398
| Inspect weld | 0.0055556
| Release pipe/unclamp | 0.0055556
| Recovery welding system | 0.31746
| Change end effector | 2
| Deploy SJS_post weld heat treatment system | 0.31746
| Clamp SJS to pipe | 0.0055556
| Perform post weld heat treatment | 6
| Release pipe/unclamp | 0.0055556
| Recovery SJS - PWHT system | 0.31746
| Change SJS end effector | 2
| Deploy SJS - NDT System | 0.31746
| Clamp to pipe | 0.0055556
| Visual inspection | 0.33333
| Volumetric inspection | 0.33333
| He leaktest | 4
| Release SJS clamps | 0.0055556
| Retract tool | 0.31746
| Connect Divertor Pipe module | 16.9651
Connect Blanket Pipe Module | Deploy SJS - welding system | 0.2381
| Clamp to pipe | 0.0041667
| Tension pipes | 0.0041667
| Inspect weld fit up | 0.25
| Fill with inert gas | 0.0083333
| Weld Divertor Port Pipe Joints near manifold | 0.0054139
| Inspect weld | 0.0041667
| Release pipe/unclamp | 0.0041667
| Recovery welding system | 0.2381
| Change end effector | 1.5
| Deploy SJS_post weld heat treatment system | 14.2857
| Clamp to pipe | 0.0041667
| Perform post weld heat treatment | 4.5
| Release pipe/unclamp | 0.0041667
| Recovery SJS - PWHT system | 0.2381
| Change SJS end effector | 1.5
| Deploy SJS - NDT System | 0.2381
| Clamp to pipe | 0.0041667
| Visual inspection | 0.25
| Volumetric inspection | 0.25
| He leaktest | 3
| Release SJS clamps | 0.0041667
| Retract tool | 0.2381
| Connect Blanket Pipe Module | 26.7733
Connect Inner Port Pipe module | Weld joint | 26.7733
| Increment to second position | 0.2381
| Weld joint | 26.7733
| Connect Inner Port Pipe module | 53.7846
Remove Contamination Control System | Disconnect mechancial fixations | 0.2
| Lift CCS from the port | 0.3
| Remove Contamination Control System | 0.3
Decommission Contamination Control System | Shut down CCS | 1
| Disconnect Services and supplies | 0.2
| Decommission Contamination Control System | 1.2
Seal Lower Port Bioshield | Positon Plug | 0.5
| Seal the port | 0.2
| Health Physics check | 0.2
| Seal Lower Port Bioshield | 0.9
Hardware Recovery Required | Hardware Recovery Required | 0 | .
Equipment Recovery Required | Equipment Recovery Required | 0
Man-in-loop recovery work | Man-in-loop recovery work | 12

## Plant Availibility Calculator
| Upper Port Hot Cell and a Lower Port Hot Cell Maintenance Strategy |  |  |  |  | Upper Port Cask System and a Lower Port Cask System Maintenance Strategy
Number of Available RM systems | 1 | 2 | 3 | 4 | 6 | 1 | 2 | 3 | 4 | 6 | RM System(s)
Maxamum number of ports maintained by a RMS | 18 | 9 | 6 | 5 | 3 | 18 | 9 | 6 | 5 | 3 | Ports
DEMO Cooldown period | 0 |  |  |  |  | 0 |  |  |  |  | Days
Total Time Cooling Down | #REF! |  |  |  |  | #REF! |  |  |  |  | Days
DEMO Pump Down Period | 0 |  |  |  |  | 0 |  |  |  |  | Days
Total Pump down time | #REF! |  |  |  |  | #REF! |  |  |  |  | Days
Target DEMO Lifetime | #REF! |  |  |  |  | #REF! |  |  |  |  | FPY
Total Time Pulsing | #REF! |  |  |  |  | #REF! |  |  |  |  | Days
Total Full Power Years | #REF! |  |  |  |  | #REF! |  |  |  |  | FPY
Total Time Spent carrying out Campaigns | #REF! |  |  |  |  | #REF! |  |  |  |  | Days
Total Time Spent in Campaigns | #REF! |  |  |  |  | #REF! |  |  |  |  | Years
Time spend "Dwelling" | #REF! |  |  |  |  | #REF! |  |  |  |  | Days
| #REF! |  |  |  |  | #REF! |  |  |  |  | Years
Number of days for Interim Maintenance | #REF! |  |  |  |  | #REF! |  |  |  |  | Days
| #REF! |  |  |  |  | #REF! |  |  |  |  | Years
Vertical Port Strategy | Upper Port Hot Cell |  |  |  |  | Upper Port Cask System |  |  |  |  | /
Number of Blanket Maintenance Outages | #REF! |  |  |  |  | #REF! |  |  |  |  | Outages
Single Blanket Maintenance Duration | 1097.4183 | 719.6386 | 479.7591 | 399.7992 | 239.8795 | 1141.5536 | 719.6386 | 479.7591 | 399.7992 | 239.8795 | Days
Total Duration of Blanket Maintenance | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Days
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Years
Divertor Port Strategy | Lower Port Hot Cell |  |  |  |  | Lower Port Cask System |  |  |  |  | /
Number of Divertor Maintenance Outages | #REF! |  |  |  |  | #REF! |  |  |  |  | Outages
Single Divertor Maintenance Duration | 396.007 | 222.966 | 148.644 | 123.87 | 74.322 | 514.2544 | 273.3705 | 182.247 | 151.8725 | 91.1235 | Days
Total Duration of Divertor Maintenance | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Total Days
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Years
Number of Minor Maintenance Outages | #REF! |  |  |  |  | #REF! |  |  |  |  | Outages
Total Duration of Minor Maintenance | #REF! |  |  |  |  | #REF! |  |  |  |  | Days
| #REF! |  |  |  |  | #REF! |  |  |  |  | Years
Total DEMO Maintenance Duration | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Days
Maintenance in Years | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Years
Total DEMO Lifetime | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Days
Total DEMO Lifetime | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Years
Undergoing Maintenance (%) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | %
Power Generating Availability (%) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | %
Testing, pumping and standby status (%) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | %
Total | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | %
| 36.13% |  | 42.6% | 43.62% | 44.71% | 35.13% |  | 42.01% | 43.11% | 44.31%
| #REF! |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
| 1097.4183 | 719.6386 | 479.7591 | 399.7992 | 239.8795 | 1141.5536 | 719.6386 | 479.7591 | 399.7992 | 239.8795
| 396.007 | 222.966 | 148.644 | 123.87 | 74.322 | 514.2544 | 273.3705 | 182.247 | 151.8725 | 91.1235
| -44.1353 | 0 | 0 | 0 | 0 | -118.2474 | -50.4045 | -33.603 | -28.0025 | -16.8015

## Lower Cask Summary
|  |  | Cask Divertor Port Long Maintenance Interval |  |  |  |  | Impact of | Estimated Duration of | Cask Short Maintenance Interval
|  |  | Maintenance |  | Failures |  | Total |  |  | Maintenance |  | Failures |  | Total
|  |  | Hardware Removal | Hardware Installation | RM Equipment | Welding Operations | Maintenance Cycle | Upper Port Hot Cell Ops | Maintenace Campaign | Divertor Removal | Divertor Installation | RM Equipment | Welding Operations | Maintenance Cycle
Single Port | Operations | hrs | 123.4265 | 391.2019 | 6.3998 | 244.9352 | 765.9633 | 725.8215 |  | 104.5923 | 134.2863 | 4.7335 | 30.8085 | 274.4206
|  | %age | 60.05% | 83.15% | 21.38% | 51.75% | 64.95% | 81.85% |  | 63.04% | 69.88% | 21.78% | 49.7% | 62.11%
| Logistics | hrs | 76.0581 | 77.8215 | 23.5356 | 68.1595 | 245.5746 | 74.1307 |  | 55.2581 | 56.4115 | 17.0021 | 21.4496 | 150.1213
|  | %age | 37% | 16.54% | 78.62% | 14.4% | 20.82% | 8.359% |  | 33.3% | 29.35% | 78.22% | 34.61% | 33.98%
|  | Idle time | 6.07 | 1.4744 | 0 | 160.1714 | 167.7159 | 86.8504 |  | 6.07 | 1.4744 | 0 | 9.7246 | 17.2691
|  | %age | 2.953% | 0.3134% | 0% | 33.84% | 14.22% | 9.794% |  | 3.658% | 0.7673% | 0% | 15.69% | 3.909%
| Total Time | hrs | 205.5546 | 470.4978 | 29.9353 | 473.2661 | 1179.2538 | 886.8027 | 1179.2538 | 165.9204 | 192.1722 | 21.7355 | 61.9827 | 441.8109
|  | days | 8.5648 | 19.6041 | 1.2473 | 19.7194 | 49.1356 | 36.9501 | 49.1356 | 6.9134 | 8.0072 | 0.90565 | 2.5826 | 18.4088
| Elapsed Time | hrs | 339.1651 | 776.3214 | 49.3933 | 780.889 | 1945.7688 | 1463.2244 | 1945.7688 | 273.7687 | 317.0841 | 35.8637 | 102.2715 | 728.988
|  | Days | 14.1319 | 32.3467 | 2.0581 | 32.537 | 81.0737 | 60.9677 | 81.0737 | 11.407 | 13.2118 | 1.4943 | 4.2613 | 30.3745
|  | Months | 0.47106 | 1.0782 | 0.068602 | 1.0846 | 2.7025 | 2.0323 | 2.7025 | 0.38023 | 0.44039 | 0.049811 | 0.14204 | 1.0125
|  | % | 17.43% | 39.9% | 2.538% | 40.13% | 100% | 100% | 100% | 37.55% | 43.5% | 4.92% | 14.03% | 100%
All 18 Ports in series | Operations | hrs | 2221.6764 | 7041.6344 | 115.1961 | 4408.8332 | 13787.3401 | 13064.7874 |  | 1882.6612 | 1882.6612 | 85.2028 | 554.5531 | 4405.0783
|  | days | 92.5698 | 293.4014 | 4.7998 | 183.7014 | 574.4725 | 544.3661 |  | 78.4442 | 78.4442 | 3.5501 | 894.7% | 169.3854
| Logistics | hrs | 1369.0467 | 1369.0467 | 423.64 | 1226.8703 | 4388.6037 | 1334.3535 |  | 994.6467 | 994.6467 | 306.037 | 386.0928 | 2681.4232
|  | days | 57.0436 | 57.0436 | 17.6517 | 51.1196 | 182.8585 | 55.5981 |  | 41.4436 | 41.4436 | 12.7515 | 830.5% | 103.9442
|  | Idle time | 109.26 | 109.26 | 0 | 2883.0854 | 3101.6054 | 1563.3069 |  | 109.26 | 109.26 | 0 | 175.043 | 393.563
| Total Time | hrs | 3699.9831 | 8519.9411 | 538.8361 | 8518.7889 | 21277.5492 | 15962.4478 | 21277.5492 | 2986.5679 | 2986.5679 | 391.2398 | 1115.6889 | 7480.0644
|  | days | 154.166 | 354.9975 | 22.4515 | 354.9495 | 886.5645 | 665.102 | 886.5645 | 124.4403 | 124.4403 | 16.3017 | 46.487 | 311.6693
| Elapsed Time | hrs | 6104.972 | 14057.9028 | 889.0796 | 14056.0017 | 35107.9562 | 26338.0388 | 35107.9562 | 4927.837 | 4927.837 | 645.5457 | 1840.8866 | 12342.1062
|  | Days | 254.3738 | 585.746 | 37.045 | 585.6667 | 1462.8315 | 1097.4183 | 1462.8315 | 205.3265 | 205.3265 | 26.8977 | 76.7036 | 514.2544
|  | Months | 8.4791 | 19.5249 | 1.2348 | 19.5222 | 48.7611 | 36.5806 | 48.7611 | 6.8442 | 6.8442 | 0.89659 | 2.5568 | 17.1418
|  | % | 17.39% | 40.04% | 2.532% | 40.04% | 100% | 100% | 100% | 39.93% | 39.93% | 5.23% | 14.92% | 100%
All 18 Ports with 2 RM Systems | Operations | hrs | 1110.8382 | 3520.8172 | 57.5981 | 2204.4166 | 6893.67 | 6532.3937 |  | 941.3306 | 1208.5765 | 42.6014 | 277.2765 | 2469.7851
|  | days | 46.2849 | 146.7007 | 0.21379 | 0.51754 | 193.717 | 272.1831 |  | 39.2221 | 50.3574 | 1.7751 | 447.3% | 102.9077
| Logistics | hrs | 684.5233 | 700.3933 | 211.82 | 613.4352 | 2210.1718 | 667.1767 |  | 497.3233 | 507.7033 | 153.0185 | 193.0464 | 1351.0916
|  | days | 28.5218 | 29.1831 | 0.78621 | 0.14402 | 58.6351 | 27.799 |  | 20.7218 | 21.1543 | 6.3758 | 830.5% | 56.2955
|  | Idle time | 54.63 | 13.27 | 0 | 1441.5427 | 1509.4427 | 781.6534 |  | 54.63 | 13.27 | 0 | 87.5215 | 155.4215
| Total Time | hrs | 1849.9915 | 4234.4805 | 269.4181 | 4259.3945 | 10613.2846 | 7981.2239 | 10613.2846 | 1493.2839 | 1729.5499 | 195.6199 | 557.8444 | 3976.2981
|  | days | 77.083 | 176.4367 | 11.2258 | 177.4748 | 442.2202 | 332.551 | 442.2202 | 62.2202 | 72.0646 | 8.1508 | 23.2435 | 165.6791
| Elapsed Time | hrs | 3052.486 | 6986.8929 | 444.5398 | 7028.0008 | 17511.9196 | 13169.0194 | 17511.9196 | 2463.9185 | 2853.7573 | 322.7729 | 920.4433 | 6560.8919
|  | Days | 127.1869 | 291.1205 | 18.5225 | 292.8334 | 729.6633 | 548.7091 | 729.6633 | 102.6633 | 118.9066 | 13.4489 | 38.3518 | 273.3705
|  | Months | 4.2396 | 9.704 | 0.61742 | 9.7611 | 24.3221 | 18.2903 | 24.3221 | 3.4221 | 3.9636 | 0.4483 | 1.2784 | 9.1123
|  | % | 17.43% | 39.9% | 2.538% | 40.13% | 100% | 150% | 150% | 37.55% | 43.5% | 4.92% | 14.03% | 100%
All 18 Ports with 3 RM Systems | Operations | hrs | 740.5588 | 2347.2115 | 38.3987 | 1469.6111 | 4595.78 | 4354.9291 |  | 627.5537 | 805.7177 | 28.4009 | 184.851 | 1646.5234
|  | days | 21.7811 | 69.0356 | 1.5999 | 61.2338 | 153.6505 | 181.4554 |  | 18.4575 | 23.6976 | 1.1834 | 298.2% | 68.6051
| Logistics | hrs | 456.3489 | 466.9289 | 141.2133 | 408.9568 | 1473.4479 | 444.7845 |  | 331.5489 | 338.4689 | 102.0123 | 128.6976 | 900.7277
|  | days | 13.422 | 13.7332 | 5.8839 | 17.0399 | 50.079 | 18.5327 |  | 9.7514 | 9.955 | 4.2505 | 830.5% | 37.5303
|  | Idle time | 36.42 | 8.8467 | 0 | 961.0285 | 1006.2951 | 521.1023 |  | 36.42 | 8.8467 | 0 | 58.3477 | 103.6143
| Total Time | hrs | 1233.3277 | 2822.987 | 179.612 | 2839.5963 | 7075.5231 | 5320.8159 | 7075.5231 | 995.5226 | 1153.0333 | 130.4133 | 371.8963 | 2650.8654
|  | days | 36.2743 | 83.029 | 7.4838 | 118.3165 | 245.1037 | 221.7007 | 245.1037 | 29.2801 | 33.9127 | 5.4339 | 15.4957 | 110.4527
| Elapsed Time | hrs | 2034.9907 | 4657.9286 | 296.3599 | 4685.3339 | 11674.6131 | 8779.3463 | 11674.6131 | 1642.6123 | 1902.5049 | 215.1819 | 613.6289 | 4373.928
|  | Days | 84.7913 | 194.0804 | 12.3483 | 195.2222 | 486.4422 | 365.8061 | 486.4422 | 68.4422 | 79.271 | 8.9659 | 25.5679 | 182.247
|  | Months | 2.8264 | 6.4693 | 0.41161 | 6.5074 | 16.2147 | 12.1935 | 16.2147 | 2.2814 | 2.6424 | 0.29886 | 0.85226 | 6.0749
|  | % | 17.43% | 39.9% | 2.538% | 40.13% | 100% | 100% | 100% | 37.55% | 43.5% | 4.92% | 14.03% | 120%
All 18 Ports with 4 RM Systems | Operations | hrs | 617.1323 | 1956.0096 | 31.9989 | 1224.6759 | 3829.8167 | 3629.0122 |  | 522.9614 | 671.4314 | 23.6674 | 154.0425 | 1372.1028
|  | days | 14.0257 | 44.4548 | 1.3333 | 51.0282 | 110.8419 | 151.2088 |  | 11.8855 | 15.2598 | 0.98614 | 248.5% | 57.171
| Logistics | hrs | 380.2907 | 389.1074 | 117.6778 | 408.9568 | 1296.0327 | 370.5832 |  | 276.2907 | 282.0574 | 85.0103 | 107.248 | 750.6064
|  | days | 8.643 | 8.8434 | 4.9032 | 17.0399 | 39.4294 | 15.441 |  | 6.2793 | 6.4104 | 3.5421 | 830.5% | 31.2753
|  | Idle time | 30.35 | 7.3722 | 0 | 961.0285 | 998.7507 | 434.2519 |  | 30.35 | 7.3722 | 0 | 48.623 | 86.3453
| Total Time | hrs | 1027.7731 | 2352.4892 | 149.6767 | 2594.6611 | 6124.6001 | 4433.8474 | 6124.6001 | 829.6022 | 960.861 | 108.6777 | 309.9136 | 2209.0545
|  | days | 23.3585 | 53.4657 | 6.2365 | 108.1109 | 191.1716 | 184.7436 | 191.1716 | 18.8546 | 21.8378 | 4.5282 | 12.9131 | 92.0439
| Elapsed Time | hrs | 1695.8256 | 3881.6072 | 246.9666 | 4281.1909 | 10105.5902 | 7315.8482 | 10105.5902 | 1368.8436 | 1585.4207 | 179.3183 | 511.3574 | 3644.94
|  | Days | 70.6594 | 161.7336 | 10.2903 | 178.383 | 421.0663 | 304.827 | 421.0663 | 57.0351 | 66.0592 | 7.4716 | 21.3066 | 151.8725
|  | Months | 2.3553 | 5.3911 | 0.34301 | 5.9461 | 14.0355 | 10.1609 | 14.0355 | 1.9012 | 2.202 | 0.24905 | 0.71022 | 5.0624
|  | % | 16.78% | 38.41% | 129.2% | 36.67% | 221% | 83.33% | 221% | 37.55% | 43.5% | 4.92% | 14.03% | 100%
All 18 Ports with 6 RM Systems | Operations | hrs | 370.2794 | 1173.6057 | 19.1994 | 734.8055 | 2297.89 | 2177.4646 |  | 313.7769 | 402.8588 | 14.2005 | 92.4255 | 823.2617
|  | days | 5.7856 | 18.3376 | 0.21379 | 30.6169 | 54.9539 | 90.7277 |  | 4.9028 | 6.2947 | 0.21778 | 149.1% | 34.3026
| Logistics | hrs | 228.1744 | 233.4644 | 70.6067 | 204.4784 | 736.7239 | 222.3922 |  | 165.7744 | 169.2344 | 51.0062 | 64.3488 | 450.3639
|  | days | 3.5652 | 3.6479 | 0.78621 | 8.5199 | 16.5193 | 9.2663 |  | 2.5902 | 2.6443 | 0.78222 | 830.5% | 18.7652
|  | Idle time | 18.21 | 4.4233 | 0 | 480.5142 | 503.1476 | 260.5511 |  | 18.21 | 4.4233 | 0 | 29.1738 | 51.8072
| Total Time | hrs | 616.6638 | 1411.4935 | 89.806 | 1419.7982 | 3537.7615 | 2660.408 | 3537.7615 | 497.7613 | 576.5166 | 65.2066 | 185.9481 | 1325.4327
|  | days | 9.6354 | 22.0546 | 3.7419 | 59.1583 | 94.5901 | 110.8503 | 110.8503 | 7.7775 | 9.0081 | 2.7169 | 7.7478 | 55.2264
| Elapsed Time | hrs | 1017.4953 | 2328.9643 | 148.1799 | 2342.6669 | 5837.3065 | 4389.6731 | 5837.3065 | 821.3062 | 951.2524 | 107.591 | 306.8144 | 2186.964
|  | Days | 42.3956 | 97.0402 | 6.1742 | 97.6111 | 243.2211 | 182.903 | 243.2211 | 34.2211 | 39.6355 | 4.483 | 12.7839 | 91.1235
|  | Months | 1.4132 | 3.2347 | 0.20581 | 3.2537 | 8.1074 | 6.0968 | 8.1074 | 1.1407 | 1.3212 | 0.14943 | 0.42613 | 3.0374
|  | % | 17.43% | 39.9% | 2.538% | 40.13% | 100% | 100% | 100% | 37.55% | 43.5% | 4.92% | 14.03% | 100%
Note on C13: Farquhar, Iain: Calculated by factoring a efficiently factor of 0.67, as well as an allowance for both un-planned maintenance and logistics tasks, equal to an additional 10%.
Note on C25: Farquhar, Iain: Calculated by factoring a efficiently factor of 0.67, as well as an allowance for both un-planned maintenance and logistics tasks equal to an additional 10%.
Note on C37: Farquhar, Iain: Calculated by factoring a efficiently factor of 0.67, as well as an allowance for both un-planned maintenance and logistics tasks equal to an additional 10%.
Note on C49: Farquhar, Iain: Calculated by factoring a efficiently factor of 0.67, as well as an allowance for both un-planned maintenance and logistics tasks equal to an additional 10%.
Note on C61: Farquhar, Iain: Calculated by factoring a efficiently factor of 0.67, as well as an allowance for both un-planned maintenance and logistics tasks equal to an additional 10%.
Note on C73: Farquhar, Iain: Calculated by factoring a efficiently factor of 0.67, as well as an allowance for both un-planned maintenance and logistics tasks equal to an additional 10%.

## Lower Cask Critical Path (hidden)
[5 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies
Group | Activity | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack
Remove Bioshield Plug | Cassette Removal Required | Operation | 0 | 0 | Cassette Removal Required | 0 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Collect Bioshield Plug Attachment | Logistics | 0.58 | 0.58 |  | N/A |  |  |  | N/A | N/A | N/A | Collect interface hardware | 0.58 |  | N/A | N/A
| Move Cask Transporter A to Lower Port | Movement | 0.23148 | 0.81148 |  | N/A | Cask Transporter (Empty Cask) | AMF Equipment Issue | Lower Port | 50 | 0.06 | 0.23148 |  | N/A |  | N/A | N/A
| Open Lower Port Plug | Operation | 0.9 | 1.7115 | Open Lower Port Plug | 0.9 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move Cask Transporter A to Bioshield Stillage | Movement | 0.41667 | 2.1281 |  | N/A | Cask Transporter (Loaded) | Lower Port | Hardware Stillage | 30 | 0.02 | 0.41667 |  | N/A |  | N/A | N/A
| Store Bioshield | Logistics | 0.58 | 2.7081 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58 |  | N/A | N/A
Perform Health Physics and engineering checks | Dock Vacuum Closure Plate Cask | Logistics | 1.9 | 5.7744 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Vacuum Closure Cask Prepared; Port Plate Equipment Cask Moved to Lower Port | 3.8744 | -1.1663
| Deploy Port Inspection System | Logistics | 0.38 | 6.1544 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Perform health physics checks | Operation | 6.7722 | 12.9267 | Perform Health Physics Checks | 6.7722 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract Port Inspection System | Logistics | 0.38 | 13.3067 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Deploy Port Inspection Hardware | Logistics | 0.38 | 13.6867 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Perform engineering checks | Operation | 5.7722 | 19.4589 | Perform engineering checks | 5.7722 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Recovery Port Inspection System | Logistics | 0.38 | 19.8389 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
Remove Vacuum Closure Plate | Deploy Lower Port Plate Equipment | Logistics | 0.38 | 20.2189 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Remove Port Plate | Operation | 21.5 | 41.7189 | Remove Vacuum Closure Plate | 21.5 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract Inner Port Equipment into Transport Cask | Logistics | 0.38 | 42.0989 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
Perform Health Physics and engineering checks | Deploy Port Inspection System | Logistics | 0.38 | 42.4789 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Perform health physics checks | Operation | 6.7722 | 49.2511 | Perform Health Physics Checks | 6.7722 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Recover Port Inspection System | Logistics | 0.38 | 49.6311 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Deploy Port Inspection Hardware | Logistics | 0.38 | 50.0111 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Perform engineering checks | Operation | 5.7722 | 55.7833 | Perform engineering checks | 5.7722 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract Port Inspection System | Logistics | 0.38 | 56.1633 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Un-Dock Vacuum Closure cask and move to AMF | Logistics | 2.3 | 58.4633 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
Install Port Threshold Support Rails | Dock Threshold Cask | Logistics | 1.9 | 60.3633 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Bioshield interface hardware Stored; Port Threshold Cask collected; Port Threshold Cask Moved to Lower Port | 13.7219 | 44.7415
| Deploy rails from cask | Logistics | 0.38 | 60.7433 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Position rails for installation | Logistics | 0.53 | 61.2733 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
| Deploy multifunction Manipulator with multifunction manipulator | Logistics | 0.38 | 61.6533 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Install Threshold rails | Operation | 10.8944 | 72.5478 | Install Threshold Rails | 10.8944 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Recover deployed RM system | Logistics | 0.38 | 72.9278 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Un-dock cask | Logistics | 2.3 | 75.2278 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
Remove in-port diagnostics | Dock Diagnostic maintenance cask | Logistics | 1.9 | 77.1278 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Vacuum Closure Cask Stored; Diagnostic Maintenance Cask Collected; Diagnostic Maintenance Cask moved to Lower Port | 60.777 | 14.4507
| Deploy diagnostic maintenance system | Logistics | 0.38 | 77.5078 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Disconnect diagnostic service connections with multifunction manipulator | Operation | 0.45917 | 77.9669 | Disconnect Diagnostic services | 0.45917 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract diagnostic system and store in cask | Logistics | 0.38 | 78.3469 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Un-Dock diagnostic maintenance cask | Logistics | 2.3 | 80.6469 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
Remove vacuum pumping assembly | Dock vacuum pumping cask | Logistics | 1.9 | 82.5469 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 |  | N/A | N/A
| Deploy multifunction Manipulator | Logistics | 0.38 | 82.9269 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Remove pumping services and fixations with multifunction manipulator | Operation | 8.1444 | 91.0714 | Disconnect vacuum pumping system | 8.1444 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract multifunction manipulator | Logistics | 0.38 | 91.4514 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Deploy pumping system lifting attachment | Logistics | 0.38 | 91.8314 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Remove pumping system assembly from the port | Operation | 3.7 | 95.5314 | Lift pumping assembly from port | 3.7 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract Cassette Handling Equipment | Logistics | 0.38 | 95.9114 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Un-Dock Vacuum pumping cask and move to AMF | Logistics | 2.3 | 98.2114 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock Cask | 2.3 |  | N/A | N/A
Remove in-port Shielding modules | Dock shielding module cask | Logistics | 1.9 | 100.1114 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Diagnostic Maintenance Cask Stored; shielding module cask collected; shielding module cask moved to Lower Port | 88.1406 | 10.0707
| Deploy shielding handling system | Logistics | 0.38 | 100.4914 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Disconnect shielding modules with multifunction manipulator | Operation | 3.35 | 103.8414 | Disconnect shielding modules | 3.35 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract shield modules and store in cask | Logistics | 0.38 | 104.2214 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Deploy Port Inspection Hardware | Logistics | 0.38 | 104.6014 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Perform engineering checks | Operation | 5.7722 | 110.3736 | Perform engineering checks | 5.7722 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Recovery Port Inspection System | Logistics | 0.38 | 110.7536 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Un-Dock shielding module cask | Logistics | 2.3 | 113.0536 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
Remove Divertor Cooling Pipe Modules | Dock Divertor Pipework Equipment Cask | Logistics | 1.9 | 114.9536 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Vacuum Pumping Cask Stored; Divertor Pipework Cask Prepared; Divertor Pipework Cask Moved to Lower Port | N/A | N/A
| Deploy Multifunction Manipulator | Logistics | 0.38 | 115.3336 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Remove Centre Cassette pipework access lid using Multifunction Manipulator | Operation | 3.83 | 119.1636 | Remove Lower Port Pipework Access Lid | 3.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove Left Cassette pipework access lid using Multifunction Manipulator | Operation | 3.83 | 122.9936 | Remove Lower Port Pipework Access Lid | 3.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove Right Cassette pipework access lid using Multifunction Manipulator | Operation | 3.83 | 126.8236 | Remove Lower Port Pipework Access Lid | 3.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract Multifunction manipulator | Logistics | 0.38 | 127.2036 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Deploy Service Joint System | Logistics | 0.38 | 127.5836 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Remove Central Divertor pipework module | Operation | 1.0255 | 128.6091 | Disconnect Divertor Pipe module | 1.0255 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Central Divertor pipework module in cask | Logistics | 0.38 | 128.9891 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Reposition Pipework equipment to the second pipework module | Logistics | 0.53 | 129.5191 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
| Remove Left Divertor pipework module | Operation | 1.0255 | 130.5446 | Disconnect Divertor Pipe module | 1.0255 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Left Divertor pipework module in cask | Logistics | 0.38 | 130.9246 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Reposition Pipework equipment to the third pipe module | Logistics | 0.53 | 131.4546 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
| Remove Right Divertor pipework module | Operation | 1.0255 | 132.4801 | Disconnect Divertor Pipe module | 1.0255 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Right Divertor pipework module in cask | Logistics | 0.38 | 132.8601 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Retract Service Joint System into cask | Logistics | 0.38 | 133.2401 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Un-Dock Divertor Pipework Module Cask | Logistics | 2.3 | 135.5401 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
Remove Central Cassette | Dock Divertor Handling Cask | Logistics | 1.9 | 137.4401 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Vacuum Pumping Cask Stored; Cassette Transport Cask Prepared; Cassette Transport Cask Moved to Lower Port | N/A | N/A
| Deploy Port Cleaning Equipment | Logistics | 0.38 | 137.8201 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Clean Port | Operation | 7.6667 | 145.4867 | Clean/re-condition port hardware | 7.6667 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Port Cleaning Equipment | Logistics | 0.38 | 145.8667 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Deploy Cassette Handling Equipment | Logistics | 0.38 | 146.2467 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Remove Central Divertor cassette | Operation | 0.85 | 147.0967 | Remove Central Divertor Cassette | 0.85 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract Cassette Handling Equipment | Logistics | 0.38 | 147.4767 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Un-Dock Full Central Cassette Transport Cask | Logistics | 2.3 | 149.7767 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
Remove Left Divertor Cassette | Dock Divertor Handling Cask | Logistics | 1.9 | 151.6767 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Divertor Pipework Modules Stored; Cassette Transport Cask Prepared; Cassette Transport Cask Moved to Lower Port | 142.9338 | 6.843
| Deploy Cassette Handling Equipment | Logistics | 0.38 | 152.0567 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Remove Left Divertor cassette | Operation | 0.85 | 152.9067 | Remove Peripheral Divertor Cassette | 0.85 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract Cassette Handling Equipment | Logistics | 0.38 | 153.2867 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Un-Dock Left Cassette Transport Cask | Logistics | 2.3 | 155.5867 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
Remove Right Divertor Cassette | Dock Divertor Handling Cask | Logistics | 1.9 | 162.3904 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Central Cassette Stored; Cassette Transport Cask Moved to Lower Port | 160.4904 | -4.9037
| Deploy Cassette Handling Equipment | Logistics | 0.38 | 162.7704 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Remove Right Divertor cassette | Operation | 0.85 | 163.6204 | Remove Peripheral Divertor Cassette | 0.85 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Un-Dock Full Right Cassette Transport Cask | Logistics | 2.3 | 165.9204 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
Cassette Removal Complete | End Time |  |  | 165.9204
| Operational Time |  |  | 104.5923 | 50.88% | 63.04%
| Logistical Time |  |  | 54.61 | 26.57% | 32.91%
| Movement Time |  |  | 0.64815 | 0.3906% | 0.3906%
Remove Outboard Blanket Pipework Modules | Dock Service Joint System Cask | Logistics | 1.9 | 167.8204 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Left Divertor Cassette Stored; Cassette Transport Cask Stored; Outboard Pipework Cask Prepared; Outboard Pipework Cask moved to Lower Port | 157.9004 | 8.02
| Deploy Multifunction Manipulator | Logistics | 0.38 | 168.2004 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Remove COB pipework access lid using Multifunction Manipulator | Operation | 3.83 | 172.0304 | Remove Lower Port Pipework Access Lid | 3.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Deploy Service Joint System from transport cask | Logistics | 0.38 | 172.4104 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Remove COB blanket pipework module | Operation | 0.76002 | 173.1705 | Disconnect Blanket Pipe Module | 0.76002 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store COB Pipe Module into Cask | Logistics | 0.38 | 173.5505 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Retract Service Joint System into cask | Logistics | 0.38 | 173.9305 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Deploy Multifunction Manipulator | Logistics | 0.38 | 174.3105 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Remove LOB pipework access lid using Multifunction Manipulator | Operation | 3.83 | 178.1405 | Remove Lower Port Pipework Access Lid | 3.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove ROB pipework access lid using Multifunction Manipulator | Operation | 3.83 | 181.9705 | Remove Lower Port Pipework Access Lid | 3.83 |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | N/A |  | N/A | N/A
| Reposition Pipework equipment to the second pipework module | Logistics | 0.53 | 182.5005 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
| Remove LOB blanket pipework module | Operation | 0.76002 | 183.2605 | Disconnect Blanket Pipe Module | 0.76002 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store LOB Pipe Module into Cask | Logistics | 0.38 | 183.6405 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Reposition Pipework equipment to the third pipe module | Logistics | 0.53 | 184.1705 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
| Remove ROB blanket pipework module | Operation | 0.76002 | 184.9305 | Disconnect Blanket Pipe Module | 0.76002 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract Service Joint System into cask | Logistics | 0.38 | 185.3105 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Store ROB Pipe Module into Cask | Logistics | 0.38 | 185.6905 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Un-Dock Outboard Pipe Module Cask | Logistics | 2.3 | 187.9905 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
Remove Two Inboard Blanket Pipework Modules | Dock Inboard Pipework Cask | Logistics | 1.9 | 189.8905 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Right Divertor Cassette Stored; Cassette Transport Cask Stored; Inboard Pipework Cask Prepared; Inboard Pipework Cask moved to Lower Port | 170.1341 | 17.8564
| Deploy Service Joint System | Logistics | 0.38 | 190.2705 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Remove LIB blanket pipework module | Operation | 0.76002 | 191.0305 | Disconnect Blanket Pipe Module | 0.76002 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store LIB Pipe Module into Cask | Logistics | 0.38 | 191.4105 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Reposition Pipework equipment to the second pipework module | Logistics | 0.53 | 191.9405 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
| Remove RIB blanket pipework module | Operation | 0.76002 | 192.7005 | Disconnect Blanket Pipe Module | 0.76002 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store RIB Pipe Module into Cask | Logistics | 0.38 | 193.0805 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Retract Service Joint System into cask | Logistics | 0.38 | 193.4605 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Un-Dock Inboard Blanket Pipe Cask | Logistics | 2.3 | 195.7605 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
Remove Inner Pipework Modules | Dock Service Joint System Cask | Logistics | 1.9 | 197.6605 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Outboard Pipework Cask Stored; Inner Port Pipework Cask Prepared; Inner Port Pipework Cask Moved to Lower Port | 195.4842 | 0.27634
| Deploy Service Joint System from transport cask | Logistics | 0.38 | 198.0405 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Remove LIB Inner Pipework module | Operation | 1.772 | 199.8126 | Disconnect Inner Port Pipe Module | 1.772 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store LIB Inner Pipework module in cask | Logistics | 0.38 | 200.1926 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Reposition Pipework equipment to the RIB inner pipework module | Logistics | 0.53 | 200.7226 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
| Remove RIB blanket pipework module | Operation | 1.772 | 202.4946 | Disconnect Inner Port Pipe Module | 1.772 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Inner RIB pipework module in cask | Logistics | 0.38 | 202.8746 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Retract Service Joint System into cask | Logistics | 0.38 | 203.2546 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Un-Dock Inner Pipework Cask | Logistics | 2.3 | 205.5546 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
Hardware Removal Complete | End Time |  |  | 205.5546
| Operational Time |  |  | 123.4265 | 60.05%
| Logistical Time |  |  | 75.41 | 36.69%
| Movement Time |  |  | 0.64815 | 0.3153%
Inspect and re-condition Lower Port | Cassette Installation Required | Operation | 0 | 0 | Cassette Installation Required | 0 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Dock Port Inspection cask | Logistics | 1.9 | 3.3744 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Inspection Cask Collected; Inspection Cask Moved to Lower Port | 1.4744 | -1.4744
| Deploy inspection system | Logistics | 0.38 | 3.7544 |  | o |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Inspect the port | Operation | 7.6667 | 11.4211 | Inspect the port | 7.6667 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract inspection equipment | Logistics | 0.38 | 11.8011 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Deploy cleaning/repair system | Logistics | 0.38 | 12.1811 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Re-condition IVC hardware/fixations | Operation | 7.6667 | 19.8478 | Clean/re-condition port hardware | 7.6667 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract cleaning/re-conditioning system | Logistics | 0.38 | 20.2278 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Un-Dock Inspection Cask | Logistics | 2.3 | 22.5278 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
Install Inner Port Pipework Modules | Dock Service Joint System Cask | Logistics | 1.9 | 24.4278 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Inner Port Pipework Collected and Prepared; Inner Port Pipework Cask Moved to Lower Port | 1.4744 | 21.0533
| Deploy Service Joint System | Logistics | 0.38 | 24.8078 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Install RIB Pipe Module | Operation | 53.7846 | 78.5924 | Connect Inner Port Pipe module | 53.7846 |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | N/A | RIB Installed | 23.8683 | 0.93944
| Collect second Inner Port Pipework Module | Logistics | 0.38 | 78.9724 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Install LIB Pipework Module | Operation | 53.7846 | 132.7571 | Connect Inner Port Pipe Module | 53.7846 |  |  |  | N/A | N/A | N/A |  | N/A | LIB Installed | 28.8928 | 50.0796
| Retract Service Joint System into cask | Logistics | 0.38 | 133.1371 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Un-Dock Empty Inner Port Pipework Cask | Logistics | 2.3 | 135.4371 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
Install Two Inboard Blanket Pipework Modules | Dock Service Joint System Cask | Logistics | 1.9 | 137.3371 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Inspection Cask Stored; Inboard Port Pipework Cask Prepared; Inboard Port Pipework Cask Moved to Lower Port | 24.0948 | 111.3422
| Deploy Service Joint System | Logistics | 0.38 | 137.7171 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Extract First Pipe Module from Cask | Logistics | 0.38 | 138.0971 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Install LIB Blanket Pipe Module | Operation | 26.7733 | 164.8703 | Connect Blanket Pipe Module | 26.7733 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Reposition Pipework equipment to the second pipework module | Logistics | 0.53 | 165.4003 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
| Extract Second Pipe Module from Cask | Logistics | 0.38 | 165.7803 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Install RIB Blanket Pipe Module | Operation | 26.7733 | 192.5536 | Connect Blanket Pipe Module | 26.7733 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract Service Joint System into cask | Logistics | 0.38 | 192.9336 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Retract Multifunction manipulator | Logistics | 0.38 | 193.3136 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Un-Dock Inboard Pipe Module Cask | Logistics | 2.3 | 195.6136 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
Install Three Outboard Blanket Pipework Modules | Dock Service Joint System Cask | Logistics | 1.9 | 197.5136 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Inner Port Pipework Cask Stored; Outboard Port Pipework Cask Prepared; Outboard Port Pipework Cask Moved to Lower Port | 137.7508 | 57.8628
| Deploy Service Joint System | Logistics | 0.38 | 197.8936 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Extract ROB Pipework Module from Cask | Logistics | 0.38 | 198.2736 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Install ROB Blanket Pipe Module | Operation | 26.7733 | 225.0469 | Connect Blanket Pipe Module | 26.7733 |  |  |  | N/A | N/A | N/A |  | N/A | ROB Installed | 33.9172 | 164.3564
| Extract LOB Pipework Module from Cask | Logistics | 0.38 | 225.4269 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Reposition Pipework equipment to the second pipework module location | Logistics | 0.53 | 225.9569 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
| Install LOB blanket pipework module | Operation | 26.7733 | 252.7301 | Connect Blanket Pipe Module | 26.7733 |  |  |  | N/A | N/A | N/A |  | N/A | LOB Installed | 38.9417 | 187.0152
| Retract Service Joint System into cask | Logistics | 0.38 | 253.1101 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Deploy Multifunction Manipulator | Logistics | 0.38 | 253.4901 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Install LOB pipework access lid using Multifunction Manipulator | Operation | 5.16 | 258.6501 | Install Lower Port Pipework Access Lid | 5.16 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Install ROB pipework access lid using Multifunction Manipulator | Operation | 5.16 | 263.8101 | Install Lower Port Pipework Access Lid | 5.16 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract Multifunction manipulator | Logistics | 0.38 | 264.1901 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Deploy Service Joint System | Logistics | 0.38 | 264.5701 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Extract COB Pipe Module from Cask | Logistics | 0.38 | 264.9501 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Reposition Pipework equipment to the third pipe module | Logistics | 0.53 | 265.4801 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
| Install COB blanket pipework module | Operation | 26.7733 | 292.2534 | Connect Blanket Pipe Module | 26.7733 |  |  |  | N/A | N/A | N/A |  | N/A | COB Installed | 43.9661 | 221.514
| Retract Service Joint System into cask | Logistics | 0.38 | 292.6334 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Deploy Multifunction Manipulator | Logistics | 0.38 | 293.0134 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Install COB pipework access lid using Multifunction Manipulator | Operation | 5.16 | 298.1734 | Install Lower Port Pipework Access Lid | 5.16 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract Multifunction manipulator | Logistics | 0.38 | 298.5534 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Un-Dock Outboard Pipework Module Cask | Logistics | 2.3 | 300.8534 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
Install Right Divertor Cassette | Dock Cassette Handling Cask | Logistics | 1.9 | 302.7534 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Inboard Pipework Cask Stored; Cassette Transport Cask Prepared; Right Divertor Cassette Exported; Cassette Transport Cask Moved to Lower Port | 198.0273 | 102.8261
| Deploy Cassette Handling Equipment | Logistics | 0.38 | 303.1334 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Install Right Divertor cassette | Operation | 0.95 | 304.0834 | Install Peripheral Divertor Cassette | 0.95 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract Cassette Handling Equipment | Logistics | 0.38 | 304.4634 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Un-Dock Empty Right Cassette Transport Cask | Logistics | 2.3 | 306.7634 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
Install Left Divertor Cassette | Dock Divertor Handling Cask | Logistics | 1.9 | 308.6634 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Outboard Pipework Cask Stored; Cassette Transport Cask Prepared; Left Divertor Cassette Exported; Cassette Transport Cask Moved to Lower Port | 302.4449 | 4.3185
| Deploy Cassette Handling Equipment | Logistics | 0.38 | 309.0434 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Install Left Divertor cassette | Operation | 0.95 | 309.9934 | Install Peripheral Divertor Cassette | 0.95 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract Cassette Handling Equipment | Logistics | 0.38 | 310.3734 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Un-Dock Empty Left Cassette Transport Cask | Logistics | 2.3 | 312.6734 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
Install Central Divertor Cassette | Dock Divertor Handling Cask | Logistics | 1.9 | 314.5734 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Empty Cassette Transporter Moved to AMF; Central Divertor Cassette Exported; Cassette Transport Cask Move to Lower Port | 312.3916 | 0.28185
| Deploy Cassette Handling Equipment | Logistics | 0.38 | 314.9534 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Install Right Divertor cassette | Operation | 0.95 | 315.9034 | Install Central Divertor Cassette | 0.95 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract Cassette Handling Equipment | Logistics | 0.38 | 316.2834 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Un-Dock Empty Central Divertor Transport Cask | Logistics | 2.3 | 318.5834 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
Install Divertor Cooling Pipework Modules | Dock Service Joint System Cask | Logistics | 1.9 | 320.4834 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Cassette Transport Cask Stored; Divertor Pipework Modules Collected and Prepared; Pipework Modules Moved to Lower Port | 314.9871 | 3.5963
| Deploy Service Joint System | Logistics | 0.38 | 320.8634 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Extract Right Divertor Pipework Module from Cask | Logistics | 0.38 | 321.2434 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Install Right Divertor Blanket Pipe Module | Operation | 16.9651 | 338.2085 | Connect Divertor Pipe module | 16.9651 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Extract Pipework Module from Cask | Logistics | 0.38 | 338.5885 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Reposition Pipework equipment to the second location | Logistics | 0.53 | 339.1185 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
| Install LOB blanket pipework module | Operation | 16.9651 | 356.0835 | Connect Divertor Pipe module | 16.9651 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Extract third Pipe Module from Cask | Logistics | 0.38 | 356.4635 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Reposition Pipework equipment to the third pipe module | Logistics | 0.53 | 356.9935 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
| Install ROB blanket pipework module | Operation | 16.9651 | 373.9586 | Connect Divertor Pipe module | 16.9651 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract Service Joint System into cask | Logistics | 0.38 | 374.3386 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Deploy Multifunction Manipulator | Logistics | 0.38 | 374.7186 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Install Centre Cassette pipework access lid using Multifunction Manipulator | Operation | 5.16 | 379.8786 | Install Lower Port Pipework Access Lid | 5.16 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Install Left Cassette pipework access lid using Multifunction Manipulator | Operation | 5.16 | 385.0386 | Install Lower Port Pipework Access Lid | 5.16 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Install Right Cassette pipework access lid using Multifunction Manipulator | Operation | 5.16 | 390.1986 | Install Lower Port Pipework Access Lid | 5.16 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract Multifunction manipulator | Logistics | 0.38 | 390.5786 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Un-Dock Empty Divertor Pipe Module Cask | Logistics | 2.3 | 392.8786 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
Install in-port Shielding modules | Dock shielding module cask | Logistics | 1.9 | 394.7786 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Store Cassette Transport Cask; Collect shielding modules cask; Move shielding modules to Lower Port | 320.4193 | 72.4592
| Deploy shielding handling system | Logistics | 0.38 | 395.1586 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Install shielding modules | Operation | 4.35 | 399.5086 | Connect shielding modules | 4.35 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract handling system into cask | Logistics | 0.38 | 399.8886 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Un-Dock empty shielding module cask | Logistics | 2.3 | 402.1886 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
Install vacuum pumping assembly | Dock vacuum pumping cask | Logistics | 1.9 | 404.0886 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Store Divertor pipe work cask; Collect vacuum pumping cask; Move vacuum pumping cask to Lower Port | N/A | N/A
| Deploy vacuum pumping handling system | Logistics | 0.38 | 404.4686 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Install pumping assembly in the port | Operation | 4.5 | 408.9686 | Lift pumping assembly into port | 4.5 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract vacuum pumping handling system | Logistics | 0.38 | 409.3486 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Deploy Multifunction Manipulator | Logistics | 0.38 | 409.7286 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Connect pumping system services with multifunction manipulator | Operation | 6.9944 | 416.723 | connect vacuum pumping system | 6.9944 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract Multifunction manipulator | Logistics | 0.38 | 417.103 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Un-Dock Vacuum pumping cask and move to AMF | Logistics | 2.3 | 419.403 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock Cask | 2.3 |  | N/A | N/A
Install in-port diagnostics | Dock Diagnostic maintenance cask | Logistics | 1.9 | 421.303 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Store Shielding Module Cask; Collect diagnostic maintenance Cask; Move Threshold Rail Cask to Lower Port | 404.0245 | 15.3785
| Deploy diagnostic maintenance system | Logistics | 0.38 | 421.683 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Install diagnostic maintenance systems | Operation | 8.8139 | 430.4969 | Connect Diagnostic services | 8.8139 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract diagnostic system handling system | Logistics | 0.38 | 430.8769 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Un-Dock diagnostic maintenance cask | Logistics | 2.3 | 433.1769 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
Remove Port Threshold Support Rails | Dock Threshold Cask | Logistics | 1.9 | 435.0769 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Store Shielding Module Cask; Collect Threshold Rail Cask; Move Threshold Rail Cask to Lower Port | N/A | N/A
| Deploy Multifunction Manipulator | Logistics | 0.38 | 435.4569 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| remove fixations and store in cask with multifunction manipulator | Operation | 8.1139 | 443.5708 | Remove Threshold Rails | 8.1139 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| recovery multifunction manipulator | Logistics | 0.38 | 443.9508 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Deploy rail handling system | Logistics | 0.38 | 444.3308 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Remove threshold rails and store in cask | Logistics | 0.38 | 444.7108 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Un-dock cask | Logistics | 2.3 | 447.0108 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
Install Vacuum closure Plate | Dock Lower Port Plate Cask | Logistics | 1.9 | 448.9108 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Store vacuum pumping cask; Collect vacuum closure plate cask; Move vacuum closure plate cask to Lower Port | N/A | N/A
| Deploy Lower Port Plate Equipment | Logistics | 0.38 | 449.2908 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Install Vacuum Closure Plate | Operation | 1.2167 | 450.5075 | Insert Vacuum Closure Plate | 1.2167 |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | N/A |  | N/A | N/A
| Fasten Port Closure Fixtures | Operation | 8.0667 | 458.5741 | Install Vacuum Closure Plate | 8.0667 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract Inner Port Equipment into Transport Cask | Logistics | 0.38 | 458.9541 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
Perform Health Physics Checks | Deploy Port Inspection System | Logistics | 0.38 | 459.3341 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 | Store Threshold rail cask; Collect Bioshield Plug interface hardware & Bioshield Plug | 395.526 | 63.4281
| Perform health physics checks | Operation | 6.7722 | 466.1064 | Perform Health Physics Checks | 6.7722 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Recovery Port Inspection System | Logistics | 0.38 | 466.4864 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Un-Dock Vacuum Closure cask and move to AMF | Logistics | 2.3 | 468.7864 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
Seal Lower Port Bioshield | Collect Bioshield Plug Attachment | Logistics | 0.58 | 469.3664 |  | N/A |  |  |  | N/A | N/A | N/A | Collect interface hardware | 0.58 |  | N/A | N/A
| Move Cask Transporter A to Lower Port | Movement | 0.23148 | 469.5978 |  | N/A | Cask Transporter (Empty Cask) | AMF Equipment Issue | Lower Port | 50 | 0.06 | 0.23148 |  | N/A |  | N/A | N/A
| Seal Port Plug | Operation | 0.9 | 470.4978 | Seal Lower Port Bioshield | 0.9 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
Divertor Installation Complete | End Time |  |  | 192.1722
| Operational Time |  |  | 134.2863 | 69.88%
| Logistical Time |  |  | 56.18 | 29.23%
| Movement Time |  |  | 0.23148 | 0.1205%
Hardware Installation Complete | End Time |  |  | 470.4978
| Operational Time |  |  | 391.2019 | 83.15%
| Logistical Time |  |  | 77.59 | 16.49%
| Movement Time |  |  | 0.23148 | 0.0492%
Divertor Maintenance Cycle Complete | End Time |  |  | 358.0926
| Operational Time |  |  | 238.8786 | 66.71%
| Logistical Time |  |  | 110.79 | 30.94%
| Movement Time |  |  | 0.87963 | 0.2456%
Full Maintenance Cycle Complete | End Time |  |  | 676.0525
| Operational Time |  |  | 514.6284 | 76.12%
| Logistical Time |  |  | 153 | 22.63%
| Movement Time |  |  | 0.87963 | 0.1301%

## Lower Cask Dependencies (hidden)
[5 empty] | Operations |  | Movement | [5 empty] | Logistics
Group | Activity | Activity Type | Time (h) | Cumulative | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h)
Vacuum Closure Cask Prepared; Port Plate Equipment Cask Moved to Lower Port | Cassette Removal Required | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Collect Port Plate Cask | Logistics | 0.88 | 0.88 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware from the AMF | 0.88
| Un-dock cask | Logistics | 2.3 | 3.18 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Move Port Plate Cask to Lower Port | Movement | 0.69444 | 3.8744 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Vacuum Closure Cask Prepared; Port Plate Equipment Cask Moved to Lower Port | Total | 0 | 3.8744 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Bioshield interface hardware Stored; Port Threshold Cask collected; Port Threshold Cask Moved to Lower Port | Store Bioshield | Trigger | 0 | 2.7081 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter to AMF Hardware Receipt | Movement | 0.23148 | 2.9396 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Dock cask | Logistics | 1.9 | 4.8396 |  | N/A |  |  |  | N/A | N/A | N/A | Dock cask and commission RM systems | 1.9
| Store Port Plate Cask | Logistics | 0.88 | 5.7196 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware in the AMF | 0.88
| Un-dock cask | Logistics | 2.3 | 8.0196 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 8.0474 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Dock cask | Logistics | 1.9 | 9.9474 |  | N/A |  |  |  | N/A | N/A | N/A | Dock cask and commission RM systems | 1.9
| Collect Port Threshold Cask | Logistics | 0.78 | 10.7274 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78
| Un-dock cask | Logistics | 2.3 | 13.0274 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Move Port Threshold Cask to Lower Port | Movement | 0.69444 | 13.7219 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Bioshield interface hardware Stored; Port Threshold Cask collected; Port Threshold Cask Moved to Lower Port | Total | 0 | 13.7219 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Vacuum Closure Cask Stored; Diagnostic Maintenance Cask Collected; Diagnostic Maintenance Cask moved to Lower Port | Un-Dock Vacuum Closure cask and move to AMF | Trigger | 0 | 58.4633 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter to AMF Hardware Receipt | Movement | 0.23148 | 58.6948 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Cassette Transport Cask | Logistics | 0.58 | 59.2748 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 59.3026 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Outboard Pipework Cask | Logistics | 0.78 | 60.0826 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78
| Move Outboard Pipework Cask to Lower Port | Movement | 0.69444 | 60.777 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Vacuum Closure Cask Stored; Diagnostic Maintenance Cask Collected; Diagnostic Maintenance Cask moved to Lower Port | Total | 0 | 60.777 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Port Threshold Cask Stored; Vacuum pumping cask prepared; vacuum pumping cask Moved to Lower Port | Cassette Removal Required | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter to AMF Hardware Receipt | Movement | 0.23148 | 0.23148 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Port Threshold Cask | Logistics | 0.58 | 0.81148 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 0.83926 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Dock cask | Logistics | 1.9 | 2.7393 |  | N/A |  |  |  | N/A | N/A | N/A | Dock cask and commission RM systems | 1.9
| Collect Vacuum Pumping Cask | Logistics | 0.78 | 3.5193 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78
| Un-dock cask | Logistics | 2.3 | 5.8193 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Move Vaccum Pumping Cask to Lower Port | Movement | 0.69444 | 6.5137 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Port Threshold Cask Stored; Vacuum pumping cask prepared; vacuum pumping cask Moved to Lower Port | Total | 0 | 6.5137 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Diagnostic Maintenance Cask Stored; shielding module cask collected; shielding module cask moved to Lower Port | Un-dock diagnostic maintenance cask | Trigger | 0 | 80.6469 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter to AMF Hardware Receipt | Movement | 0.23148 | 80.8784 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Dock cask | Logistics | 1.9 | 82.7784 |  | N/A |  |  |  | N/A | N/A | N/A | Dock cask and commission RM systems | 1.9
| Store Diagnostic maintenance cask | Logistics | 0.88 | 83.6584 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware in the AMF | 0.88
| Un-dock cask | Logistics | 2.3 | 85.9584 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Store Casks | Logistics | 0.58 | 86.5384 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 86.5662 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Divertor pipework cask | Logistics | 0.88 | 87.4462 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware from the AMF | 0.88
| Move Divertor pipework Cask to Lower Port | Movement | 0.69444 | 88.1406 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Diagnostic Maintenance Cask Stored; shielding module cask collected; shielding module cask moved to Lower Port | Total | 0 | 88.1406 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Vaccum Pumping Cask Stored; Divertor Pipework Cask Prepared; Divertor Pipework Cask Moved to Lower Port | Un-Dock Vacuum pumping cask and move to AMF | Trigger | 0 | 98.2114 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter to AMF Hardware Receipt | Movement | 0.23148 | 98.4429 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Dock cask | Logistics | 1.9 | 100.3429 |  | N/A |  |  |  | N/A | N/A | N/A | Dock cask and commission RM systems | 1.9
| Store Port Plate Cask | Logistics | 0.88 | 101.2229 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware in the AMF | 0.88
| Un-dock cask | Logistics | 2.3 | 103.5229 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 103.5506 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Store Port Plate | Logistics | 0.58 | 104.1306 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Collect Cassette Transport Cask | Logistics | 0.78 | 104.9106 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78
| Move Cassette Transport Cask to Lower Port | Movement | 0.69444 | 105.6051 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Vaccum Pumping Cask Stored; Divertor Pipework Cask Prepared; Divertor Pipework Cask Moved to Lower Port | Total | 0 | 105.6051 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Divertor Pipework Modules Stored; Cassette Transport Cask Prepared; Cassette Transport Cask Moved to Lower Port | Un-Dock Divertor Pipework Module Cask | Trigger | 0 | 135.5401 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter to AMF Hardware Receipt | Movement | 0.23148 | 135.7715 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Dock cask | Logistics | 1.9 | 137.6715 |  | N/A |  |  |  | N/A | N/A | N/A | Dock cask and commission RM systems | 1.9
| Store Divertor Pipework Modules | Logistics | 0.88 | 138.5515 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware in the AMF | 0.88
| Un-dock cask | Logistics | 2.3 | 140.8515 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 140.8793 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Store Cask | Logistics | 0.58 | 141.4593 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Collect Cassette Transport Cask | Logistics | 0.78 | 142.2393 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78
| Move Cassette Transport Cask to Lower Port | Movement | 0.69444 | 142.9338 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Divertor Pipework Modules Stored; Cassette Transport Cask Prepared; Cassette Transport Cask Moved to Lower Port | Total | 0 | 142.9338 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Central Cassette Stored; Cassette Transport Cask Moved to Lower Port | Un-Dock Full Central Cassette Transport Cask | Trigger | 0 | 149.7767 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter to AMF Hardware Receipt | Movement | 0.69444 | 150.4712 |  | N/A | Cask Transporter (Loaded) | Lower Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Dock cask | Logistics | 1.9 | 152.3712 |  | N/A |  |  |  | N/A | N/A | N/A | Dock cask and commission RM systems | 1.9
| Store Central Cassette Cask | Logistics | 0.58 | 152.9512 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Un-dock cask | Logistics | 2.3 | 155.2512 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 155.279 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Dock cask | Logistics | 1.9 | 157.179 |  | N/A |  |  |  | N/A | N/A | N/A | Dock cask and commission RM systems | 1.9
| Collect Cassette Transport Cask | Logistics | 0.78 | 157.959 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78
| Un-dock cask | Logistics | 2.3 | 160.259 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Move Cassette Transport Cask to Lower Port | Movement | 0.23148 | 160.4904 |  | N/A | Cask Transporter (Empty Cask) | AMF Equipment Issue | Lower Port | 50 | 0.06 | 0.23148 |  | N/A
| Central Cassette Stored; Cassette Transport Cask Moved to Lower Port | Total | 0 | 160.4904 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Left Divertor Cassette Stored; Cassette Transport Cask Stored; Outboard Pipework Cask Prepared; Outboard Pipework Cask moved to Lower Port | Un-Dock Left Cassette Transport Cask | Trigger | 0 | 155.5867 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter to AMF Hardware Receipt | Movement | 0.23148 | 155.8182 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Cassette Transport Cask | Logistics | 0.58 | 156.3982 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 156.426 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Outboard Pipework Cask | Logistics | 0.78 | 157.206 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78
| Move Outboard Pipework Cask to Lower Port | Movement | 0.69444 | 157.9004 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Left Divertor Cassette Stored; Cassette Transport Cask Stored; Outboard Pipework Cask Prepared; Outboard Pipework Cask moved to Lower Port | Total | 0 | 157.9004 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Right Divertor Cassette Stored; Cassette Transport Cask Stored; Inboard Pipework Cask Prepared; Inboard Pipework Cask moved to Lower Port | Un-Dock Full Right Cassette Transport Cask | Trigger | 0 | 165.9204 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter to AMF Hardware Receipt | Movement | 0.23148 | 166.1519 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Dock cask | Logistics | 1.9 | 168.0519 |  | N/A |  |  |  | N/A | N/A | N/A | Dock cask and commission RM systems | 1.9
| Store Cassette Transport Cask | Logistics | 0.58 | 168.6319 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 168.6597 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Inboard Pipework Cask | Logistics | 0.78 | 169.4397 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78
| Move Inboard Pipework Cask to Lower Port | Movement | 0.69444 | 170.1341 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Right Divertor Cassette Stored; Cassette Transport Cask Stored; Inboard Pipework Cask Prepared; Inboard Pipework Cask moved to Lower Port | Total | 0 | 170.1341 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Outboard Pipework Cask Stored; Inner Port Pipework Cask Prepared; Inner Port Pipework Cask Moved to Lower Port | Un-Dock Outboard Pipe Module Cask | Trigger | 0 | 187.9905 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter to AMF Hardware Receipt | Movement | 0.23148 | 188.222 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Dock cask | Logistics | 1.9 | 190.122 |  | N/A |  |  |  | N/A | N/A | N/A | Dock cask and commission RM systems | 1.9
| Store Outboard Pipework Modules | Logistics | 0.88 | 191.002 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware in the AMF | 0.88
| Un-dock cask | Logistics | 2.3 | 193.302 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Store Casks | Logistics | 0.58 | 193.882 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 193.9098 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Inner Port Pipework Cask | Logistics | 0.88 | 194.7898 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware from the AMF | 0.88
| Move Inner Port Pipework Cask to Lower Port | Movement | 0.69444 | 195.4842 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Outboard Pipework Cask Stored; Inner Port Pipework Cask Prepared; Inner Port Pipework Cask Moved to Lower Port | Total | 0 | 195.4842 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
N/A
N/A
N/A
N/A
Inspection Cask Collected; Inspection Cask Moved to Lower Port | Cassette Installation Required | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Collect Inspection Cask | Logistics | 0.78 | 0.78 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78
| Move Inspection Cask to Lower Port | Movement | 0.69444 | 1.4744 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Inspection Cask Collected; Inspection Cask Moved to Lower Port | Total | 0 | 1.4744 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
COB Installed | Cassette Installation Required | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Lower Port COB pipework joint cut and pipework removed | Operation | 43.9661 | 43.9661 | Install COB Blanket Segment | 43.9661 |  |  |  | N/A | N/A | N/A |  | N/A
| COB Installed | Total | 0 | 43.9661 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Installed | Cassette Installation Required | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Lower Port LOB pipework joint cut and pipework removed | Operation | 38.9417 | 38.9417 | Install LOB Blanket Segment | 38.9417 |  |  |  | N/A | N/A | N/A |  | N/A
| LOB Installed | Total | 0 | 38.9417 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Installed | Cassette Installation Required | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Lower Port ROB pipework joint cut and pipework removed | Operation | 33.9172 | 33.9172 | Install ROB Blanket Segment | 33.9172 |  |  |  | N/A | N/A | N/A |  | N/A
| ROB Installed | Total | 0 | 33.9172 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Installed | Cassette Installation Required | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Lower Port LIB pipework joint cut and pipework removed | Operation | 28.8928 | 28.8928 | Install LIB Blanket Segment | 28.8928 |  |  |  | N/A | N/A | N/A |  | N/A
| LIB Installed | Total | 0 | 28.8928 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Installed | Cassette Installation Required | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Lower Port RIB pipework joint cut and pipework removed | Operation | 23.8683 | 23.8683 | Install RIB Blanket Segment | 23.8683 |  |  |  | N/A | N/A | N/A |  | N/A
| RIB Installed | Total | 0 | 23.8683 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Inner Port Pipework Collected and Prepared; Inner Port Pipework Cask Moved to Lower Port | Cassette Installation Required | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Collect Port Plate & Pipework Cask | Logistics | 0.78 | 0.78 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78
| Move Port Plate & Pipework Cask to Lower Port | Movement | 0.69444 | 1.4744 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Inner Port Pipework Collected and Prepared; Inner Port Pipework Cask Moved to Lower Port | Total | 0 | 1.4744 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Inspection Cask Stored; Inboard Port Pipework Cask Prepared; Inboard Port Pipework Cask Moved to Lower Port | Un-Dock Inspection Cask | Trigger | 0 | 22.5278 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move cask to AMF equipment reciept | Movement | 0.69444 | 2.1689 |  | N/A | Cask Transporter (Loaded) | Lower Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store cask | Logistics | 0.58 | 2.0544 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.092593 | 22.6204 |  | N/A | Cask Transporter (Empty Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.06 | 0.092593 |  | N/A
| Collect Right Cassette Transport Cask | Logistics | 0.78 | 23.4004 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78
| Move Pipework Cask to Lower Port | Movement | 0.69444 | 24.0948 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Inspection Cask Stored; Inboard Port Pipework Cask Prepared; Inboard Port Pipework Cask Moved to Lower Port | Total | 0 | 24.0948 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Inner Port Pipework Cask Stored; Outboard Port Pipework Cask Prepared; Outboard Port Pipework Cask Moved to Lower Port | Un-Dock Empty Inner Port Pipework Cask | Trigger | 0 | 135.4371 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Inner Port Pipework Cask to AMF Equipment Receipt | Movement | 0.23148 | 135.6685 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Inner Port Pipework Cask | Logistics | 0.58 | 136.2485 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 136.2763 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Right Cassette Transport Cask | Logistics | 0.78 | 137.0563 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78
| Move Pipework Cask to Lower Port | Movement | 0.69444 | 137.7508 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Inner Port Pipework Cask Stored; Outboard Port Pipework Cask Prepared; Outboard Port Pipework Cask Moved to Lower Port | Total | 0 | 137.7508 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Inboard Pipework Cask Stored; Cassette Transport Cask Prepared; Right Divertor Cassette Exported; Cassette Transport Cask Moved to Lower Port | Un-Dock Inboard Pipe Module Cask | Trigger | 0 | 195.6136 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Inboard Pipework Cask to AMF Equipment Receipt | Movement | 0.23148 | 195.8451 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Issue | 50 | 0.06 | 0.23148 |  | N/A
| Store Inboard Pipework Cask | Logistics | 0.58 | 196.4251 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Move cask transporter to AMF equipment Issue | Movement | 0.027778 | 196.4529 |  | N/A | Cask Transporter (No Cask) | AMF equipment Receipt | AMF equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Dock cask | Logistics | 1.9 | 198.3251 |  | N/A |  |  |  | N/A | N/A | N/A | Dock cask and commission RM systems | 1.9
| Collect Right Cassette Transport Cask | Logistics | 0.88 | 197.3329 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware from the AMF | 0.88
| Un-dock cask | Logistics | 2.3 | 200.6251 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Move Pipework Cask to Lower Port | Movement | 0.69444 | 198.0273 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Inboard Pipework Cask Stored; Cassette Transport Cask Prepared; Right Divertor Cassette Exported; Cassette Transport Cask Moved to Lower Port | Total | 0 | 198.0273 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Outboard Pipework Cask Stored; Cassette Transport Cask Prepared; Left Divertor Cassette Exported; Cassette Transport Cask Moved to Lower Port | Un-Dock Outboard Pipework Module Cask | Trigger | 0 | 300.8534 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Inboard Pipework Cask to AMF Equipment Receipt | Movement | 0.23148 | 301.0849 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Issue | 50 | 0.06 | 0.23148 |  | N/A
| Store Inboard Pipework Cask | Logistics | 0.58 | 301.6649 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Move to AMF equipment Issue | Movement | 0 | 301.6649 |  | N/A | Cask Transport (Unloaded) | AMF equipment Receipt | AMF equipment Issue | 20 | N/A | Error |  | N/A
| Collect Left Cassette Transport Cask | Logistics | 0.78 | 302.4449 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78
| Outboard Pipework Cask Stored; Cassette Transport Cask Prepared; Left Divertor Cassette Exported; Cassette Transport Cask Moved to Lower Port | Total | 0 | 302.4449 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Cassette Transport Cask Stored; Outboard Blanket Pipework Modules Collected and Prepared; Outboard Blanket Pipework Modules Moved to Lower Port | Un-Dock Empty Left Cassette Transport Cask | Trigger | 0 | 312.6734 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter to AMF Equipment Receipt | Movement | 0.23148 | 312.9049 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Cassette Transport Cask | Logistics | 0.58 | 313.4849 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 313.5127 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Lower Port Pipework Cask | Logistics | 0.78 | 314.2927 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78
| Move Lower Port Pipework Cask to Lower Port | Movement | 0.69444 | 314.9871 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Cassette Transport Cask Stored; Outboard Blanket Pipework Modules Collected and Prepared; Outboard Blanket Pipework Modules Moved to Lower Port | Total | 0 | 314.9871 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Inner Port Pipework Cask Stored; Inboard Blanket Pipework Modules Collected and Prepared; Inboard Blanket Pipework Modules Moved to Lower Port | Un-Dock Inboard Pipe Module Cask | Trigger | 0 | 195.6136 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter to AMF Equipment Receipt | Movement | 0.23148 | 195.8451 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Cassette Transport Cask | Logistics | 0.58 | 196.4251 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 196.4529 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Port Plate & Pipework Cask | Logistics | 0.78 | 197.2329 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78
| Move Port Plate & Pipework Cask to Lower Port | Movement | 0.69444 | 197.9273 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Inner Port Pipework Cask Stored; Inboard Blanket Pipework Modules Collected and Prepared; Inboard Blanket Pipework Modules Moved to Lower Port | Total | 0 | 197.9273 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Empty Cassette Transporter Moved to AMF; Central Divertor Cassette Exported; Cassette Transport Cask Move to Lower Port | Un-Dock Empty Right Cassette Transport Cask | Trigger | 0 | 306.7634 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.23148 | 306.9949 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Issue | 50 | 0.06 | 0.23148 |  | N/A
| Dock cask | Logistics | 1.9 | 308.8949 |  | N/A |  |  |  | N/A | N/A | N/A | Dock cask and commission RM systems | 1.9
| Collect Right Divertor Cassette | Logistics | 0.78 | 309.6749 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78
| Un-dock cask | Logistics | 2.3 | 311.9749 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Move Cassette Transport cask to Lower Port | Movement | 0.41667 | 312.3916 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | Lower Port | 30 | 0.02 | 0.41667 |  | N/A
| Empty Cassette Transporter Moved to AMF; Central Divertor Cassette Exported; Cassette Transport Cask Move to Lower Port | Total | 0 | 312.3916 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Cassette Transport Cask Stored; Divertor Pipework Modules Collected and Prepared; Pipework Modules Moved to Lower Port | Un-Dock Empty Left Cassette Transport Cask | Trigger | 0 | 312.6734 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter to AMF Equipment Receipt | Movement | 0.23148 | 312.9049 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Cassette Transport Cask | Logistics | 0.58 | 313.4849 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 313.5127 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Divertor Pipework Cask | Logistics | 0.78 | 314.2927 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78
| Move Port Plate & Pipework Cask to Lower Port | Movement | 0.69444 | 314.9871 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Cassette Transport Cask Stored; Divertor Pipework Modules Collected and Prepared; Pipework Modules Moved to Lower Port | Total | 0 | 314.9871 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Store Cassette Transport Cask; Collect shielding modules cask; Move shielding modules to Lower Port | Un-Dock Empty Central Divertor Transport Cask | Trigger | 0 | 318.5834 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter to AMF Equipment Receipt | Movement | 0.23148 | 318.8149 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Cassette Transport Cask | Logistics | 0.58 | 319.3949 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 319.4227 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Port shielding module cask | Logistics | 0.58 | 320.0027 |  | N/A |  |  |  | N/A | N/A | N/A | Collect interface hardware | 0.58
| Move shielding modules to port | Movement | 0.41667 | 320.4193 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | Lower Port | 30 | 0.02 | 0.41667 |  | N/A
| Store Cassette Transport Cask; Collect shielding modules cask; Move shielding modules to Lower Port | Total | 0 | 320.4193 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Store Divertor pipe work cask; Collect vaccum pumping cask; Move vacuum pumping cask to Lower Port | Un-Dock Empty Divertor Pipe Module Cask | Trigger | 0 | 392.8786 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter to AMF Equipment Receipt | Movement | 0.23148 | 393.1101 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store divertor pipework cask | Logistics | 0.58 | 393.6901 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 393.7178 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect vacuum pumping cask | Logistics | 0.58 | 394.2978 |  | N/A |  |  |  | N/A | N/A | N/A | Collect interface hardware | 0.58
| Move cask to Lower Port | Movement | 0.41667 | 394.7145 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | Lower Port | 30 | 0.02 | 0.41667 |  | N/A
| Store Divertor pipe work cask; Collect vaccum pumping cask; Move vacuum pumping cask to Lower Port | Total | 0 | 394.7145 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Store Shielding Module Cask; Collect diagnostic maintenance Cask; Move Threshold Rail Cask to Lower Port | Un-Dock empty shielding module cask | Trigger | 0 | 402.1886 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter to AMF Equipment Receipt | Movement | 0.23148 | 402.4201 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Shielding Module Cask | Logistics | 0.58 | 403.0001 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 403.0278 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect disangostic maintenance cask | Logistics | 0.58 | 403.6078 |  | N/A |  |  |  | N/A | N/A | N/A | Collect interface hardware | 0.58
| Move shielding modules to port | Movement | 0.41667 | 404.0245 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | Lower Port | 30 | 0.02 | 0.41667 |  | N/A
| Store Shielding Module Cask; Collect diagnostic maintenance Cask; Move Threshold Rail Cask to Lower Port | Total | 0 | 404.0245 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Store vacuum pumping cask; Collect vaccum closure plate cask; Move vacuum closure plate cask to Lower Port | Un-Dock Empty Divertor Pipe Module Cask | Trigger | 0 | 392.8786 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter to AMF Equipment Receipt | Movement | 0.23148 | 393.1101 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store divertor pipework cask | Logistics | 0.58 | 393.6901 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 393.7178 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect vacuum pumping cask | Logistics | 0.58 | 394.2978 |  | N/A |  |  |  | N/A | N/A | N/A | Collect interface hardware | 0.58
| Move cask to Lower Port | Movement | 0.41667 | 394.7145 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | Lower Port | 30 | 0.02 | 0.41667 |  | N/A
| Store vacuum pumping cask; Collect vaccum closure plate cask; Move vacuum closure plate cask to Lower Port | Total | 0 | 394.7145 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Store Threshold rail cask; Collect Bioshield Plug interface hardware & Bioshield Plug | Un-Dock Empty Divertor Pipe Module Cask | Trigger | 0 | 392.8786 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter to AMF Equipment Receipt | Movement | 0.23148 | 393.1101 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Threshold rail cask | Logistics | 0.58 | 393.6901 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 393.7178 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Bioshield interface hardware | Logistics | 0.58 | 394.2978 |  | N/A |  |  |  | N/A | N/A | N/A | Collect interface hardware | 0.58
| Move Lower Port Pipework Cask to bioshield stillage | Movement | 0.23148 | 394.5293 |  | N/A | Cask Transporter (Empty Cask) | AMF Equipment Issue | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Collect Bioshield plug | Logistics | 0.58 | 395.1093 |  | N/A |  |  |  | N/A | N/A | N/A | Collect interface hardware | 0.58
| Move Bioshield Plug to Lower Port | Movement | 0.41667 | 395.526 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | Lower Port | 30 | 0.02 | 0.41667 |  | N/A
| Store Threshold rail cask; Collect Bioshield Plug interface hardware & Bioshield Plug | Total | 0 | 395.526 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A

## Lower Cask Movement & Logistics (hidden)
Logistical Activities |  |  | Equipment Speed
Activity | Sub activity | Time | Equipment | Speed (m/s)
Deploy Equipment | Deploy Equipment | 0 | Cask Transporter (Loaded) | 0.02
Collect interface hardware | Position | 0.28 | Cask Transporter (No Cask) | 0.2
|  |  | Cask Transporter (Empty Cask) | 0.06
| Lower onto storage location | 0.2 | Multifunction Manipulator | 0.02
| Make Connections/Commission | 0.1 | Closure Plate Disconnection Equipment | 0.02
| Collect interface hardware | 0.58 | Closure Plate Connection Equipment | 0.02
Store PP Hardware in the AMF | Position | 0.28
| Lower onto storage location | 0.2 | Distance Table
| Release fastenings | 0.2 | To: From : | Equipment Stillage | Lower Port | Hardware Stillage | AMF Equipment Issue | AMF Equipment Receipt | AMF Hardware Receipt | AMF Hardware Issue
| Retract RM system | 0.2 | Equipment Stillage |  | 15 | 10 | 50 | 50 | 50 | 50
| Store PP Hardware in the AMF | 0.88 | Lower Port | 15 |  | 30 | 50 | 50 | 50 | 50
Store Equipment / Hardware Cask | Position | 0.28 | Hardware Stillage | 10 | 30 |  | 50 | 50 | 50 | 50
| Lower onto storage location | 0.2 | AMF Equipment Issue | 50 | 50 | 50 |  | 20 | 20 | 20
| Release Connections/Commission | 0.1 | AMF Equipment Receipt | 50 | 50 | 50 | 20 |  | 20 | 20
| Store Equipment / Hardware Cask | 0.58 | AMF Hardware Receipt | 50 | 50 | 50 | 20 | 20 |  | 10
Collect PP hardware from the AMF | Position | 0.28 | AMF Hardware Issue | 50 | 50 | 50 | 20 | 20 | 10
| Engage lifting fastenings | 0.2
| Lift from storage location | 0.2
| Move PP into the cask | 0.2
| Collect PP hardware from the AMF | 0.88
Collect Equipment / Hardware Cask | Position | 0.28
| Connect fastenings | 0.3
| Lift from storage location | 0.2
| Collect Equipment / Hardware Cask | 0.78
Dock Cask and Commission RM Systems | Dock to interface cask | 0.2
| Connect double lidded door and frame | 0.3
| Connect Cask services | 0.1
| Connect RM System Services | 0.1
| RM System Software Check | 0.2
| RM System Hardware Check | 0.2
| Disconnect door | 0.3
| Store door | 0.5
| Dock Cask and Commission RM Systems | 1.9
Un-Dock Cask | Replace door | 0.5
| Attach to frame | 0.3
| Disconnect door and frame | 0.3
| Disconnect Services | 0.1
| Demonstrate seals | 1
| Undock from interface cask | 0.1
| Un-Dock Cask | 2.3
Deploy Tool / Hardware From Transport Cask | Position Vertical Crane | 0.28
| Make Connections/commission] | 0.1
| Deploy Tool / Hardware From Transport Cask | 0.38
Store Tool / Hardware In Transport Cask | Position in storage location | 0.28
| Break connections | 0.1
| Store Tool / Hardware In Transport Cask | 0.38
Reposition tool within Port | Move tool to new position | 0.33
| Confirm positon within port | 0.1
| Make fine position adjustments | 0.1
| Reposition tool within Port | 0.53
Logistical Activity List
Deploy Equipment
Collect interface hardware
Store PP Hardware in the AMF
Store Equipment / Hardware Cask
Collect PP hardware from the AMF
Dock Cask and Commission RM Systems
Un-Dock Cask
#REF!
Deploy Tool / Hardware From Transport Cask
Store Tool / Hardware In Transport Cask
Reposition tool within Port

## Lower Cask Recovery Scenarios (hidden)
Delay caused by failure and recovery of remote handling equipment
Additional tasks required to recover from failures
General Assumptions:
There are two sorts of process failure considered; failure of a weld and failure of a mechanical connection, both uncovered by failure to pass acceptance criteria
In addition five types of equipment failure are considered; Pipe interface hardware, Overhead Crane, Blanket transporter system, divertor cask system and Multifunction manipulator system
| Single Port | Full DEMO Maintenance
No. Systems | 1 | 1 | 2 | 3 | 4 | 6
Operational contribution | 6.3998 | 115.1961 | 57.5981 | 38.3987 | 31.9989 | 19.1994
Logistical contribution | 23.5356 | 423.64 | 211.82 | 141.2133 | 117.6778 | 70.6067
Idle time due to waiting for dependant operations | 0 | 0 | 0 | 0 | 0 | 0
Expected Delay | 29.9353 | 538.8361 | 269.4181 | 179.612 | 149.6767 | 89.806
Operational contribution | 4.7335 | 85.2028 | 42.6014 | 28.4009 | 23.6674 | 14.2005
Logistical contribution | 17.0021 | 306.037 | 153.0185 | 102.0123 | 85.0103 | 51.0062
Idle time due to waiting for dependant operations | 0 | 0 | 0 | 0 | 0 | 0
Expected Delay | 21.7355 | 391.2398 | 195.6199 | 130.4133 | 108.6777 | 65.2066
Cask Failures during Divertor Maintenance
Assumptions:
Recovery of RHE is completed using standard predetermined procedures. | [16 empty] | Cask Failures during Divertor Maintenance | Single Port | Full Maintenance Campaign
Rare and time consuming special recoveries are not considered | [16 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
[17 empty] | Duration of RM operations (h) | 676.0525 | 12168.9442 | 6084.4721 | 4056.3147 | 3380.2623 | 2028.1574
Failure rate: | 0.009% | [15 empty] | Estimated number of failures, impacting all RM systems equally | 0.060845 | 1.0952 | 0.5476 | 0.36507 | 0.30422 | 0.18253
Failure rate of casks per hour | 0.009% | [15 empty] | Operational contribution | 0.36507 | 6.5712 | 3.2856 | 2.1904 | 1.8253 | 1.0952
|  |  |  | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies |  |  | Logistical contribution | 0.20467 | 3.6841 | 1.8421 | 1.228 | 1.0234 | 0.61402
RH Cask RHE failure (Sub Tasks) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack | Idle time due to waiting for dependant operations | 0 | 0 | 0 | 0 | 0 | 0
Hardware transporter failure detected during maintenance operations | Operation | 0 | 0 | Recovery Operation | N/A |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A | Total Duration of Recovery Tasks | 0.56974 | 10.2554 | 5.1277 | 3.4185 | 2.8487 | 1.7092
Deploy Recovery System into ex-vessel area | Movement | 0.069444 | 0.069444 |  | N/A | Hardware Transporter (no load) | AMF Equipment Issue | Divertor Port | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A
Connect recovery system to transporter payload | Logistics | 1.8 | 1.8694 |  | N/A |  |  |  | N/A | N/A | N/A | Connect recovery system to hardware | 1.8 |  | N/A | N/A
Remove payload from failed transporter using recovery system | Operation | 6 | 7.8694 | Recovery Operation | 6 |  |  |  | N/A | N/A | N/A |  | N/A | Replacement transporter commissioned; moved to port to collect abandoned payload | N/A | N/A
Move replacement transporter to Lower Port | Movement | 0.69444 | 8.5639 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A
Deploy Payload into the port | Logistics | 0.8 | 9.3639 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
| Total |  | 9.3639
Lower Port Cask Transporter failure during full port maintenance
Assumptions:
Recovery of RHE is completed using standard predetermined procedures.
Rare and time consuming special recoveries are not considered
Failure rate: | 0.0111%
Failure rate of RH transporter RHE per hour | 0.0111%
|  |  |  | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies
RH Cask RHE failure (Sub Tasks) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack | Lower Port Cask Transporter failure during full port maintenance | Single Port | Full Maintenance Campaign
Deploy Recovery System into ex-vessel area | Movement | 0.069444 | 0.069444 |  | N/A | Cask Transporter (no cask) | AMF Equipment Issue | Lower Port | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
Dock recovery system to the failed cask | Logistics | 1.9 | 1.9694 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 |  | N/A | N/A | Time taken in a single port | 23.2407 | 23.2407 | 23.2407 | 23.2407 | 23.2407 | 23.2407
Recover failed RHE into cask for replacement | Operation | 3 | 4.9694 | Recovery Operation | 3 |  |  |  | N/A | N/A | N/A | Store Tool in Transport Cask | N/A |  | N/A | N/A | Duration of RM operations (h) | 23.2407 | 418.3333 | 209.1667 | 139.4444 | 116.2037 | 69.7222
Un-dock Recovery system | Logistics | 2.3 | 7.2694 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A | Estimated number of recoveries required | 0.0025797 | 0.046435 | 0.023218 | 0.015478 | 0.012899 | 0.0077392
Un-dock Cask | Logistics | 2.3 | 9.5694 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A | Operational contribution | 0.0077392 | 0.13931 | 0.069653 | 0.046435 | 0.038696 | 0.023218
Move to AMF Hardware Receipt | Movement | 0.69444 | 10.2639 |  | N/A | Cask Transporter (Loaded) | Lower Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A | Logistical contribution | 0.02992 | 0.53857 | 0.26928 | 0.17952 | 0.1496 | 0.089761
Store Failed Cask | Logistics | 0.58 | 10.8439 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware cask | 0.58 |  | N/A | N/A | Idle time due to waiting for dependant operations | 0 | 0 | 0 | 0 | 0 | 0
Issue Replacement Cask | Logistics | 0.78 | 11.6239 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78 |  | N/A | N/A | Total Duration of Recovery Tasks | 0.03766 | 0.67787 | 0.33894 | 0.22596 | 0.1883 | 0.11298
Transport Cask to Lower Port | Movement | 0.69444 | 12.3183 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A
Dock Cask and Commission RM Systems | Logistics | 1.9 | 14.2183 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 |  | N/A | N/A
Deploy Divertor Handling Equipment | Logistics | 0.38 | 14.5983 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Total |  | 14.5983
Multifunction Manipulator failure
Assumptions:
Recovery of Multifunction Manipulator is completed using standard predetermined procedures.
Rare and time consuming special recoveries are not considered
A replacement system (if required) is available on demand from the AMF
Failure rate: | 2%
Failure rate of Multifunction Manipulator per hour | 2%
[17 empty] | Multifunction Manipulator failure | Single Port | Full Maintenance Campaign
|  |  |  | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies |  |  | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
RH Cask RHE failure (Sub Tasks) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack | Duration of Multifunction Manipulator Tasks per port | 87.8419 | 87.8419 | 87.8419 | 87.8419 | 87.8419 | 87.8419
Deploy Recovery System into ex-vessel area | Movement | 0.069444 | 0.069444 |  | N/A | Cask Transporter (no cask) | AMF Equipment Issue | Lower Port | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A | Duration of RM operations (h) | 87.8419 | 1581.155 | 790.5775 | 527.0517 | 439.2097 | 263.5258
Dock recovery system to the failed cask | Logistics | 1.9 | 1.9694 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 |  | N/A | N/A | Estimated number of failures, impacting all RM systems equally | 1.7568 | 31.6231 | 15.8115 | 10.541 | 8.7842 | 5.2705
Recover failed MM into cask for replacement | Operation | 3 | 4.9694 | Recovery Operation | 3 |  |  |  | N/A | N/A | N/A | Store Tool in Transport Cask | N/A |  | N/A | N/A | Operational contribution | 5.2705 | 94.8693 | 47.4346 | 31.6231 | 26.3526 | 15.8115
Un-dock Recovery system | Logistics | 2.3 | 7.2694 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A | Logistical contribution | 20.3764 | 366.7753 | 183.3876 | 122.2584 | 101.882 | 61.1292
Un-dock Cask | Logistics | 2.3 | 9.5694 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A | Idle time due to waiting for dependant operations | 0 | 0 | 0 | 0 | 0 | 0
Move to AMF Hardware Receipt | Movement | 0.69444 | 10.2639 |  | N/A | Cask Transporter (Loaded) | Lower Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A | Total Duration of Recovery Tasks | 25.6469 | 461.6446 | 230.8223 | 153.8815 | 128.2346 | 76.9408
Store Failed Cask | Logistics | 0.58 | 10.8439 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware cask | 0.58 |  | N/A | N/A
Issue Replacement Cask | Logistics | 0.78 | 11.6239 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78 |  | N/A | N/A
Transport Cask to Lower Port | Movement | 0.69444 | 12.3183 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A
Dock Cask and Commission RM Systems | Logistics | 1.9 | 14.2183 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 |  | N/A | N/A
Deploy Divertor Handling Equipment | Logistics | 0.38 | 14.5983 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Total |  | 14.5983
Divertor handling system failure
Assumptions:
Recovery of Divertor handling system is completed using standard predetermined procedures.
Rare and time consuming special recoveries are not considered
A replacement system (if required) is available on demand from the AMF
Failure rate: | 0.501%
Divertor handling system failure per hour | 0.501%
[17 empty] | Divertor handling system failure | Single Port | Full Maintenance Campaign
|  |  |  | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies |  |  | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
RH Cask RHE failure (Sub Tasks) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack | Duration of port hardware removal | 23.22 | 23.22 | 23.22 | 23.22 | 23.22 | 23.22
Deploy Recovery System into ex-vessel area | Movement | 0.069444 | 0.069444 |  | N/A | Cask Transporter (no cask) | AMF Equipment Issue | Lower Port | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A | Duration of port hardware installation | 27.11 | 27.11 | 27.11 | 27.11 | 27.11 | 27.11
Dock recovery system to the failed cask | Logistics | 1.9 | 1.9694 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 |  | N/A | N/A | Duration of RM operations (h) | 50.33 | 905.94 | 452.97 | 301.98 | 251.65 | 150.99
Recover failed MM into cask for replacement | Operation | 3 | 4.9694 | Recovery Operation | 3 |  |  |  | N/A | N/A | N/A | Store Tool in Transport Cask | N/A |  | N/A | N/A | Estimated number of failures, impacting all RM systems equally | 0.25215 | 4.5388 | 2.2694 | 1.5129 | 1.2608 | 0.75646
Un-dock Recovery system | Logistics | 2.3 | 7.2694 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A | Operational contribution | 0.75646 | 13.6163 | 6.8081 | 4.5388 | 3.7823 | 2.2694
Un-dock Cask | Logistics | 2.3 | 9.5694 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A | Logistical contribution | 2.9246 | 52.642 | 26.321 | 17.5473 | 14.6228 | 8.7737
Move to AMF Hardware Receipt | Movement | 0.69444 | 10.2639 |  | N/A | Cask Transporter (Loaded) | Lower Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A | Idle time due to waiting for dependant operations | 0 | 0 | 0 | 0 | 0 | 0
Store Failed Cask | Logistics | 0.58 | 10.8439 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware cask | 0.58 |  | N/A | N/A | Total Duration of Recovery Tasks | 3.681 | 66.2583 | 33.1292 | 22.0861 | 18.4051 | 11.0431
Issue Replacement Cask | Logistics | 0.78 | 11.6239 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78 |  | N/A | N/A
Transport Cask to Lower Port | Movement | 0.69444 | 12.3183 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A
Dock Cask and Commission RM Systems | Logistics | 1.9 | 14.2183 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 |  | N/A | N/A
Deploy Divertor Handling Equipment | Logistics | 0.38 | 14.5983 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Total |  | 14.5983
Cask Failures during Divertor Maintenance
Assumptions:
Recovery of RHE is completed using standard predetermined procedures. | [16 empty] | Cask Failures during Divertor Maintenance | Single Port | Full Maintenance Campaign
Rare and time consuming special recoveries are not considered | [16 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
[17 empty] | Duration of RM operations (h) | 676.0525 | 12168.9442 | 6084.4721 | 4056.3147 | 3380.2623 | 2028.1574
Failure rate: | 0.009% | [15 empty] | Estimated number of failures, impacting all RM systems equally | 0.060845 | 1.0952 | 0.5476 | 0.36507 | 0.30422 | 0.18253
Failure rate of casks per hour | 0.009% | [15 empty] | Operational contribution | 0.36507 | 6.5712 | 3.2856 | 2.1904 | 1.8253 | 1.0952
|  |  |  | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies |  |  | Logistical contribution | 0.20467 | 3.6841 | 1.8421 | 1.228 | 1.0234 | 0.61402
RH Cask RHE failure (Sub Tasks) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack | Idle time due to waiting for dependant operations | 0 | 0 | 0 | 0 | 0 | 0
Hardware transporter failure detected during maintenance operations | Operation | 0 | 0 | Recovery Operation | N/A |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A | Total Duration of Recovery Tasks | 0.56974 | 10.2554 | 5.1277 | 3.4185 | 2.8487 | 1.7092
Deploy Recovery System into ex-vessel area | Movement | 0.069444 | 0.069444 |  | N/A | Hardware Transporter (no load) | AMF Equipment Issue | Divertor Port | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A
Connect recovery system to transporter payload | Logistics | 1.8 | 1.8694 |  | N/A |  |  |  | N/A | N/A | N/A | Connect recovery system to hardware | 1.8 |  | N/A | N/A
Remove payload from failed transporter using recovery system | Operation | 6 | 7.8694 | Recovery Operation | 6 |  |  |  | N/A | N/A | N/A |  | N/A | Replacement transporter commissioned; moved to port to collect abandoned payload | N/A | N/A
Move replacement transporter to Lower Port | Movement | 0.69444 | 8.5639 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A
Deploy Payload into the port | Logistics | 0.8 | 9.3639 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
| Total | 9.3639
Lower Port hardware transporter failure during divertor maintenance
Assumptions:
Recovery of RHE is completed using standard predetermined procedures.
Rare and time consuming special recoveries are not considered
[17 empty] | Lower Port hardware transporter failure during divertor maintenance | Single Port | Full Maintenance Campaign
Failure rate: | 0.0111% | [15 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
Failure rate of RHE per hour | 0.0111% | [15 empty] | Divertor removal operations | 165.9204 | 2986.5679 | 1493.2839 | 995.5226 | 829.6022 | 497.7613
|  |  |  | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies |  |  | Divertor installation operations | 192.1722 | 3459.0998 | 1729.5499 | 1153.0333 | 960.861 | 576.5166
RH Cask RHE failure (Sub Tasks) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack | Duration of RM operations (h) | 358.0926 | 6445.6676 | 3222.8338 | 2148.5559 | 1790.4632 | 1074.2779
Deploy Recovery System into ex-vessel area | Movement | 0.069444 | 0.069444 |  | N/A | Cask Transporter (no cask) | AMF Equipment Issue | Lower Port | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A | Estimated number of failures, impacting all RM systems equally | 0.039748 | 0.71547 | 0.35773 | 0.23849 | 0.19874 | 0.11924
Dock recovery system to the failed cask | Logistics | 1.9 | 1.9694 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 |  | N/A | N/A | Operational contribution | 0.11924 | 2.1464 | 1.0732 | 0.71547 | 0.59622 | 0.35773
Recover failed RHE into cask for replacement | Operation | 3 | 4.9694 | Recovery Operation | 3 |  |  |  | N/A | N/A | N/A | Store Tool in Transport Cask | N/A |  | N/A | N/A | Logistical contribution | 0.36959 | 6.6527 | 3.3263 | 2.2176 | 1.848 | 1.1088
Un-dock Cask | Logistics | 2.3 | 7.2694 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A | Idle time due to waiting for dependant operations | 0 | 0 | 0 | 0 | 0 | 0
Move to AMF Hardware Receipt | Movement | 0.69444 | 7.9639 |  | N/A | Cask Transporter (Loaded) | Lower Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A | Total Duration of Recovery Tasks | 0.48884 | 8.7991 | 4.3995 | 2.933 | 2.4442 | 1.4665
Store Failed Cask | Logistics | 0.58 | 8.5439 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware cask | 0.58 |  | N/A | N/A
Issue Replacement Cask | Logistics | 0.78 | 9.3239 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78 |  | N/A | N/A
Transport Cask to Lower Port | Movement | 0.69444 | 10.0183 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A
Dock Cask and Commission RM Systems | Logistics | 1.9 | 11.9183 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 |  | N/A | N/A
Deploy Divertor Handling Equipment | Logistics | 0.38 | 12.2983 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Total |  | 12.2983
Multifunction Manipulator failure
Assumptions:
Recovery of Multifunction Manipulator is completed using standard predetermined procedures.
Rare and time consuming special recoveries are not considered
A replacement Multifunction Manipulator (if required) is available on demand from the AMF
Failure rate: | 2%
Failure rate of Multifunction Manipulator per hour | 2%
[17 empty] | Multifunction Manipulator failure | Single Port | Full Maintenance Campaign
|  |  |  | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies |  |  | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
RH Cask RHE failure (Sub Tasks) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack | Duration of hardware removal tasks per port | 25.3436 | 25.3436 | 25.3436 | 25.3436 | 25.3436 | 25.3436
Deploy Recovery System into ex-vessel area | Movement | 0.069444 | 0.069444 |  | N/A | Cask Transporter (no cask) | AMF Equipment Issue | Lower Port | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A | Duration of hardware installation tasks per port | 32.8683 | 32.8683 | 32.8683 | 32.8683 | 32.8683 | 32.8683
Dock recovery system to the failed cask | Logistics | 1.9 | 1.9694 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 |  | N/A | N/A | Duration of RM operations (h) | 58.2119 | 1047.815 | 523.9075 | 349.2717 | 291.0597 | 174.6358
Recover failed MM into cask for replacement | Operation | 3 | 4.9694 | Recovery Operation | 3 |  |  |  | N/A | N/A | N/A | Store Tool in Transport Cask | N/A |  | N/A | N/A | Estimated number of failures, impacting all RM systems equally | 1.1642 | 20.9563 | 10.4782 | 6.9854 | 5.8212 | 3.4927
Un-dock Recovery system | Logistics | 2.3 | 7.2694 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A | Operational contribution | 3.4927 | 62.8689 | 31.4345 | 20.9563 | 17.4636 | 10.4781
Un-dock Cask | Logistics | 2.3 | 9.5694 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A | Logistical contribution | 13.5032 | 243.0582 | 121.5291 | 81.0194 | 67.5162 | 40.5097
Move to AMF Hardware Receipt | Movement | 0.69444 | 10.2639 |  | N/A | Cask Transporter (Loaded) | Lower Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A | Idle time due to waiting for dependant operations | 0 | 0 | 0 | 0 | 0 | 0
Store Failed Cask | Logistics | 0.58 | 10.8439 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware cask | 0.58 |  | N/A | N/A | Total Duration of Recovery Tasks | 16.9959 | 305.9271 | 152.9635 | 101.9757 | 84.9797 | 50.9878
Issue Replacement Cask | Logistics | 0.78 | 11.6239 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78 |  | N/A | N/A
Transport Cask to Lower Port | Movement | 0.69444 | 12.3183 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A
Dock Cask and Commission RM Systems | Logistics | 1.9 | 14.2183 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 |  | N/A | N/A
Deploy Divertor Handling Equipment | Logistics | 0.38 | 14.5983 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Total |  | 14.5983
Divertor handling system failure
Assumptions:
Recovery of Divertor handling system is completed using standard predetermined procedures.
Rare and time consuming special recoveries are not considered
A replacement system (if required) is available on demand from the AMF
Failure rate: | 0.501%
Failure rate of Multifunction Manipulator per hour | 0.501%
[17 empty] | Divertor handling system failure | Single Port | Full Maintenance Campaign
|  |  |  | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies |  |  | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
RH Cask RHE failure (Sub Tasks) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack | Duration of hardware removal tasks | 23.22 | 23.22 | 23.22 | 23.22 | 23.22 | 23.22
Deploy Recovery System into ex-vessel area | Movement | 0.069444 | 0.069444 |  | N/A | Cask Transporter (no cask) | AMF Equipment Issue | Lower Port | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A | Duration of hardware installation tasks | 27.11 | 27.11 | 27.11 | 27.11 | 27.11 | 27.11
Dock recovery system to the failed cask | Logistics | 1.9 | 1.9694 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 |  | N/A | N/A | Duration of RM operations (h) | 50.33 | 905.94 | 452.97 | 301.98 | 251.65 | 150.99
Recover failed MM into cask for replacement | Operation | 3 | 4.9694 | Recovery Operation | 3 |  |  |  | N/A | N/A | N/A | Store Tool in Transport Cask | N/A |  | N/A | N/A | Estimated number of failures, impacting all RM systems equally | 0.25215 | 4.5388 | 2.2694 | 1.5129 | 1.2608 | 0.75646
Un-dock Recovery system | Logistics | 2.3 | 7.2694 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A | Operational contribution | 0.75646 | 13.6163 | 6.8081 | 4.5388 | 3.7823 | 2.2694
Un-dock Cask | Logistics | 2.3 | 9.5694 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A | Logistical contribution | 2.9246 | 52.642 | 26.321 | 17.5473 | 14.6228 | 8.7737
Move to AMF Hardware Receipt | Movement | 0.69444 | 10.2639 |  | N/A | Cask Transporter (Loaded) | Lower Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A | Idle time due to waiting for dependant operations | 0 | 0 | 0 | 0 | 0 | 0
Store Failed Cask | Logistics | 0.58 | 10.8439 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware cask | 0.58 |  | N/A | N/A | Total Duration of Recovery Tasks | 3.681 | 66.2583 | 33.1292 | 22.0861 | 18.4051 | 11.0431
Issue Replacement Cask | Logistics | 0.78 | 11.6239 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78 |  | N/A | N/A
Transport Cask to Lower Port | Movement | 0.69444 | 12.3183 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A
Dock Cask and Commission RM Systems | Logistics | 1.9 | 14.2183 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 |  | N/A | N/A
Deploy Divertor Handling Equipment | Logistics | 0.38 | 14.5983 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Total |  | 14.5983
Note on D25: O Crofts: Uses multiple dextrous manipulators and deployment systems
Note on C32: Farquhar, Iain: Failed transporter moved to the AMF for repair
Note on D44: O Crofts: Uses multiple dextrous manipulators and deployment systems
Note on D69: Farquhar, Iain: Uses complex RM systems
Note on D97: Farquhar, Iain: Uses complex RM systems
Note on D124: O Crofts: Uses multiple dextrous manipulators and deployment systems
Note on C131: Farquhar, Iain: Failed transporter moved to the AMF for repair
Note on D143: O Crofts: Uses multiple dextrous manipulators and deployment systems
Note on D167: Farquhar, Iain: Uses complex RM systems
Note on D195: Farquhar, Iain: Uses complex RM systems

## Lower Cask Weld Failures (hidden)
Delay caused by failure and recovery from failed welding operations
Welding Assumptions | [14 empty] | Estimated delay
Operations Assumptions
TIG welding and laser cutting is the current worst case scenario
In-situ surface treatment is not possible, so all hardware must be removed and replaced/reconditioned before it can be re-welded
All other positioning, delivery and retrieval operations are of a similar length to nominal operations
Service Joint system is capable of cutting and pipes without tool change
No additional blanket modules will need to be removed to access impacted blanket module
RM Tooling is able to cut and weld all pipes within a pipe module simultaneously
No logistical bottlenecks occur during recovery operations
Both upper and lower port welding operations are carried out simulations for each blanket, to prevent unnecessary cutting of welds
Design Assumptions
Each upper port pipe module contains 5 pipes
Each lower port pipe module contains 3 pipes
All other positioning, delivery and retrieval operations are of a similar length to nominal operations
Service Joint system is capable of cutting and pipes without tool change
|  | Single Port | Full DEMO Maintenance
| No. Systems | 1 | 1 | 2 | 3 | 4 | 6
Full Lower Port Maintenance
| Operational contribution | 244.9352 | 4408.8332 | 2204.4166 | 1469.6111 | 1224.6759 | 734.8055
| Logistical contribution | 68.1595 | 1226.8703 | 613.4352 | 408.9568 | 340.7973 | 204.4784
| Idle time due to waiting for dependant operations | 160.1714 | 2883.0854 | 1441.5427 | 961.0285 | 800.8571 | 480.5142
| Estimated Delay | 473.2661 | 8518.7889 | 4259.3945 | 2839.5963 | 2366.3303 | 1419.7982
Divertor Only Maintenance
| Operational contribution | 30.8085 | 554.5531 | 277.2765 | 184.851 | 154.0425 | 92.4255
| Logistical contribution | 21.4496 | 386.0928 | 193.0464 | 128.6976 | 107.248 | 64.3488
| Idle time due to waiting for dependant operations | 9.7246 | 175.043 | 87.5215 | 58.3477 | 48.623 | 29.1738
| Estimated Delay | 61.9827 | 1115.6889 | 557.8444 | 371.8963 | 309.9136 | 185.9481
| Total Delay | 535.2488 | 9634.4778 | 4817.2389 | 3211.4926 | 2676.2438 | 1605.7463
Estimated Operational Durations (taken from Hotcell Critical Path)
Failure of COB Lower Port Welds
Assumptions:
TIG welding and laser cutting is the current worst case scenario
|  | Any LOB pipe joint failures are detected prior to the installation of the COB pipework | [14 empty] | Single Port | DEMO
|  | In-situ surface treatment is not possible, so all hardware must be removed and replaced/reconditioned before it can be re-welded | [13 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
|  | All other positioning, delivery and retrieval operations are of a similar length to nominal operations | [13 empty] | Duration of welding operations (h) | 26.7733 | 481.9189 | 240.9594 | 160.6396 | 133.8664 | 80.3198
|  | Service Joint system is capable of cutting and pipes without tool change | [13 empty] | Estimated number of failures, impacting all RM systems equally | 0.29451 | 5.3011 | 2.6506 | 1.767 | 1.4725 | 0.88352
|  | No additional blanket modules will need to be removed to access impacted blanket module | [13 empty] | Operational contribution | 53.1488 | 956.679 | 478.3395 | 318.893 | 265.7442 | 159.4465
[16 empty] | Logistical contribution | 10.7465 | 193.4374 | 96.7187 | 64.4791 | 53.7326 | 32.2396
[16 empty] | Idle time due to waiting for dependant operations | 26.8532 | 483.3575 | 241.6787 | 161.1192 | 134.266 | 80.5596
|  | Failure rate: | 1.1% | [12 empty] | Total Duration of Recovery Operations | 90.7485 | 1633.4739 | 816.7369 | 544.4913 | 453.7427 | 272.2456
|  | Assuming a weld failure rate of | 0.1%
|  | Assuming a tool failure rate of | 1%
|  | Probability of Secondary Failure/hr or Event | 0.0359%
[6 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies
| Group | Pipe weld failure (Sub Tasks) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack
| Cut Failed Welds | Lower Port COB weld failure identified | Operation | 0 | 0 | Hardware Recovery Required | 0 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Cut Failed COB Pipe Module Weld | Operation | 12.603 | 12.603 | Disconnect Blanket pipe module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove Pipe Module from the port | Store COB Pipe Module into Cask | Logistics | 0.38 | 12.983 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Retract Service Joint System into cask | Logistics | 0.38 | 13.363 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Remove Remaining Pipe Modules from Port | Deploy Multifunction Manipulator | Logistics | 0.38 | 13.743 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Remove LOB pipework access lid using Multifunction Manipulator | Operation | 3.83 | 17.573 | Remove Lower Port Pipework Access Lid | 3.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Remove ROB pipework access lid using Multifunction Manipulator | Operation | 3.83 | 21.403 | Remove Lower Port Pipework Access Lid | 3.83 |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | N/A |  | N/A | N/A
|  | Reposition Pipework equipment to the second pipework module | Logistics | 0.53 | 21.933 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Remove LOB blanket pipework module | Operation | 12.603 | 34.5359 | Disconnect Blanket Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store LOB Pipe Module into Cask | Logistics | 0.38 | 34.9159 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Reposition Pipework equipment to the third pipe module | Logistics | 0.53 | 35.4459 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Remove ROB blanket pipework module | Operation | 12.603 | 48.0489 | Disconnect Blanket Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Service Joint System into cask | Logistics | 0.38 | 48.4289 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Store ROB Pipe Module into Cask | Logistics | 0.38 | 48.8089 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Outboard Pipe Module Cask | Logistics | 2.3 | 51.1089 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Remove Two Inboard Blanket Pipework Modules | Dock Inboard Pipework Cask | Logistics | 1.9 | 53.0089 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Right Divertor Cassette Stored; Cassette Transport Cask Stored; Inboard Pipework Cask Prepared; Inboard Pipework Cask moved to Lower Port | 4.2137 | 46.8952
|  | Deploy Service Joint System | Logistics | 0.38 | 53.3889 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Remove LIB blanket pipework module | Operation | 12.603 | 65.9919 | Disconnect Blanket Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store LIB Pipe Module into Cask | Logistics | 0.38 | 66.3719 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Reposition Pipework equipment to the second pipework module | Logistics | 0.53 | 66.9019 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Remove RIB blanket pipework module | Operation | 12.603 | 79.5048 | Disconnect Blanket Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store RIB Pipe Module into Cask | Logistics | 0.38 | 79.8848 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Retract Service Joint System into cask | Logistics | 0.38 | 80.2648 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Inboard Blanket Pipe Cask | Logistics | 2.3 | 82.5648 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Remove Inner Pipework Modules | Dock Service Joint System Cask | Logistics | 1.9 | 84.4648 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Outboard Pipework Cask Stored; Inner Port Pipework Cask Prepared; Inner Port Pipework Cask Moved to Lower Port | 53.5226 | 29.0422
|  | Deploy Service Joint System from transport cask | Logistics | 0.38 | 84.8448 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Remove LIB Inner Pipework module | Operation | 7.523 | 92.3678 | Disconnect Inner Port Pipe Module | 7.523 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store LIB Inner Pipework module in cask | Logistics | 0.38 | 92.7478 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Reposition Pipework equipment to the RIB inner pipework module | Logistics | 0.53 | 93.2778 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Remove RIB blanket pipework module | Operation | 7.523 | 100.8008 | Disconnect Inner Port Pipe Module | 7.523 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Inner RIB pipework module in cask | Logistics | 0.38 | 101.1808 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Retract Service Joint System into cask | Logistics | 0.38 | 101.5608 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Inner Pipework Cask | Logistics | 2.3 | 103.8608 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Install Inner Port Pipework Modules | Dock Service Joint System Cask | Logistics | 1.9 | 105.7608 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Removed Inboard blankets stored, New Inner Port Pipe Modules Collected and moved to port | 84.8785 | 18.9822
|  | Deploy Service Joint System | Logistics | 0.38 | 106.1408 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Install RIB Pipe Module | Operation | 17.6227 | 123.7634 | Connect Inner Port Pipe module | 17.6227 |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | N/A | RIB Blanket Segment Installed | 91.4617 | 14.6791
|  | Collect second Inner Port Pipework Module from Cask | Logistics | 0.38 | 124.1434 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Install LIB Pipework Module | Operation | 17.6227 | 232.9466 | Connect Inner Port Pipe Module | 17.6227 |  |  |  | N/A | N/A | N/A |  | N/A | LIB Blanket Segment Installed | 215.3239 | -91.1805
|  | Retract Service Joint System into cask | Logistics | 0.38 | 233.3266 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Empty Inner Port Pipework Cask | Logistics | 2.3 | 235.6266 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Install Two Inboard Blanket Pipework Modules | Dock Service Joint System Cask | Logistics | 1.9 | 237.5266 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Removed Inner Port Pipe Modules stored, New Inboard Pipe Modules Collected and moved to port | 106.1745 | 129.4521
|  | Deploy Service Joint System | Logistics | 0.38 | 237.9066 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Extract First Pipe Module from Cask | Logistics | 0.38 | 238.2866 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Install LIB Blanket Pipe Module | Operation | 10.0363 | 248.3229 | Connect Blanket Pipe Module | 10.0363 |  |  |  | N/A | N/A | N/A |  | N/A | RIB Blanket Segment Installed | 91.4617 | 146.8249
|  | Reposition Pipework equipment to the second pipework module | Logistics | 0.53 | 248.8529 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Extract Second Pipe Module from Cask | Logistics | 0.38 | 249.2329 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Install RIB Blanket Pipe Module | Operation | 10.0363 | 259.2692 | Connect Blanket Pipe Module | 10.0363 |  |  |  | N/A | N/A | N/A |  | N/A | LIB Blanket Segment Installed | 215.3239 | 33.909
|  | Retract Service Joint System into cask | Logistics | 0.38 | 259.6492 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Retract Multifunction manipulator | Logistics | 0.38 | 260.0292 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Inboard Pipe Module Cask | Logistics | 2.3 | 262.3292 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Install Three Outboard Blanket Pipework Modules | Dock Service Joint System Cask | Logistics | 1.9 | 264.2292 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Inner Port Pipe Cask stored; New Outboard Pipe Modules Collected and moved to port | 237.9403 | 24.389
|  | Deploy Service Joint System | Logistics | 0.38 | 264.6092 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Extract ROB Pipework Module from Cask | Logistics | 0.38 | 264.9892 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Install ROB Blanket Pipe Module | Operation | 10.0363 | 275.0256 | Connect Blanket Pipe Module | 10.0363 |  |  |  | N/A | N/A | N/A |  | N/A | ROB Blanket Segment Installed | 100.2606 | 164.7287
|  | Extract LOB Pipework Module from Cask | Logistics | 0.38 | 275.4056 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Reposition Pipework equipment to the second pipework module location | Logistics | 0.53 | 275.9356 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Install LOB blanket pipework module | Operation | 10.0363 | 285.9719 | Connect Blanket Pipe Module | 10.0363 |  |  |  | N/A | N/A | N/A |  | N/A | LOB Blanket Segment Installed | 106.07 | 169.8656
|  | Retract Service Joint System into cask | Logistics | 0.38 | 286.3519 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Deploy Multifunction Manipulator | Logistics | 0.38 | 286.7319 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Install LOB pipework access lid using Multifunction Manipulator | Operation | 4.66 | 291.3919 | Install Lower Port Pipework Access Lid | 4.66 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Install ROB pipework access lid using Multifunction Manipulator | Operation | 4.66 | 296.0519 | Install Lower Port Pipework Access Lid | 4.66 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Multifunction manipulator | Logistics | 0.38 | 296.4319 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Deploy Service Joint System | Logistics | 0.38 | 296.8119 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Extract COB Pipe Module from Cask | Logistics | 0.38 | 297.1919 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Reposition Pipework equipment to the third pipe module | Logistics | 0.53 | 297.7219 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Install COB blanket pipework module | Operation | 10.0363 | 307.7582 | Connect Blanket Pipe Module | 10.0363 |  |  |  | N/A | N/A | N/A |  | N/A | COB Blanket Segment Installed | 111.8794 | 185.8424
|  | Retract Service Joint System into cask | Logistics | 0.38 | 308.1382 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  |  | Total |  | 308.1382
Failure of LOB Lower Port Welds
Assumptions:
TIG welding and laser cutting is the current worst case scenario
|  | Any LOB pipe joint failures are detected prior to the installation of the COB pipework | [14 empty] | Single Port | DEMO
|  | In-situ surface treatment is not possible, so all hardware must be removed and replaced/reconditioned before it can be re-welded | [13 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
|  | All other positioning, delivery and retrieval operations are of a similar length to nominal operations | [13 empty] | Duration of welding operations (h) | 26.7733 | 481.9189 | 240.9594 | 160.6396 | 133.8664 | 80.3198
|  | Service Joint system is capable of cutting and pipes without tool change | [13 empty] | Estimated number of failures, impacting all RM systems equally | 0.29451 | 5.3011 | 2.6506 | 1.767 | 1.4725 | 0.88352
|  | No additional blanket modules will need to be removed to access impacted blanket module | [13 empty] | Operational contribution | 41.4807 | 746.6529 | 373.3264 | 248.8843 | 207.4036 | 124.4421
[16 empty] | Logistical contribution | 9.539 | 171.7029 | 85.8514 | 57.2343 | 47.6952 | 28.6171
[10 empty] | 48 | [5 empty] | Idle time due to waiting for dependant operations | 0 | 0 | 0 | 0 | 0 | 0
|  | Failure rate: | 1.1% | [12 empty] | Total Duration of Recovery Operations | 51.0198 | 918.3557 | 459.1779 | 306.1186 | 255.0988 | 153.0593
|  | Assuming a weld failure rate of | 0.1%
|  | Assuming a tool failure rate of | 1%
|  | Probability of Secondary Failure/hr or Event | 0.0359%
[6 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies
| Group | Pipe weld failure (Sub Tasks) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack
| Cut Failed Welds | Lower Port LOB weld failure identified | Operation | 0 | 0 | Hardware Recovery Required | 0 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Cut Failed LOB Pipe Module Weld | Operation | 12.603 | 12.603 | Disconnect Blanket pipe module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove Remaining Pipe Module from the port | Store LOB Pipe Module into Cask | Logistics | 0.38 | 12.983 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Reposition Pipework equipment to the third pipe module | Logistics | 0.53 | 13.513 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Remove ROB blanket pipework module | Operation | 12.603 | 26.1159 | Disconnect Blanket Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Service Joint System into cask | Logistics | 0.38 | 26.4959 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Store ROB Pipe Module into Cask | Logistics | 0.38 | 26.8759 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Outboard Pipe Module Cask | Logistics | 2.3 | 29.1759 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Remove Two Inboard Blanket Pipework Modules | Dock Inboard Pipework Cask | Logistics | 1.9 | 31.0759 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Right Divertor Cassette Stored; Cassette Transport Cask Stored; Inboard Pipework Cask Prepared; Inboard Pipework Cask moved to Lower Port | 4.2137 | 24.9622
|  | Deploy Service Joint System | Logistics | 0.38 | 31.4559 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Remove LIB blanket pipework module | Operation | 12.603 | 44.0589 | Disconnect Blanket Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store LIB Pipe Module into Cask | Logistics | 0.38 | 44.4389 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Reposition Pipework equipment to the second pipework module | Logistics | 0.53 | 44.9689 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Remove RIB blanket pipework module | Operation | 12.603 | 57.5719 | Disconnect Blanket Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store RIB Pipe Module into Cask | Logistics | 0.38 | 57.9519 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Retract Service Joint System into cask | Logistics | 0.38 | 58.3319 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Inboard Blanket Pipe Cask | Logistics | 2.3 | 60.6319 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Remove Inner Pipework Modules | Dock Service Joint System Cask | Logistics | 1.9 | 62.5319 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Outboard Pipework Cask Stored; Inner Port Pipework Cask Prepared; Inner Port Pipework Cask Moved to Lower Port | 31.5896 | 29.0422
|  | Deploy Service Joint System from transport cask | Logistics | 0.38 | 62.9119 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Remove LIB Inner Pipework module | Operation | 7.523 | 70.4348 | Disconnect Inner Port Pipe Module | 7.523 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store LIB Inner Pipework module in cask | Logistics | 0.38 | 70.8148 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Reposition Pipework equipment to the RIB inner pipework module | Logistics | 0.53 | 71.3448 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Remove RIB blanket pipework module | Operation | 7.523 | 78.8678 | Disconnect Inner Port Pipe Module | 7.523 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Inner RIB pipework module in cask | Logistics | 0.38 | 79.2478 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Retract Service Joint System into cask | Logistics | 0.38 | 79.6278 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Inner Pipework Cask | Logistics | 2.3 | 81.9278 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Install Inner Port Pipework Modules | Dock Service Joint System Cask | Logistics | 1.9 | 83.8278 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Removed Inboard blankets stored, New Inner Port Pipe Modules Collected and moved to port | 62.9456 | 18.9822
|  | Deploy Service Joint System | Logistics | 0.38 | 84.2078 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Install RIB Pipe Module | Operation | 17.6227 | 101.8305 | Connect Inner Port Pipe module | 17.6227 |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | N/A | RIB Blanket Segment Installed | 63.6522 | 20.5556
|  | Collect second Inner Port Pipework Module from Cask | Logistics | 0.38 | 102.2105 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Install LIB Pipework Module | Operation | 17.6227 | 119.8331 | Connect Inner Port Pipe Module | 17.6227 |  |  |  | N/A | N/A | N/A |  | N/A | LIB Blanket Segment Installed | 68.0517 | 34.1588
|  | Retract Service Joint System into cask | Logistics | 0.38 | 120.2131 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Empty Inner Port Pipework Cask | Logistics | 2.3 | 122.5131 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Install Two Inboard Blanket Pipework Modules | Dock Service Joint System Cask | Logistics | 1.9 | 124.4131 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Removed Inner Port Pipe Modules stored, New Inboard Pipe Modules Collected and moved to port | 84.2415 | 38.2716
|  | Deploy Service Joint System | Logistics | 0.38 | 124.7931 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Extract First Pipe Module from Cask | Logistics | 0.38 | 125.1731 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Install LIB Blanket Pipe Module | Operation | 10.0363 | 135.2095 | Connect Blanket Pipe Module | 10.0363 |  |  |  | N/A | N/A | N/A |  | N/A | LIB Blanket Segment Installed | 68.0517 | 57.1214
|  | Reposition Pipework equipment to the second pipework module | Logistics | 0.53 | 135.7395 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Extract Second Pipe Module from Cask | Logistics | 0.38 | 136.1195 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Install RIB Blanket Pipe Module | Operation | 10.0363 | 146.1558 | Connect Blanket Pipe Module | 10.0363 |  |  |  | N/A | N/A | N/A |  | N/A | RIB Blanket Segment Installed | 63.6522 | 72.4672
|  | Retract Service Joint System into cask | Logistics | 0.38 | 146.5358 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Retract Multifunction manipulator | Logistics | 0.38 | 146.9158 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Inboard Pipe Module Cask | Logistics | 2.3 | 149.2158 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Install Outboard Blanket Pipework Modules | Dock Service Joint System Cask | Logistics | 1.9 | 151.1158 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Removed Inner Port Pipe Modules stored, New Inboard Pipe Modules Collected and moved to port | 84.2415 | 64.9743
|  | Deploy Service Joint System | Logistics | 0.38 | 151.4958 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Extract ROB Pipework Module from Cask | Logistics | 0.38 | 151.8758 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Install ROB Blanket Pipe Module | Operation | 10.0363 | 161.9121 | Connect Blanket Pipe Module | 10.0363 |  |  |  | N/A | N/A | N/A |  | N/A | ROB Blanket Segment Installed | 72.4511 | 79.4247
|  | Extract LOB Pipework Module from Cask | Logistics | 0.38 | 162.2921 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Reposition Pipework equipment to the second pipework module location | Logistics | 0.53 | 162.8221 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Install LOB blanket pipework module | Operation | 10.0363 | 172.8585 | Connect Blanket Pipe Module | 10.0363 |  |  |  | N/A | N/A | N/A |  | N/A | LOB Blanket Segment Installed | 78.2606 | 84.5615
|  | Retract Service Joint System into cask | Logistics | 0.38 | 173.2385 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  |  | Total |  | 173.2385
Failure of ROB Lower Port Welds
Assumptions:
TIG welding and laser cutting is the current worst case scenario
|  | Any LOB pipe joint failures are detected prior to the installation of the COB pipework | [14 empty] | Single Port | Full Maintenance Campaign
|  | In-situ surface treatment is not possible, so all hardware must be removed and replaced/reconditioned before it can be re-welded | [13 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
|  | All other positioning, delivery and retrieval operations are of a similar length to nominal operations | [13 empty] | Duration of welding operations (h) | 26.7733 | 481.9189 | 240.9594 | 160.6396 | 133.8664 | 80.3198
|  | Service Joint system is capable of cutting and pipes without tool change | [13 empty] | Estimated number of failures, impacting all RM systems equally | 0.29451 | 5.3011 | 2.6506 | 1.767 | 1.4725 | 0.88352
|  | No additional blanket modules will need to be removed to access impacted blanket module | [13 empty] | Operational contribution | 34.8133 | 626.6395 | 313.3197 | 208.8798 | 174.0665 | 104.4399
[16 empty] | Logistical contribution | 8.2197 | 147.9539 | 73.977 | 49.318 | 41.0983 | 24.659
[16 empty] | Idle time due to waiting for dependant operations | 1.2704 | 22.8674 | 11.4337 | 7.6225 | 6.3521 | 3.8112
|  | Failure rate: | 1.1% | [12 empty] | Total Duration of Recovery Operations | 44.3034 | 797.4608 | 398.7304 | 265.8203 | 221.5169 | 132.9101
|  | Assuming a weld failure rate of | 0.1%
|  | Assuming a tool failure rate of | 1%
|  | Probability of Secondary Failure/hr or Event | 0.0359%
[6 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies
| Group | Pipe weld failure (Sub Tasks) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack
| Cut Failed Welds | Lower Port ROB weld failure identified | Operation | 0 | 0 | Hardware Recovery Required | 0 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Cut Failed ROB Pipe Module Weld | Operation | 12.603 | 12.603 | Disconnect Blanket pipe module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store ROB Pipe Module into Cask | Logistics | 0.38 | 12.983 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Outboard Pipe Module Cask | Logistics | 2.3 | 15.283 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Remove Two Inboard Blanket Pipework Modules | Deploy Service Joint System | Logistics | 0.38 | 15.663 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 | Right Divertor Cassette Stored; Cassette Transport Cask Stored; Inboard Pipework Cask Prepared; Inboard Pipework Cask moved to Lower Port | 4.2137 | 10.6893
|  | Remove LIB blanket pipework module | Operation | 12.603 | 28.2659 | Disconnect Blanket Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store LIB Pipe Module into Cask | Logistics | 0.38 | 28.6459 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Reposition Pipework equipment to the second pipework module | Logistics | 0.53 | 29.1759 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Remove RIB blanket pipework module | Operation | 12.603 | 41.7789 | Disconnect Blanket Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store RIB Pipe Module into Cask | Logistics | 0.38 | 42.1589 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Retract Service Joint System into cask | Logistics | 0.38 | 42.5389 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Inboard Blanket Pipe Cask | Logistics | 2.3 | 44.8389 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Remove Inner Pipework Modules | Dock Service Joint System Cask | Logistics | 1.9 | 51.0526 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Outboard Pipework Cask Stored; Inner Port Pipework Cask Prepared; Inner Port Pipework Cask Moved to Lower Port | 47.2526 | -4.3137
|  | Deploy Service Joint System from transport cask | Logistics | 0.38 | 51.4326 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Remove LIB Inner Pipework module | Operation | 7.523 | 58.9556 | Disconnect Inner Port Pipe Module | 7.523 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store LIB Inner Pipework module in cask | Logistics | 0.38 | 59.3356 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Reposition Pipework equipment to the RIB inner pipework module | Logistics | 0.53 | 59.8656 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Remove RIB blanket pipework module | Operation | 7.523 | 67.3885 | Disconnect Inner Port Pipe Module | 7.523 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Inner RIB pipework module in cask | Logistics | 0.38 | 67.7685 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Retract Service Joint System into cask | Logistics | 0.38 | 68.1485 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Inner Pipework Cask | Logistics | 2.3 | 70.4485 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Install Inner Port Pipework Modules | Dock Service Joint System Cask | Logistics | 1.9 | 72.3485 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Removed Inboard blankets stored, New Inner Port Pipe Modules Collected and moved to port | 47.1526 | 21.3959
|  | Deploy Service Joint System | Logistics | 0.38 | 72.7285 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Install RIB Pipe Module | Operation | 17.6227 | 90.3512 | Connect Inner Port Pipe module | 17.6227 |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | N/A | RIB Blanket segment installed | 54.7487 | 0.35715
|  | Collect second Inner Port Pipework Module from Cask | Logistics | 0.38 | 90.7312 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Install LIB Pipework Module | Operation | 17.6227 | 108.3539 | Connect Inner Port Pipe Module | 17.6227 |  |  |  | N/A | N/A | N/A |  | N/A | LIB Blanket segment installed | 59.1482 | 13.9604
|  | Retract Service Joint System into cask | Logistics | 0.38 | 108.7339 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Empty Inner Port Pipework Cask | Logistics | 2.3 | 111.0339 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Install Two Inboard Blanket Pipework Modules | Dock Service Joint System Cask | Logistics | 1.9 | 112.9339 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Removed Inner Port Pipe Modules stored, New Inboard Pipe Modules Collected and moved to port | 72.7622 | 36.3716
|  | Deploy Service Joint System | Logistics | 0.38 | 113.3139 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Extract First Pipe Module from Cask | Logistics | 0.38 | 113.6939 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Install LIB Blanket Pipe Module | Operation | 10.0363 | 123.7302 | Connect Blanket Pipe Module | 10.0363 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Reposition Pipework equipment to the second pipework module | Logistics | 0.53 | 124.2602 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Extract Second Pipe Module from Cask | Logistics | 0.38 | 124.6402 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Install RIB Blanket Pipe Module | Operation | 10.0363 | 134.6765 | Connect Blanket Pipe Module | 10.0363 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Service Joint System into cask | Logistics | 0.38 | 135.0565 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Retract Multifunction manipulator | Logistics | 0.38 | 135.4365 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Inboard Pipe Module Cask | Logistics | 2.3 | 137.7365 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Install Outboard Blanket Pipework Module | Dock Service Joint System Cask | Logistics | 1.9 | 139.6365 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Inner Port Pipe Cask stored; New Outboard Pipe Modules Collected and moved to port | 113.3476 | 22.489
|  | Deploy Service Joint System | Logistics | 0.38 | 140.0165 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Extract ROB Pipework Module from Cask | Logistics | 0.38 | 140.3965 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Install ROB Blanket Pipe Module | Operation | 10.0363 | 150.4329 | Connect Blanket Pipe Module | 10.0363 |  |  |  | N/A | N/A | N/A |  | N/A | ROB Blanket Segment Installed | 63.5476 | 66.8126
|  | Retract Service Joint System into cask | Logistics | 0.38 | 150.8129 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  |  | Total |  | 150.4329
Failure of LIB Lower Port Welds
Assumptions:
TIG welding and laser cutting is the current worst case scenario
|  | Any LOB pipe joint failures are detected prior to the installation of the COB pipework | [13 empty] | Bore Pipe Welds | Single Port | Full Maintenance Campaign
|  | In-situ surface treatment is not possible, so all hardware must be removed and replaced/reconditioned before it can be re-welded | [13 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
|  | All other positioning, delivery and retrieval operations are of a similar length to nominal operations | [13 empty] | Duration of welding operations (h) | 26.7733 | 481.9189 | 240.9594 | 160.6396 | 133.8664 | 80.3198
|  | Service Joint system is capable of cutting and pipes without tool change | [13 empty] | Estimated number of failures, impacting all RM systems equally | 0.29451 | 5.3011 | 2.6506 | 1.767 | 1.4725 | 0.88352
|  | No additional blanket modules will need to be removed to access impacted blanket module | [13 empty] | Operational contribution | 28.1459 | 506.6261 | 253.3131 | 168.8754 | 140.7295 | 84.4377
[16 empty] | Logistical contribution | 6.379 | 114.822 | 57.411 | 38.274 | 31.895 | 19.137
[16 empty] | Idle time due to waiting for dependant operations | 2.2557 | 40.6024 | 20.3012 | 13.5341 | 11.2785 | 6.7671
|  | Failure rate: | 1.1% | [12 empty] | Total Duration of Recovery Operations | 36.7806 | 662.0506 | 331.0253 | 220.6835 | 183.9029 | 110.3418
|  | Assuming a weld failure rate of | 0.1%
|  | Assuming a tool failure rate of | 1%
|  | Probability of Secondary Failure/hr or Event | 0.0359%
[6 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies
| Group | Pipe weld failure (Sub Tasks) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack
| Cut Failed Welds | Weld Failure identified LIB Lower Port pipe Module joint | Operation | 0 | 0 | Hardware Recovery Required | 0 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Cut Failed Pipe Module Weld | Operation | 12.603 | 12.603 | Disconnect Blanket Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove Pipe Module from the port | Store pipe Module into Cask | Logistics | 0.38 | 12.983 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Retract Service Joint System into cask | Logistics | 0.38 | 13.363 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Undock Outboard Pipe Module Cask | Logistics | 2.3 | 15.663 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Remove remaining Inboard blanket module | Reposition Pipework equipment to the second pipework module | Logistics | 0.53 | 16.193 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Remove RIB blanket pipework module | Operation | 12.603 | 28.7959 | Disconnect Blanket Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store RIB Pipe Module into Cask | Logistics | 0.38 | 29.1759 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Retract Service Joint System into cask | Logistics | 0.38 | 29.5559 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Inboard Blanket Pipe Cask | Logistics | 2.3 | 31.8559 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Remove Inner Pipework Modules | Dock Service Joint System Cask | Logistics | 1.9 | 33.7559 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Outboard Port Pipework Cask Stored; Inner Port Pipework cask Prepared; Inner Port Pipework Cask Moved to Lower Port | 2.4137 | 27.5422
|  | Deploy Service Joint System from transport cask | Logistics | 0.38 | 34.1359 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Remove LIB Inner Pipework module | Operation | 7.523 | 41.6589 | Disconnect inner port pipe module | 7.523 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store LIB Inner Pipework module in cask | Logistics | 0.38 | 42.0389 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Reposition Pipework equipment to the RIB inner pipework module | Logistics | 0.53 | 42.5689 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Remove RIB blanket pipework module | Operation | 7.523 | 50.0919 | Disconnect inner port pipe module | 7.523 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Inner RIB pipework module in cask | Logistics | 0.38 | 50.4719 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Retract Service Joint System into cask | Logistics | 0.38 | 50.8519 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Inner Pipework Cask | Logistics | 2.3 | 53.1519 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Install Inner Port Pipework Modules | Dock Service Joint System Cask | Logistics | 1.9 | 55.0519 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Removed Inboard blankets stored, New Inner Port Pipe Modules Collected and moved to port | 34.1696 | 17.0822
|  | Deploy Service Joint System | Logistics | 0.38 | 55.4319 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Install RIB Pipe Module | Operation | 17.6227 | 80.7138 | Connect Inner Port Pipe module | 17.6227 |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | N/A | RIB Blanket segment installed | 45.4684 | -7.6592
|  | Collect second Inner Port Pipework Module from Cask | Logistics | 0.38 | 81.0938 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Install LIB Pipework Module | Operation | 17.6227 | 98.7164 | Connect Inner Port Pipe module | 17.6227 |  |  |  | N/A | N/A | N/A |  | N/A | LIB Blanket segment installed | 49.8679 | 13.6032
|  | Retract Service Joint System into cask | Logistics | 0.38 | 99.0964 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Empty Inner Port Pipework Cask | Logistics | 2.3 | 101.3964 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Dock Cask with replacement blanket pipe modules | Dock replacement pipe modules | Logistics | 1.9 | 103.2964 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Removed Inner Port Pipe Modules stored, New Inboard Pipe Modules Collected and moved to port | 55.4656 | 44.0309
|  | Deploy Service Joint System | Logistics | 0.38 | 103.6764 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Extract blanket pipe module | Logistics | 0.38 | 104.0564 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Install pipe module | Operation | 10.0363 | 114.0928 | Connect Blanket Pipe Module | 10.0363 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Extract outboard Pipe Module from Cask | Logistics | 0.38 | 114.4728 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 | RIB Upper Port Pipe Module installed | 70.6757 | 43.0371
|  | Install LIB blanket pipework module | Operation | 10.0363 | 124.5091 | Connect Blanket Pipe Module | 10.0363 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Service Joint System into cask | Logistics | 0.38 | 124.8891 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  |  | Total |  | 124.8891
Failure of LIB Inner Port Welds
Assumptions:
TIG welding and laser cutting is the current worst case scenario
|  | Any LOB pipe joint failures are detected prior to the installation of the COB pipework | [14 empty] | Single Port | Full Maintenance Campaign
|  | In-situ surface treatment is not possible, so all hardware must be removed and replaced/reconditioned before it can be re-welded | [13 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
|  | All other positioning, delivery and retrieval operations are of a similar length to nominal operations | [13 empty] | Duration of welding operations (h) | 53.7846 | 968.1235 | 484.0617 | 322.7078 | 268.9232 | 161.3539
|  | Service Joint system is capable of cutting and pipes without tool change | [13 empty] | Estimated number of failures, impacting all RM systems equally | 0.59163 | 10.6494 | 5.3247 | 3.5498 | 2.9582 | 1.7749
|  | No additional blanket modules will need to be removed to access impacted blanket module | [13 empty] | Operational contribution | 29.7539 | 535.5697 | 267.7848 | 178.5232 | 148.7694 | 89.2616
[16 empty] | Logistical contribution | 5.7329 | 103.1923 | 51.5961 | 34.3974 | 28.6645 | 17.1987
[16 empty] | Idle time due to waiting for dependant operations | 67.6293 | 1217.3265 | 608.6633 | 405.7755 | 338.1463 | 202.8878
|  | Failure rate: | 1.1% | [12 empty] | Total Duration of Recovery Operations | 103.116 | 1856.0885 | 928.0442 | 618.6962 | 515.5801 | 309.3481
|  | Assuming a weld failure rate of | 0.1%
|  | Assuming a tool failure rate of | 1%
|  | Probability of Secondary Failure/hr or Event | 0.0359%
[6 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies
| Group | Pipe weld failure (Sub Tasks) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack
| Cut Failed Welds | Inner LIB Weld Failure identified | Operation | 0 | 0 | Hardware Recovery Required | 0 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Cut Failed Pipe Module Weld | Operation | 7.523 | 7.523 | Disconnect Inner Port Pipe Module | 7.523 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove Pipe Module from the port | Store pipe Module into Cask | Logistics | 0.38 | 7.903 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Retract Service Joint System into cask | Logistics | 0.38 | 8.283 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Undock Inner Port Pipe Module Cask | Logistics | 2.3 | 10.583 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Remove Inner RIB Pipe module | Reposition Pipework equipment to the RIB inner pipework module | Logistics | 0.53 | 11.113 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Remove RIB blanket pipework module | Operation | 7.523 | 18.6359 | Disconnect Inner Port Pipe Module | 7.523 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Inner RIB pipework module in cask | Logistics | 0.38 | 19.0159 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Retract Service Joint System into cask | Logistics | 0.38 | 19.3959 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Inner Pipework Cask | Logistics | 2.3 | 21.6959 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Install Inner Port Pipework Modules | Dock Service Joint System Cask | Logistics | 1.9 | 23.5959 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Inboard Port Pipework Cask Stored; Inner Port Pipework cask Prepared; Inner Port Pipework Cask Moved to Lower Port | 2.4137 | 8.1693
|  | Deploy Service Joint System | Logistics | 0.38 | 23.9759 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Install RIB Pipe Module | Operation | 17.6227 | 155.9084 | Connect Inner Port Pipe module | 17.6227 |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | N/A | RIB Blanket segment installed | 138.2858 | -114.3098
|  | Collect second Inner Port Pipework Module from Cask | Logistics | 0.38 | 156.2884 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Install LIB Pipework Module | Operation | 17.6227 | 173.9111 | Connect Inner Port Pipe Module | 17.6227 |  |  |  | N/A | N/A | N/A |  | N/A | LIB Blanket segment installed | 59.1482 | 79.5176
|  | Retract Service Joint System into cask | Logistics | 0.38 | 174.2911 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  |  | Total |  | 174.2911
Failure of RIB Inner Port Welds
Assumptions:
TIG welding and laser cutting is the current worst case scenario
|  | Any LOB pipe joint failures are detected prior to the installation of the COB pipework | [14 empty] | Single Port | Full Maintenance Campaign
|  | In-situ surface treatment is not possible, so all hardware must be removed and replaced/reconditioned before it can be re-welded | [13 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
|  | All other positioning, delivery and retrieval operations are of a similar length to nominal operations | [13 empty] | Duration of welding operations (h) | 53.7846 | 968.1235 | 484.0617 | 322.7078 | 268.9232 | 161.3539
|  | Service Joint system is capable of cutting and pipes without tool change | [13 empty] | Estimated number of failures, impacting all RM systems equally | 0.59163 | 10.6494 | 5.3247 | 3.5498 | 2.9582 | 1.7749
|  | No additional blanket modules will need to be removed to access impacted blanket module | [13 empty] | Operational contribution | 17.8824 | 321.8836 | 160.9418 | 107.2945 | 89.4121 | 53.6473
[16 empty] | Logistical contribution | 4.5201 | 81.3611 | 40.6805 | 27.1204 | 22.6003 | 13.5602
[16 empty] | Idle time due to waiting for dependant operations | 11.0173 | 198.3118 | 99.1559 | 66.1039 | 55.0866 | 33.052
|  | Failure rate: | 1.1% | [12 empty] | Total Duration of Recovery Operations | 33.4198 | 601.5565 | 300.7782 | 200.5188 | 167.099 | 100.2594
|  | Assuming a weld failure rate of | 0.1%
|  | Assuming a tool failure rate of | 1%
|  | Probability of Secondary Failure/hr or Event | 0.0359%
[6 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies
| Group | Pipe weld failure (Sub Tasks) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack
| Cut Failed Welds | Weld Failure identified at Module joint | Operation | 0 | 0 | Hardware Recovery Required | 0 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Cut Failed Pipe Module Weld | Operation | 12.603 | 12.603 | Disconnect Blanket Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove Pipe Module from the port | Store RIB Pipe Module into Cask | Logistics | 0.38 | 12.983 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Retract Service Joint System into cask | Logistics | 0.38 | 13.363 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Undock Outboard Pipe Module Cask | Logistics | 2.3 | 15.663 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Install Inner Port Pipework Modules | Dock Service Joint System Cask | Logistics | 1.9 | 17.563 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Replacement Pipe modules collected from stores | 11.5952 | 4.0678
|  | Deploy Service Joint System | Logistics | 0.38 | 17.943 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Install RIB Pipe Module | Operation | 17.6227 | 54.1876 | Connect Inner Port Pipe Module | 17.6227 |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | N/A | RIB Blanket segment installed | 36.5649 | -18.6219
|  | Un-Dock Empty Inner Port Pipework Cask | Logistics | 2.3 | 56.4876 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
|  |  | ` |  | 56.4876
Failure of RIB Lower Port Welds
Assumptions:
TIG welding and laser cutting is the current worst case scenario
|  | Any LOB pipe joint failures are detected prior to the installation of the COB pipework | [14 empty] | Single Port | Full Maintenance Campaign
|  | In-situ surface treatment is not possible, so all hardware must be removed and replaced/reconditioned before it can be re-welded | [13 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
|  | All other positioning, delivery and retrieval operations are of a similar length to nominal operations | [13 empty] | Duration of welding operations (h) | 26.7733 | 481.9189 | 240.9594 | 160.6396 | 133.8664 | 80.3198
|  | Service Joint system is capable of cutting and pipes without tool change | [13 empty] | Estimated number of failures, impacting all RM systems equally | 0.29451 | 5.3011 | 2.6506 | 1.767 | 1.4725 | 0.88352
|  | No additional blanket modules will need to be removed to access impacted blanket module | [13 empty] | Operational contribution | 8.9016 | 160.2293 | 80.1147 | 53.4098 | 44.5081 | 26.7049
[16 empty] | Logistical contribution | 1.5727 | 28.3079 | 14.154 | 9.436 | 7.8633 | 4.718
[16 empty] | Idle time due to waiting for dependant operations | 41.4209 | 745.5768 | 372.7884 | 248.5256 | 207.1047 | 124.2628
|  | Failure rate: | 1.1% | [12 empty] | Total Duration of Recovery Operations | 51.8952 | 934.1141 | 467.057 | 311.3714 | 259.4761 | 155.6857
|  | Assuming a weld failure rate of | 0.1%
|  | Assuming a tool failure rate of | 1%
|  | Probability of Secondary Failure/hr or Event | 0.0359%
[6 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies
| Group | Pipe weld failure (Sub Tasks) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack
| Cut Failed Welds | Inner RIB Weld Failure identified | Operation | 0 | 0 | Hardware Recovery Required | 0 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Cut Failed RIB Pipe Module Weld | Operation | 12.603 | 12.603 | Disconnect Blanket pipe module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store RIB Pipe Module into Cask | Logistics | 0.38 | 12.983 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Install Inner Port Pipework Modules | Dock Service Joint System Cask | Logistics | 1.9 | 14.883 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Inboard Port Pipework Cask Stored; Inner Port Pipework cask Prepared; Inner Port Pipework Cask Moved to Lower Port | 2.4137 | 8.6693
|  | Deploy Service Joint System | Logistics | 0.38 | 15.263 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Install RIB Pipe Module | Operation | 17.6227 | 173.5311 | Connect Inner Port Pipe module | 17.6227 |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | N/A | RIB Blanket segment installed | 138.2858 | -140.6455
|  | Retract Service Joint System into cask | Logistics | 0.38 | 173.9111 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Empty Inner Port Pipework Cask | Logistics | 2.3 | 176.2111 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
|  |  | Total |  | 176.2111
Failure of central divertor coolant welds
Assumptions:
TIG welding and laser cutting is the current worst case scenario
|  | Any LOB pipe joint failures are detected prior to the installation of the COB pipework | [14 empty] | Single Port | Full Maintenance Campaign
|  | In-situ surface treatment is not possible, so all hardware must be removed and replaced/reconditioned before it can be re-welded | [13 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
|  | All other positioning, delivery and retrieval operations are of a similar length to nominal operations | [13 empty] | Duration of welding operations (h) | 16.9651 | 305.371 | 152.6855 | 101.7903 | 84.8253 | 50.8952
|  | Service Joint system is capable of cutting and pipes without tool change | [13 empty] | Estimated number of failures, impacting all RM systems equally | 0.18662 | 3.3591 | 1.6795 | 1.1197 | 0.93308 | 0.55985
|  | No additional blanket modules will need to be removed to access impacted blanket module | [13 empty] | Operational contribution | 14.0886 | 253.595 | 126.7975 | 84.5317 | 70.4431 | 42.2658
[16 empty] | Logistical contribution | 7.5131 | 135.2366 | 67.6183 | 45.0789 | 37.5657 | 22.5394
[16 empty] | Idle time due to waiting for dependant operations | 1.2466 | 22.4387 | 11.2193 | 7.4796 | 6.233 | 3.7398
|  | Failure rate: | 1.1% | [12 empty] | Total Duration of Recovery Operations | 22.8483 | 411.2703 | 205.6351 | 137.0901 | 114.2417 | 68.545
|  | Assuming a weld failure rate of | 0.1%
|  | Assuming a tool failure rate of | 1%
|  | Probability of Secondary Failure/hr or Event | 0.04761%
[6 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies
| Group | Pipe weld failure (Sub Tasks) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack
| Cut Failed Welds | Weld Failure identified at central divertor pipe module joint | Operation | 0 | 0 | Hardware Recovery Required | 0 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Cut Failed Pipe Module Weld | Operation | 12.603 | 12.603 | Disconnect Divertor Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Pipe Module into Cask | Logistics | 0.38 | 12.983 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Remove Divertor Cooling Pipe Modules | Reposition Pipework equipment to the second pipework module | Logistics | 0.53 | 13.513 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Remove Left Divertor pipework module | Operation | 12.603 | 26.1159 | Disconnect Divertor Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Left Divertor pipework module in cask | Logistics | 0.38 | 26.4959 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Reposition Pipework equipment to the third pipe module | Logistics | 0.53 | 27.0259 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Remove Right Divertor pipework module | Operation | 12.603 | 39.6289 | Disconnect Divertor Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Right Divertor pipework module in cask | Logistics | 0.38 | 40.0089 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Retract Service Joint System into cask | Logistics | 0.38 | 40.3889 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Divertor Pipework Module Cask | Logistics | 2.3 | 42.6889 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Remove Central Cassette | Dock Divertor Handling Cask | Logistics | 1.9 | 44.5889 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Current payload stored; Divertor transport cask collected; cask moved to Lower Port | 7.3659 | 35.323
|  | Deploy Port Cleaning Equipment | Logistics | 0.38 | 44.9689 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Clean Port | Operation | 4.1 | 49.0689 | Clean Port | 4.1 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Port Cleaning Equipment | Logistics | 0.38 | 49.4489 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Deploy Cassette Handling Equipment | Logistics | 0.38 | 49.8289 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Remove Central Divertor cassette | Operation | 5.2 | 55.0289 | Remove Central Divertor Cassette | 5.2 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Cassette Handling Equipment | Logistics | 0.38 | 55.4089 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock failed Central Cassette Transport Cask | Logistics | 2.3 | 57.7089 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Remove Left Divertor Cassette | Dock Divertor Handling Cask | Logistics | 1.9 | 59.6089 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Failed Divertor Pipework Modules Stored; Cassette Transport Cask Prepared; Cassette Transport Cask Moved to Lower Port | 50.0826 | 7.6263
|  | Deploy Cassette Handling Equipment | Logistics | 0.38 | 59.9889 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Remove Left Divertor cassette | Operation | 1 | 60.9889 | Remove Peripheral Divertor Cassette | 1 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Cassette Handling Equipment | Logistics | 0.38 | 61.3689 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Left Cassette Transport Cask | Logistics | 2.3 | 63.6689 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Remove Right Divertor Cassette | Dock Divertor Handling Cask | Logistics | 1.9 | 70.7226 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Central Cassette Stored; Cassette Transport Cask Moved to Lower Port | 68.8226 | -5.1537
|  | Deploy Cassette Handling Equipment | Logistics | 0.38 | 71.1026 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Remove Right divertor cassette | Operation | 1 | 72.1026 | Remove Peripheral Divertor Cassette | 1 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Cassette Handling Equipment | Logistics | 0.38 | 72.4826 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Right Cassette Transport Cask | Logistics | 2.3 | 74.7826 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Install Right Divertor Cassette | Dock Cassette Handling Cask | Logistics | 1.9 | 76.6826 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Left Cassette Stored; Replacement Right Cassette collected; Transport Cask Moved to Lower Port | 71.1552 | 3.6274
|  | Deploy Cassette Handling Equipment | Logistics | 0.38 | 77.0626 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Install Right Divertor cassette | Operation | 1 | 78.0626 | Install Peripheral Divertor Cassette | 1 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Cassette Handling Equipment | Logistics | 0.38 | 78.4426 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Empty Right Cassette Transport Cask | Logistics | 2.3 | 80.7426 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Install Left Divertor Cassette | Dock Divertor Handling Cask | Logistics | 1.9 | 84.1689 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Right Cassette Stored; Replacement Left Cassette collected; Transport Cask Moved to Lower Port | 82.2689 | -1.5263
|  | Deploy Cassette Handling Equipment | Logistics | 0.38 | 84.5489 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Install Left Divertor cassette | Operation | 1 | 85.5489 | Install Peripheral Divertor Cassette | 1 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Cassette Handling Equipment | Logistics | 0.38 | 85.9289 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Empty Left Cassette Transport Cask | Logistics | 2.3 | 88.2289 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Install Central Divertor Cassette | Dock Divertor Handling Cask | Logistics | 1.9 | 90.1289 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Collect replacement central cassette from stores; Move transporter to Lower Port | 87.4174 | 0.81148
|  | Deploy Cassette Handling Equipment | Logistics | 0.38 | 90.5089 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Install Right Divertor cassette | Operation | 0.8 | 91.3089 | Install Central Divertor Cassette | 0.8 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Cassette Handling Equipment | Logistics | 0.38 | 91.6889 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Empty Central Divertor Transport Cask | Logistics | 2.3 | 93.9889 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Install Divertor Cooling Pipework Modules | Dock Service Joint System Cask | Logistics | 1.9 | 95.8889 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Store failed central Divertor; Collect replacement cassette from stores; Move transporter to Lower Port | 65.1952 | 28.7937
|  | Deploy Service Joint System | Logistics | 0.38 | 96.2689 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Extract Right Divertor Pipework Module from Cask | Logistics | 0.38 | 96.6489 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Install Right Divertor Blanket Pipe Module | Operation | 7.8621 | 104.511 | Connect Divertor Pipe Module | 7.8621 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Extract Pipework Module from Cask | Logistics | 0.38 | 104.891 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Reposition Pipework equipment to the second pipework module location | Logistics | 0.53 | 105.421 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Install left divertor pipework module | Operation | 7.8621 | 113.2832 | Connect Divertor Pipe Module | 7.8621 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Extract third Pipe Module from Cask | Logistics | 0.38 | 113.6632 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Reposition Pipework equipment to the third pipe module | Logistics | 0.53 | 114.1932 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Install central divertor pipework module | Operation | 7.8621 | 122.0553 | Connect Divertor Pipe Module | 7.8621 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Service Joint System into cask | Logistics | 0.38 | 122.4353 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  |  | Total |  | 122.4353
Failure of Left divertor coolant welds
Assumptions:
TIG welding and laser cutting is the current worst case scenario
|  | Any LOB pipe joint failures are detected prior to the installation of the COB pipework | [14 empty] | Single Port | Full Maintenance Campaign
|  | In-situ surface treatment is not possible, so all hardware must be removed and replaced/reconditioned before it can be re-welded | [13 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
|  | All other positioning, delivery and retrieval operations are of a similar length to nominal operations | [13 empty] | Duration of welding operations (h) | 16.9651 | 305.371 | 152.6855 | 101.7903 | 84.8253 | 50.8952
|  | Service Joint system is capable of cutting and pipes without tool change | [13 empty] | Estimated number of failures, impacting all RM systems equally | 0.18662 | 3.3591 | 1.6795 | 1.1197 | 0.93308 | 0.55985
|  | No additional blanket modules will need to be removed to access impacted blanket module | [13 empty] | Operational contribution | 10.2695 | 184.851 | 92.4255 | 61.617 | 51.3475 | 30.8085
[16 empty] | Logistical contribution | 7.1735 | 129.1231 | 64.5615 | 43.041 | 35.8675 | 21.5205
[16 empty] | Idle time due to waiting for dependant operations | 4.7765 | 85.9763 | 42.9882 | 28.6588 | 23.8823 | 14.3294
|  | Failure rate: | 1.1% | [12 empty] | Total Duration of Recovery Operations | 22.2195 | 399.9504 | 199.9752 | 133.3168 | 111.0973 | 66.6584
|  | Assuming a weld failure rate of | 0.1%
|  | Assuming a tool failure rate of | 1%
|  | Probability of Secondary Failure/hr or Event | 0.04761%
[6 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies
| Group | Pipe weld failure (Sub Tasks) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack
| Cut Failed Welds | Weld Failure identified at left divertor pipe module joint | Operation | 0 | 0 | Hardware Recovery Required | 0 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Cut Failed Pipe Module Weld | Operation | 12.603 | 12.603 | Disconnect Divertor Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Pipe Module into Cask | Logistics | 0.38 | 12.983 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
| Remove Divertor Cooling Pipe Modules | Reposition Pipework equipment to the second pipework module | Logistics | 0.53 | 13.513 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Remove central Divertor pipework module | Operation | 12.603 | 26.1159 | Disconnect Divertor Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store central Divertor pipework module in cask | Logistics | 0.38 | 26.4959 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Retract Service Joint System into cask | Logistics | 0.38 | 26.8759 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Divertor Pipework Module Cask | Logistics | 2.3 | 29.1759 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Remove Central Cassette | Dock Divertor Handling Cask | Logistics | 1.9 | 31.0759 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Current payload stored; Divertor transport cask collected; cask moved to Lower Port | 7.3659 | 21.81
|  | Deploy Port Cleaning Equipment | Logistics | 0.38 | 31.4559 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Clean Port | Operation | 4.1 | 35.5559 | Clean Port | 4.1 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Port Cleaning Equipment | Logistics | 0.38 | 35.9359 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Deploy Cassette Handling Equipment | Logistics | 0.38 | 36.3159 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Remove Central Divertor cassette | Operation | 5.2 | 41.5159 | Remove Central Divertor Cassette | 5.2 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Cassette Handling Equipment | Logistics | 0.38 | 41.8959 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Full Central Cassette Transport Cask | Logistics | 2.3 | 44.1959 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Remove Left Divertor Cassette | Dock Divertor Handling Cask | Logistics | 1.9 | 46.0959 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Failed Divertor Pipework Modules Stored; Cassette Transport Cask Prepared; Cassette Transport Cask Moved to Lower Port | 36.5696 | 7.6263
|  | Deploy Cassette Handling Equipment | Logistics | 0.38 | 46.4759 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Remove Left Divertor cassette | Operation | 1 | 47.4759 | Remove Peripheral Divertor Cassette | 1 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Cassette Handling Equipment | Logistics | 0.38 | 47.8559 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Failed Cassette Transport Cask | Logistics | 2.3 | 50.1559 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Remove Right Divertor Cassette | Dock Divertor Handling Cask | Logistics | 1.9 | 52.0559 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Central Cassette Stored; Cassette Transport Cask Moved to Lower Port | 41.0167 | 9.1393
|  | Deploy Cassette Handling Equipment | Logistics | 0.38 | 52.4359 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Remove Right divertor cassette | Operation | 1 | 53.4359 | Remove Peripheral Divertor Cassette | 1 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Cassette Handling Equipment | Logistics | 0.38 | 53.8159 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Failed right Cassette Transport Cask | Logistics | 2.3 | 56.1159 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Install Right Divertor Cassette | Dock Cassette Handling Cask | Logistics | 1.9 | 58.0159 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Left Cassette Stored; Replacement Right Cassette collected; Transport Cask Moved to Lower Port | 47.3767 | 8.7393
|  | Deploy Cassette Handling Equipment | Logistics | 0.38 | 58.3959 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Install Right Divertor cassette | Operation | 1 | 59.3959 | Install Peripheral Divertor Cassette | 1 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Cassette Handling Equipment | Logistics | 0.38 | 59.7759 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Empty Right Cassette Transport Cask | Logistics | 2.3 | 62.0759 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Install Left Divertor Cassette | Dock Divertor Handling Cask | Logistics | 1.9 | 69.1296 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Central Cassette Stored; Replacement Cassette collected; Transport Cask Moved to Lower Port | 55.3096 | -5.1537
|  | Deploy Cassette Handling Equipment | Logistics | 0.38 | 69.5096 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Install Left Divertor cassette | Operation | 1 | 70.5096 | Install Peripheral Divertor Cassette | 1 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Cassette Handling Equipment | Logistics | 0.38 | 70.8896 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Empty Left Cassette Transport Cask | Logistics | 2.3 | 73.1896 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Install Central Divertor Cassette | Dock Divertor Handling Cask | Logistics | 1.9 | 82.5759 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Store failed left Divertor; Collect replacement cassette from stores; Move transporter to Lower Port | 80.6759 | -7.4863
|  | Deploy Cassette Handling Equipment | Logistics | 0.38 | 82.9559 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Install Right Divertor cassette | Operation | 0.8 | 83.7559 | Install Central Divertor Cassette | 0.8 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Cassette Handling Equipment | Logistics | 0.38 | 84.1359 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Empty Central Divertor Transport Cask | Logistics | 2.3 | 86.4359 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Install Divertor Cooling Pipework Modules | Dock Service Joint System Cask | Logistics | 1.9 | 101.2911 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Divertor cassette transport stored; Replacement pipe modules collected; replacement pipework transported to the lower port | 99.3911 | -12.9552
|  | Deploy Service Joint System | Logistics | 0.38 | 101.6711 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Extract Right Divertor Pipework Module from Cask | Logistics | 0.38 | 102.0511 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Install Left Divertor Blanket Pipe Module | Operation | 7.8621 | 109.9133 | Connect Divertor Pipe Module | 7.8621 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Extract Pipework Module from Cask | Logistics | 0.38 | 110.2933 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Reposition Pipework equipment to the second pipework module location | Logistics | 0.53 | 110.8233 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Install central divertor pipework module | Operation | 7.8621 | 118.6854 | Connect Divertor Pipe Module | 7.8621 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Service Joint System into cask | Logistics | 0.38 | 119.0654 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  |  | Total |  | 119.0654
Failure of Right divertor coolant welds
Assumptions:
TIG welding and laser cutting is the current worst case scenario
|  | Any LOB pipe joint failures are detected prior to the installation of the COB pipework | [14 empty] | Single Port | Full Maintenance Campaign
|  | In-situ surface treatment is not possible, so all hardware must be removed and replaced/reconditioned before it can be re-welded | [13 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
|  | All other positioning, delivery and retrieval operations are of a similar length to nominal operations | [13 empty] | Duration of welding operations (h) | 16.9651 | 305.371 | 152.6855 | 101.7903 | 84.8253 | 50.8952
|  | Service Joint system is capable of cutting and pipes without tool change | [13 empty] | Estimated number of failures, impacting all RM systems equally | 0.18662 | 3.3591 | 1.6795 | 1.1197 | 0.93308 | 0.55985
|  | No additional blanket modules will need to be removed to access impacted blanket module | [13 empty] | Operational contribution | 6.4504 | 116.107 | 58.0535 | 38.7023 | 32.252 | 19.3512
[16 empty] | Logistical contribution | 6.763 | 121.7331 | 60.8666 | 40.5777 | 33.8148 | 20.2889
[16 empty] | Idle time due to waiting for dependant operations | 3.7016 | 66.628 | 33.314 | 22.2093 | 18.5078 | 11.1047
|  | Failure rate: | 1.1% | [12 empty] | Total Duration of Recovery Operations | 16.9149 | 304.4681 | 152.2341 | 101.4894 | 84.5745 | 50.7447
|  | Assuming a weld failure rate of | 0.1%
|  | Assuming a tool failure rate of | 1%
|  | Probability of Secondary Failure/hr or Event | 0.04761%
[6 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies
| Group | Pipe weld failure (Sub Tasks) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack
| Cut Failed Welds | Weld Failure identified at right divertor pipe module joint | Operation | 0 | 0 | Hardware Recovery Required | 0 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Cut Failed Pipe Module Weld | Operation | 12.603 | 12.603 | Disconnect Divertor Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Pipe Module into Cask | Logistics | 0.38 | 12.983 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Failed Divertor Pipework Module Cask | Logistics | 2.3 | 15.283 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Remove Central Cassette | Dock Divertor Handling Cask | Logistics | 1.9 | 17.183 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Current payload stored; Divertor transport cask collected; cask moved to Lower Port | 7.3659 | 7.917
|  | Deploy Port Cleaning Equipment | Logistics | 0.38 | 17.563 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Clean Port | Operation | 4.1 | 21.663 | Clean Port | 4.1 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Port Cleaning Equipment | Logistics | 0.38 | 22.043 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Deploy Cassette Handling Equipment | Logistics | 0.38 | 22.423 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Remove Central Divertor cassette | Operation | 5.2 | 27.623 | Remove Central Divertor Cassette | 5.2 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Cassette Handling Equipment | Logistics | 0.38 | 28.003 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Full Central Cassette Transport Cask | Logistics | 2.3 | 30.303 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Remove Left Divertor Cassette | Dock Divertor Handling Cask | Logistics | 1.9 | 32.203 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | failed Divertor Pipework Modules Stored; Cassette Transport Cask Prepared; Cassette Transport Cask Moved to Lower Port | 22.6767 | 7.6263
|  | Deploy Cassette Handling Equipment | Logistics | 0.38 | 32.583 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Remove Left Divertor cassette | Operation | 1 | 33.583 | Remove Peripheral Divertor Cassette | 1 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Cassette Handling Equipment | Logistics | 0.38 | 33.963 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Left Cassette Transport Cask | Logistics | 2.3 | 36.263 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Remove Right Divertor Cassette | Dock Divertor Handling Cask | Logistics | 1.9 | 42.9167 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Central Cassette Stored; Cassette Transport Cask Moved to Lower Port | 41.0167 | -4.7537
|  | Deploy Cassette Handling Equipment | Logistics | 0.38 | 43.2967 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Remove Right divertor cassette | Operation | 1 | 44.2967 | Remove Peripheral Divertor Cassette | 1 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Cassette Handling Equipment | Logistics | 0.38 | 44.6767 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Failed right Cassette Transport Cask | Logistics | 2.3 | 46.9767 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Install Right Divertor Cassette | Dock Cassette Handling Cask | Logistics | 1.9 | 49.2767 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Left Cassette Stored; Replacement Right Cassette collected; Transport Cask Moved to Lower Port | 47.3767 | -0.4
|  | Deploy Cassette Handling Equipment | Logistics | 0.38 | 49.6567 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Install Right Divertor cassette | Operation | 1 | 50.6567 | Install Peripheral Divertor Cassette | 1 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Cassette Handling Equipment | Logistics | 0.38 | 51.0367 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Empty Right Cassette Transport Cask | Logistics | 2.3 | 53.3367 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Install Left Divertor Cassette | Dock Divertor Handling Cask | Logistics | 1.9 | 62.723 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Store failed right Divertor; Collect replacement left cassette from stores; Move transporter to Lower Port | 60.823 | -7.4863
|  | Deploy Cassette Handling Equipment | Logistics | 0.38 | 63.103 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Install Left Divertor cassette | Operation | 1 | 64.103 | Install Peripheral Divertor Cassette | 1 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Cassette Handling Equipment | Logistics | 0.38 | 64.483 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Empty Left Cassette Transport Cask | Logistics | 2.3 | 66.783 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Install Central Divertor Cassette | Dock Divertor Handling Cask | Logistics | 1.9 | 68.683 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Collect replacement central cassette from stores; Move transporter to Lower Port | 60.0115 | 6.7715
|  | Deploy Cassette Handling Equipment | Logistics | 0.38 | 69.063 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Install Right Divertor cassette | Operation | 0.8 | 69.863 | Install Central Divertor Cassette | 0.8 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Cassette Handling Equipment | Logistics | 0.38 | 70.243 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Empty Central Divertor Transport Cask | Logistics | 2.3 | 72.543 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
| Install Divertor Cooling Pipework Modules | Dock Service Joint System Cask | Logistics | 1.9 | 81.6382 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 | Divertor cassette transport stored; Replacement pipe modules collected; replacement pipework transported to the lower port | 79.7382 | -7.1952
|  | Deploy Service Joint System | Logistics | 0.38 | 82.0182 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Extract Right Divertor Pipework Module from Cask | Logistics | 0.38 | 82.3982 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
|  | Install Right Divertor Blanket Pipe Module | Operation | 7.8621 | 90.2603 | Connect Divertor Pipe Module | 7.8621 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Service Joint System into cask | Logistics | 0.38 | 90.6403 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool / Hardware In Transport Cask | 0.38 |  | N/A | N/A
|  |  | Total |  | 90.6403

## LowerCask Recovery Dependencies (hidden)
[5 empty] | Operations |  | Movement | [5 empty] | Logistics
Group | Activity | Activity Type | Time (h) | Cumulative | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h)
Lower Port Pipe COB Weld Failure
Right Divertor Cassette Stored; Cassette Transport Cask Stored; Inboard Pipework Cask Prepared; Inboard Pipework Cask moved to Lower Port | Weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter to AMF Hardware Receipt | Movement | 0.23148 | 0.23148 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Dock cask | Logistics | 1.9 | 2.1315 |  | N/A |  |  |  | N/A | N/A | N/A | Dock cask and commission RM systems | 1.9
| Store Cassette Transport Cask | Logistics | 0.58 | 2.7115 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 2.7393 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Inboard Pipework Cask | Logistics | 0.78 | 3.5193 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78
| Move Inboard Pipework Cask to Lower Port | Movement | 0.69444 | 4.2137 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Right Divertor Cassette Stored; Cassette Transport Cask Stored; Inboard Pipework Cask Prepared; Inboard Pipework Cask moved to Lower Port | Total | 0 | 4.2137 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Outboard Pipework Cask Stored; Inner Port Pipework Cask Prepared; Inner Port Pipework Cask Moved to Lower Port | Un-dock Outboard Pipe Module Cask | Trigger | 0 | 51.1089 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter to AMF Hardware Receipt | Movement | 0.23148 | 51.3404 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Casks | Logistics | 0.58 | 51.9204 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 51.9482 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Inner Port Pipework Cask | Logistics | 0.88 | 52.8282 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware from the AMF | 0.88
| Move Inner Port Pipework Cask to Lower Port | Movement | 0.69444 | 53.5226 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Outboard Pipework Cask Stored; Inner Port Pipework Cask Prepared; Inner Port Pipework Cask Moved to Lower Port | Total | 0 | 53.5226 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Removed Inboard blankets stored, New Inner Port Pipe Modules Collected and moved to port | Un-dock Inboard Blanket Pipe Cask | Trigger | 0 | 82.5648 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Inboard Port Pipework Cask to AMF Equipment Receipt | Movement | 0.23148 | 82.7963 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Inboard Port Pipework Cask | Logistics | 0.58 | 83.3763 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 83.4041 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Replacement Inner Port Pipework cask | Logistics | 0.78 | 84.1841 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78
| Move Pipework Cask to Lower Port | Movement | 0.69444 | 84.8785 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Removed Inboard blankets stored, New Inner Port Pipe Modules Collected and moved to port | Total | 0 | 84.8785 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Removed Inner Port Pipe Modules stored, New Inboard Pipe Modules Collected and moved to port | Un-Dock Inner Pipework Cask | Trigger | 0 | 103.8608 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Inner Port Pipework Cask to AMF Equipment Receipt | Movement | 0.23148 | 104.0923 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Inner Port Pipework Cask | Logistics | 0.58 | 104.6723 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 104.7 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Replacement Inboard Port Pipework cask | Logistics | 0.78 | 105.48 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78
| Move Pipework Cask to Lower Port | Movement | 0.69444 | 106.1745 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Removed Inner Port Pipe Modules stored, New Inboard Pipe Modules Collected and moved to port | Total | 0 | 106.1745 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Inner Port Pipe Cask stored; New Outboard Pipe Modules Collected and moved to port | Un-Dock Empty Inner Port Pipework Cask | Trigger | 0 | 235.6266 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Inner Port Pipework Cask to AMF Equipment Receipt | Movement | 0.23148 | 235.858 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Inner Port Pipework Cask | Logistics | 0.58 | 236.438 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 236.4658 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Replacement Outboard Port Pipework cask | Logistics | 0.78 | 237.2458 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78
| Move Pipework Cask to Lower Port | Movement | 0.69444 | 237.9403 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Inner Port Pipe Cask stored; New Outboard Pipe Modules Collected and moved to port | Total | 0 | 237.9403 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
COB Blanket segment installed | Lower Port COB weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 111.8794 | 111.8794 | Install COB Blanket Segment | 111.8794 |  |  |  | N/A | N/A | N/A |  | N/A
| COB Blanket segment installed | Total | 0 | 111.8794 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
COB Upper Port Pipe Module installed | Lower Port COB weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 331.2599 | 331.2599 | Insert COB Pipe Module | 331.2599 |  |  |  | N/A | N/A | N/A |  | N/A
| COB Upper Port Pipe Module installed | Total | 0 | 331.2599 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Blanket segment installed | Lower Port COB weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 106.07 | 106.07 | Install LOB Blanket Segment | 106.07 |  |  |  | N/A | N/A | N/A |  | N/A
| LOB Blanket segment installed | Total | 0 | 106.07 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Upper Port Pipe Module installed | Lower Port COB weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 277.3933 | 277.3933 | Insert LOB Pipe Module | 277.3933 |  |  |  | N/A | N/A | N/A |  | N/A
| LOB Upper Port Pipe Module installed | Total | 0 | 277.3933 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Blanket segment installed | Lower Port COB weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 100.2606 | 100.2606 | Install ROB Blanket Segment | 100.2606 |  |  |  | N/A | N/A | N/A |  | N/A
| ROB Blanket segment installed | Total | 0 | 100.2606 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Upper Port Pipe Module installed | Lower Port COB weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 240.4733 | 240.4733 | Insert ROB Pipe Module | 240.4733 |  |  |  | N/A | N/A | N/A |  | N/A
| ROB Upper Port Pipe Module installed | Total | 0 | 240.4733 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Blanket segment installed | Lower Port COB weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 215.3239 | 215.3239 | Install LIB Blanket Segment | 215.3239 |  |  |  | N/A | N/A | N/A |  | N/A
| LIB Blanket segment installed | Total | 0 | 215.3239 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Upper Port Pipe Module installed | Lower Port COB weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 168.515 | 168.515 | Insert LIB Pipe Module | 168.515 |  |  |  | N/A | N/A | N/A |  | N/A
| LIB Upper Port Pipe Module installed | Total | 0 | 168.515 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Blanket segment installed | Lower Port COB weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 91.4617 | 91.4617 | Install RIB Blanket Segment | 91.4617 |  |  |  | N/A | N/A | N/A |  | N/A
| RIB Blanket segment installed | Total | 0 | 91.4617 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Upper Port Pipe Module installed | Lower Port COB weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 116.6689 | 116.6689 | Insert RIB Pipe Module | 116.6689 |  |  |  | N/A | N/A | N/A |  | N/A
| RIB Upper Port Pipe Module installed | Total | 0 | 116.6689 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Lower Port Pipe LOB Weld Failure
Right Divertor Cassette Stored; Cassette Transport Cask Stored; Inboard Pipework Cask Prepared; Inboard Pipework Cask moved to Lower Port | Weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter to AMF Hardware Receipt | Movement | 0.23148 | 0.23148 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Dock cask | Logistics | 1.9 | 2.1315 |  | N/A |  |  |  | N/A | N/A | N/A | Dock cask and commission RM systems | 1.9
| Store Cassette Transport Cask | Logistics | 0.58 | 2.7115 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 2.7393 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Inboard Pipework Cask | Logistics | 0.78 | 3.5193 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78
| Move Inboard Pipework Cask to Lower Port | Movement | 0.69444 | 4.2137 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Right Divertor Cassette Stored; Cassette Transport Cask Stored; Inboard Pipework Cask Prepared; Inboard Pipework Cask moved to Lower Port | Total | 0 | 4.2137 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Outboard Pipework Cask Stored; Inner Port Pipework Cask Prepared; Inner Port Pipework Cask Moved to Lower Port | Un-dock Outboard Pipe Module Cask | Trigger | 0 | 29.1759 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter to AMF Hardware Receipt | Movement | 0.23148 | 29.4074 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Casks | Logistics | 0.58 | 29.9874 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 30.0152 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Inner Port Pipework Cask | Logistics | 0.88 | 30.8952 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware from the AMF | 0.88
| Move Inner Port Pipework Cask to Lower Port | Movement | 0.69444 | 31.5896 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Outboard Pipework Cask Stored; Inner Port Pipework Cask Prepared; Inner Port Pipework Cask Moved to Lower Port | Total | 0 | 31.5896 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Removed Inboard blankets stored, New Inner Port Pipe Modules Collected and moved to port | Un-dock Inboard Blanket Pipe Cask | Trigger | 0 | 60.6319 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Inboard Port Pipework Cask to AMF Equipment Receipt | Movement | 0.23148 | 60.8633 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Inboard Port Pipework Cask | Logistics | 0.58 | 61.4433 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 61.4711 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Replacement Inner Port Pipework cask | Logistics | 0.78 | 62.2511 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78
| Move Pipework Cask to Lower Port | Movement | 0.69444 | 62.9456 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Removed Inboard blankets stored, New Inner Port Pipe Modules Collected and moved to port | Total | 0 | 62.9456 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Removed Inner Port Pipe Modules stored, New Inboard Pipe Modules Collected and moved to port | Un-Dock Inner Pipework Cask | Trigger | 0 | 81.9278 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Inner Port Pipework Cask to AMF Equipment Receipt | Movement | 0.23148 | 82.1593 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Inner Port Pipework Cask | Logistics | 0.58 | 82.7393 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 82.7671 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Replacement Inboard Port Pipework cask | Logistics | 0.78 | 83.5471 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78
| Move Pipework Cask to Lower Port | Movement | 0.69444 | 84.2415 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Removed Inner Port Pipe Modules stored, New Inboard Pipe Modules Collected and moved to port | Total | 0 | 84.2415 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Inner Port Pipe Cask stored; New Outboard Pipe Modules Collected and moved to port | Un-Dock Empty Inner Port Pipework Cask | Trigger | 0 | 122.5131 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Inner Port Pipework Cask to AMF Equipment Receipt | Movement | 0.23148 | 122.7446 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Inner Port Pipework Cask | Logistics | 0.58 | 123.3246 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 123.3524 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Replacement Outboard Port Pipework cask | Logistics | 0.78 | 124.1324 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78
| Move Pipework Cask to Lower Port | Movement | 0.69444 | 124.8268 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Inner Port Pipe Cask stored; New Outboard Pipe Modules Collected and moved to port | Total | 0 | 124.8268 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Blanket segment installed | Lower Port COB weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 78.2606 | 78.2606 | Install LOB Blanket Segment | 78.2606 |  |  |  | N/A | N/A | N/A |  | N/A
| LOB Blanket segment installed | Total | 0 | 78.2606 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Upper Port Pipe Module installed | Lower Port COB weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 266.2471 | 266.2471 | Insert LOB Pipe Module | 266.2471 |  |  |  | N/A | N/A | N/A |  | N/A
| LOB Upper Port Pipe Module installed | Total | 0 | 266.2471 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Blanket segment installed | Lower Port COB weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 72.4511 | 72.4511 | Install ROB Blanket Segment | 72.4511 |  |  |  | N/A | N/A | N/A |  | N/A
| ROB Blanket segment installed | Total | 0 | 72.4511 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Upper Port Pipe Module installed | Lower Port COB weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 229.3272 | 229.3272 | Insert ROB Pipe Module | 229.3272 |  |  |  | N/A | N/A | N/A |  | N/A
| ROB Upper Port Pipe Module installed | Total | 0 | 229.3272 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Blanket segment installed | Lower Port COB weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 68.0517 | 68.0517 | Install LIB Blanket Segment | 68.0517 |  |  |  | N/A | N/A | N/A |  | N/A
| LIB Blanket segment installed | Total | 0 | 68.0517 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Upper Port Pipe Module installed | Lower Port COB weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 192.4072 | 192.4072 | Insert LIB Pipe Module | 192.4072 |  |  |  | N/A | N/A | N/A |  | N/A
| LIB Upper Port Pipe Module installed | Total | 0 | 192.4072 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Blanket segment installed | Lower Port COB weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 63.6522 | 63.6522 | Install RIB Blanket Segment | 63.6522 |  |  |  | N/A | N/A | N/A |  | N/A
| RIB Blanket segment installed | Total | 0 | 63.6522 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Upper Port Pipe Module installed | Lower Port COB weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 88.8595 | 88.8595 | Insert RIB Pipe Module | 88.8595 |  |  |  | N/A | N/A | N/A |  | N/A
| RIB Upper Port Pipe Module installed | Total | 0 | 88.8595 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Lower Port Pipe ROB Weld Failure
Right Divertor Cassette Stored; Cassette Transport Cask Stored; Inboard Pipework Cask Prepared; Inboard Pipework Cask moved to Lower Port | Weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter to AMF Hardware Receipt | Movement | 0.23148 | 0.23148 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Dock cask | Logistics | 1.9 | 2.1315 |  | N/A |  |  |  | N/A | N/A | N/A | Dock cask and commission RM systems | 1.9
| Store Cassette Transport Cask | Logistics | 0.58 | 2.7115 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 2.7393 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Inboard Pipework Cask | Logistics | 0.78 | 3.5193 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78
| Move Inboard Pipework Cask to Lower Port | Movement | 0.69444 | 4.2137 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Right Divertor Cassette Stored; Cassette Transport Cask Stored; Inboard Pipework Cask Prepared; Inboard Pipework Cask moved to Lower Port | Total | 0 | 4.2137 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Outboard Pipework Cask Stored; Inner Port Pipework Cask Prepared; Inner Port Pipework Cask Moved to Lower Port | Un-Dock Inboard Blanket Pipe Cask | Trigger | 0 | 44.8389 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter to AMF Hardware Receipt | Movement | 0.23148 | 45.0704 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Casks | Logistics | 0.58 | 45.6504 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 45.6782 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Inner Port Pipework Cask | Logistics | 0.88 | 46.5582 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware from the AMF | 0.88
| Move Inner Port Pipework Cask to Lower Port | Movement | 0.69444 | 47.2526 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Outboard Pipework Cask Stored; Inner Port Pipework Cask Prepared; Inner Port Pipework Cask Moved to Lower Port | Total | 0 | 47.2526 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Removed Inboard blankets stored, New Inner Port Pipe Modules Collected and moved to port | Un-dock Inboard Blanket Pipe Cask | Trigger | 0 | 44.8389 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Inboard Port Pipework Cask to AMF Equipment Receipt | Movement | 0.23148 | 45.0704 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Inboard Port Pipework Cask | Logistics | 0.58 | 45.6504 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 45.6782 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Replacement Inner Port Pipework cask | Logistics | 0.78 | 46.4582 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78
| Move Pipework Cask to Lower Port | Movement | 0.69444 | 47.1526 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Removed Inboard blankets stored, New Inner Port Pipe Modules Collected and moved to port | Total | 0 | 47.1526 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Removed Inner Port Pipe Modules stored, New Inboard Pipe Modules Collected and moved to port | Un-Dock Inner Pipework Cask | Trigger | 0 | 70.4485 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Inner Port Pipework Cask to AMF Equipment Receipt | Movement | 0.23148 | 70.68 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Inner Port Pipework Cask | Logistics | 0.58 | 71.26 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 71.2878 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Replacement Inboard Port Pipework cask | Logistics | 0.78 | 72.0678 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78
| Move Pipework Cask to Lower Port | Movement | 0.69444 | 72.7622 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Removed Inner Port Pipe Modules stored, New Inboard Pipe Modules Collected and moved to port | Total | 0 | 72.7622 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Inner Port Pipe Cask stored; New Outboard Pipe Modules Collected and moved to port | Un-Dock Empty Inner Port Pipework Cask | Trigger | 0 | 111.0339 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Inner Port Pipework Cask to AMF Equipment Receipt | Movement | 0.23148 | 111.2653 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Inner Port Pipework Cask | Logistics | 0.58 | 111.8453 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 111.8731 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Replacement Outboard Port Pipework cask | Logistics | 0.78 | 112.6531 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78
| Move Pipework Cask to Lower Port | Movement | 0.69444 | 113.3476 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Inner Port Pipe Cask stored; New Outboard Pipe Modules Collected and moved to port | Total | 0 | 113.3476 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Blanket segment installed | Lower Port COB weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 63.5476 | 63.5476 | Install ROB Blanket Segment | 63.5476 |  |  |  | N/A | N/A | N/A |  | N/A
| ROB Blanket segment installed | Total | 0 | 63.5476 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Upper Port Pipe Module installed | Lower Port COB weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 192.4072 | 192.4072 | Insert ROB Pipe Module | 192.4072 |  |  |  | N/A | N/A | N/A |  | N/A
| ROB Upper Port Pipe Module installed | Total | 0 | 192.4072 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Blanket segment installed | Lower Port COB weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 59.1482 | 59.1482 | Install LIB Blanket Segment | 59.1482 |  |  |  | N/A | N/A | N/A |  | N/A
| LIB Blanket segment installed | Total | 0 | 59.1482 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Upper Port Pipe Module installed | Lower Port COB weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 153.5795 | 153.5795 | Insert LIB Pipe Module | 153.5795 |  |  |  | N/A | N/A | N/A |  | N/A
| LIB Upper Port Pipe Module installed | Total | 0 | 153.5795 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Blanket segment installed | Lower Port COB weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 54.7487 | 54.7487 | Install RIB Blanket Segment | 54.7487 |  |  |  | N/A | N/A | N/A |  | N/A
| RIB Blanket segment installed | Total | 0 | 54.7487 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Upper Port Pipe Module installed | Lower Port COB weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 79.9559 | 79.9559 | Insert RIB Pipe Module | 79.9559 |  |  |  | N/A | N/A | N/A |  | N/A
| RIB Upper Port Pipe Module installed | Total | 0 | 79.9559 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Lower Port Pipe LIB Weld Failure
Outboard Port Pipework Cask Stored; Inner Port Pipework cask Prepared; Inner Port Pipework Cask Moved to Lower Port | Weld Failure identified LIB Lower Port pipe Module joint | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter to AMF Hardware Receipt | Movement | 0.23148 | 0.23148 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Casks | Logistics | 0.58 | 0.81148 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 0.83926 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Inner Port Pipework Cask | Logistics | 0.88 | 1.7193 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware from the AMF | 0.88
| Move Inner Port Pipework Cask to Lower Port | Movement | 0.69444 | 2.4137 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Outboard Port Pipework Cask Stored; Inner Port Pipework cask Prepared; Inner Port Pipework Cask Moved to Lower Port | Total | 0 | 2.4137 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Removed Inboard blankets stored, New Inner Port Pipe Modules Collected and moved to port | Un-dock Inboard Blanket Pipe Cask | Trigger | 0 | 31.8559 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Inboard Port Pipework Cask to AMF Equipment Receipt | Movement | 0.23148 | 32.0874 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Inboard Port Pipework Cask | Logistics | 0.58 | 32.6674 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 32.6952 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Replacement Inner Port Pipework cask | Logistics | 0.78 | 33.4752 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78
| Move Pipework Cask to Lower Port | Movement | 0.69444 | 34.1696 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Removed Inboard blankets stored, New Inner Port Pipe Modules Collected and moved to port | Total | 0 | 34.1696 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Removed Inner Port Pipe Modules stored, New Inboard Pipe Modules Collected and moved to port | Un-Dock Inner Pipework Cask | Trigger | 0 | 53.1519 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Inner Port Pipework Cask to AMF Equipment Receipt | Movement | 0.23148 | 53.3833 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Inner Port Pipework Cask | Logistics | 0.58 | 53.9633 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 53.9911 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Replacement Inboard Port Pipework cask | Logistics | 0.78 | 54.7711 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78
| Move Pipework Cask to Lower Port | Movement | 0.69444 | 55.4656 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Removed Inner Port Pipe Modules stored, New Inboard Pipe Modules Collected and moved to port | Total | 0 | 55.4656 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Blanket segment installed | Lower Port COB weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 49.8679 | 49.8679 | Install LIB Blanket Segment | 49.8679 |  |  |  | N/A | N/A | N/A |  | N/A
| LIB Blanket segment installed | Total | 0 | 49.8679 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Upper Port Pipe Module installed | Lower Port COB weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 107.5956 | 107.5956 | Insert LIB Pipe Module | 107.5956 |  |  |  | N/A | N/A | N/A |  | N/A
| LIB Upper Port Pipe Module installed | Total | 0 | 107.5956 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Blanket segment installed | Lower Port COB weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 45.4684 | 45.4684 | Install RIB Blanket Segment | 45.4684 |  |  |  | N/A | N/A | N/A |  | N/A
| RIB Blanket segment installed | Total | 0 | 45.4684 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Upper Port Pipe Module installed | Lower Port COB weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 70.6757 | 70.6757 | Insert RIB Pipe Module | 70.6757 |  |  |  | N/A | N/A | N/A |  | N/A
| RIB Upper Port Pipe Module installed | Total | 0 | 70.6757 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Lower Port Pipe RIB Weld Failure
Replacement Pipe modules collected from stores | Weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move cask to AMF hardware receipt | Movement | 0.69444 | 0.69444 |  | N/A | Cask Transporter (loaded) | Lower Port | AMF hardware issue | 50 | 0.02 | 0.69444 |  | N/A
| Dock cask | Logistics | 1.9 | 2.5944 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9
| Store current hardware | Logistics | 0.88 | 3.4744 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP hardware in the AMF | 0.88
| Un-dock cask | Logistics | 2.3 | 5.7744 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| move cask to AMF hardware issue | Movement | 0.046296 | 5.8207 |  | N/A | Cask Transporter (Empty cask) | AMF Hardware Receipt | AMF hardware issue | 10 | 0.06 | 0.046296 |  | N/A
| Dock cask | Logistics | 1.9 | 7.7207 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9
| Collect replacement pipe module | Logistics | 0.88 | 8.6007 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware from the AMF | 0.88
| Un-dock cask | Logistics | 2.3 | 10.9007 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Move to the lower port | Movement | 0.69444 | 11.5952 |  | N/A | Cask Transporter (loaded) | AMF Hardware issue | Lower port | 50 | 0.02 | 0.69444 |  | N/A
| Replacement Pipe modules collected from stores | Total | 0 | 11.5952 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Blanket segment installed | Lower Port COB weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 36.5649 | 36.5649 | Install RIB Blanket Segment | 36.5649 |  |  |  | N/A | N/A | N/A |  | N/A
| RIB Blanket segment installed | Total | 0 | 36.5649 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Upper Port Pipe Module installed | Lower Port COB weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 61.7721 | 61.7721 | Insert RIB Pipe Module | 61.7721 |  |  |  | N/A | N/A | N/A |  | N/A
| RIB Upper Port Pipe Module installed | Total | 0 | 61.7721 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Inner Port Pipe Weld Failure
Inboard Port Pipework Cask Stored; Inner Port Pipework cask Prepared; Inner Port Pipework Cask Moved to Lower Port | Inner LIB Weld Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter to AMF Hardware Receipt | Movement | 0.23148 | 0.23148 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Casks | Logistics | 0.58 | 0.81148 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 0.83926 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Inner Port Pipework Cask | Logistics | 0.88 | 1.7193 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware from the AMF | 0.88
| Move Inner Port Pipework Cask to Lower Port | Movement | 0.69444 | 2.4137 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Inboard Port Pipework Cask Stored; Inner Port Pipework cask Prepared; Inner Port Pipework Cask Moved to Lower Port | Total | 0 | 2.4137 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Blanket segment installed | Lower Port COB weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 149.0874 | 149.0874 | Install LIB Blanket Segment | 149.0874 |  |  |  | N/A | N/A | N/A |  | N/A
| LIB Blanket segment installed | Total | 0 | 149.0874 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Upper Port Pipe Module installed | Lower Port COB weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 252.2486 | 252.2486 | Install LIB Pipe Module | 252.2486 |  |  |  | N/A | N/A | N/A |  | N/A
| LIB Upper Port Pipe Module installed | Total | 0 | 252.2486 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Blanket segment installed | Lower Port COB weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 138.2858 | 138.2858 | Install RIB Blanket Segment | 138.2858 |  |  |  | N/A | N/A | N/A |  | N/A
| RIB Blanket segment installed | Total | 0 | 138.2858 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Upper Port Pipe Module installed | Lower Port COB weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 195.518 | 195.518 | Install RIB Pipe Module | 195.518 |  |  |  | N/A | N/A | N/A |  | N/A
| RIB Upper Port Pipe Module installed | Total | 0 | 195.518 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Inner Port Pipe Weld Failure
Inboard Port Pipework Cask Stored; Inner Port Pipework cask Prepared; Inner Port Pipework Cask Moved to Lower Port | Inner RIB Weld Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter to AMF Hardware Receipt | Movement | 0.23148 | 0.23148 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Casks | Logistics | 0.58 | 0.81148 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 0.83926 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Inner Port Pipework Cask | Logistics | 0.88 | 1.7193 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware from the AMF | 0.88
| Move Inner Port Pipework Cask to Lower Port | Movement | 0.69444 | 2.4137 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Inboard Port Pipework Cask Stored; Inner Port Pipework cask Prepared; Inner Port Pipework Cask Moved to Lower Port | Total | 0 | 2.4137 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Blanket segment installed | Lower Port COB weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 138.2858 | 138.2858 | Install RIB Blanket Segment | 138.2858 |  |  |  | N/A | N/A | N/A |  | N/A
| RIB Blanket segment installed | Total | 0 | 138.2858 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Upper Port Pipe Module installed | Lower Port COB weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 195.518 | 195.518 | Install RIB Pipe Module | 195.518 |  |  |  | N/A | N/A | N/A |  | N/A
| RIB Upper Port Pipe Module installed | Total | 0 | 195.518 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Central Divertor cooling Weld Failure
Current payload stored; Divertor transport cask collected; cask moved to Lower Port | Weld Failure identified at central divertor pipe module joint | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move cask to AMF hardware receipt | Movement | 0.69444 | 0.69444 |  | N/A | Cask Transporter (loaded) | Lower Port | AMF hardware issue | 50 | 0.02 | 0.69444 |  | N/A
| Dock cask | Logistics | 1.9 | 2.5944 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9
| Store current hardware | Logistics | 0.88 | 3.4744 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP hardware in the AMF | 0.88
| Un-dock cask | Logistics | 2.3 | 5.7744 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Store current cask | Logistics | 0.58 | 6.3544 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / hardware cask | 0.58
| Collect divertor transport cask | Logistics | 0.78 | 7.1344 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / hardware cask | 0.78
| Move cask to lower port | Movement | 0.23148 | 7.3659 |  | N/A | Cask Transporter (Empty cask) | AMF equipment issue | Lower Port | 50 | 0.06 | 0.23148 |  | N/A
| Current payload stored; Divertor transport cask collected; cask moved to Lower Port | Total | 0 | 7.3659 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Current payload stored; Divertor transport cask collected; cask moved to Lower Port | Weld Failure identified at central divertor pipe module joint | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move cask to AMF hardware receipt | Movement | 0.69444 | 0.69444 |  | N/A | Cask Transporter (loaded) | Lower Port | AMF hardware issue | 50 | 0.02 | 0.69444 |  | N/A
| Dock cask | Logistics | 1.9 | 2.5944 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9
| Store current hardware | Logistics | 0.88 | 3.4744 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP hardware in the AMF | 0.88
| Un-dock cask | Logistics | 2.3 | 5.7744 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Store current cask | Logistics | 0.58 | 6.3544 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / hardware cask | 0.58
| Collect divertor transport cask | Logistics | 0.78 | 7.1344 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / hardware cask | 0.78
| Move cask to lower port | Movement | 0.23148 | 7.3659 |  | N/A | Cask Transporter (Empty cask) | AMF equipment issue | Lower Port | 50 | 0.06 | 0.23148 |  | N/A
| Current payload stored; Divertor transport cask collected; cask moved to Lower Port | Total | 0 | 7.3659 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
failed Divertor Pipework Modules Stored; Cassette Transport Cask Prepared; Cassette Transport Cask Moved to Lower Port | Un-Dock Divertor Pipework Module Cask | Trigger | 0 | 42.6889 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter to AMF Hardware Receipt | Movement | 0.23148 | 42.9204 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Dock cask | Logistics | 1.9 | 44.8204 |  | N/A |  |  |  | N/A | N/A | N/A | Dock cask and commission RM systems | 1.9
| Store Divertor Pipework Modules | Logistics | 0.88 | 45.7004 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware in the AMF | 0.88
| Un-dock cask | Logistics | 2.3 | 48.0004 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 48.0282 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Store Cask | Logistics | 0.58 | 48.6082 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Collect Cassette Transport Cask | Logistics | 0.78 | 49.3882 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78
| Move Cassette Transport Cask to Lower Port | Movement | 0.69444 | 50.0826 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| failed Divertor Pipework Modules Stored; Cassette Transport Cask Prepared; Cassette Transport Cask Moved to Lower Port | Total | 0 | 50.0826 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Central Cassette Stored; Cassette Transport Cask Moved to Lower Port | Un-Dock failed Central Cassette Transport Cask | Trigger | 0 | 57.7089 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter to AMF Hardware Receipt | Movement | 0.69444 | 58.4033 |  | N/A | Cask Transporter (Loaded) | Lower Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Dock cask | Logistics | 1.9 | 60.3033 |  | N/A |  |  |  | N/A | N/A | N/A | Dock cask and commission RM systems | 1.9
| Store Central Cassette | Logistics | 0.88 | 61.1833 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP hardware in the AMF | 0.88
| Un-dock cask | Logistics | 2.3 | 63.4833 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 63.5111 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Dock cask | Logistics | 1.9 | 65.4111 |  | N/A |  |  |  | N/A | N/A | N/A | Dock cask and commission RM systems | 1.9
| Collect replacement divertor cassette | Logistics | 0.88 | 66.2911 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware from the AMF | 0.88
| Un-dock cask | Logistics | 2.3 | 68.5911 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Move Cassette Transport Cask to Lower Port | Movement | 0.23148 | 68.8226 |  | N/A | Cask Transporter (Empty Cask) | AMF Equipment Issue | Lower Port | 50 | 0.06 | 0.23148 |  | N/A
| Central Cassette Stored; Cassette Transport Cask Moved to Lower Port | Total | 0 | 68.8226 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Left Cassette Stored; Replacement Right Cassette collected; Transport Cask Moved to Lower Port | Un-Dock Left Cassette Transport Cask | Trigger | 0 | 63.6689 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move cask to AMF equipment receipt | Movement | 0.23148 | 63.9004 |  | N/A | Cask Transporter (Empty cask) | Lower Port | AMF equipment receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store divertor cask | Logistics | 0.58 | 64.4804 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / hardware cask | 0.58
| Move to AMF equipment issue | Movement | 0.027778 | 64.5082 |  | N/A | Cask Transporter (no cask) | AMF equipment receipt | AMF equipment issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect divertor pipework cask | Logistics | 0.78 | 65.2882 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / hardware cask | 0.78
| Move to AMF hardware issue | Movement | 0.092593 | 65.3808 |  | N/A | Cask Transporter (Empty cask) | AMF equipment Issue | AMF hardware issue | 20 | 0.06 | 0.092593 |  | N/A
| Dock cask | Logistics | 1.9 | 67.2808 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9
| Collect replacement pipework modules | Logistics | 0.88 | 68.1608 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware from the AMF | 0.88
| Un-dock caks | Logistics | 2.3 | 70.4608 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Move to lower port | Movement | 0.69444 | 71.1552 |  | N/A | Cask Transporter (loaded) | AMF hardware issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Left Cassette Stored; Replacement Right Cassette collected; Transport Cask Moved to Lower Port | Total | 0 | 71.1552 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Right Cassette Stored; Replacement Left Cassette collected; Transport Cask Moved to Lower Port | Un-Dock Right Cassette Transport Cask | Trigger | 0 | 74.7826 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move cask to AMF equipment receipt | Movement | 0.23148 | 75.0141 |  | N/A | Cask Transporter (Empty cask) | Lower Port | AMF equipment receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store divertor cask | Logistics | 0.58 | 75.5941 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / hardware cask | 0.58
| Move to AMF equipment issue | Movement | 0.027778 | 75.6219 |  | N/A | Cask Transporter (no cask) | AMF equipment receipt | AMF equipment issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect divertor pipework cask | Logistics | 0.78 | 76.4019 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / hardware cask | 0.78
| Move to AMF hardware issue | Movement | 0.092593 | 76.4945 |  | N/A | Cask Transporter (Empty cask) | AMF equipment Issue | AMF hardware issue | 20 | 0.06 | 0.092593 |  | N/A
| Dock cask | Logistics | 1.9 | 78.3945 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9
| Collect replacement pipework modules | Logistics | 0.88 | 79.2745 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware from the AMF | 0.88
| Un-dock caks | Logistics | 2.3 | 81.5745 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Move to lower port | Movement | 0.69444 | 82.2689 |  | N/A | Cask Transporter (loaded) | AMF hardware issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Right Cassette Stored; Replacement Left Cassette collected; Transport Cask Moved to Lower Port | Total | 0 | 82.2689 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Collect replacement central cassette from stores; Move transporter to Lower Port | un-dock empty right cassette transport cask | Trigger | 0 | 80.7426 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move to AMF equipment issue | Movement | 0.027778 | 80.7704 |  | N/A | Cask Transporter (no cask) | AMF equipment receipt | AMF equipment issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect divertor pipework cask | Logistics | 0.78 | 81.5504 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / hardware cask | 0.78
| Move to AMF hardware issue | Movement | 0.092593 | 81.643 |  | N/A | Cask Transporter (Empty cask) | AMF equipment Issue | AMF hardware issue | 20 | 0.06 | 0.092593 |  | N/A
| Dock cask | Logistics | 1.9 | 83.543 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9
| Collect replacement pipework modules | Logistics | 0.88 | 84.423 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware from the AMF | 0.88
| Un-dock caks | Logistics | 2.3 | 86.723 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Move to lower port | Movement | 0.69444 | 87.4174 |  | N/A | Cask Transporter (loaded) | AMF hardware issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Collect replacement central cassette from stores; Move transporter to Lower Port | Total | 0 | 87.4174 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Divertor cassette transport stored; Replacement pipe modules collected; replacement pipework transported to the lower port | Un-Dock Empty Central Divertor Transport Cask | Trigger | 0 | 93.9889 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move cask to AMF hardware receipt | Movement | 0.69444 | 94.6833 |  | N/A | Cask Transporter (loaded) | Lower Port | AMF hardware issue | 50 | 0.02 | 0.69444 |  | N/A
| Dock cask | Logistics | 1.9 | 96.5833 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9
| Store Divertor cassette | Logistics | 0.88 | 97.4633 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP hardware in the AMF | 0.88
| Un-dock cask | Logistics | 2.3 | 99.7633 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Move to AMF equipment receipt | Movement | 0.046296 | 99.8096 |  | N/A | Cask transporter (empty cask) | AMF hardware issue | AMF hardware receipt | 10 | 0.06 | 0.046296 |  | N/A
| Store cassette transporter cask | Logistics | 0.58 | 100.3896 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / hardware cask | 0.58
| Collect divertor pipework cask | Logistics | 0.78 | 101.1696 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / hardware cask | 0.78
| Dock cask | Logistics | 1.9 | 103.0696 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9
| Collect replacement divertor cooling pipework | Logistics | 0.88 | 103.9496 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware from the AMF | 0.88
| Un-dock cask | Logistics | 2.3 | 106.2496 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Move to the lower port | Movement | 0.69444 | 106.9441 |  | N/A | Cask Transporter (loaded) | AMF Hardware issue | Lower port | 50 | 0.02 | 0.69444 |  | N/A
| Divertor cassette transport stored; Replacement pipe modules collected; replacement pipework transported to the lower port | Total | 0 | 106.9441 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Store failed central Divertor; Collect replacement cassette from stores; Move transporter to Lower Port | Un-Dock failed Central Cassette Transport Cask | Trigger | 0 | 57.7089 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move cask to AMF equipment receipt | Movement | 0.23148 | 57.9404 |  | N/A | Cask Transporter (Empty cask) | Lower Port | AMF equipment receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store divertor cask | Logistics | 0.58 | 58.5204 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / hardware cask | 0.58
| Move to AMF equipment issue | Movement | 0.027778 | 58.5482 |  | N/A | Cask Transporter (no cask) | AMF equipment receipt | AMF equipment issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect divertor pipework cask | Logistics | 0.78 | 59.3282 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / hardware cask | 0.78
| Move to AMF hardware issue | Movement | 0.092593 | 59.4208 |  | N/A | Cask Transporter (Empty cask) | AMF equipment Issue | AMF hardware issue | 20 | 0.06 | 0.092593 |  | N/A
| Dock cask | Logistics | 1.9 | 61.3208 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9
| Collect replacement pipework modules | Logistics | 0.88 | 62.2008 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware from the AMF | 0.88
| Un-dock caks | Logistics | 2.3 | 64.5008 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Move to lower port | Movement | 0.69444 | 65.1952 |  | N/A | Cask Transporter (loaded) | AMF hardware issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Store failed central Divertor; Collect replacement cassette from stores; Move transporter to Lower Port | Total | 0 | 65.1952 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Left Divertor cooling Weld Failure
Current payload stored; Divertor transport cask collected; cask moved to Lower Port | Weld Failure identified at left divertor pipe module joint | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move cask to AMF hardware receipt | Movement | 0.69444 | 0.69444 |  | N/A | Cask Transporter (loaded) | Lower Port | AMF hardware issue | 50 | 0.02 | 0.69444 |  | N/A
| Dock cask | Logistics | 1.9 | 2.5944 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9
| Store current hardware | Logistics | 0.88 | 3.4744 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP hardware in the AMF | 0.88
| Un-dock cask | Logistics | 2.3 | 5.7744 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Store current cask | Logistics | 0.58 | 6.3544 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / hardware cask | 0.58
| Collect divertor transport cask | Logistics | 0.78 | 7.1344 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / hardware cask | 0.78
| Move cask to lower port | Movement | 0.23148 | 7.3659 |  | N/A | Cask Transporter (Empty cask) | AMF equipment issue | Lower Port | 50 | 0.06 | 0.23148 |  | N/A
| Current payload stored; Divertor transport cask collected; cask moved to Lower Port | Total | 0 | 7.3659 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
failed Divertor Pipework Modules Stored; Cassette Transport Cask Prepared; Cassette Transport Cask Moved to Lower Port | Un-Dock Divertor Pipework Module Cask | Trigger | 0 | 29.1759 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter to AMF Hardware Receipt | Movement | 0.23148 | 29.4074 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Dock cask | Logistics | 1.9 | 31.3074 |  | N/A |  |  |  | N/A | N/A | N/A | Dock cask and commission RM systems | 1.9
| Store Divertor Pipework Modules | Logistics | 0.88 | 32.1874 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware in the AMF | 0.88
| Un-dock cask | Logistics | 2.3 | 34.4874 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 34.5152 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Store Cask | Logistics | 0.58 | 35.0952 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Collect Cassette Transport Cask | Logistics | 0.78 | 35.8752 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78
| Move Cassette Transport Cask to Lower Port | Movement | 0.69444 | 36.5696 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| failed Divertor Pipework Modules Stored; Cassette Transport Cask Prepared; Cassette Transport Cask Moved to Lower Port | Total | 0 | 36.5696 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Central Cassette Stored; Replacement Cassette collected; Transport Cask Moved to Lower Port | Un-Dock Full Central Cassette Transport Cask | Trigger | 0 | 44.1959 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter to AMF Hardware Receipt | Movement | 0.69444 | 44.8904 |  | N/A | Cask Transporter (Loaded) | Lower Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Dock cask | Logistics | 1.9 | 46.7904 |  | N/A |  |  |  | N/A | N/A | N/A | Dock cask and commission RM systems | 1.9
| Store Central Cassette | Logistics | 0.88 | 47.6704 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP hardware in the AMF | 0.88
| Un-dock cask | Logistics | 2.3 | 49.9704 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 49.9982 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Dock cask | Logistics | 1.9 | 51.8982 |  | N/A |  |  |  | N/A | N/A | N/A | Dock cask and commission RM systems | 1.9
| Collect replacement divertor cassette | Logistics | 0.88 | 52.7782 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware from the AMF | 0.88
| Un-dock cask | Logistics | 2.3 | 55.0782 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Move Cassette Transport Cask to Lower Port | Movement | 0.23148 | 55.3096 |  | N/A | Cask Transporter (Empty Cask) | AMF Equipment Issue | Lower Port | 50 | 0.06 | 0.23148 |  | N/A
| Central Cassette Stored; Replacement Cassette collected; Transport Cask Moved to Lower Port | Total | 0 | 55.3096 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Store failed left Divertor; Collect replacement cassette from stores; Move transporter to Lower Port | Un-Dock Empty Left Cassette Transport Cask | Trigger | 0 | 73.1896 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move cask to AMF equipment receipt | Movement | 0.23148 | 73.4211 |  | N/A | Cask Transporter (Empty cask) | Lower Port | AMF equipment receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store divertor cask | Logistics | 0.58 | 74.0011 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / hardware cask | 0.58
| Move to AMF equipment issue | Movement | 0.027778 | 74.0289 |  | N/A | Cask Transporter (no cask) | AMF equipment receipt | AMF equipment issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect divertor pipework cask | Logistics | 0.78 | 74.8089 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / hardware cask | 0.78
| Move to AMF hardware issue | Movement | 0.092593 | 74.9015 |  | N/A | Cask Transporter (Empty cask) | AMF equipment Issue | AMF hardware issue | 20 | 0.06 | 0.092593 |  | N/A
| Dock cask | Logistics | 1.9 | 76.8015 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9
| Collect replacement pipework modules | Logistics | 0.88 | 77.6815 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware from the AMF | 0.88
| Un-dock caks | Logistics | 2.3 | 79.9815 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Move to lower port | Movement | 0.69444 | 80.6759 |  | N/A | Cask Transporter (loaded) | AMF hardware issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Store failed left Divertor; Collect replacement cassette from stores; Move transporter to Lower Port | Total | 0 | 80.6759 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Collect replacement central cassette from stores; Move transporter to Lower Port | un-dock empty right cassette transport cask | Trigger | 0 | 53.3367 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move to AMF equipment issue | Movement | 0.027778 | 53.3644 |  | N/A | Cask Transporter (no cask) | AMF equipment receipt | AMF equipment issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect divertor pipework cask | Logistics | 0.78 | 54.1444 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / hardware cask | 0.78
| Move to AMF hardware issue | Movement | 0.092593 | 54.237 |  | N/A | Cask Transporter (Empty cask) | AMF equipment Issue | AMF hardware issue | 20 | 0.06 | 0.092593 |  | N/A
| Dock cask | Logistics | 1.9 | 56.137 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9
| Collect replacement pipework modules | Logistics | 0.88 | 57.017 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware from the AMF | 0.88
| Un-dock caks | Logistics | 2.3 | 59.317 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Move to lower port | Movement | 0.69444 | 60.0115 |  | N/A | Cask Transporter (loaded) | AMF hardware issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Collect replacement central cassette from stores; Move transporter to Lower Port | Total | 0 | 60.0115 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Divertor cassette transport stored; Replacement pipe modules collected; replacement pipework transported to the lower port | Un-Dock Empty Central Divertor Transport Cask | Trigger | 0 | 86.4359 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move cask to AMF hardware receipt | Movement | 0.69444 | 87.1304 |  | N/A | Cask Transporter (loaded) | Lower Port | AMF hardware issue | 50 | 0.02 | 0.69444 |  | N/A
| Dock cask | Logistics | 1.9 | 89.0304 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9
| Store Divertor cassette | Logistics | 0.88 | 89.9104 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP hardware in the AMF | 0.88
| Un-dock cask | Logistics | 2.3 | 92.2104 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Move to AMF equipment receipt | Movement | 0.046296 | 92.2567 |  | N/A | Cask transporter (empty cask) | AMF hardware issue | AMF hardware receipt | 10 | 0.06 | 0.046296 |  | N/A
| Store cassette transporter cask | Logistics | 0.58 | 92.8367 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / hardware cask | 0.58
| Collect divertor pipework cask | Logistics | 0.78 | 93.6167 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / hardware cask | 0.78
| Dock cask | Logistics | 1.9 | 95.5167 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9
| Collect replacement divertor cooling pipework | Logistics | 0.88 | 96.3967 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware from the AMF | 0.88
| Un-dock cask | Logistics | 2.3 | 98.6967 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Move to the lower port | Movement | 0.69444 | 99.3911 |  | N/A | Cask Transporter (loaded) | AMF Hardware issue | Lower port | 50 | 0.02 | 0.69444 |  | N/A
| Divertor cassette transport stored; Replacement pipe modules collected; replacement pipework transported to the lower port | Total | 0 | 99.3911 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Right Divertor cooling Weld Failure
Current payload stored; Divertor transport cask collected; cask moved to Lower Port | Weld Failure identified at right divertor pipe module joint | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move cask to AMF hardware receipt | Movement | 0.69444 | 0.69444 |  | N/A | Cask Transporter (loaded) | Lower Port | AMF hardware issue | 50 | 0.02 | 0.69444 |  | N/A
| Dock cask | Logistics | 1.9 | 2.5944 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9
| Store current hardware | Logistics | 0.88 | 3.4744 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP hardware in the AMF | 0.88
| Un-dock cask | Logistics | 2.3 | 5.7744 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Store current cask | Logistics | 0.58 | 6.3544 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / hardware cask | 0.58
| Collect divertor transport cask | Logistics | 0.78 | 7.1344 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / hardware cask | 0.78
| Move cask to lower port | Movement | 0.23148 | 7.3659 |  | N/A | Cask Transporter (Empty cask) | AMF equipment issue | Lower Port | 50 | 0.06 | 0.23148 |  | N/A
| Current payload stored; Divertor transport cask collected; cask moved to Lower Port | Total | 0 | 7.3659 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
failed Divertor Pipework Modules Stored; Cassette Transport Cask Prepared; Cassette Transport Cask Moved to Lower Port | Un-Dock Failed Divertor Pipework Module Cask | Trigger | 0 | 15.283 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter to AMF Hardware Receipt | Movement | 0.23148 | 15.5144 |  | N/A | Cask Transporter (Empty Cask) | Lower Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Dock cask | Logistics | 1.9 | 17.4144 |  | N/A |  |  |  | N/A | N/A | N/A | Dock cask and commission RM systems | 1.9
| Store Divertor Pipework Modules | Logistics | 0.88 | 18.2944 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware in the AMF | 0.88
| Un-dock cask | Logistics | 2.3 | 20.5944 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 20.6222 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Store Cask | Logistics | 0.58 | 21.2022 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Collect Cassette Transport Cask | Logistics | 0.78 | 21.9822 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78
| Move Cassette Transport Cask to Lower Port | Movement | 0.69444 | 22.6767 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| failed Divertor Pipework Modules Stored; Cassette Transport Cask Prepared; Cassette Transport Cask Moved to Lower Port | Total | 0 | 22.6767 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Central Cassette Stored; Cassette Transport Cask Moved to Lower Port | Un-Dock Full Central Cassette Transport Cask | Trigger | 0 | 30.303 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter to AMF Hardware Receipt | Movement | 0.69444 | 30.9974 |  | N/A | Cask Transporter (Loaded) | Lower Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Dock cask | Logistics | 1.9 | 32.8974 |  | N/A |  |  |  | N/A | N/A | N/A | Dock cask and commission RM systems | 1.9
| Store Central Cassette Cask | Logistics | 0.58 | 33.4774 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware Cask | 0.58
| Un-dock cask | Logistics | 2.3 | 35.7774 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 35.8052 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Dock cask | Logistics | 1.9 | 37.7052 |  | N/A |  |  |  | N/A | N/A | N/A | Dock cask and commission RM systems | 1.9
| Collect Cassette Transport Cask | Logistics | 0.78 | 38.4852 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78
| Un-dock cask | Logistics | 2.3 | 40.7852 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Move Cassette Transport Cask to Lower Port | Movement | 0.23148 | 41.0167 |  | N/A | Cask Transporter (Empty Cask) | AMF Equipment Issue | Lower Port | 50 | 0.06 | 0.23148 |  | N/A
| Central Cassette Stored; Cassette Transport Cask Moved to Lower Port | Total | 0 | 41.0167 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Left Cassette Stored; Replacement Right Cassette collected; Transport Cask Moved to Lower Port | Un-dock left cassette transport cask | Trigger | 0 | 36.263 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter to AMF Hardware Receipt | Movement | 0.69444 | 36.9574 |  | N/A | Cask Transporter (Loaded) | Lower Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Dock cask | Logistics | 1.9 | 38.8574 |  | N/A |  |  |  | N/A | N/A | N/A | Dock cask and commission RM systems | 1.9
| Store Central Cassette | Logistics | 0.88 | 39.7374 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP hardware in the AMF | 0.88
| Un-dock cask | Logistics | 2.3 | 42.0374 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Move Cask Transporter to AMF Equipment Issue | Movement | 0.027778 | 42.0652 |  | N/A | Cask Transporter (No Cask) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Dock cask | Logistics | 1.9 | 43.9652 |  | N/A |  |  |  | N/A | N/A | N/A | Dock cask and commission RM systems | 1.9
| Collect replacement divertor cassette | Logistics | 0.88 | 44.8452 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware from the AMF | 0.88
| Un-dock cask | Logistics | 2.3 | 47.1452 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Move Cassette Transport Cask to Lower Port | Movement | 0.23148 | 47.3767 |  | N/A | Cask Transporter (Empty Cask) | AMF Equipment Issue | Lower Port | 50 | 0.06 | 0.23148 |  | N/A
| Left Cassette Stored; Replacement Right Cassette collected; Transport Cask Moved to Lower Port | Total | 0 | 47.3767 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Store failed right Divertor; Collect replacement left cassette from stores; Move transporter to Lower Port | un-dock empty right cassette transport cask | Trigger | 0 | 53.3367 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move cask to AMF equipment receipt | Movement | 0.23148 | 53.5682 |  | N/A | Cask Transporter (Empty cask) | Lower Port | AMF equipment receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store divertor cask | Logistics | 0.58 | 54.1482 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / hardware cask | 0.58
| Move to AMF equipment issue | Movement | 0.027778 | 54.1759 |  | N/A | Cask Transporter (no cask) | AMF equipment receipt | AMF equipment issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect divertor pipework cask | Logistics | 0.78 | 54.9559 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / hardware cask | 0.78
| Move to AMF hardware issue | Movement | 0.092593 | 55.0485 |  | N/A | Cask Transporter (Empty cask) | AMF equipment Issue | AMF hardware issue | 20 | 0.06 | 0.092593 |  | N/A
| Dock cask | Logistics | 1.9 | 56.9485 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9
| Collect replacement pipework modules | Logistics | 0.88 | 57.8285 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware from the AMF | 0.88
| Un-dock caks | Logistics | 2.3 | 60.1285 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Move to lower port | Movement | 0.69444 | 60.823 |  | N/A | Cask Transporter (loaded) | AMF hardware issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Store failed right Divertor; Collect replacement left cassette from stores; Move transporter to Lower Port | Total | 0 | 60.823 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Collect replacement central cassette from stores; Move transporter to Lower Port | un-dock empty right cassette transport cask | Trigger | 0 | 53.3367 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move to AMF equipment issue | Movement | 0.027778 | 53.3644 |  | N/A | Cask Transporter (no cask) | AMF equipment receipt | AMF equipment issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect divertor pipework cask | Logistics | 0.78 | 54.1444 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / hardware cask | 0.78
| Move to AMF hardware issue | Movement | 0.092593 | 54.237 |  | N/A | Cask Transporter (Empty cask) | AMF equipment Issue | AMF hardware issue | 20 | 0.06 | 0.092593 |  | N/A
| Dock cask | Logistics | 1.9 | 56.137 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9
| Collect replacement pipework modules | Logistics | 0.88 | 57.017 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware from the AMF | 0.88
| Un-dock caks | Logistics | 2.3 | 59.317 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Move to lower port | Movement | 0.69444 | 60.0115 |  | N/A | Cask Transporter (loaded) | AMF hardware issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A
| Collect replacement central cassette from stores; Move transporter to Lower Port | Total | 0 | 60.0115 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Divertor cassette transport stored; Replacement pipe modules collected; replacement pipework transported to the lower port | un-dock empty left cassette transport cask | Trigger | 0 | 66.783 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move cask to AMF hardware receipt | Movement | 0.69444 | 67.4774 |  | N/A | Cask Transporter (loaded) | Lower Port | AMF hardware issue | 50 | 0.02 | 0.69444 |  | N/A
| Dock cask | Logistics | 1.9 | 69.3774 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9
| Store Divertor cassette | Logistics | 0.88 | 70.2574 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP hardware in the AMF | 0.88
| Un-dock cask | Logistics | 2.3 | 72.5574 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Move to AMF equipment receipt | Movement | 0.046296 | 72.6037 |  | N/A | Cask transporter (empty cask) | AMF hardware issue | AMF hardware receipt | 10 | 0.06 | 0.046296 |  | N/A
| Store cassette transporter cask | Logistics | 0.58 | 73.1837 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / hardware cask | 0.58
| Collect divertor pipework cask | Logistics | 0.78 | 73.9637 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / hardware cask | 0.78
| Dock cask | Logistics | 1.9 | 75.8637 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9
| Collect replacement divertor cooling pipework | Logistics | 0.88 | 76.7437 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware from the AMF | 0.88
| Un-dock cask | Logistics | 2.3 | 79.0437 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock cask | 2.3
| Move to the lower port | Movement | 0.69444 | 79.7382 |  | N/A | Cask Transporter (loaded) | AMF Hardware issue | Lower port | 50 | 0.02 | 0.69444 |  | N/A
| Divertor cassette transport stored; Replacement pipe modules collected; replacement pipework transported to the lower port | Total | 0 | 79.7382 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A

## Lower Hot Cell Summary
|  |  | Hot Cell Long Maintenance Interval |  |  |  |  | Impact of | Estimated Duration of | Hot Cell Short Maintenance Interval
|  |  | Maintenance |  | Failures |  | Total |  |  | Maintenance |  | Failures |  | Total
|  |  | Hardware Removal | Hardware Installation | RM Equipment | Welding Operations | Maintenance Cycle | Upper Port Hot Cell Ops | Maintenace Campaign | Divertor Removal | Divertor Installation | RM Equipment | Welding Operations | Maintenance Cycle
Single Port | Operations | hrs | 120.3542 | 497.9483 | 5.5942 | 282.9127 | 906.8095 | 725.8215 |  | 101.5201 | 142.9085 | 2.8746 | 30.8085 | 278.1117
|  | %age | 73.26% | 91.61% | 28.49% | 64.95% | 77.97% | 81.85% |  | 76.12% | 82.27% | 20.62% | 78.34% | 77.18%
| Logistics | hrs | 41.6381 | 44.0559 | 14.0434 | 34.6721 | 134.4096 | 74.1307 |  | 30.3181 | 29.2659 | 11.0654 | 7.7035 | 78.3529
|  | %age | 25.34% | 8.105% | 71.51% | 7.96% | 11.56% | 8.359% |  | 22.73% | 16.85% | 79.38% | 19.59% | 21.74%
|  | Idle time | 2.3023 | 1.54 | 0 | 117.9909 | 121.8332 | 86.8504 |  | 1.5297 | 1.54 | 0 | 0.81551 | 3.8852
|  | %age | 1.401% | 0.2833% | 0% | 27.09% | 10.48% | 9.794% |  | 1.147% | 0.8865% | 0% | 2.074% | 1.078%
| Total Time | hrs | 164.2947 | 543.5443 | 19.6376 | 435.5757 | 1163.0523 | 886.8027 | 1163.0523 | 133.3679 | 173.7144 | 13.9399 | 39.3275 | 360.3498
|  | days | 6.8456 | 22.6477 | 0.81824 | 18.149 | 48.4605 | 36.9501 | 48.4605 | 5.557 | 7.2381 | 0.58083 | 1.6386 | 15.0146
| Elapsed Time | hrs | 271.0862 | 896.8481 | 32.4021 | 718.6999 | 1919.0363 | 1463.2244 | 1919.0363 | 220.0571 | 286.6288 | 23.0009 | 64.8904 | 594.5772
|  | Days | 11.2953 | 37.3687 | 1.3501 | 29.9458 | 79.9598 | 60.9677 | 79.9598 | 9.169 | 11.9429 | 0.95837 | 2.7038 | 24.774
|  | Months | 0.37651 | 1.2456 | 0.045003 | 0.99819 | 2.6653 | 2.0323 | 2.6653 | 0.30563 | 0.3981 | 0.031946 | 0.090126 | 0.8258
|  | % | 14.13% | 46.73% | 1.688% | 37.45% | 100% | 100% | 100% | 37.01% | 48.21% | 3.868% | 3.381% | 92.47%
All 18 Ports in series | Operations | hrs | 2166.3764 | 8963.0703 | 100.6958 | 282.9127 | 11513.0551 | 13064.7874 |  | 1827.3612 | 1827.3612 | 51.7698 | 554.5531 | 4261.0453
|  | days | 90.2657 | 373.4613 | 4.1957 | 11.788 | 479.7106 | 544.3661 |  | 76.14 | 76.14 | 2.1571 | 23.1064 | 177.5436
| Logistics | hrs | 749.4867 | 793.0067 | 252.7818 | 34.6721 | 1829.9472 | 1334.3535 |  | 545.7267 | 545.7267 | 199.192 | 138.6629 | 1429.3082
|  | days | 31.2286 | 33.0419 | 10.5326 | 1.4447 | 76.2478 | 55.5981 |  | 22.7386 | 22.7386 | 8.2997 | 5.7776 | 59.5545
|  | Idle time | 41.4413 | 41.4413 | 0 | 117.9909 | 200.8735 | 1563.3069 |  | 27.5346 | 27.5346 | 0 | 14.6792 | 69.7484
| Total Time | hrs | 2957.3043 | 9797.5182 | 353.4776 | 435.5757 | 13543.8758 | 15962.4478 | 13543.8758 | 2400.6225 | 2400.6225 | 250.9618 | 707.8951 | 5760.1019
|  | days | 123.221 | 408.2299 | 14.7282 | 18.149 | 564.3282 | 665.102 | 665.102 | 100.0259 | 100.0259 | 10.4567 | 29.4956 | 240.0042
| Elapsed Time | hrs | 4879.5521 | 16165.9051 | 583.238 | 718.6999 | 22347.3951 | 26338.0388 | 22347.3951 | 3961.0271 | 3961.0271 | 414.087 | 1168.027 | 9504.1681
|  | Days | 203.3147 | 673.5794 | 24.3016 | 29.9458 | 931.1415 | 1097.4183 | 931.1415 | 165.0428 | 165.0428 | 17.2536 | 48.6678 | 396.007
|  | Months | 6.7772 | 22.4526 | 0.81005 | 0.99819 | 31.038 | 36.5806 | 31.038 | 5.5014 | 5.5014 | 0.57512 | 1.6223 | 13.2002
|  | % | 21.83% | 72.34% | 2.61% | 3.216% | 100% | 100% | 100% | 41.68% | 41.68% | 4.357% | 5.227% | 92.94%
All 18 Ports with 2 RM Systems | Operations | hrs | 1083.1882 | 4481.5351 | 50.3479 | 2546.2142 | 8161.2854 | 6532.3937 |  | 913.6806 | 1286.1765 | 25.8673 | 277.2765 | 2503.001
|  | days | 45.1328 | 186.7306 | 2.0978 | 106.0923 | 340.0536 | 272.1831 |  | 38.07 | 53.5907 | 1.0778 | 11.5532 | 104.2917
| Logistics | hrs | 374.7433 | 396.5033 | 126.3909 | 312.0488 | 1209.6863 | 667.1767 |  | 272.8633 | 263.3933 | 99.5861 | 69.3314 | 705.1742
|  | days | 15.6143 | 16.521 | 5.2663 | 13.002 | 50.4036 | 27.799 |  | 11.3693 | 10.9747 | 4.1494 | 2.8888 | 29.3823
|  | Idle time | 20.7206 | 13.86 | 0 | 1061.9184 | 1096.499 | 781.6534 |  | 13.7673 | 13.86 | 0 | 7.3396 | 34.9669
| Total Time | hrs | 1478.6522 | 4891.8985 | 176.7388 | 3920.1813 | 10467.4708 | 7981.2239 | 10467.4708 | 1200.3112 | 1563.4299 | 125.4534 | 353.9476 | 3243.1421
|  | days | 61.6105 | 203.8291 | 7.3641 | 163.3409 | 436.1446 | 332.551 | 436.1446 | 50.013 | 65.1429 | 5.2272 | 14.7478 | 135.1309
| Elapsed Time | hrs | 2439.7761 | 8071.6325 | 291.619 | 6468.2992 | 17271.3268 | 13169.0194 | 17271.3268 | 1980.5135 | 2579.6593 | 206.9981 | 584.0135 | 5351.1845
|  | Days | 101.6573 | 336.318 | 12.1508 | 269.5125 | 719.6386 | 548.7091 | 719.6386 | 82.5214 | 107.4858 | 8.6249 | 24.3339 | 222.966
|  | Months | 3.3886 | 11.2106 | 0.40503 | 8.9837 | 23.988 | 18.2903 | 23.988 | 2.7507 | 3.5829 | 0.2875 | 0.81113 | 7.4322
|  | % | 14.13% | 46.73% | 1.688% | 37.45% | 100% | 150% | 100% | 37.01% | 48.21% | 3.868% | 3.381% | 92.47%
All 18 Ports with 3 RM Systems | Operations | hrs | 722.1255 | 2987.6901 | 33.5653 | 1697.4761 | 5440.8569 | 4354.9291 |  | 609.1204 | 857.451 | 17.2449 | 184.851 | 1668.6673
|  | days | 21.239 | 87.8732 | 1.3986 | 70.7282 | 181.2389 | 181.4554 |  | 17.9153 | 25.2191 | 0.71854 | 7.7021 | 69.5278
| Logistics | hrs | 249.8289 | 264.3356 | 84.2606 | 208.0325 | 806.4575 | 444.7845 |  | 181.9089 | 175.5956 | 66.3907 | 46.221 | 470.1162
|  | days | 7.3479 | 7.7746 | 3.5109 | 8.668 | 27.3014 | 18.5327 |  | 5.3503 | 5.1646 | 2.7663 | 1.9259 | 19.5882
|  | Idle time | 13.8138 | 9.24 | 0 | 707.9456 | 730.9994 | 521.1023 |  | 9.1782 | 9.24 | 0 | 4.8931 | 23.3113
| Total Time | hrs | 985.7681 | 3261.2657 | 117.8259 | 2613.4542 | 6978.3138 | 5320.8159 | 6978.3138 | 800.2075 | 1042.2866 | 83.6356 | 235.965 | 2162.0947
|  | days | 28.9932 | 95.9196 | 4.9094 | 108.8939 | 238.7161 | 221.7007 | 238.7161 | 23.5355 | 30.6555 | 3.4848 | 9.8319 | 90.0873
| Elapsed Time | hrs | 1626.5174 | 5381.0883 | 194.4127 | 4312.1995 | 11514.2178 | 8779.3463 | 11514.2178 | 1320.3424 | 1719.7729 | 137.9988 | 389.3423 | 3567.4563
|  | Days | 67.7716 | 224.212 | 8.1005 | 179.675 | 479.7591 | 365.8061 | 479.7591 | 55.0143 | 71.6572 | 5.7499 | 16.2226 | 148.644
|  | Months | 2.2591 | 7.4737 | 0.27002 | 5.9892 | 15.992 | 12.1935 | 15.992 | 1.8338 | 2.3886 | 0.19166 | 0.54075 | 4.9548
|  | % | 14.13% | 46.73% | 1.688% | 37.45% | 100% | 100% | 100% | 37.01% | 48.21% | 3.868% | 3.381% | 92.47%
All 18 Ports with 4 RM Systems | Operations | hrs | 601.7712 | 2489.7417 | 27.971 | 1414.5634 | 4534.0474 | 3629.0122 |  | 507.6003 | 714.5425 | 14.3707 | 154.0425 | 1390.5561
|  | days | 13.6766 | 56.585 | 1.1655 | 58.9401 | 130.3673 | 151.2088 |  | 11.5364 | 16.2396 | 0.59878 | 6.4184 | 57.9398
| Logistics | hrs | 208.1907 | 220.2796 | 70.2172 | 173.3604 | 672.048 | 370.5832 |  | 151.5907 | 146.3296 | 55.3256 | 38.5175 | 391.7635
|  | days | 4.7316 | 5.0064 | 2.9257 | 7.2234 | 19.887 | 15.441 |  | 3.4452 | 3.3257 | 2.3052 | 1.6049 | 16.3235
|  | Idle time | 11.5115 | 7.7 | 0 | 589.9547 | 609.1661 | 434.2519 |  | 7.6485 | 7.7 | 0 | 4.0776 | 19.4261
| Total Time | hrs | 821.4734 | 2717.7214 | 98.1882 | 2177.8785 | 5815.2615 | 4433.8474 | 5815.2615 | 666.8396 | 868.5722 | 69.6963 | 196.6375 | 1801.7456
|  | days | 18.6699 | 61.7664 | 4.0912 | 90.7449 | 175.2724 | 184.7436 | 184.7436 | 15.1554 | 19.7403 | 2.904 | 8.1932 | 75.0727
| Elapsed Time | hrs | 1355.4312 | 4484.2403 | 162.0105 | 3593.4996 | 9595.1815 | 7315.8482 | 9595.1815 | 1100.2853 | 1433.1441 | 114.999 | 324.4519 | 2972.8803
|  | Days | 56.4763 | 186.8433 | 6.7504 | 149.7291 | 399.7992 | 304.827 | 399.7992 | 45.8452 | 59.7143 | 4.7916 | 13.5188 | 123.87
|  | Months | 1.8825 | 6.2281 | 0.22501 | 4.991 | 13.3266 | 10.1609 | 13.3266 | 1.5282 | 1.9905 | 0.15972 | 0.45063 | 4.129
|  | % | 14.13% | 46.73% | 1.688% | 37.45% | 100% | 83.33% | 100% | 37.01% | 48.21% | 3.868% | 3.381% | 92.47%
All 18 Ports with 6 RM Systems | Operations | hrs | 361.0627 | 1493.845 | 16.7826 | 848.7381 | 2720.4285 | 2177.4646 |  | 304.5602 | 428.7255 | 8.6224 | 92.4255 | 834.3337
|  | days | 5.6416 | 23.3413 | 0.69928 | 35.3641 | 65.0463 | 90.7277 |  | 4.7588 | 6.6988 | 0.35927 | 3.8511 | 34.7639
| Logistics | hrs | 124.9144 | 132.1678 | 42.1303 | 104.0163 | 403.2288 | 222.3922 |  | 90.9544 | 87.7978 | 33.1954 | 23.1105 | 235.0581
|  | days | 1.9518 | 2.0651 | 1.7554 | 4.334 | 10.1063 | 9.2663 |  | 1.4212 | 1.3718 | 1.3831 | 0.96294 | 9.7941
|  | Idle time | 6.9069 | 4.62 | 0 | 353.9728 | 365.4997 | 260.5511 |  | 4.5891 | 4.62 | 0 | 2.4465 | 11.6556
| Total Time | hrs | 492.8841 | 1630.6328 | 58.9129 | 1306.7271 | 3489.1569 | 2660.408 | 3489.1569 | 400.1037 | 521.1433 | 41.8178 | 117.9825 | 1081.0474
|  | days | 7.7013 | 25.4786 | 2.4547 | 54.447 | 90.0816 | 110.8503 | 110.8503 | 6.2516 | 8.1429 | 1.7424 | 4.9159 | 45.0436
| Elapsed Time | hrs | 813.2587 | 2690.5442 | 97.2063 | 2156.0997 | 5757.1089 | 4389.6731 | 5757.1089 | 660.1712 | 859.8864 | 68.9994 | 194.6712 | 1783.7282
|  | Days | 33.8858 | 112.106 | 4.0503 | 89.8375 | 239.8795 | 182.903 | 239.8795 | 27.5071 | 35.8286 | 2.875 | 8.1113 | 74.322
|  | Months | 1.1295 | 3.7369 | 0.13501 | 2.9946 | 7.996 | 6.0968 | 7.996 | 0.9169 | 1.1943 | 0.095832 | 0.27038 | 2.4774
|  | % | 14.13% | 46.73% | 1.688% | 37.45% | 100% | 100% | 100% | 37.01% | 48.21% | 3.868% | 3.381% | 92.47%
Note on C13: Farquhar, Iain: Calculated by factoring a efficiently factor of 0.67, as well as an allowance for both un-planned maintenance and logistics tasks, equal to an additional 10%.
Note on C25: Farquhar, Iain: Calculated by factoring a efficiently factor of 0.67, as well as an allowance for both un-planned maintenance and logistics tasks equal to an additional 10%.
Note on C37: Farquhar, Iain: Calculated by factoring a efficiently factor of 0.67, as well as an allowance for both un-planned maintenance and logistics tasks equal to an additional 10%.
Note on C49: Farquhar, Iain: Calculated by factoring a efficiently factor of 0.67, as well as an allowance for both un-planned maintenance and logistics tasks equal to an additional 10%.
Note on C61: Farquhar, Iain: Calculated by factoring a efficiently factor of 0.67, as well as an allowance for both un-planned maintenance and logistics tasks equal to an additional 10%.
Note on C73: Farquhar, Iain: Calculated by factoring a efficiently factor of 0.67, as well as an allowance for both un-planned maintenance and logistics tasks equal to an additional 10%.

## Lower Hot Cell Critical Path (hidden)
[5 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies
Group | Activity | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack
Remove Bioshield Plug | Cassette Removal Required | Operation | 0 | 0 | cassette Removal Required | 0 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Collect Bioshield Plug Attachment | Logistics | 0.58 | 0.58 |  | N/A |  |  |  | N/A | N/A | N/A | Collect interface hardware | 0.58 |  | N/A | N/A
| Move Cask Transporter A to Divertor Port | Movement | 0.23148 | 0.81148 |  | N/A | Hardware Transporter (Empty stillage) | AMF Equipment Issue | Divertor Port | 50 | 0.06 | 0.23148 |  | N/A |  | N/A | N/A
| Open Divertor Port Plug | Operation | 0.9 | 1.7115 | Open Lower Port Plug | 0.9 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move Cask Transporter A to Bioshield Stillage | Movement | 0.41667 | 2.1281 |  | N/A | Hardware Transporter (Loaded) | Divertor Port | Hardware Stillage | 30 | 0.02 | 0.41667 |  | N/A |  | N/A | N/A
| Store Bioshield | Logistics | 0.58 | 2.7081 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware in a hot cell stillage | 0.58 |  | N/A | N/A
Install Contamination Control System | Deploy contamination control system above the port | Logistics | 0.8 | 3.5081 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Contamination Control System Prepared; Contamination Control System Moved to Lower Port | 1.3744 | 1.3337
| Install CCS in the port | Operation | 0.5 | 4.0081 | Install Contamination Control System | 0.5 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| recover CCS lifting interface | Logistics | 0.6 | 4.6081 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Deploy multifunction Manipulator | Logistics | 0.8 | 5.4081 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
| Comission CCS | Operation | 2.2 | 7.6081 | Commission Contamination Control System | 2.2 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Recover multifunction manipulator | Logistics | 0.6 | 8.2081 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
Perform Health Physics and engineering checks | Deploy Port Inspection System | Logistics | 0.8 | 9.0081 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Bioshield interface hardware stored; Port Inspection System collected; Transport Moved to Lower Port | 5.1293 | 3.0789
| Perform health physics checks | Operation | 6.7722 | 15.7804 | Perform Health Physics Checks | 6.7722 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Recovery Port Inspection System | Logistics | 0.6 | 16.3804 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Deploy Port Inspection Hardware | Logistics | 1.28 | 17.6604 |  | N/A | [5 empty] | N/A | Deploy RM system into the port | 1.28 |  | N/A | N/A
| Perform engineering checks | Operation | 5.7722 | 23.4326 | Perform engineering checks | 5.7722 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract Port Inspection System | Logistics | 1.1 | 24.5326 |  | N/A |  |  |  | N/A | N/A | N/A | Recovery RM system from the port | 1.1 |  | N/A | N/A
Open Vacuum Closure Plate | Deploy Divertor Closure Plate Equipment | Logistics | 0.8 | 25.3326 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Contamination Control System Interface stored; Vacuum Closure Plate Interface collected; Transport Moved to Lower Port | 7.0293 | 17.5033
| Remove Vacuum Closure Plate | Operation | 21.5 | 46.8326 | Remove Vacuum Closure Plate | 21.5 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract Vacuum Closure Plate Equipment | Logistics | 0.6 | 47.4326 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
Perform Health Physics and engineering checks | Deploy Port Inspection System | Logistics | 0.8 | 48.2326 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
| Perform health physics checks | Operation | 6.7722 | 55.0048 | Perform Health Physics Checks | 6.7722 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Recovery Port Inspection System | Logistics | 0.6 | 55.6048 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Deploy Port Inspection Hardware | Logistics | 1.28 | 56.8848 |  | N/A | [5 empty] | N/A | Deploy RM system into the port | 1.28 |  | N/A | N/A
| Perform engineering checks | Operation | 5.7722 | 62.657 | Perform engineering checks | 5.7722 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract Port Inspection System | Logistics | 1.1 | 63.757 |  | N/A |  |  |  | N/A | N/A | N/A | Recovery RM system from the port | 1.1 |  | N/A | N/A
Install Threshold Rail System | Place rails into port area | Logistics | 0.8 | 64.557 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Port Plate Equipment Stored; Threshold rail hardware collected; Transport Moved to Lower Port | 49.9463 | 13.8107
| Postion rails for installation | Logistics | 0.53 | 65.087 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
| Deploy multifunction Manipulator | Logistics | 0.8 | 65.887 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
| Install Threshold rails | Operation | 10.8944 | 76.7815 | Install Threshold Rails | 10.8944 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Recover deployed RM system | Logistics | 0.6 | 77.3815 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
Remove in-port diagnostic system | Deploy diagnostic maintenance system | Logistics | 0.8 | 78.1815 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Vacuum closure plate Stored; Diagnostic maintenance hardware collected; Transport Moved to Lower Port | 49.9463 | 27.4352
| Disconnect diagnostic service connections | Operation | 0.45917 | 78.6406 | Disconnect Diagnostic services | 0.45917 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract diagnostic system and store in the AMF | Logistics | 0.38 | 79.0206 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
Remove vacuum pumping assembly | Deploy multifunction Manipulator | Logistics | 0.8 | 79.8206 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Threshold rail handling system Stored; vacuum pumping interface hardware collected; Transport Moved to Lower Port | 49.9463 | 29.0744
| Remove pumping services and fixations | Operation | 8.1444 | 87.9651 | Disconnect vacuum pumping system | 8.1444 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract multifunction manipulator | Logistics | 0.6 | 88.5651 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Deploy pumping system lifting attachment | Logistics | 0.8 | 89.3651 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
| Remove vacuum pumping system assembly from the port | Operation | 3.7 | 93.0651 | Lift pumping assembly from port | 3.7 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
Remove Shielding Modules | Deploy shielding handling system | Logistics | 0.8 | 93.8651 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Diagnostic maintenance system stored; shielding module hardware collected; Transport Moved to Lower port | 81.5344 | 11.5307
| Disconnect shielding modules | Operation | 3.35 | 97.2151 | Disconnect shielding modules | 3.35 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract sheild modules and store in cask | Logistics | 0.38 | 97.5951 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
Remove Divertor Pipe Module | Deploy Multifunction Manipulator | Logistics | 0.8 | 98.3951 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Vacuum pumping hardware stored; Divertor pipework maintenance system collected; Transport Moved to Lower Port | 95.5788 | 2.0163
| Remove Centre Cassette pipework access lid using Multifunction Manipulator | Operation | 3.83 | 102.2251 | Remove Lower Port Pipework Access Lid | 3.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove Left Cassette pipework access lid using Multifunction Manipulator | Operation | 3.83 | 106.0551 | Remove Lower Port Pipework Access Lid | 3.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove Right Cassette pipework access lid using Multifunction Manipulator | Operation | 3.83 | 109.8851 | Remove Lower Port Pipework Access Lid | 3.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract Multifunction manipulator | Logistics | 0.6 | 110.4851 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Deploy Service Joint System | Logistics | 0.8 | 111.2851 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
| Remove Central Divertor pipework module | Operation | 1.0255 | 112.3106 | Disconnect Divertor Pipe module | 1.0255 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Reposition Pipework equipment to the second pipework module | Logistics | 0.53 | 112.8406 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
| Remove Left Divertor pipework module | Operation | 1.0255 | 113.8661 | Disconnect Divertor Pipe module | 1.0255 |  |  |  | N/A | N/A | N/A |  | N/A | Sheilding Modules stored; Divertor pipework maintenance system collected; Transport Moved to Lower Port | 100.1088 | 12.7318
| Reposition Pipework equipment to the third pipe module | Logistics | 0.53 | 114.3961 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
| Remove Right Divertor pipework module | Operation | 1.0255 | 115.4215 | Disconnect Divertor Pipe module | 1.0255 |  |  |  | N/A | N/A | N/A |  | N/A | Central Divertor Pipework Module Stored; Pipe Module handling System Moved to Lower Port | 114.1165 | 0.27956
| Remove divertor pipework handling system from the port | Logistics | 0.6 | 116.0215 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
Clean Port and Remove Central Cassette | Deploy Port Cleaning Equipment | Logistics | 0.8 | 118.0875 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Left Divertor Pipework Module Stored; Pipe Module handling System stored; Central divertor system and maintenance system collected and moved to Lower Port | 117.2875 | -1.266
| Clean Port | Operation | 7.6667 | 125.7542 | Clean/re-condition port hardware | 7.6667 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Port Cleaning Equipment | Logistics | 0.6 | 126.3542 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Deploy Cassette Handling Equipment | Logistics | 0.8 | 127.1542 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
| Remove Central Divertor cassette | Operation | 0.85 | 128.0042 | Remove Central Divertor Cassette | 0.85 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove Central Cassette from the port | Logistics | 0.6 | 128.6042 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
Remove Left Divertor Cassette | Deploy Cassette Handling Equipment | Logistics | 0.8 | 129.4042 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Right Divertor Pipework Module Stored; Pipe Module handling System stored; Divertor handling system collected and moved to Lower Port | 119.3708 | 9.2334
| Remove Left Divertor cassette | Operation | 0.85 | 130.2542 | Remove Peripheral Divertor Cassette | 0.85 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove Left Cassette from the port | Logistics | 0.6 | 130.8542 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
Remove Right Divertor Cassette | Deploy Cassette Handling Equipment | Logistics | 0.8 | 131.9179 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Central Cassette Stored; Cassette Transport Cask Moved to Lower Port | 131.1179 | -0.2637
| Remove Right Divertor cassette | Operation | 0.85 | 132.7679 | Remove Peripheral Divertor Cassette | 0.85 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove Right Cassette from the port | Logistics | 0.6 | 133.3679 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
Cassette Removal Complete | End Time |  |  | 133.3679
| Operational Time |  |  | 101.5201 | 61.79% | 76.12%
| Logistical Time |  |  | 29.67 | 18.06% | 22.25%
| Movement Time |  |  | 0.64815 | 0.486% | 0.486%
Remove Outboard Pipe Modules | Deploy Multifunction Manipulator | Logistics | 0.8 | 134.9405 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Left Divertor Cassette Stored; Cassette Handling system Stored; Blanket Pipe Module Interface hardware Prepared; Blanket Pipe Module Interface hardware moved to Lower Port | 134.1405 | -0.77259
| Remove COB pipework access lid using Multifunction Manipulator | Operation | 3.83 | 138.7705 | Remove Lower Port Pipework Access Lid | 3.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Deploy Service Joint System | Logistics | 0.8 | 139.5705 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
| Disconnect COB blanket pipework module | Operation | 0.76002 | 140.3305 | Disconnect Blanket Pipe Module | 0.76002 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove COB pipe module from the port | Logistics | 0.6 | 140.9305 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Retract Service Joint System | Logistics | 0.6 | 141.5305 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Deploy Multifunction Manipulator | Logistics | 0.8 | 142.3305 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
| Remove LOB pipework access lid using Multifunction Manipulator | Operation | 3.83 | 146.1605 | Remove Lower Port Pipework Access Lid | 3.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove ROB pipework access lid using Multifunction Manipulator | Operation | 3.83 | 149.9905 | Remove Lower Port Pipework Access Lid | 3.83 |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | N/A |  | N/A | N/A
| Reposition Pipework equipment to the second pipework module | Logistics | 0.53 | 150.5205 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
| Disconnect LOB blanket pipework module | Operation | 0.76002 | 151.2805 | Disconnect Blanket Pipe Module | 0.76002 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove LOB pipe module from the port | Logistics | 0.6 | 151.8805 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 | Right Divertor Cassette Stored; Cassette Transport Cask Stored; Blanket Pipe Module Interface hardware Prepared; Blanket Pipe Module Interface hardware moved to Lower Port | 135.8816 | 15.3989
| Reposition Pipework equipment to the third pipe module | Logistics | 0.53 | 152.4105 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
| Disconnect ROB blanket pipework module | Operation | 0.76002 | 153.1706 | Disconnect Blanket Pipe Module | 0.76002 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove ROB pipe module from the port | Logistics | 0.6 | 153.7706 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 | COB pipe module stored; Pipe Module handling System Moved to Lower Port | 142.7365 | 10.4341
Remove Inboard pipe modules | Deploy Service Joint System | Logistics | 0.8 | 154.5706 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
| Disconnect LIB blanket pipework module | Operation | 0.76002 | 155.3306 | Disconnect Blanket Pipe Module | 0.76002 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove LIB Pipe Module from the port | Logistics | 0.6 | 155.9306 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 | LOB pipe module stored; Pipe Module handling System Moved to Lower Port | 153.6865 | 1.6441
| Reposition Pipework equipment to the second pipework module | Logistics | 0.53 | 156.4606 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
| Disconnect RIB blanket pipework module | Operation | 0.76002 | 157.2206 | Disconnect Blanket Pipe Module | 0.76002 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove RIB Pipe Module from the port | Logistics | 0.6 | 157.8206 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 | ROB pipe module stored; Pipe Module handling System Moved to Lower Port | 142.7365 | 14.4842
| Retract Service Joint System | Logistics | 0.6 | 158.4206 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
Remove Inner Port Pipe modules | Disconnect LIB Inner Pipework module | Operation | 1.772 | 160.1926 | Disconnect Inner Port Pipe Module | 1.772 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove Inner LIB Pipe Module from port | Logistics | 0.6 | 160.7926 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 | LIB pipe module stored; Pipe Module handling System Moved to Lower Port | 157.7365 | 2.4561
| Reposition Pipework equipment to the RIB inner pipework module | Logistics | 0.53 | 161.3226 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
| Disconnect RIB Inner Pipe module | Operation | 1.772 | 163.0947 | Disconnect Inner Port Pipe Module | 1.772 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove Inner RIB Pipe Module from port | Logistics | 0.6 | 163.6947 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 | RIB pipe module stored; Pipe Module handling System Moved to Lower Port | 159.6265 | 3.4682
| Retract Blanket Pipe Module Handling System from port | Logistics | 0.6 | 164.2947 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
Hardware Removal Complete | End Time |  |  | 164.2947
| Operational Time |  |  | 120.3542 | 73.26%
| Logistical Time |  |  | 40.99 | 24.95%
| Movement Time |  |  | 0.64815 | 0.3945%
Inspect and re-condition Lower Port | Cassette Installation Required | Operation | 0 | 0 | cassette Removal Required | 0 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Collect Port Inspection Hardware | Logistics | 0.8 | 41.79 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
| Move Inspection Hardware to Divertor Port | Movement | 0.69444 | 1.3426 |  | N/A | Hardware Transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 | Deploy Tool / Hardware into the Port | N/A |  | N/A | N/A
| Deploy inspection system | Logistics | 0.8 | 0.8 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
| Inspect the port | Operation | 7.6667 | 8.4667 | Inspect the port | 7.6667 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract inspection equipment | Logistics | 0.6 | 9.0667 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Deploy cleaning/repair system | Logistics | 0.8 | 9.8667 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
| Re-condition IVC hardware/fixations | Operation | 7.6667 | 17.5333 | Clean/re-condition port hardware | 7.6667 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract port maintenance system | Logistics | 0.6 | 18.1333 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
Install Inner Port Pipe Modules | Deploy Service Joint System | Logistics | 0.8 | 18.9333 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Inner Port Pipework Collected and Prepared; RIB inner pipe module collected; Inner Port Pipework Cask Moved to Lower Port | 2.147 | 15.9863
| Install RIB Inner pipe module | Logistics | 0.8 | 19.7333 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
| Connect RIB Inner pipe module | Operation | 53.7846 | 73.518 | Connect Inner Port Pipe module | 53.7846 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Collect LIB inner pipe module | Logistics | 0.53 | 74.048 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 | Inspection Cask Stored; Blanket Pipe Module handling system collected; LIB Inner Pipe Module collected; hardware transporter moved to Lower Port | 21.8826 | 51.6354
| Install LIB Inner pipe module | Logistics | 0.8 | 74.848 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
| Connect LIB inner Pipe Module | Operation | 53.7846 | 128.6326 | Connect Inner Port Pipe module | 53.7846 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract Service Joint System | Logistics | 0.6 | 129.2326 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Retract Multifunction manipulator | Logistics | 0.6 | 129.8326 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
Install Inboard Blanket Pipe Modules | Install RIB pipe module | Logistics | 0.8 | 130.6326 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | RIB pipe module collected; Pipe Module handling System Moved to Lower Port | 75.1239 | 54.7087
| Connect RIB Pipe Module | Operation | 53.7846 | 184.4172 | Connect Inner Port Pipe module | 53.7846 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Collect second Port Pipework Module | Logistics | 0.8 | 185.2172 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | LIB pipe module collected; Pipe Module handling System Moved to Lower Port | 130.4385 | 53.9787
| Install RIB pipe module | Logistics | 0.8 | 186.0172 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
| Connect LIB Pipe Module | Operation | 53.7846 | 239.8019 | Connect Inner Port Pipe module | 53.7846 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
Install Outboard Blanket Pipe Modules | Extract ROB Pipework Module | Logistics | 0.8 | 240.6019 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | ROB pipe module collected; Pipe Module handling System Moved to Lower Port | 186.2232 | 53.5787
| Connect ROB Pipe Module | Operation | 26.7733 | 267.3752 | Connect Blanket Pipe Module | 26.7733 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Extract LOB Pipework Module | Logistics | 0.8 | 268.1752 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
| Reposition Pipework equipment to the second pipework module location | Logistics | 0.53 | 268.7052 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
| Connect LOB pipe module | Operation | 26.7733 | 295.4784 | Connect Blanket Pipe Module | 26.7733 |  |  |  | N/A | N/A | N/A |  | N/A | LOB pipe module collected; Pipe Module handling System Moved to Lower Port | 241.6078 | 27.0973
| Retract Service Joint System | Logistics | 0.6 | 296.0784 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Deploy Multifunction Manipulator | Logistics | 0.8 | 296.8784 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
| Install LOB pipework access lid using Multifunction Manipulator | Operation | 5.16 | 302.0384 | Install Lower Port Pipework Access Lid | 5.16 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Install ROB pipework access lid using Multifunction Manipulator | Operation | 5.16 | 307.1984 | Install Lower Port Pipework Access Lid | 5.16 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract Multifunction manipulator | Logistics | 0.6 | 307.7984 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Deploy Service Joint System | Logistics | 0.8 | 308.5984 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
| Extract COB Pipe Module | Logistics | 0.8 | 309.3984 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | COB pipe module collected; Pipe Module handling System Moved to Lower Port | 269.1811 | 39.4173
| Reposition Pipework equipment to the third pipe module | Logistics | 0.53 | 309.9284 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
| Connect COB pipework module | Operation | 26.7733 | 336.7017 | Connect Blanket Pipe Module | 26.7733 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract Service Joint System | Logistics | 0.6 | 337.3017 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Deploy Multifunction Manipulator | Logistics | 0.8 | 338.1017 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
| Install COB pipework access lid using Multifunction Manipulator | Operation | 5.16 | 343.2617 | Install Lower Port Pipework Access Lid | 5.16 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove Blanket pipe module handling system from port | Logistics | 0.6 | 343.8617 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
Install Right Divertor Cassette | Deploy Cassette Handling Equipment | Logistics | 0.8 | 344.6617 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Blanket pipe module handling system stored; divertor cassette handling system collect; Divertor cassette collected; hardware transporter moved to port | 298.7647 | 45.097
| Install Right Divertor cassette | Operation | 0.95 | 345.6117 | Install Peripheral Divertor Cassette | 0.95 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract Right Cassette Handling Equipment | Logistics | 0.38 | 345.9917 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.38 |  | N/A | N/A
Install Left Divertor Cassette | Deploy Cassette Handling Equipment | Logistics | 0.8 | 347.948 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Blanket pipe module handling system stored; second divertor cassette handling system collect; Divertor cassette collected; hardware transporter moved to port | 347.148 | -1.1563
| Install Left Divertor cassette | Operation | 0.95 | 348.898 | Install Peripheral Divertor Cassette | 0.95 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract Left Cassette Handling Equipment | Logistics | 0.38 | 349.278 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.38 |  | N/A | N/A
Install Central Divertor Cassette | Deploy Cassette Handling Equipment | Logistics | 0.8 | 350.078 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Divertor cassette collected; Divertor cassette handling System Moved to Lower Port | 347.7976 | 1.4804
| Install Central Divertor cassette | Operation | 0.95 | 351.028 | Install Central Divertor Cassette | 0.95 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract Central Cassette Handling Equipment | Logistics | 0.38 | 351.408 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.38 |  | N/A | N/A
Install Divertor Pipe Modules | Deploy Service Joint System and Multifunction manipulator | Logistics | 0.8 | 352.5917 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Divertor Handling system Stored; Divertor Pipework handling system collected; Right Divertor pipe module collected; Transport Moved to Lower Port | 351.7917 | -0.3837
| Collect Right Pipe Module from transport | Logistics | 0.8 | 353.3917 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
| Connect Right divertor Pipe Module | Operation | 16.9651 | 370.3568 | Connect Divertor Pipe module | 16.9651 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Collect next Pipe Module from transport | Logistics | 0.8 | 371.1568 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Divertor Handling system Stored; Divertor Pipework handling system collected; Left Divertor pipe module collected; Transport Moved to Lower Port | 351.7917 | 18.5651
| Reposition Pipework equipment to the second location | Logistics | 0.53 | 371.6868 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
| Connect Left divertor pipe module | Operation | 16.9651 | 388.6518 | Connect Divertor Pipe module | 16.9651 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Collect final pipe module from hardware transport | Logistics | 0.8 | 389.4518 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Divertor pipe module collected; Divertor cassette handling System Moved to Lower Port | 372.1627 | 16.4891
| Reposition Pipework equipment to the third pipe module | Logistics | 0.53 | 389.9818 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
| Connect Central divertor pipe module | Operation | 16.9651 | 406.9469 | Connect Divertor Pipe module | 16.9651 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract Service Joint System | Logistics | 0.6 | 407.5469 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Deploy Multifunction Manipulator | Logistics | 0.8 | 408.3469 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
| Install Centre Cassette pipework access lid using Multifunction Manipulator | Operation | 5.16 | 413.5069 | Install Lower Port Pipework Access Lid | 5.16 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Install Left Cassette pipework access lid using Multifunction Manipulator | Operation | 5.16 | 418.6669 | Install Lower Port Pipework Access Lid | 5.16 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Install Right Cassette pipework access lid using Multifunction Manipulator | Operation | 5.16 | 423.8269 | Install Lower Port Pipework Access Lid | 5.16 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract Multifunction manipulator | Logistics | 0.6 | 424.4269 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
Install Shielding Modules | Deploy shielding handling system | Logistics | 0.8 | 425.2269 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Store Divertor pipework handling system; Collect Shield module handling system & shield modules; Move to Lower Port | 390.7877 | 33.6391
| Install shielding modules | Operation | 4.35 | 429.5769 | Connect shielding modules | 4.35 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract sheild module handling system | Logistics | 0.38 | 429.9569 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
Install vacuum pumping assembly | Deploy pumping system lifting attachment | Logistics | 0.8 | 430.7569 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Store Divertor pipework handling system; Collect Vacuum Plumping system handling system & vaccum pumping sled; move to port | 409.0828 | 20.8741
| Install vacuum pumping system assembly from the port | Operation | 3.7 | 434.4569 | Lift pumping assembly from port | 3.7 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Deploy multifunction Manipulator | Logistics | 0.8 | 435.2569 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
| Connect pumping services and fixations | Operation | 8.1444 | 443.4013 | Disconnect vacuum pumping system | 8.1444 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract multifunction manipulator | Logistics | 0.6 | 444.0013 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Retract pumping sled handling system | Logistics | 0.6 | 444.6013 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
Install in-port diagnostic system | Deploy diagnostic maintenance system | Logistics | 0.8 | 445.4013 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Store Shield Module handling system; Collect in-port diagnostic system; move to port | 432.0928 | 12.5085
| Connect diagnostic service connections | Operation | 8.8139 | 454.2152 | Connect Diagnostic services | 8.8139 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Recover diagnostic handling system | Logistics | 0.38 | 454.5952 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
Remove Threshold Rail System | Deploy Rail Handling System | Logistics | 0.8 | 455.3952 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Store Pumping system handling system; Collect threshold rail lifting interface; Move to Lower Port | 446.7372 | 7.858
| Deploy multifunction Manipulator | Logistics | 0.8 | 456.1952 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
| Disconnect Threshold rails | Operation | 8.1139 | 464.3091 | Remove Threshold Rails | 8.1139 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Recover multifunction manipulator | Logistics | 0.6 | 464.9091 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Recover Rails from the port | Logistics | 0.6 | 465.5091 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
Perform Health Physics Checks | Deploy Port Inspection System | Logistics | 0.8 | 466.3091 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Store diagnostic handling system; Collect port inspection system; Move to Lower Port | 456.7311 | 8.778
| Perform health physics checks | Operation | 6.7722 | 473.0813 | Perform Health Physics Checks | 6.7722 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Recovery Port Inspection System | Logistics | 0.6 | 473.6813 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
Install Lower Vacuum Closure Plate | Deploy Divertor Vacuum Closure Plate Equipment | Logistics | 0.8 | 474.4813 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Store threshold rail handling system; Collect vacuum closure plate & handling system; Move to Lower Port | 467.645 | 6.0363
| Install Vacuum Closure Plate | Operation | 1.2167 | 475.698 | Insert Vacuum Closure Plate | 1.2167 |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | N/A |  | N/A | N/A
| Fasten Port Closure Fixtures | Operation | 8.0667 | 483.7646 | install Vacuum Closure Plate | 8.0667 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract Vaccum closure plate lifting interface | Logistics | 0.6 | 484.3646 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
Perform Health Physics Checks | Deploy Port Inspection System | Logistics | 0.8 | 485.1646 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
| Perform health physics checks | Operation | 6.7722 | 491.9369 | Perform Health Physics Checks | 6.7722 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Recovery Port Inspection System and store in the AMF | Logistics | 0.6 | 492.5369 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
Remove Contamination Control System from the port | Deploy multifunction Manipulator | Logistics | 0.8 | 493.3369 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Store vacuum closure plate handling system; Collect CCS handling system; Move to Lower Port | 486.5006 | 6.0363
| Decomission CCS | Operation | 1.2 | 494.5369 | Decommission Contamination Control System | 1.2 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Deploy contamination control system above the port | Logistics | 0.8 | 495.3369 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
| Remove CCS in the port | Operation | 0.3 | 495.6369 | Remove Contamination Control System | 0.3 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| recover CCS lifting interface | Logistics | 0.6 | 496.2369 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
Seal Lower Port Bioshield | Collect Bioshield Plug Attachment | Logistics | 0.58 | 496.8169 |  | N/A |  |  |  | N/A | N/A | N/A | Collect interface hardware | 0.58 | Store Port Inspection system; Collect Bioshield plug handling system; collect bioshield plug; move to port | 495.4843 | 0.75259
| Move Cask Transporter A to Divertor Port | Movement | 0.23148 | 497.0483 |  | N/A | Hardware Transporter (Empty Stillage) | AMF Equipment Issue | Divertor Port | 50 | 0.06 | 0.23148 |  | N/A |  | N/A | N/A
| Seal Port Plug | Operation | 0.9 | 497.9483 | Seal Lower Port Bioshield | 0.9 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
Divertor Installation Complete | End Time |  |  | 172.1744
| Operational Time |  |  | 142.9085 | 83%
| Logistical Time |  |  | 28.34 | 16.46%
| Movement Time |  |  | 0.92593 | 0.5378%
Hardware Installation Complete | End Time |  |  | 497.9483
| Operational Time |  |  | 453.8469 | 91.14%
| Logistical Time |  |  | 43.13 | 8.662%
| Movement Time |  |  | 0.92593 | 0.1859%
Divertor Maintenance Cycle Complete | End Time |  |  | 305.5423
| Operational Time |  |  | 244.4286 | 80%
| Logistical Time |  |  | 58.01 | 18.99%
| Movement Time |  |  | 1.5741 | 0.5152%
Full Maintenance Cycle Complete | End Time |  |  | 662.243
| Operational Time |  |  | 574.2011 | 86.71%
| Logistical Time |  |  | 84.12 | 12.7%
| Movement Time |  |  | 1.5741 | 0.2377%

## Lower Hot Cell Logistics (hidden)
Logistical Activities |  |  | Equipment Speed
Activity | Sub activity | Time | Equipment | Speed (m/s)
Deploy Equipment | Deploy Equipment | 0 | hardware transporter (Loaded) | 0.02
Collect interface hardware | Position | 0.28 | hardware transporter (No load) | 0.2
|  |  | hardware transporter (Empty stillage) | 0.06
| Lower onto storage location | 0.2 | Multifunction Manipulator | 0.02
| Make Connections/Commission | 0.1 | Closure Plate Disconnection Equipment | 0.02
| Collect interface hardware | 0.58 | Closure Plate Connection Equipment | 0.02
Store Hardware in the AMF | Position | 0.28
| Lower onto storage location | 0.2 | Distance Table
| Release fastenings | 0.2 | To: From : | Equipment Stillage | Divertor Port | Hardware Stillage | AMF Equipment Issue | AMF Equipment Receipt | AMF Hardware Receipt | AMF Hardware Issue
| Retract RM system | 0.2 | Equipment Stillage |  | 15 | 10 | 50 | 50 | 50 | 50
| Store Hardware in the AMF | 0.88 | Divertor Port | 15 |  | 30 | 50 | 50 | 50 | 50
Store Equipment / Hardware in a hot cell stillage | Position | 0.28 | Hardware Stillage | 10 | 30 |  | 50 | 50 | 50 | 50
| Lower onto storage location | 0.2 | AMF Equipment Issue | 50 | 50 | 50 |  | 20 | 20 | 20
| Release Connections/Commission | 0.1 | AMF Equipment Receipt | 50 | 50 | 50 | 20 |  | 20 | 20
| Store Equipment / Hardware in a hot cell stillage | 0.58 | AMF Hardware Receipt | 50 | 50 | 50 | 20 | 20 |  | 10
Collect hardware from the AMF | Position | 0.28 | AMF Hardware Issue | 50 | 50 | 50 | 20 | 20 | 10
| Engage lifting fastenings | 0.2
| Lift from storage location | 0.2
| Collect hardware from the AMF | 0.68
Collect Equipment / Hardware from stillage | Position | 0.28
| Connect fastenings | 0.3
| Lift from storage location | 0.2
| Collect Equipment / Hardware from stillage | 0.78
Dock Cask and Commission RM Systems | Dock to interface cask | 0.2
| Connect double lidded door and frame | 0.3
| Connect Cask services | 0.1
| Connect RM System Services | 0.1
| RM System Software Check | 0.2
| RM System Hardware Check | 0.2
| Disconnect door | 0.3
| Store door | 0.5
| Dock Cask and Commission RM Systems | 1.9
Un-Dock Cask | Replace door | 0.5
| Attach to frame | 0.3
| Disconnect door and frame | 0.3
| Disconnect Services | 0.1
| Demonstrate seals | 1
| Undock from interface cask | 0.1
| Un-Dock Cask | 2.3
Deploy Tool / Hardware into the Port | Connect tool / hardware to Divertor port interface | 0.2
| Confirm mechancial connections | 0.1
| Make service connections/commission | 0.1
| Release from AMF hardware transporter | 0.1
| Transfer hardware into the port | 0.3
| Deploy Tool / Hardware into the Port | 0.8
Recover Tool / Hardware from the Port | Recover divertor port interface from port | 0.3
| Make mechanical connections to AMF transporter | 0.1
| Disconnect any service connections | 0.1
| Release mechanical connections with interface | 0.1
| Recover Tool / Hardware from the Port | 0.6
Reposition tool within Port | Move tool to new position | 0.33
| Confirm positon within port | 0.1
| Make fine position adjustments | 0.1
| Reposition tool within Port | 0.53
Connect recovery system to hardware | Make mechanical connections to the failed hardware | 0.1
| Confirm mechancial connections | 0.1
| Connect services and supplies | 0.1
| Commission handling systems | 1
| Deploy handling system | 0.5
| Connect recovery system to hardware | 1.8
Disconnect recovery system from hardware | Recovery deployed end effectors | 0.5
| Disconnect services and supplies | 0.5
| Release mechancial connections | 0.2
| Confirm disconnection | 0.1
| Disconnect recovery system from hardware | 1.3

## Lower Hot Cell Hardware Failure (hidden)
Delay caused by failure and recovery of remote handling equipment
Additional tasks required to recover from failures
General Assumptions:
There are two sorts of process failure considered; failure of a weld and failure of a mechanical connection, both uncovered by failure to pass acceptance criteria
In addition five types of equipment failure are considered; Pipe interface hardware, Overhead Crane, Blanket transporter system, divertor cask system and Multifunction manipulator system
| Single Port | Full DEMO Maintenance
No. Systems | 1 | 1 | 2 | 3 | 4 | 6
Operational contribution | 5.5942 | 100.6958 | 50.3479 | 33.5653 | 27.971 | 16.7826
Logistical contribution | 14.0434 | 252.7818 | 126.3909 | 84.2606 | 70.2172 | 42.1303
Idle time waiting for dependant operations | 0 | 0 | 0 | 0 | 0 | 0
Expected Delay | 19.6376 | 353.4776 | 176.7388 | 117.8259 | 98.1882 | 58.9129
Operational contribution | 2.8746 | 51.7698 | 25.8673 | 17.2449 | 14.3707 | 8.6224
Logistical contribution | 11.0654 | 199.192 | 99.5861 | 66.3907 | 55.3256 | 33.1954
Idle time waiting for dependant operations | 0 | 0 | 0 | 0 | 0 | 0
Expected Delay | 13.9399 | 250.9618 | 125.4534 | 83.6356 | 69.6963 | 41.8178
Hardware Transporter failure at the divertor port
Assumptions:
Recovery of RHE is completed using standard predetermined procedures. | [16 empty] | Hardware Transporter failure at the divertor port | Single Port | Full Maintenance Campaign
Rare and time consuming special recoveries are not considered | [16 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
[17 empty] | Duration of RM operations (h) | 662.243 | 11920.3746 | 5960.1873 | 3973.4582 | 3311.2152 | 1986.7291
Failure rate: | 0.0111% | [15 empty] | Estimated number of failures, impacting all RM systems equally | 0.073509 | 1.3232 | 0.66158 | 0.44105 | 0.36754 | 0.22053
Failure rate of RH transporter RHE per hour | 0.0111% | [15 empty] | Operational contribution | 0.44105 | 7.939 | 3.9695 | 2.6463 | 2.2053 | 1.3232
|  |  |  | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies |  |  | Logistical contribution | 0.24728 | 4.451 | 2.2255 | 1.4837 | 1.2364 | 0.74183
RH Cask RHE failure (Sub Tasks) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack | Idle time waiting for dependant operations | 0 | 0 | 0 | 0 | 0 | 0
Hardware transporter failure detected during maintenance operations | Operation | 0 | 0 | Recovery Operation | N/A |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A | Total Duration of Recovery Operations | 0.68833 | 12.3899 | 6.195 | 4.13 | 3.4416 | 2.065
Deploy Recovery System into ex-vessel area | Movement | 0.069444 | 0.069444 |  | N/A | Hardware Transporter (no load) | AMF Equipment Issue | Divertor Port | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A
Connect recovery system to transporter payload | Logistics | 1.8 | 1.8694 |  | N/A |  |  |  | N/A | N/A | N/A | Connect recovery system to hardware | 1.8 |  | N/A | N/A
Remove payload from failed transporter using recovery system | Operation | 6 | 7.8694 | Recovery Operation | 6 |  |  |  | N/A | N/A | N/A |  | N/A | Replacement transporter commissioned; moved to port to collect abandoned payload | 1.6193 | 0.25019
Move replacement transporter to Lower Port | Movement | 0.69444 | 8.5639 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A
Deploy Payload into the port | Logistics | 0.8 | 9.3639 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
| Total |  | 9.3639
Multifunction Manipulator failure
Assumptions:
Recovery of Multifunction Manipulator is completed using standard predetermined procedures. | [16 empty] | Multifunction Manipulator failure | Single Port | Full Maintenance Campaign
Rare and time consuming special recoveries are not considered | [16 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
A replacement system (if required) is available on demand from the AMF | [16 empty] | Duration of Multifunction Manipulator Tasks per port | 69.14 | 69.14 | 69.14 | 69.14 | 69.14 | 69.14
[17 empty] | Duration of RM operations (h) | 69.14 | 1244.52 | 622.26 | 414.84 | 345.7 | 207.42
Failure rate: | 2% | [15 empty] | Estimated number of failures, impacting all RM systems equally | 1.3828 | 24.8904 | 12.4452 | 8.2968 | 6.914 | 4.1484
Failure rate of Multifunction Manipulator per hour | 2% | [15 empty] | Operational contribution | 4.1484 | 74.6712 | 37.3356 | 24.8904 | 20.742 | 12.4452
[17 empty] | Logistical contribution | 12.6519 | 227.7333 | 113.8667 | 75.9111 | 63.2593 | 37.9556
|  |  |  | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies |  |  | Idle time waiting for dependant operations | 0 | 0 | 0 | 0 | 0 | 0
RH Cask RHE failure (Sub Tasks) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack | Total Duration of Recovery Operations | 16.8003 | 302.4045 | 151.2023 | 100.8015 | 84.0013 | 50.4008
mfm failure detected during maintenance operations | Operation | 0 | 0 | Recovery Operation | N/A |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
Deploy Recovery System into ex-vessel area | Movement | 0.069444 | 0.069444 |  | N/A | Hardware Transporter (no load) | AMF Equipment Issue | Divertor Port | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A
Connect recovery system to port | Logistics | 0.8 | 0.86944 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
Remove Engage with failed Multifunctional manipulator | Logistics | 1.8 | 2.6694 |  | N/A |  |  |  | N/A | N/A | N/A | Connect recovery system to hardware | 1.8 |  | N/A | N/A
Extract failed hardware from the port | Logistics | 0.6 | 3.2694 |  | N/A | hardware transporter (Loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
Remove PP hardware from the multifunction manipulator and place it in a laydown area | Operation | 3 | 6.2694 | Recovery Operation | 3 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
Disconnect the failed manipulator from the recovery system | Logistics | 1.3 | 7.5694 |  | N/A |  |  |  | N/A | N/A | N/A | disconnect recovery system from hardware | 1.3 |  | N/A | N/A
Connect replacement multifunction manipulator to the recovery system | Logistics | 1.8 | 9.3694 |  | N/A |  |  |  | N/A | N/A | N/A | Connect recovery system to hardware | 1.8 | Hardware transporter moved to the AMF; Replacement MFM issued; MFM moved to port | 2.2822 | 5.2872
Deploy replacement multifunction manipulator into the port | Logistics | 0.8 | 10.1694 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
Disconnect recovery system from the port | Logistics | 1.3 | 11.4694 |  | N/A |  |  |  | N/A | N/A | N/A | disconnect recovery system from hardware | 1.3 |  | N/A | N/A
Transport recovery system back to the AMF | Logistics | 0.68 | 12.1494 |  | N/A |  |  |  | N/A | N/A | N/A | Collect hardware from the AMF | 0.68 |  | N/A | N/A
| Total |  | 12.1494
Divertor handling system failure
Assumptions:
Recovery of Divertor handling system is completed using standard predetermined procedures. | [16 empty] | Divertor handling system failure | Single Port | Full Maintenance Campaign
Rare and time consuming special recoveries are not considered | [16 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
A replacement system (if required) is available on demand from the AMF | [16 empty] | Duration of port hardware removal | 40.11 | 40.11 | 40.11 | 40.11 | 40.11 | 40.11
[17 empty] | Duration of RM operations (h) | 40.11 | 721.98 | 360.99 | 240.66 | 200.55 | 120.33
Failure rate: | 0.501% | [15 empty] | Estimated number of failures, impacting all RM systems equally | 0.20095 | 3.6171 | 1.8086 | 1.2057 | 1.0048 | 0.60285
Failure rate of cassette handling system per hour | 0.501% | [15 empty] | Operational contribution | 1.0048 | 18.0856 | 9.0428 | 6.0285 | 5.0238 | 3.0143
[17 empty] | Logistical contribution | 1.1443 | 20.5975 | 10.2987 | 6.8658 | 5.7215 | 3.4329
|  |  |  | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies |  |  | Idle time waiting for dependant operations | 0 | 0 | 0 | 0 | 0 | 0
RH Cask RHE failure (Sub Tasks) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack | Total Duration of Recovery Operations | 2.1491 | 38.6831 | 19.3415 | 12.8944 | 10.7453 | 6.4472
cassette handling system failure detected during maintenance operations | Operation | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
Deploy Recovery System into ex-vessel area | Movement | 0.69444 | 0.69444 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor port | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A
Connect recovery system to the failed hardware | Logistics | 1.8 | 2.4944 |  | N/A |  |  |  | N/A | N/A | N/A | Connect recovery system to hardware | 1.8 |  | N/A | N/A
Disconnect divertor cassette and place in a suitable laydown area | Logistics | 0.6 | 3.0944 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
Disconnect recovery hardware from the failed divertor transporter | Operation | 3 | 6.0944 | Recovery Operation | 3 |  |  |  | N/A | N/A | N/A | disconnect recovery system from hardware | N/A |  | N/A | N/A
Install replacement divertor cassette handling system | Logistics | 1.8 | 7.8944 |  | N/A |  |  |  | N/A | N/A | N/A | Connect recovery system to hardware | 1.8 |  | N/A | N/A
collect divertor cassette from the laydown area | Operation | 2 | 9.8944 | Recovery Operation | 2 |  |  |  | N/A | N/A | N/A | Connect recovery system to hardware | N/A |  | N/A | N/A
Deploy replacement Divertor Handling Equipment into the port | Logistics | 0.8 | 10.6944 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy tool / hardware into the port | 0.8 |  | N/A | N/A
| Total |  | 10.6944
Hardware Transporter failure at the divertor port during divertor maintenance
Assumptions:
Recovery of RHE is completed using standard predetermined procedures. | [16 empty] | Hardware Transporter failure at the divertor port during divertor maintenance | Single Port | Full Maintenance Campaign
Rare and time consuming special recoveries are not considered | [16 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
[17 empty] | Duration of hardware removal movements a single port | 12.2037 | 14.4952 | 11.5556 | 11.5556 | 11.5556 | 11.5556
Failure rate: | 0.0111% | [15 empty] | Duration of hardware installation movements a single port | 9.6296 | 9.6296 | 9.6296 | 9.6296 | 9.6296 | 9.6296
Failure rate of RH transporter RHE per hour | 0.0111% | [15 empty] | Duration of RM operations (h) | 21.8333 | 434.2467 | 190.6667 | 127.1111 | 105.9259 | 63.5556
|  |  |  | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies |  |  | Estimated number of failures, impacting all RM systems equally | 0.0024235 | 0.048201 | 0.021164 | 0.014109 | 0.011758 | 0.0070547
RH Cask RHE failure (Sub Tasks) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack | Operational contribution | 0.014541 | 0.28921 | 0.12698 | 0.084656 | 0.070547 | 0.042328
Hardware transporter failure detected during maintenance operations | Operation | 0 | 0 | Recovery Operation | N/A |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A | Logistical contribution | 0.0081524 | 0.16214 | 0.071193 | 0.047462 | 0.039552 | 0.023731
Deploy Recovery System into ex-vessel area | Movement | 0.069444 | 0.069444 |  | N/A | Hardware Transporter (no load) | AMF Equipment Issue | Divertor Port | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A | Idle time waiting for dependant operations | 0 | 0 | 0 | 0 | 0 | 0
Connect recovery system to transporter payload | Logistics | 1.8 | 1.8694 |  | N/A |  |  |  | N/A | N/A | N/A | Connect recovery system to hardware | 1.8 |  | N/A | N/A | Total Duration of Recovery Operations | 0.022693 | 0.45135 | 0.19818 | 0.13212 | 0.1101 | 0.066059
Remove payload from failed transporter using recovery system | Operation | 6 | 7.8694 | Recovery Operation | 6 |  |  |  | N/A | N/A | N/A |  | N/A | Replacement transporter commissioned; moved to port to collect abandoned payload | N/A | N/A
Move replacement transporter to Lower Port | Movement | 0.69444 | 8.5639 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A
Deploy Payload into the port | Logistics | 0.8 | 9.3639 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
| Total |  | 9.3639
Multifunction Manipulator failure
Assumptions:
Recovery of Multifunction Manipulator is completed using standard predetermined procedures. | [16 empty] | Multifunction Manipulator failure | Single Port | Full Maintenance Campaign
Rare and time consuming special recoveries are not considered | [16 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
A replacement Multifunction Manipulator (if required) is available on demand from the AMF | [16 empty] | Duration of hardware removal tasks per port | 16.49 | 16.49 | 16.49 | 16.49 | 16.49 | 16.49
[17 empty] | Duration of hardware installation tasks per port | 21.28 | 21.28 | 21.28 | 21.28 | 21.28 | 21.28
Failure rate: | 2% | [15 empty] | Duration of RM operations (h) | 37.77 | 679.86 | 339.93 | 226.62 | 188.85 | 113.31
Failure rate of Multifunction Manipulator per hour | 2% | [15 empty] | Estimated number of failures, impacting all RM systems equally | 0.7554 | 13.5972 | 6.7986 | 4.5324 | 3.777 | 2.2662
[17 empty] | Operational contribution | 2.2662 | 40.7916 | 20.3958 | 13.5972 | 11.331 | 6.7986
|  |  |  | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies |  |  | Logistical contribution | 8.7614 | 157.7049 | 78.8524 | 52.5683 | 43.8069 | 26.2841
RH Cask RHE failure (Sub Tasks) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack | Idle time waiting for dependant operations | 0 | 0 | 0 | 0 | 0 | 0
Deploy Recovery System into ex-vessel area | Movement | 0.069444 | 0.069444 |  | N/A | Cask Transporter (no cask) | AMF Equipment Issue | Lower Port | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A | Total Duration of Recovery Operations | 11.0276 | 198.4965 | 99.2482 | 66.1655 | 55.1379 | 33.0827
Dock recovery system to the failed cask | Logistics | 1.9 | 1.9694 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 |  | N/A | N/A
Recover failed MM into cask for replacement | Operation | 3 | 4.9694 | Recovery Operation | 3 |  |  |  | N/A | N/A | N/A | Store Tool in Transport Cask | N/A |  | N/A | N/A
Un-dock Recovery system | Logistics | 2.3 | 7.2694 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
Un-dock Cask | Logistics | 2.3 | 9.5694 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
Move to AMF Hardware Receipt | Movement | 0.69444 | 10.2639 |  | N/A | Cask Transporter (Loaded) | Lower Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A
Store Failed Cask | Logistics | 0.58 | 10.8439 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware cask | 0.58 |  | N/A | N/A
Issue Replacement Cask | Logistics | 0.78 | 11.6239 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78 |  | N/A | N/A
Transport Cask to Lower Port | Movement | 0.69444 | 12.3183 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A
Dock Cask and Commission RM Systems | Logistics | 1.9 | 14.2183 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 |  | N/A | N/A
Deploy Divertor Handling Equipment | Logistics | 0.38 | 14.5983 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Total |  | 14.5983
Divertor handling system failure
Assumptions:
Recovery of Divertor handling system is completed using standard predetermined procedures. | [16 empty] | Divertor handling system failure | Single Port | Full Maintenance Campaign
Rare and time consuming special recoveries are not considered | [16 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
A replacement system (if required) is available on demand from the AMF | [16 empty] | Duration of hardware removal tasks | 17.64 | 17.64 | 17.64 | 17.64 | 17.64 | 17.64
[17 empty] | Duration of hardware installation tasks | 21.87 | 21.87 | 21.87 | 21.87 | 21.87 | 21.87
Failure rate: | 0.501% | [15 empty] | Duration of RM operations (h) | 39.51 | 711.18 | 355.59 | 237.06 | 197.55 | 118.53
Failure rate of Multifunction Manipulator per hour | 0.501% | [15 empty] | Estimated number of failures, impacting all RM systems equally | 0.19795 | 3.563 | 1.7815 | 1.1877 | 0.98973 | 0.59384
[17 empty] | Operational contribution | 0.59384 | 10.689 | 5.3445 | 3.563 | 2.9692 | 1.7815
|  |  |  | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies |  |  | Logistical contribution | 2.2958 | 41.325 | 20.6625 | 13.775 | 11.4792 | 6.8875
RH Cask RHE failure (Sub Tasks) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack | Idle time waiting for dependant operations | 0 | 0 | 0 | 0 | 0 | 0
Deploy Recovery System into ex-vessel area | Movement | 0.069444 | 0.069444 |  | N/A | Cask Transporter (no cask) | AMF Equipment Issue | Lower Port | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A | Total Duration of Recovery Operations | 2.8897 | 52.014 | 26.007 | 17.338 | 14.4483 | 8.669
Dock recovery system to the failed cask | Logistics | 1.9 | 1.9694 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 |  | N/A | N/A
Recover failed MM into cask for replacement | Operation | 3 | 4.9694 | Recovery Operation | 3 |  |  |  | N/A | N/A | N/A | Store Tool in Transport Cask | N/A |  | N/A | N/A
Un-dock Recovery system | Logistics | 2.3 | 7.2694 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
Un-dock Cask | Logistics | 2.3 | 9.5694 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Cask | 2.3 |  | N/A | N/A
Move to AMF Hardware Receipt | Movement | 0.69444 | 10.2639 |  | N/A | Cask Transporter (Loaded) | Lower Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A
Store Failed Cask | Logistics | 0.58 | 10.8439 |  | N/A |  |  |  | N/A | N/A | N/A | Store Equipment / Hardware cask | 0.58 |  | N/A | N/A
Issue Replacement Cask | Logistics | 0.78 | 11.6239 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Equipment / Hardware Cask | 0.78 |  | N/A | N/A
Transport Cask to Lower Port | Movement | 0.69444 | 12.3183 |  | N/A | Cask Transporter (Loaded) | AMF Equipment Issue | Lower Port | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A
Dock Cask and Commission RM Systems | Logistics | 1.9 | 14.2183 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 |  | N/A | N/A
Deploy Divertor Handling Equipment | Logistics | 0.38 | 14.5983 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware From Transport Cask | 0.38 |  | N/A | N/A
| Total |  | 14.5983
Note on D25: O Crofts: Uses multiple dextrous manipulators and deployment systems
Note on C32: Farquhar, Iain: Failed transporter moved to the AMF for repair
Note on D45: Farquhar, Iain: Uses complex RM systems
Note on D74: Farquhar, Iain: Uses complex RM systems
Note on D98: O Crofts: Uses multiple dextrous manipulators and deployment systems
Note on C105: Farquhar, Iain: Failed transporter moved to the AMF for repair
Note on D118: Farquhar, Iain: Uses complex RM systems
Note on D146: Farquhar, Iain: Uses complex RM systems

## Lower Hot Cell Weld Failure (hidden)
Delay caused by failure and recovery from failed welding operations
Welding Assumptions | [14 empty] | Expected Delay
Operations Assumptions
TIG welding and laser cutting is the current worst case scenario
In-situ surface treatment is not possible, so all hardware must be removed and replaced/reconditioned before it can be re-welded
All other positioning, delivery and retrieval operations are of a similar length to nominal operations
Service Joint system is capable of cutting and pipes without tool change
No additional blanket modules will need to be removed to access impacted blanket module
RM Tooling is able to cut and weld all pipes within a pipe module simultaneously
No logistical bottlenecks occur during recovery operations
Both upper and lower port welding operations are carried out simultaneously for each blanket, to prevent unnecessary cutting of welds
Design Assumptions
Each upper port pipe module contains 5 pipes
Each lower port pipe module contains 3 pipes
All other positioning, delivery and retrieval operations are of a similar length to nominal operations
Service Joint system is capable of cutting and pipes without tool change
|  | Single Port | Full DEMO Maintenance
| No. Systems | 1 | 1 | 2 | 3 | 4 | 6
Full Lower Port Maintenance
| Operational contribution | 282.9127 | 5092.4284 | 2546.2142 | 1697.4761 | 1414.5634 | 848.7381
| Logistical contribution | 34.6721 | 624.0975 | 312.0488 | 208.0325 | 173.3604 | 104.0163
| Idle time waiting for dependant operations | 117.9909 | 2123.8368 | 1061.9184 | 707.9456 | 589.9547 | 353.9728
| Estimated Delay | 364.9187 | 7607.0849 | 3803.5425 | 2535.695 | 2113.0791 | 1267.8475
Divertor Only Maintenance
| Operational contribution | 30.8085 | 554.5531 | 277.2765 | 184.851 | 154.0425 | 92.4255
| Logistical contribution | 7.7035 | 138.6629 | 69.3314 | 46.221 | 38.5175 | 23.1105
| Idle time waiting for dependant operations | 0.81551 | 14.6792 | 7.3396 | 4.8931 | 4.0776 | 2.4465
| Estimated Delay | 39.3275 | 707.8951 | 353.9476 | 235.965 | 196.6375 | 117.9825
Estimated Operational Durations (taken from Hotcell Critical Path)
Failure of COB Lower Port Welds
Assumptions:
TIG welding and laser cutting is the current worst case scenario
|  | Any LOB pipe joint failures are detected prior to the Connection of the COB pipework | [14 empty] | Single Port | Full Maintenance Campaign
|  | In-situ surface treatment is not possible, so all hardware must be removed and replaced/reconditioned before it can be re-welded | [13 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
|  | All other positioning, delivery and retrieval operations are of a similar length to nominal operations | [13 empty] | Duration of welding operations (h) | 26.7733 | 481.9189 | 240.9594 | 160.6396 | 133.8664 | 80.3198
|  | Service Joint system is capable of cutting and pipes without tool change | [13 empty] | Estimated number of failures, impacting all RM systems equally | 0.29451 | 5.3011 | 2.6506 | 1.767 | 1.4725 | 0.88352
|  | No additional blanket modules will need to be removed to access impacted blanket module | [13 empty] | Operational contribution | 57.6173 | 1037.111 | 518.5555 | 345.7037 | 288.0864 | 172.8518
[16 empty] | Logistical contribution | 6.6293 | 119.3279 | 59.664 | 39.776 | 33.1466 | 19.888
[16 empty] | Idle time waiting for dependant operations | 0.66187 | 11.9137 | 5.9569 | 3.9712 | 3.3094 | 1.9856
|  | Failure rate: | 1.1% | [12 empty] | Total Duration of Recovery Operations | 64.9085 | 1168.3526 | 584.1763 | 389.4509 | 324.5424 | 194.7254
|  | Assuming a weld failure rate of | 0.1%
|  | Assuming a tool failure rate of | 1%
|  | Probability of Secondary Failure/hr or Event | 0.0359%
[6 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies
| Group | Pipe weld failure (Sub Tasks) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack
| Cut Failed Welds | Lower Port COB weld failure identified | Operation | 0 | 0 | Hardware Recovery Required | 0 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Cut Failed Pipe Module Weld | Operation | 12.603 | 12.603 | Disconnect blanket pipe module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove Pipe Module from Port | Remove COB pipe module from the port | Logistics | 0.6 | 13.203 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Remove remaining Outboard pipe modules | Deploy Multifunction Manipulator | Logistics | 0.8 | 14.003 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
|  | Remove LOB pipework access lid using Multifunction Manipulator | Operation | 3.83 | 17.833 | Remove Lower Port Pipework Access Lid | 3.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Remove ROB pipework access lid using Multifunction Manipulator | Operation | 3.83 | 21.663 | Remove Lower Port Pipework Access Lid | 3.83 |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | N/A |  | N/A | N/A
|  | Reposition Pipework equipment to the second pipework module | Logistics | 0.53 | 22.193 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Disconnect LOB blanket pipework module | Operation | 12.603 | 34.7959 | Disconnect Blanket Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Remove LOB pipe module from the port | Logistics | 0.6 | 35.3959 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 | Pumping handling system store; pipe module handing system collected; Pipe Module handling System Moved to Lower Port | 1.8059 | 32.99
|  | Reposition Pipework equipment to the third pipe module | Logistics | 0.53 | 35.9259 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Disconnect ROB blanket pipework module | Operation | 12.603 | 48.5289 | Disconnect Blanket Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Remove ROB pipe module from the port | Logistics | 0.6 | 49.1289 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 | COB pipe module stored; Pipe Module handling System Moved to Lower Port | 15.0089 | 33.52
| Remove Inboard pipe modules | Deploy Service Joint System | Logistics | 0.8 | 49.9289 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
|  | Disconnect LIB blanket pipework module | Operation | 12.603 | 62.5319 | Disconnect Blanket Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Remove LIB Pipe Module from the port | Logistics | 0.6 | 63.1319 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 | LOB pipe module stored; Pipe Module handling System Moved to Lower Port | 37.2019 | 25.33
|  | Reposition Pipework equipment to the second pipework module | Logistics | 0.53 | 63.6619 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Disconnect RIB blanket pipework module | Operation | 12.603 | 76.2648 | Disconnect Blanket Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Remove RIB Pipe Module from the port | Logistics | 0.6 | 76.8648 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 | ROB pipe module stored; Pipe Module handling System Moved to Lower Port | 50.9348 | 25.33
|  | Retract Service Joint System into cask | Logistics | 0.6 | 77.4648 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Remove Inner Port Pipe modules | Disconnect LIB Inner Pipework module | Operation | 7.523 | 84.9878 | Disconnect Inner Port Pipe Module | 7.523 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Remove Inner LIB Pipe Module from port | Logistics | 0.6 | 85.5878 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 | LIB pipe module stored; Pipe Module handling System Moved to Lower Port | 64.9378 | 20.05
|  | Reposition Pipework equipment to the RIB inner pipework module | Logistics | 0.53 | 86.1178 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Disconnect RIB Inner Pipe module | Operation | 7.523 | 93.6408 | Disconnect Inner Port Pipe Module | 7.523 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Remove Inner RIB Pipe Module from port | Logistics | 0.6 | 94.2408 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 | RIB pipe module stored; Pipe Module handling System Moved to Lower Port | N/A | N/A
|  | Retract Blanket Pipe Module Handling System from port | Logistics | 0.6 | 94.8408 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Install Inner Port Pipe Modules | Deploy Service Joint System | Logistics | 0.8 | 95.6408 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
|  | Install RIB Inner pipe module | Logistics | 0.8 | 98.0823 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | LIB Inner pipe module stored; Replacement RIB Inner Port Pipe Module collected; Transporter moved to port | 97.2823 | -1.6415
|  | Connect RIB Inner pipe module | Operation | 17.6227 | 115.7049 | Connect Inner Port Pipe module | 17.6227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Collect LIB inner pipe module | Logistics | 0.53 | 116.2349 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Install LIB Inner pipe module | Logistics | 0.8 | 117.0349 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Inner LIB pipe module collected; Pipe Module handling System Moved to Lower Port | 95.2467 | 20.9882
|  | Connect LIB inner Pipe Module | Operation | 17.6227 | 134.6576 | Connect Inner Port Pipe module | 17.6227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Service Joint System into cask | Logistics | 0.6 | 135.2576 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
|  | Retract Multifunction manipulator | Logistics | 0.6 | 135.8576 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Install Inboard Blanket Pipe Modules | Install RIB pipe module | Logistics | 0.8 | 137.2635 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | RIB pipe module collected; Pipe Module handling System Moved to Lower Port | 136.4635 | -0.60593
|  | Connect RIB Pipe Module | Operation | 17.6227 | 154.8862 | Connect Inner Port Pipe module | 17.6227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Collect second Port Pipework Module | Logistics | 0.8 | 155.6862 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
|  | Install LIB pipe module | Logistics | 0.8 | 156.4862 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | LIB pipe module collected; Pipe Module handling System Moved to Lower Port | 136.4635 | 19.2227
|  | Connect LIB Pipe Module | Operation | 17.6227 | 174.1088 | Connect Inner Port Pipe module | 17.6227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Install Outboard Blanket Pipe Modules | Install ROB Pipe Module | Logistics | 0.8 | 174.9088 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | ROB pipe module collected; Pipe Module handling System Moved to Lower Port | 156.6921 | 17.4167
|  | Connect ROB Pipe Module | Operation | 10.0363 | 184.9452 | Connect Blanket Pipe Module | 10.0363 |  |  |  | N/A | N/A | N/A |  | N/A | ROB Blanket Segment Installed | 101.5939 | 73.3149
|  | Extract LOB Pipework Module from Cask | Logistics | 0.8 | 185.7452 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
|  | Reposition Pipework equipment to the second pipework module location | Logistics | 0.53 | 186.2752 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 | LOB pipe module collected; Pipe Module handling System Moved to Lower Port | 175.9148 | 9.8304
|  | Connect LOB pipe module | Operation | 10.0363 | 196.3115 | Connect Blanket Pipe Module | 10.0363 |  |  |  | N/A | N/A | N/A |  | N/A | LOB Blanket Segment Installed | 107.37 | 78.9052
|  | Retract Service Joint System into cask | Logistics | 0.6 | 196.9115 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
|  | Deploy Multifunction Manipulator | Logistics | 0.8 | 197.7115 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
|  | Install LOB pipework access lid using Multifunction Manipulator | Operation | 4.66 | 202.3715 | Install Lower Port Pipework Access Lid | 4.66 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Install ROB pipework access lid using Multifunction Manipulator | Operation | 4.66 | 207.0315 | Install Lower Port Pipework Access Lid | 4.66 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Multifunction manipulator | Logistics | 0.6 | 207.6315 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
|  | Deploy Service Joint System | Logistics | 0.8 | 208.4315 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
|  | Install COB Pipe Module | Logistics | 0.8 | 209.2315 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | COB pipe module collected; Pipe Module handling System Moved to Lower Port | 186.7511 | 21.6804
|  | Reposition Pipework equipment to the third pipe module | Logistics | 0.53 | 209.7615 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Connect COB pipework module | Operation | 10.0363 | 219.7978 | Connect Blanket Pipe Module | 10.0363 |  |  |  | N/A | N/A | N/A |  | N/A | COB Blanket segment installed | 113.1461 | 96.6154
|  | Retract Service Joint System | Logistics | 0.6 | 220.3978 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
|  |  | Total |  | 220.3978
Failure of LOB Lower Port Welds
Assumptions:
TIG welding and laser cutting is the current worst case scenario
|  | Any LOB pipe joint failures are detected prior to the Connection of the COB pipework | [14 empty] | Single Port | Full Maintenance Campaign
|  | In-situ surface treatment is not possible, so all hardware must be removed and replaced/reconditioned before it can be re-welded | [13 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
|  | All other positioning, delivery and retrieval operations are of a similar length to nominal operations | [13 empty] | Duration of welding operations (h) | 26.7733 | 481.9189 | 240.9594 | 160.6396 | 133.8664 | 80.3198
|  | Service Joint system is capable of cutting and pipes without tool change | [13 empty] | Estimated number of failures, impacting all RM systems equally | 0.29451 | 5.3011 | 2.6506 | 1.767 | 1.4725 | 0.88352
|  | No additional blanket modules will need to be removed to access impacted blanket module | [13 empty] | Operational contribution | 45.9492 | 827.0848 | 413.5424 | 275.6949 | 229.7458 | 137.8475
[16 empty] | Logistical contribution | 5.0802 | 91.4441 | 45.7221 | 30.4814 | 25.4011 | 15.2407
[16 empty] | Idle time waiting for dependant operations | 6.9622 | 125.3202 | 62.6601 | 41.7734 | 34.8112 | 20.8867
|  | Failure rate: | 1.1% | [12 empty] | Total Duration of Recovery Operations | 57.9916 | 1043.8491 | 521.9245 | 347.9497 | 289.9581 | 173.9748
|  | Assuming a weld failure rate of | 0.1%
|  | Assuming a tool failure rate of | 1%
|  | Probability of Secondary Failure/hr or Event | 0.0359%
[6 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies
| Group | Pipe weld failure (Sub Tasks) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack
| Cut Failed Welds | Lower Port LOB weld failure identified | Operation | 0 | 0 | Hardware Recovery Required | 0 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Cut Failed Pipe Module Weld | Operation | 12.603 | 12.603 | Disconnect blanket pipe module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove Pipe Module from Port | Remove LOB pipe module from the port | Logistics | 0.6 | 13.203 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Remove remaining Outboard pipe modules | Deploy Multifunction Manipulator | Logistics | 0.8 | 14.003 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
|  | Reposition Pipework equipment to the second pipework module | Logistics | 0.53 | 14.533 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Disconnect ROB blanket pipework module | Operation | 12.603 | 27.1359 | Disconnect Blanket Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Remove ROB pipe module from the port | Logistics | 0.6 | 27.7359 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 | Pumping handling system store; pipe module handing system collected; Pipe Module handling System Moved to Lower Port | 1.8059 | 25.33
| Remove Inboard pipe modules | Deploy Service Joint System | Logistics | 0.8 | 28.5359 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
|  | Disconnect LIB blanket pipework module | Operation | 12.603 | 41.1389 | Disconnect Blanket Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Remove LIB Pipe Module from the port | Logistics | 0.6 | 41.7389 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 | LOB pipe module stored; Pipe Module handling System Moved to Lower Port | 37.2019 | 3.937
|  | Reposition Pipework equipment to the second pipework module | Logistics | 0.53 | 42.2689 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Disconnect RIB blanket pipework module | Operation | 12.603 | 54.8719 | Disconnect Blanket Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Remove RIB Pipe Module from the port | Logistics | 0.6 | 55.4719 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 | ROB pipe module stored; Pipe Module handling System Moved to Lower Port | 50.9348 | 3.937
|  | Retract Service Joint System into cask | Logistics | 0.6 | 56.0719 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Remove Inner Port Pipe modules | Disconnect LIB Inner Pipework module | Operation | 7.523 | 63.5948 | Disconnect Inner Port Pipe Module | 7.523 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Remove Inner LIB Pipe Module from port | Logistics | 0.6 | 65.5378 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 | LIB pipe module stored; Pipe Module handling System Moved to Lower Port | 64.9378 | -1.343
|  | Reposition Pipework equipment to the RIB inner pipework module | Logistics | 0.53 | 66.0678 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Disconnect RIB Inner Pipe module | Operation | 7.523 | 73.5908 | Disconnect Inner Port Pipe Module | 7.523 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Remove Inner RIB Pipe Module from port | Logistics | 0.6 | 79.2708 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 | RIB pipe module stored; Blanket Pipe Module handling System Stored | 78.6708 | -5.08
|  | Retract Blanket Pipe Module Handling System from port | Logistics | 0.6 | 79.8708 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Install Inner Port Pipe Modules | Deploy Service Joint System | Logistics | 0.8 | 80.6708 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
|  | Install RIB Inner pipe module | Logistics | 0.8 | 98.0823 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | LIB Inner pipe module stored; Replacement RIB Inner Port Pipe Module collected; Transporter moved to port | 97.2823 | -16.6115
|  | Connect RIB Inner pipe module | Operation | 17.6227 | 115.7049 | Connect Inner Port Pipe module | 17.6227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Collect LIB inner pipe module | Logistics | 0.53 | 116.2349 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Install LIB Inner pipe module | Logistics | 0.8 | 117.0349 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Inner LIB pipe module collected; Pipe Module handling System Moved to Lower Port | 95.2467 | 20.9882
|  | Connect LIB inner Pipe Module | Operation | 17.6227 | 134.6576 | Connect Inner Port Pipe module | 17.6227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Service Joint System into cask | Logistics | 0.6 | 135.2576 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
|  | Retract Multifunction manipulator | Logistics | 0.6 | 135.8576 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Install Inboard Blanket Pipe Modules | Install RIB pipe module | Logistics | 0.8 | 137.2635 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | RIB pipe module collected; Pipe Module handling System Moved to Lower Port | 136.4635 | -0.60593
|  | Connect RIB Pipe Module | Operation | 17.6227 | 154.8862 | Connect Inner Port Pipe module | 17.6227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Collect second Port Pipework Module | Logistics | 0.8 | 155.6862 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
|  | Install LIB pipe module | Logistics | 0.8 | 156.4862 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | LIB pipe module collected; Pipe Module handling System Moved to Lower Port | 136.4635 | 19.2227
|  | Connect LIB Pipe Module | Operation | 17.6227 | 174.1088 | Connect Inner Port Pipe module | 17.6227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Install replacement Outboard pipe modules | Install ROB Pipe Module | Logistics | 0.8 | 174.9088 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | ROB pipe module collected; Pipe Module handling System Moved to Lower Port | 156.6921 | 17.4167
|  | Connect ROB Pipe Module | Operation | 10.0363 | 184.9452 | Connect Blanket Pipe Module | 10.0363 |  |  |  | N/A | N/A | N/A |  | N/A | ROB Blanket Segment Installed | 101.5939 | 73.3149
|  | Extract LOB Pipework Module from Cask | Logistics | 0.8 | 185.7452 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
|  | Reposition Pipework equipment to the second pipework module location | Logistics | 0.53 | 186.2752 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 | LOB pipe module collected; Pipe Module handling System Moved to Lower Port | 175.9148 | 9.8304
|  | Connect LOB pipe module | Operation | 10.0363 | 196.3115 | Connect Blanket Pipe Module | 10.0363 |  |  |  | N/A | N/A | N/A |  | N/A | LOB Blanket Segment Installed | 107.37 | 78.9052
|  | Retract Service Joint System into cask | Logistics | 0.6 | 196.9115 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
|  |  | Total |  | 196.9115
Failure of ROB Lower Port Welds
Assumptions:
TIG welding and laser cutting is the current worst case scenario
|  | Any LOB pipe joint failures are detected prior to the Connection of the COB pipework | [14 empty] | Single Port | Full Maintenance Campaign
|  | In-situ surface treatment is not possible, so all hardware must be removed and replaced/reconditioned before it can be re-welded | [13 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
|  | All other positioning, delivery and retrieval operations are of a similar length to nominal operations | [13 empty] | Duration of welding operations (h) | 26.7733 | 481.9189 | 240.9594 | 160.6396 | 133.8664 | 80.3198
|  | Service Joint system is capable of cutting and pipes without tool change | [13 empty] | Estimated number of failures, impacting all RM systems equally | 0.29451 | 5.3011 | 2.6506 | 1.767 | 1.4725 | 0.88352
|  | No additional blanket modules will need to be removed to access impacted blanket module | [13 empty] | Operational contribution | 39.2817 | 707.0714 | 353.5357 | 235.6905 | 196.4087 | 117.8452
[16 empty] | Logistical contribution | 4.1201 | 74.1625 | 37.0812 | 24.7208 | 20.6007 | 12.3604
[16 empty] | Idle time waiting for dependant operations | 3.7824 | 68.0839 | 34.0419 | 22.6946 | 18.9122 | 11.3473
|  | Failure rate: | 1.1% | [12 empty] | Total Duration of Recovery Operations | 47.1843 | 849.3178 | 424.6589 | 283.1059 | 235.9216 | 141.553
|  | Assuming a weld failure rate of | 0.1%
|  | Assuming a tool failure rate of | 1%
|  | Probability of Secondary Failure/hr or Event | 0.0359%
[6 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies
| Group | Pipe weld failure (Sub Tasks) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack
| Cut Failed Welds | Lower Port ROB weld failure identified | Operation | 0 | 0 | Hardware Recovery Required | 0 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Cut Failed Pipe Module Weld | Operation | 12.603 | 12.603 | Disconnect blanket pipe module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove Pipe Module from Port | Remove ROB pipe module from the port | Logistics | 0.6 | 13.203 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Remove Inboard pipe modules | Deploy Service Joint System | Logistics | 0.8 | 14.003 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
|  | Disconnect LIB blanket pipework module | Operation | 12.603 | 26.6059 | Disconnect Blanket Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Remove LIB Pipe Module from the port | Logistics | 0.6 | 27.2059 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 | Pumping handling system store; pipe module handing system collected; Pipe Module handling System Moved to Lower Port | 1.8059 | 24.8
|  | Reposition Pipework equipment to the second pipework module | Logistics | 0.53 | 27.7359 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Disconnect RIB blanket pipework module | Operation | 12.603 | 40.3389 | Disconnect Blanket Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Remove RIB Pipe Module from the port | Logistics | 0.6 | 51.5348 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 | ROB pipe module stored; Pipe Module handling System Moved to Lower Port | 50.9348 | -10.5959
|  | Retract Service Joint System into cask | Logistics | 0.6 | 52.1348 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Remove Inner Port Pipe modules | Disconnect LIB Inner Pipework module | Operation | 7.523 | 59.6578 | Disconnect Inner Port Pipe Module | 7.523 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Remove Inner LIB Pipe Module from port | Logistics | 0.6 | 60.2578 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 | LIB pipe module stored; Pipe Module handling System Moved to Lower Port | 53.3408 | 6.317
|  | Reposition Pipework equipment to the RIB inner pipework module | Logistics | 0.53 | 60.7878 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Disconnect RIB Inner Pipe module | Operation | 7.523 | 68.3108 | Disconnect Inner Port Pipe Module | 7.523 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Remove Inner RIB Pipe Module from port | Logistics | 0.6 | 68.9108 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 | RIB pipe module stored; Blanket Pipe Module handling System Stored | 53.3408 | 14.97
|  | Retract Blanket Pipe Module Handling System from port | Logistics | 0.6 | 69.5108 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Install Inner Port Pipe Modules | Deploy Service Joint System | Logistics | 0.8 | 70.3108 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
|  | Install RIB Inner pipe module | Logistics | 0.8 | 72.7522 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | LIB Inner pipe module stored; Replacement RIB Inner Port Pipe Module collected; Transporter moved to port | 71.9522 | -1.6415
|  | Connect RIB Inner pipe module | Operation | 17.6227 | 90.3749 | Connect Inner Port Pipe module | 17.6227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Collect LIB inner pipe module | Logistics | 0.53 | 90.9049 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Install LIB Inner pipe module | Logistics | 0.8 | 91.7049 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Inner LIB pipe module collected; Pipe Module handling System Moved to Lower Port | 69.9167 | 20.9882
|  | Connect LIB inner Pipe Module | Operation | 17.6227 | 109.3276 | Connect Inner Port Pipe module | 17.6227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Service Joint System into cask | Logistics | 0.6 | 109.9276 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
|  | Retract Multifunction manipulator | Logistics | 0.6 | 110.5276 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Install Inboard Blanket Pipe Modules | Install RIB pipe module | Logistics | 0.8 | 111.9335 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | RIB pipe module collected; Pipe Module handling System Moved to Lower Port | 111.1335 | -0.60593
|  | Connect RIB Pipe Module | Operation | 17.6227 | 129.5562 | Connect Inner Port Pipe module | 17.6227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Collect second Port Pipework Module | Logistics | 0.8 | 130.3562 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
|  | Install LIB pipe module | Logistics | 0.8 | 131.1562 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | LIB pipe module collected; Pipe Module handling System Moved to Lower Port | 111.1335 | 19.2227
|  | Connect LIB Pipe Module | Operation | 17.6227 | 148.7788 | Connect Inner Port Pipe module | 17.6227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Install replacement ROB Pipe Module | Install ROB Pipe Module | Logistics | 0.8 | 149.5788 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | ROB pipe module collected; Pipe Module handling System Moved to Lower Port | 131.3621 | 17.4167
|  | Connect ROB Pipe Module | Operation | 10.0363 | 159.6152 | Connect Blanket Pipe Module | 10.0363 |  |  |  | N/A | N/A | N/A |  | N/A | ROB Blanket Segment Installed | 125.6908 | 23.888
|  | Retract Service Joint System into cask | Logistics | 0.6 | 160.2152 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
|  |  | Total |  | 160.2152
Failure of LIB Inner Port Welds
Assumptions:
TIG welding and laser cutting is the current worst case scenario
|  | Any LOB pipe joint failures are detected prior to the Connection of the COB pipework | [14 empty] | Single Port | Full Maintenance Campaign
|  | In-situ surface treatment is not possible, so all hardware must be removed and replaced/reconditioned before it can be re-welded | [13 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
|  | All other positioning, delivery and retrieval operations are of a similar length to nominal operations | [13 empty] | Duration of welding operations (h) | 53.7846 | 968.1235 | 484.0617 | 322.7078 | 268.9232 | 161.3539
|  | Service Joint system is capable of cutting and pipes without tool change | [13 empty] | Estimated number of failures, impacting all RM systems equally | 0.59163 | 10.6494 | 5.3247 | 3.5498 | 2.9582 | 1.7749
|  | No additional blanket modules will need to be removed to access impacted blanket module | [13 empty] | Operational contribution | 35.7648 | 643.7672 | 321.8836 | 214.5891 | 178.8242 | 107.2945
[16 empty] | Logistical contribution | 3.1534 | 56.7611 | 28.3805 | 18.9204 | 15.767 | 9.4602
[16 empty] | Idle time waiting for dependant operations | 47.0844 | 847.5186 | 423.7593 | 282.5062 | 235.4218 | 141.2531
|  | Failure rate: | 1.1% | [12 empty] | Total Duration of Recovery Operations | 86.0026 | 1548.0469 | 774.0234 | 516.0156 | 430.013 | 258.0078
|  | Assuming a weld failure rate of | 0.1%
|  | Assuming a tool failure rate of | 1%
|  | Probability of Secondary Failure/hr or Event | 0.0359%
[6 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies
| Group | Pipe weld failure (Sub Tasks) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack
| Cut Failed Welds | Weld Failure identified at LIB Inner Port Module joint | Operation | 0 | 0 | Hardware Recovery Required | 0 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Cut Failed Pipe Module Weld | Operation | 12.603 | 12.603 | Disconnect Blanket Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove Pipe Module from the port | Remove LIB Inner Port Pipe Module from the port | Logistics | 0.6 | 13.203 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Remove RIB Inner Port Pipe Module | Reposition Pipework equipment to the RIB inner pipework module | Logistics | 0.53 | 13.733 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Disconnect Inner RIB Pipe Module | Operation | 12.603 | 26.3359 | Disconnect Blanket Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | N/A |  | N/A | N/A
|  | Remove RIB Inner Pipework module from the port | Logistics | 0.6 | 26.9359 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 | New RIB pipe module stored; Pipe Module handling System Moved to Lower Port | 1.8059 | 23.93
|  | Retract Service Joint System | Logistics | 0.6 | 27.5359 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Install replacement Inner Port Pipe Modules | Deploy Service Joint System | Logistics | 0.8 | 28.3359 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
|  | Collect RIB Inner Port Pipe Module from hardware transporter | Logistics | 0.8 | 31.5774 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | LIB Inner pipe module stored; Replacement RIB Inner Port Pipe Module collected; Transporter moved to port | 29.9774 | -2.4415
|  | Connect RIB inner pipe module | Operation | 17.6227 | 126.3426 | Connect Inner Port Pipe module | 17.6227 |  |  |  | N/A | N/A | N/A |  | N/A | LIB Blanket segment installed | 91.0973 | -77.1425
|  | Collect LIB Inner Port Pipe Module from hardware transporter | Logistics | 0.8 | 127.1426 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | LIB Inner pipe module collected; Pipe Module handling System Moved to Lower Port | N/A | N/A
|  | Connect LIB inner pipe module | Operation | 17.6227 | 144.7653 | Connect Inner Port Pipe module | 17.6227 |  |  |  | N/A | N/A | N/A |  | N/A | RIB Blanket segment installed | 56.5038 | 53.0162
|  | Retract Service Joint System | Logistics | 0.6 | 145.3653 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
|  |  | Total |  | 145.3653
Failure of LIB Lower Port Welds
Assumptions:
TIG welding and laser cutting is the current worst case scenario
|  | Any LOB pipe joint failures are detected prior to the Connection of the COB pipework | [13 empty] | Bore Pipe Welds | Single Port | Full Maintenance Campaign
|  | In-situ surface treatment is not possible, so all hardware must be removed and replaced/reconditioned before it can be re-welded | [13 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
|  | All other positioning, delivery and retrieval operations are of a similar length to nominal operations | [13 empty] | Duration of welding operations (h) | 26.7733 | 481.9189 | 240.9594 | 160.6396 | 133.8664 | 80.3198
|  | Service Joint system is capable of cutting and pipes without tool change | [13 empty] | Estimated number of failures, impacting all RM systems equally | 0.29451 | 5.3011 | 2.6506 | 1.767 | 1.4725 | 0.88352
|  | No additional blanket modules will need to be removed to access impacted blanket module | [13 empty] | Operational contribution | 31.1381 | 560.4854 | 280.2427 | 186.8285 | 155.6904 | 93.4142
[16 empty] | Logistical contribution | 3.375 | 60.7507 | 30.3753 | 20.2502 | 16.8752 | 10.1251
[16 empty] | Idle time waiting for dependant operations | 15.0929 | 271.6716 | 135.8358 | 90.5572 | 75.4643 | 45.2786
|  | Failure rate: | 1.1% | [12 empty] | Total Duration of Recovery Operations | 49.606 | 892.9077 | 446.4538 | 297.6359 | 248.0299 | 148.8179
|  | Assuming a weld failure rate of | 0.1%
|  | Assuming a tool failure rate of | 1%
|  | Probability of Secondary Failure/hr or Event | 0.0359%
[6 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies
| Group | Pipe weld failure (Sub Tasks) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack
| Cut Failed Welds | Weld Failure identified at LIB Module joint | Operation | 0 | 0 | Hardware Recovery Required | 0 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Cut Failed Pipe Module Weld | Operation | 12.603 | 12.603 | Disconnect Blanket Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove Failed Pipe Module from the port | Remove LIB Pipe Module from the port | Logistics | 0.6 | 13.203 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Remove RIB Pipe Module | Reposition Pipework equipment to the second pipework module | Logistics | 0.53 | 13.733 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Disconnect RIB blanket pipework module | Operation | 12.603 | 27.0119 | Disconnect Blanket Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A | New ROB pipe module stored; Pipe Module handling System Moved to Lower Port | 1.8059 | -0.67593
|  | Remove RIB Pipe Module from the port | Logistics | 0.6 | 27.6119 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
|  | Retract Service Joint System | Logistics | 0.6 | 28.2119 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Remove Inner Port Pipe Module | Deploy Service Joint System | Logistics | 0.8 | 29.0119 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
|  | Disconnect Inner LIB Pipe Module | Operation | 12.603 | 41.6148 | Disconnect Blanket Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | N/A |  | N/A | N/A
|  | Remove LIB Inner Pipework module from the port | Logistics | 0.6 | 42.2148 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 | LIB pipe module stored; Pipe Module handling System Moved to Lower Port | 15.0089 | 26.0059
|  | Reposition Pipework equipment to the RIB inner pipework module | Logistics | 0.53 | 42.7448 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Disconnect Inner RIB Pipe Module | Operation | 12.603 | 55.3478 | Disconnect Blanket Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | N/A |  | N/A | N/A
|  | Remove RIB Inner Pipework module from the port | Logistics | 0.6 | 55.9478 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 | RIB pipe module stored; Blanket Pipe Module handling System Stored | 29.4178 | 25.33
|  | Retract Service Joint System | Logistics | 0.6 | 56.5478 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Install replacement Inner Port Pipe Modules | Deploy Service Joint System | Logistics | 0.8 | 57.3478 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
|  | Collect RIB Inner Port Pipe Module from hardware transporter | Logistics | 0.8 | 58.1478 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | LIB Inner pipe module stored; Replacement RIB Inner Port Pipe Module collected; Transporter moved to port | 45.2563 | 11.2915
|  | Connect RIB inner pipe module | Operation | 17.6227 | 126.3426 | Connect Inner Port Pipe module | 17.6227 |  |  |  | N/A | N/A | N/A |  | N/A | LIB Blanket segment installed | 91.0973 | -50.5722
|  | Collect LIB Inner Port Pipe Module from hardware transporter | Logistics | 0.8 | 127.1426 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Inner LIB pipe module collected; Pipe Module handling System Moved to Lower Port | 57.5537 | 67.9889
|  | Connect LIB inner pipe module | Operation | 17.6227 | 144.7653 | Connect Inner Port Pipe module | 17.6227 |  |  |  | N/A | N/A | N/A |  | N/A | RIB Blanket segment installed | 86.1978 | 23.3221
|  | Retract Service Joint System | Logistics | 0.6 | 145.3653 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Install replacement LIB Pipe module | Deploy Service Joint System | Logistics | 0.8 | 146.1653 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
|  | Collect RIB Pipe Module from hardware transporter | Logistics | 0.8 | 146.9653 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | RIB pipe module collected; Pipe Module handling System Moved to Lower Port | 128.1485 | 17.2167
|  | Connect RIB Pipe Module | Operation | 10.0363 | 157.0016 | Connect Blanket Pipe Module | 10.0363 |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | N/A |  | N/A | N/A
|  | Collect second Inner Port Pipework Module from hardware transporter | Logistics | 0.8 | 157.8016 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
|  | Connect LIB Pipework Module | Operation | 10.0363 | 167.8379 | Connect Blanket Pipe Module | 10.0363 |  |  |  | N/A | N/A | N/A |  | N/A | LIB pipe module collected; Pipe Module handling System Moved to Lower Port | 146.5712 | 1.1941
|  | Retract Service Joint System into cask | Logistics | 0.6 | 168.4379 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
|  |  | Total |  | 168.4379
Failure of RIB Inner Port Welds
Assumptions:
TIG welding and laser cutting is the current worst case scenario
|  | Any LOB pipe joint failures are detected prior to the Connection of the COB pipework | [14 empty] | Single Port | Full Maintenance Campaign
|  | In-situ surface treatment is not possible, so all hardware must be removed and replaced/reconditioned before it can be re-welded | [13 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
|  | All other positioning, delivery and retrieval operations are of a similar length to nominal operations | [13 empty] | Duration of welding operations (h) | 53.7846 | 968.1235 | 484.0617 | 322.7078 | 268.9232 | 161.3539
|  | Service Joint system is capable of cutting and pipes without tool change | [13 empty] | Estimated number of failures, impacting all RM systems equally | 0.59163 | 10.6494 | 5.3247 | 3.5498 | 2.9582 | 1.7749
|  | No additional blanket modules will need to be removed to access impacted blanket module | [13 empty] | Operational contribution | 17.8824 | 321.8836 | 160.9418 | 107.2945 | 89.4121 | 53.6473
[16 empty] | Logistical contribution | 1.6566 | 29.8182 | 14.9091 | 9.9394 | 8.2828 | 4.9697
[16 empty] | Idle time waiting for dependant operations | 35.0976 | 631.757 | 315.8785 | 210.5857 | 175.488 | 105.2928
|  | Failure rate: | 1.1% | [12 empty] | Total Duration of Recovery Operations | 54.6366 | 983.4587 | 491.7294 | 327.8196 | 273.183 | 163.9098
|  | Assuming a weld failure rate of | 0.1%
|  | Assuming a tool failure rate of | 1%
|  | Probability of Secondary Failure/hr or Event | 0.0359%
[6 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies
| Group | Pipe weld failure (Sub Tasks) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack
| Cut Failed Welds | Weld Failure identified at RIB Inner Port Module joint | Operation | 0 | 0 | Hardware Recovery Required | 0 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Cut Failed Pipe Module Weld | Operation | 12.603 | 12.603 | Disconnect Blanket Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove Pipe Module from the port | Remove RIB Inner Port Pipe Module from the port | Logistics | 0.6 | 13.203 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Install Replacement Inner Port Pipe Module | Deploy Service Joint System | Logistics | 0.8 | 14.003 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
|  | Collect RIB Inner Port Pipe Module from hardware transporter | Logistics | 0.8 | 14.803 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | New LIB Inner Port pipe module stored; Replacement RIB Inner Port Pipe collected; Hardware transporter moved to Lower Port | 1.8059 | 11.397
|  | Connect RIB inner pipe module | Operation | 17.6227 | 91.7491 | Connect Inner Port Pipe module | 17.6227 |  |  |  | N/A | N/A | N/A |  | N/A | RIB Blanket segment installed | 56.5038 | -59.3235
|  | Retract Multifunction manipulator | Logistics | 0.6 | 92.3491 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
|  |  | Total |  | 92.3491
Failure of RIB Lower Port Welds
Assumptions:
TIG welding and laser cutting is the current worst case scenario
|  | Any LOB pipe joint failures are detected prior to the Connection of the COB pipework | [14 empty] | Single Port | Full Maintenance Campaign
|  | In-situ surface treatment is not possible, so all hardware must be removed and replaced/reconditioned before it can be re-welded | [13 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
|  | All other positioning, delivery and retrieval operations are of a similar length to nominal operations | [13 empty] | Duration of welding operations (h) | 26.7733 | 481.9189 | 240.9594 | 160.6396 | 133.8664 | 80.3198
|  | Service Joint system is capable of cutting and pipes without tool change | [13 empty] | Estimated number of failures, impacting all RM systems equally | 0.29451 | 5.3011 | 2.6506 | 1.767 | 1.4725 | 0.88352
|  | No additional blanket modules will need to be removed to access impacted blanket module | [13 empty] | Operational contribution | 24.4707 | 440.472 | 220.236 | 146.824 | 122.3533 | 73.412
[16 empty] | Logistical contribution | 2.9539 | 53.1701 | 26.5851 | 17.7234 | 14.7695 | 8.8617
[16 empty] | Idle time waiting for dependant operations | 8.494 | 152.8926 | 76.4463 | 50.9642 | 42.4702 | 25.4821
|  | Failure rate: | 1.1% | [12 empty] | Total Duration of Recovery Operations | 35.9186 | 646.5348 | 323.2674 | 215.5116 | 179.593 | 107.7558
|  | Assuming a weld failure rate of | 0.1%
|  | Assuming a tool failure rate of | 1%
|  | Probability of Secondary Failure/hr or Event | 0.0359%
[6 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies
| Group | Pipe weld failure (Sub Tasks) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack
| Cut Failed Welds | Weld Failure identified at RIB Module joint | Operation | 0 | 0 | Hardware Recovery Required | 0 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Cut Failed Pipe Module Weld | Operation | 12.603 | 12.603 | Disconnect Blanket Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove Pipe Module from the port | Remove RIB pipe module from the port | Logistics | 0.6 | 13.203 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Remove Inner Pipework Modules | Deploy Service Joint System | Logistics | 1.9 | 15.103 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Cask and Commission RM Systems | 1.9 |  | N/A | N/A
|  | Disconnect Inner LIB Pipe Module | Operation | 12.603 | 27.7059 | Disconnect Blanket Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | N/A | New LIB pipe module stored; Pipe Module handling System Moved to Lower Port | 1.8059 | 13.297
|  | Remove LIB Inner Pipework module from the port | Logistics | 0.6 | 28.3059 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
|  | Reposition Pipework equipment to the RIB inner pipework module | Logistics | 0.6 | 28.9059 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
|  | Remove Inner RIB Pipe Module from port | Logistics | 0.53 | 29.4359 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Remove Inner RIB pipework module from the port | Operation | 12.603 | 42.0389 | Disconnect Blanket Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A | RIB pipe module stored; Pipe Module handling System Moved to Lower Port | 15.0089 | 14.427
|  | Retract Service Joint System | Logistics | 0.6 | 42.6389 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Install replacement inner port pipe modules | Deploy Service Joint System | Logistics | 0.8 | 43.4389 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
|  | Collect RIB Inner Port Pipe Module from hardware transporter | Logistics | 0.8 | 44.2389 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | LIB Inner pipe module stored; Replacement RIB Inner Port Pipe Module collected; Transporter moved to port | 32.4774 | 10.9615
|  | Connect RIB inner pipe module | Operation | 17.6227 | 74.1264 | Connect Inner Port Pipe module | 17.6227 |  |  |  | N/A | N/A | N/A |  | N/A | RIB Blanket segment installed | 56.5038 | -12.2649
|  | Collect LIB Inner Port Pipe Module from hardware transporter | Logistics | 0.8 | 76.5324 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Inner LIB pipe module collected; Pipe Module handling System Moved to Lower Port | 75.7324 | -1.6059
|  | Connect LIB inner pipe module | Operation | 17.6227 | 108.7199 | Connect Inner Port Pipe module | 17.6227 |  |  |  | N/A | N/A | N/A |  | N/A | LIB Blanket segment installed | 91.0973 | -14.5649
|  | Retract Service Joint System | Logistics | 0.6 | 109.3199 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Install replacement RIB pipe module | Deploy Service Joint System | Logistics | 0.8 | 110.1199 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
|  | Collect RIB Pipe Module from hardware transporter | Logistics | 0.8 | 111.3259 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | RIB pipe module collected; Pipe Module handling System Moved to Lower Port | 110.5259 | -0.40593
|  | Connect RIB Pipe Module | Operation | 10.0363 | 121.3622 | Connect Blanket Pipe Module | 10.0363 |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | N/A |  | N/A | N/A
|  | Retract Service Joint System into cask | Logistics | 0.6 | 121.9622 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
|  |  | ` |  | 121.9622
Failure of central divertor coolant welds
Assumptions:
TIG welding and laser cutting is the current worst case scenario
|  | Any LOB pipe joint failures are detected prior to the Connection of the COB pipework | [14 empty] | Single Port | Full Maintenance Campaign
|  | In-situ surface treatment is not possible, so all hardware must be removed and replaced/reconditioned before it can be re-welded | [13 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
|  | All other positioning, delivery and retrieval operations are of a similar length to nominal operations | [13 empty] | Duration of welding operations (h) | 16.9651 | 305.371 | 152.6855 | 101.7903 | 84.8253 | 50.8952
|  | Service Joint system is capable of cutting and pipes without tool change | [13 empty] | Estimated number of recoveries required | 0.18662 | 3.3591 | 1.6795 | 1.1197 | 0.93308 | 0.55985
|  | No additional blanket modules will need to be removed to access impacted blanket module | [13 empty] | Operational contribution | 14.0886 | 253.595 | 126.7975 | 84.5317 | 70.4431 | 42.2658
[16 empty] | Logistical contribution | 2.9523 | 53.1407 | 26.5703 | 17.7136 | 14.7613 | 8.8568
[16 empty] | Idle time waiting for dependant operations | 0.27184 | 4.8931 | 2.4465 | 1.631 | 1.3592 | 0.81551
|  | Failure rate: | 1.1% | [12 empty] | Total Duration of Recovery Operations | 17.3127 | 311.6287 | 155.8144 | 103.8762 | 86.5635 | 51.9381
|  | Assuming a weld failure rate of | 0.1%
|  | Assuming a tool failure rate of | 1%
|  | Probability of Secondary Failure/hr or Event | 0.04761%
[6 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies
| Group | Pipe weld failure (Sub Tasks) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack
| Cut Failed Welds | Weld Failure identified at central divertor pipe module joint | Operation | 0 | 0 | Hardware Recovery Required | 0 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Cut Failed Pipe Module Weld | Operation | 12.603 | 12.603 | Disconnect Divertor Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | remove central divertor cassette pipe module from port | Logistics | 0.6 | 13.203 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Remove remaining divertor pipework | Reposition Pipework equipment to the second pipework module | Logistics | 0.53 | 13.733 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Remove Left Divertor pipework module | Operation | 12.603 | 26.3359 | Disconnect Divertor Pipe module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A | Current payload stored; Divertor pipe module transporter collected; transporter moved to Divertor Port | 3.3659 | 10.367
|  | Reposition Pipework equipment to the third pipe module | Logistics | 0.53 | 26.8659 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Remove Right Divertor pipework module | Operation | 12.603 | 39.4689 | Disconnect Divertor Pipe module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Remove divertor pipework handling system from the port | Logistics | 0.6 | 40.0689 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 | Central Divertor pipe module stored and transporter moved to divertor Port | 15.4719 | 23.997
| Remove Central Cassette | Deploy Port Cleaning Equipment | Logistics | 0.8 | 40.8689 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Left Divertor Pipework Module Stored; pipe module handling system stored; Divertor cassette transporter collected and moved to Lower Port | 29.7574 | 10.3115
|  | Clean Port | Operation | 4.1 | 44.9689 | Clean Port | 4.1 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Port Cleaning Equipment | Logistics | 0.6 | 45.5689 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
|  | Deploy Cassette Handling Equipment | Logistics | 0.8 | 46.3689 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
|  | Remove Central Divertor cassette from the port | Operation | 5.2 | 51.5689 | Remove Central Divertor Cassette | 5.2 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Cassette Handling Equipment | Logistics | 0.6 | 52.1689 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Remove Left Divertor Cassette | Deploy Cassette Handling Equipment | Logistics | 0.8 | 52.9689 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Right Divertor Pipework Module Stored; pipe module handling system stored; Divertor cassette transporter collected and moved to Lower Port | 29.7574 | 22.4115
|  | Remove Left Divertor cassette | Operation | 1 | 53.9689 | Remove Peripheral Divertor Cassette | 1 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Remove Left Cassette from the port | Logistics | 0.38 | 54.3489 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.38 |  | N/A | N/A
| Remove Right Divertor Cassette | Deploy Cassette Handling Equipment | Logistics | 0.8 | 55.1489 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Central Divertor cassette stored and transporter moved to divertor Port | 53.8378 | 0.51111
|  | Remove Right Divertor cassette | Operation | 1 | 56.1489 | Remove Peripheral Divertor Cassette | 1 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Remove Right Cassette from the port | Logistics | 0.38 | 56.5289 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.38 |  | N/A | N/A
| Install Right Divertor Cassette | Deploy Cassette Handling Equipment | Logistics | 0.8 | 58.1441 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Left Divertor cassette stored; replacement right divertor cassette collected; transporter moved to divertor Port | 57.3441 | -0.81519
|  | Install Right Divertor cassette | Operation | 1 | 59.1441 | Install Peripheral Divertor Cassette | 1 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Right Cassette Handling Equipment | Logistics | 0.38 | 59.5241 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.38 |  | N/A | N/A
| Install Left Divertor Cassette | Deploy Cassette Handling Equipment | Logistics | 0.8 | 60.3241 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Right Divertor cassette stored; replacement left divertor cassette collected; transporter moved to divertor Port | 59.5241 | 0
|  | Install Left Divertor cassette | Operation | 1 | 61.3241 | Install Peripheral Divertor Cassette | 1 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Left Cassette Handling Equipment | Logistics | 0.38 | 61.7041 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.38 |  | N/A | N/A
| Install Central Divertor Cassette | Deploy Cassette Handling Equipment | Logistics | 0.8 | 62.593 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Replacement Central Divertor cassette collected and transporter moved to divertor Port | 61.793 | -0.088889
|  | Install Central Divertor cassette | Operation | 0.8 | 63.393 | Install Central Divertor Cassette | 0.8 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Central Cassette Handling Equipment | Logistics | 0.38 | 63.773 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.38 |  | N/A | N/A
| Install Divertor Pipe Modules | Deploy Service Joint System and Multifunction manipulator | Logistics | 0.8 | 64.573 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
|  | Collect Right Pipe Module from transport | Logistics | 0.8 | 65.9256 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Divertor handling system stored; pipe module handling system collected; Replacement right divertor cassette pipe module collected and moved to Lower Port | 65.1256 | -0.55259
|  | Connect Right Divertor Pipe Module | Operation | 7.8621 | 73.7877 | Connect Divertor Pipe module | 7.8621 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Collect next Pipe Module from transport | Logistics | 0.8 | 74.5877 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
|  | Reposition Pipework equipment to the second location | Logistics | 0.53 | 75.1177 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 | Divertor handling system stored; pipe module handling system collected; Replacement left divertor cassette pipe module collected and moved to Lower Port | 62.9456 | 11.6421
|  | Connect Left divertor pipe module | Operation | 7.8621 | 82.9799 | Connect Divertor Pipe module | 7.8621 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Collect final pipe module from hardware transport | Logistics | 0.8 | 83.7799 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
|  | Reposition Pipework equipment to the third pipe module | Logistics | 0.53 | 84.3099 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 | Replacement Central Divertor pipe module collected and transporter moved to divertor Port | 76.0566 | 7.7233
|  | Connect Central divertor pipe module | Operation | 7.8621 | 92.172 | Connect Divertor Pipe module | 7.8621 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Service Joint System | Logistics | 0.6 | 92.772 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
|  |  | Total |  | 92.772
Failure of Left divertor coolant welds
Assumptions:
TIG welding and laser cutting is the current worst case scenario
|  | Any LOB pipe joint failures are detected prior to the Connection of the COB pipework | [14 empty] | Single Port | Full Maintenance Campaign
|  | In-situ surface treatment is not possible, so all hardware must be removed and replaced/reconditioned before it can be re-welded | [13 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
|  | All other positioning, delivery and retrieval operations are of a similar length to nominal operations | [13 empty] | Duration of welding operations (h) | 16.9651 | 305.371 | 152.6855 | 101.7903 | 84.8253 | 50.8952
|  | Service Joint system is capable of cutting and pipes without tool change | [13 empty] | Estimated number of recoveries required | 0.18662 | 3.3591 | 1.6795 | 1.1197 | 0.93308 | 0.55985
|  | No additional blanket modules will need to be removed to access impacted blanket module | [13 empty] | Operational contribution | 10.2695 | 184.851 | 92.4255 | 61.617 | 51.3475 | 30.8085
[16 empty] | Logistical contribution | 2.6052 | 46.8928 | 23.4464 | 15.6309 | 13.0258 | 7.8155
[16 empty] | Idle time waiting for dependant operations | 0.27184 | 4.8931 | 2.4465 | 1.631 | 1.3592 | 0.81551
|  | Failure rate: | 1.1% | [12 empty] | Total Duration of Recovery Operations | 13.1465 | 236.6369 | 118.3184 | 78.879 | 65.7325 | 39.4395
|  | Assuming a weld failure rate of | 0.1%
|  | Assuming a tool failure rate of | 1%
|  | Probability of Secondary Failure/hr or Event | 0.04761%
[6 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies
| Group | Pipe weld failure (Sub Tasks) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack
| Cut Failed Welds | Weld Failure identified at left divertor pipe module joint | Operation | 0 | 0 | Hardware Recovery Required | 0 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Cut Failed Pipe Module Weld | Operation | 12.603 | 12.603 | Disconnect Divertor Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Remove left divertor pipe module from the port | Logistics | 0.6 | 13.203 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Remove remaining divertor pipe modules | Reposition Pipework equipment to the third pipe module | Logistics | 0.53 | 13.733 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 |  | N/A | N/A
|  | Remove Right Divertor pipework module from the port | Operation | 12.603 | 26.3359 | Disconnect Divertor Pipe module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A | Current payload stored; Divertor pipe module transporter collected; transporter moved to Divertor Port | 3.3659 | 10.367
|  | Remove right divertor pipe module from the port | Logistics | 0.6 | 26.9359 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Remove Central Cassette | Deploy Port Cleaning Equipment | Logistics | 0.8 | 27.7359 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Left Divertor Pipework Module Stored; pipe module handling system stored; Divertor cassette transporter collected and moved to Lower Port | 16.6244 | 10.3115
|  | Clean Port | Operation | 4.1 | 31.8359 | Clean Port | 4.1 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Port Cleaning Equipment | Logistics | 0.6 | 32.4359 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
|  | Deploy Cassette Handling Equipment | Logistics | 0.8 | 33.2359 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
|  | Remove Central Divertor cassette from the port | Operation | 5.2 | 38.4359 | Remove Central Divertor Cassette | 5.2 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Cassette Handling Equipment | Logistics | 0.6 | 39.0359 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Remove Left Divertor Cassette | Deploy Cassette Handling Equipment | Logistics | 0.8 | 39.8359 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Right Divertor Pipework Module Stored; pipe module handling system stored; Divertor cassette transporter collected and moved to Lower Port | 30.3574 | 8.6785
|  | Remove Left Divertor cassette | Operation | 1 | 40.8359 | Remove Peripheral Divertor Cassette | 1 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Remove Left Cassette from the port | Logistics | 0.38 | 41.2159 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.38 |  | N/A | N/A
| Remove Right Divertor Cassette | Deploy Cassette Handling Equipment | Logistics | 0.8 | 42.0159 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Central Divertor cassette stored and transporter moved to divertor Port | 40.7048 | 0.51111
|  | Remove Right Divertor cassette | Operation | 1 | 43.0159 | Remove Peripheral Divertor Cassette | 1 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Remove Right Cassette from the port | Logistics | 0.38 | 43.3959 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.38 |  | N/A | N/A
| Install Right Divertor Cassette | Deploy Cassette Handling Equipment | Logistics | 0.8 | 45.0111 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Left Divertor cassette stored; replacement right divertor cassette collected; transporter moved to divertor Port | 44.2111 | -0.81519
|  | Install Right Divertor cassette | Operation | 1 | 46.0111 | Install Peripheral Divertor Cassette | 1 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Right Cassette Handling Equipment | Logistics | 0.38 | 46.3911 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.38 |  | N/A | N/A
| Install Left Divertor Cassette | Deploy Cassette Handling Equipment | Logistics | 0.8 | 47.1911 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Right Divertor cassette stored; replacement left divertor cassette collected; transporter moved to divertor Port | 46.3911 | 0
|  | Install Left Divertor cassette | Operation | 1 | 48.1911 | Install Peripheral Divertor Cassette | 1 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Left Cassette Handling Equipment | Logistics | 0.38 | 48.5711 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.38 |  | N/A | N/A
| Install Central Divertor Cassette | Deploy Cassette Handling Equipment | Logistics | 0.8 | 49.46 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Replacement Central Divertor cassette collected and transporter moved to divertor Port | 48.66 | -0.088889
|  | Install Central Divertor cassette | Operation | 0.8 | 50.26 | Install Central Divertor Cassette | 0.8 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Central Cassette Handling Equipment | Logistics | 0.38 | 50.64 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.38 |  | N/A | N/A
| Install Divertor Pipe Modules | Deploy Service Joint System and Multifunction manipulator | Logistics | 0.8 | 51.44 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
|  | Collect Right Pipe Module from transport | Logistics | 0.8 | 52.7926 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Divertor handling system stored; pipe module handling system collected; Replacement right divertor cassette pipe module collected and moved to Lower Port | 51.9926 | -0.55259
|  | Connect Right Divertor Pipe Module | Operation | 7.8621 | 60.6547 | Connect Divertor Pipe module | 7.8621 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Collect next Pipe Module from transport | Logistics | 0.8 | 61.4547 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
|  | Reposition Pipework equipment to the second location | Logistics | 0.53 | 61.9847 |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.53 | Divertor handling system stored; pipe module handling system collected; Replacement left divertor cassette pipe module collected and moved to Lower Port | 49.8126 | 11.6421
|  | Connect Left divertor pipe module | Operation | 7.8621 | 69.8469 | Connect Divertor Pipe module | 7.8621 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Service Joint System | Logistics | 0.6 | 70.4469 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
|  |  | Total |  | 70.4469
Failure of Right divertor coolant welds
Assumptions:
TIG welding and laser cutting is the current worst case scenario
|  | Any LOB pipe joint failures are detected prior to the Connection of the COB pipework | [14 empty] | Single Port | Full Maintenance Campaign
|  | In-situ surface treatment is not possible, so all hardware must be removed and replaced/reconditioned before it can be re-welded | [13 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
|  | All other positioning, delivery and retrieval operations are of a similar length to nominal operations | [13 empty] | Duration of welding operations (h) | 16.9651 | 305.371 | 152.6855 | 101.7903 | 84.8253 | 50.8952
|  | Service Joint system is capable of cutting and pipes without tool change | [13 empty] | Estimated number of recoveries required | 0.18662 | 3.3591 | 1.6795 | 1.1197 | 0.93308 | 0.55985
|  | No additional blanket modules will need to be removed to access impacted blanket module | [13 empty] | Operational contribution | 6.4504 | 116.107 | 58.0535 | 38.7023 | 32.252 | 19.3512
[16 empty] | Logistical contribution | 2.1461 | 38.6294 | 19.3147 | 12.8765 | 10.7304 | 6.4382
[16 empty] | Idle time waiting for dependant operations | 0.27184 | 4.8931 | 2.4465 | 1.631 | 1.3592 | 0.81551
|  | Failure rate: | 1.1% | [12 empty] | Total Duration of Recovery Operations | 8.8683 | 159.6295 | 79.8148 | 53.2098 | 44.3415 | 26.6049
|  | Assuming a weld failure rate of | 0.1%
|  | Assuming a tool failure rate of | 1%
|  | Probability of Secondary Failure/hr or Event | 0.04761%
[6 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies
| Group | Pipe weld failure (Sub Tasks) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack
| Cut Failed Welds | Weld Failure identified at left divertor pipe module joint | Operation | 0 | 0 | Hardware Recovery Required | 0 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Cut Failed Pipe Module Weld | Operation | 12.603 | 12.603 | Disconnect Divertor Pipe Module | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Remove right divertor pipe module from the port | Logistics | 0.6 | 13.203 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Remove Central Cassette | Deploy Port Cleaning Equipment | Logistics | 0.8 | 14.003 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Current payload stored; Divertor cassette transporter collected; transporter moved to Divertor Port | 3.3659 | 9.837
|  | Clean Port | Operation | 4.1 | 18.103 | Clean Port | 4.1 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Port Cleaning Equipment | Logistics | 0.6 | 18.703 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
|  | Deploy Cassette Handling Equipment | Logistics | 0.8 | 19.503 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
|  | Remove Central Divertor cassette from the port | Operation | 5.2 | 24.703 | Remove Central Divertor Cassette | 5.2 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Cassette Handling Equipment | Logistics | 0.6 | 25.303 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Remove Left Divertor Cassette | Deploy Cassette Handling Equipment | Logistics | 0.8 | 26.103 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Right Divertor Pipework Module Stored; pipe module handling system stored; Divertor cassette transporter collected and moved to Lower Port | 16.6244 | 8.6785
|  | Remove Left Divertor cassette | Operation | 1 | 27.103 | Remove Peripheral Divertor Cassette | 1 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Remove Left Cassette from the port | Logistics | 0.38 | 27.483 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.38 |  | N/A | N/A
| Remove Right Divertor Cassette | Deploy Cassette Handling Equipment | Logistics | 0.8 | 28.283 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Central Divertor cassette stored and transporter moved to divertor Port | 26.9719 | 0.51111
|  | Remove Right Divertor cassette | Operation | 1 | 29.283 | Remove Peripheral Divertor Cassette | 1 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Remove Right Cassette from the port | Logistics | 0.38 | 29.663 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.38 |  | N/A | N/A
| Install Right Divertor Cassette | Deploy Cassette Handling Equipment | Logistics | 0.8 | 31.2782 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Left Divertor cassette stored; replacement right divertor cassette collected; transporter moved to divertor Port | 30.4782 | -0.81519
|  | Install Right Divertor cassette | Operation | 1 | 32.2782 | Install Peripheral Divertor Cassette | 1 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Right Cassette Handling Equipment | Logistics | 0.38 | 32.6582 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.38 |  | N/A | N/A
| Install Left Divertor Cassette | Deploy Cassette Handling Equipment | Logistics | 0.8 | 33.4582 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Right Divertor cassette stored; replacement left divertor cassette collected; transporter moved to divertor Port | 32.6582 | 0
|  | Install Left Divertor cassette | Operation | 1 | 34.4582 | Install Peripheral Divertor Cassette | 1 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Left Cassette Handling Equipment | Logistics | 0.38 | 34.8382 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.38 |  | N/A | N/A
| Install Central Divertor Cassette | Deploy Cassette Handling Equipment | Logistics | 0.8 | 35.727 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Replacement Central Divertor cassette collected and transporter moved to divertor Port | 34.927 | -0.088889
|  | Install Central Divertor cassette | Operation | 0.8 | 36.527 | Install Central Divertor Cassette | 0.8 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Central Cassette Handling Equipment | Logistics | 0.38 | 36.907 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.38 |  | N/A | N/A
| Install Divertor Pipe Modules | Deploy Service Joint System and Multifunction manipulator | Logistics | 0.8 | 37.707 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 |  | N/A | N/A
|  | Collect Right Pipe Module from transport | Logistics | 0.8 | 39.0596 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool / Hardware into the Port | 0.8 | Divertor handling system stored; pipe module handling system collected; Replacement right divertor cassette pipe module collected and moved to Lower Port | 38.2596 | -0.55259
|  | Connect Right Divertor Pipe Module | Operation | 7.8621 | 46.9218 | Connect Divertor Pipe module | 7.8621 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Retract Service Joint System | Logistics | 0.6 | 47.5218 |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
|  |  | Total |  | 47.5218

## Lower HotCell RecoveryLogistics (hidden)
[5 empty] | Operations |  | Movement | [5 empty] | Logistics
Group | Activity | Activity Type | Time (h) | Cumulative | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h)
Divertor Port Pipe COB Weld Failure
COB pipe module stored; Pipe Module handling System Moved to Lower Port | Remove COB pipe module from the port | Trigger | 0 | 13.203 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 13.8974 |  | N/A | hardware transporter (Loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 14.7774 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.23148 | 15.0089 |  | N/A | hardware transporter (Empty Stillage) | AMF Equipment Issue | Divertor Port | 50 | 0.06 | 0.23148 |  | N/A
| COB pipe module stored; Pipe Module handling System Moved to Lower Port | Total | 0 | 15.0089 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Pumping handling system store; pipe module handing system collected; Pipe Module handling System Moved to Lower Port | Lower Port COB weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 0.69444 |  | N/A | hardware transporter (Loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 1.5744 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.23148 | 1.8059 |  | N/A | hardware transporter (Empty Stillage) | AMF Equipment Issue | Divertor Port | 50 | 0.06 | 0.23148 |  | N/A
| Pumping handling system store; pipe module handing system collected; Pipe Module handling System Moved to Lower Port | Total | 0 | 1.8059 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB pipe module stored; Pipe Module handling System Moved to Lower Port | Remove LOB pipe module from the port | Trigger | 0 | 35.3959 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 36.0904 |  | N/A | hardware transporter (Loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 36.9704 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.23148 | 37.2019 |  | N/A | hardware transporter (Empty Stillage) | AMF Equipment Issue | Divertor Port | 50 | 0.06 | 0.23148 |  | N/A
| LOB pipe module stored; Pipe Module handling System Moved to Lower Port | Total | 0 | 37.2019 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB pipe module stored; Pipe Module handling System Moved to Lower Port | Remove ROB pipe module from the port | Trigger | 0 | 49.1289 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 49.8233 |  | N/A | hardware transporter (Loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 50.7033 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.23148 | 50.9348 |  | N/A | hardware transporter (Empty Stillage) | AMF Equipment Issue | Divertor Port | 50 | 0.06 | 0.23148 |  | N/A
| ROB pipe module stored; Pipe Module handling System Moved to Lower Port | Total | 0 | 50.9348 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB pipe module stored; Pipe Module handling System Moved to Lower Port | Remove LIB pipe module from the port | Trigger | 0 | 63.1319 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 63.8263 |  | N/A | hardware transporter (Loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 64.7063 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.23148 | 64.9378 |  | N/A | hardware transporter (Empty Stillage) | AMF Equipment Issue | Divertor Port | 50 | 0.06 | 0.23148 |  | N/A
| LIB pipe module stored; Pipe Module handling System Moved to Lower Port | Total | 0 | 64.9378 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB pipe module stored; Blanket Pipe Module handling System Stored | Remove RIB pipe module from the port | Trigger | 0 | 76.8648 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 77.5593 |  | N/A | hardware transporter (Loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 78.4393 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.23148 | 78.6708 |  | N/A | hardware transporter (Empty Stillage) | AMF Equipment Issue | Divertor Port | 50 | 0.06 | 0.23148 |  | N/A
| RIB pipe module stored; Blanket Pipe Module handling System Stored | Total | 0 | 78.6708 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Inner pipe module stored; Blanket Pipe Module handling System Stored | Retract Blanket Pipe Module Handling System from port | Trigger | 0 | 94.8408 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.23148 | 95.0723 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 95.9523 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Issue | Movement | 0.027778 | 95.98 |  | N/A | hardware transporter (no load) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Cassette Transport Cask | Logistics | 0.68 | 96.66 |  | N/A |  |  |  | N/A | N/A | N/A | Collect hardware from the AMF | 0.68
| Move Cassette Transport Cask to Divertor Port | Movement | 0.69444 | 97.3545 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| LIB Inner pipe module stored; Blanket Pipe Module handling System Stored | Total | 0 | 97.3545 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Inner pipe module stored; Replacement RIB Inner Port Pipe Module collected; Transporter moved to port | Remove Inner RIB Pipe Module from port | Trigger | 0 | 94.2408 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move to AMF equipment reciept | Movement | 0.69444 | 94.9352 |  | N/A | hardware transporter (Loaded) | Divertor Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Inner Port Pipe Module | Logistics | 0.88 | 95.8152 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| move to AMF hardware issue | Movement | 0.092593 | 95.9078 |  | N/A | hardware transporter (empty stillage) | AMF Equipment Issue | AMF hardware issue | 20 | 0.06 | 0.092593 |  | N/A
| Collect RIB inner pipe module | Logistics | 0.68 | 96.5878 |  | N/A |  |  |  | N/A | N/A | N/A | Collect hardware from the AMF | 0.68
| Move hardware transporter to divertor port | Movement | 0.69444 | 97.2823 |  | N/A | hardware transporter (loaded) | AMF hardware issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| LIB Inner pipe module stored; Replacement RIB Inner Port Pipe Module collected; Transporter moved to port | Total | 0 | 97.2823 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Inner LIB pipe module collected; Pipe Module handling System Moved to Lower Port | Connect RIB inner pipe module | Trigger | 0 | 93.6408 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware issue | Movement | 0.23148 | 93.8723 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Hardware issue | 50 | 0.06 | 0.23148 |  | N/A
| Collect blanket Pipe Module | Logistics | 0.68 | 94.5523 |  | N/A |  |  |  | N/A | N/A | N/A | Collect hardware from the AMF | 0.68
| Move hardware transporter to Divertor Port | Movement | 0.69444 | 95.2467 |  | N/A | hardware transporter (loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Inner LIB pipe module collected; Pipe Module handling System Moved to Lower Port | Total | 0 | 95.2467 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB pipe module collected; Pipe Module handling System Moved to Lower Port | Connect LIB Inner Pipe Module | Trigger | 0 | 134.6576 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware issue | Movement | 0.23148 | 134.8891 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Hardware issue | 50 | 0.06 | 0.23148 |  | N/A
| Collect blanket Pipe Module | Logistics | 0.88 | 135.7691 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.69444 | 136.4635 |  | N/A | hardware transporter (loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| RIB pipe module collected; Pipe Module handling System Moved to Lower Port | Total | 0 | 136.4635 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB pipe module collected; Pipe Module handling System Moved to Lower Port | Connect LIB Inner Pipe Module | Trigger | 0 | 134.6576 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware issue | Movement | 0.23148 | 134.8891 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Hardware issue | 50 | 0.06 | 0.23148 |  | N/A
| Collect blanket Pipe Module | Logistics | 0.88 | 135.7691 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.69444 | 136.4635 |  | N/A | hardware transporter (loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| LIB pipe module collected; Pipe Module handling System Moved to Lower Port | Total | 0 | 136.4635 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB pipe module collected; Pipe Module handling System Moved to Lower Port | Connect RIB pipe module | Trigger | 0 | 154.8862 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware issue | Movement | 0.23148 | 155.1177 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Hardware issue | 50 | 0.06 | 0.23148 |  | N/A
| Collect blanket Pipe Module | Logistics | 0.88 | 155.9977 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.69444 | 156.6921 |  | N/A | hardware transporter (loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| ROB pipe module collected; Pipe Module handling System Moved to Lower Port | Total | 0 | 156.6921 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB pipe module collected; Pipe Module handling System Moved to Lower Port | Connect LIB Pipe Module | Trigger | 0 | 174.1088 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware issue | Movement | 0.23148 | 174.3403 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Hardware issue | 50 | 0.06 | 0.23148 |  | N/A
| Collect blanket Pipe Module | Logistics | 0.88 | 175.2203 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.69444 | 175.9148 |  | N/A | hardware transporter (loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| LOB pipe module collected; Pipe Module handling System Moved to Lower Port | Total | 0 | 175.9148 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
COB pipe module collected; Pipe Module handling System Moved to Lower Port | Connect ROB Pipe Module | Trigger | 0 | 184.9452 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware issue | Movement | 0.23148 | 185.1766 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Hardware issue | 50 | 0.06 | 0.23148 |  | N/A
| Collect blanket Pipe Module | Logistics | 0.88 | 186.0566 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.69444 | 186.7511 |  | N/A | hardware transporter (loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| COB pipe module collected; Pipe Module handling System Moved to Lower Port | Total | 0 | 186.7511 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
COB Blanket segment installed | Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 113.1461 | 113.1461 | Install COB Blanket Segment | 113.1461 |  |  |  | N/A | N/A | N/A |  | N/A
| COB Blanket segment installed | Total | 0 | 113.1461 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
COB Upper Port Pipe Module installed | Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 338.6818 | 338.6818 | Insert COB Pipe Module | 338.6818 |  |  |  | N/A | N/A | N/A |  | N/A
| COB Upper Port Pipe Module installed | Total | 0 | 338.6818 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Blanket segment installed | Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 107.37 | 107.37 | Install LOB Blanket Segment | 107.37 |  |  |  | N/A | N/A | N/A |  | N/A
| LOB Blanket segment installed | Total | 0 | 107.37 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Upper Port Pipe Module installed | Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 283.859 | 283.859 | Insert LOB Pipe Module | 283.859 |  |  |  | N/A | N/A | N/A |  | N/A
| LOB Upper Port Pipe Module installed | Total | 0 | 283.859 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Blanket segment installed | Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 101.5939 | 101.5939 | Install ROB Blanket Segment | 101.5939 |  |  |  | N/A | N/A | N/A |  | N/A
| ROB Blanket segment installed | Total | 0 | 101.5939 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Upper Port Pipe Module installed | Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 229.0362 | 229.0362 | Insert ROB Pipe Module | 229.0362 |  |  |  | N/A | N/A | N/A |  | N/A
| ROB Upper Port Pipe Module installed | Total | 0 | 229.0362 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Blanket segment installed | Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 96.6944 | 96.6944 | Install LIB Blanket Segment | 96.6944 |  |  |  | N/A | N/A | N/A |  | N/A
| LIB Blanket segment installed | Total | 0 | 96.6944 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Upper Port Pipe Module installed | Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 174.2134 | 174.2134 | Insert LIB Pipe Module | 174.2134 |  |  |  | N/A | N/A | N/A |  | N/A
| LIB Upper Port Pipe Module installed | Total | 0 | 174.2134 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Blanket segment installed | Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 91.795 | 91.795 | Install RIB Blanket Segment | 91.795 |  |  |  | N/A | N/A | N/A |  | N/A
| RIB Blanket segment installed | Total | 0 | 91.795 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Upper Port Pipe Module installed | Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 119.3906 | 119.3906 | Insert RIB Pipe Module | 119.3906 |  |  |  | N/A | N/A | N/A |  | N/A
| RIB Upper Port Pipe Module installed | Total | 0 | 119.3906 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Divertor Port Pipe LOB Weld Failure
Pumping handling system store; pipe module handing system collected; Pipe Module handling System Moved to Lower Port | Lower Port LOB weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 0.69444 |  | N/A | hardware transporter (Loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 1.5744 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.23148 | 1.8059 |  | N/A | hardware transporter (Empty Stillage) | AMF Equipment Issue | Divertor Port | 50 | 0.06 | 0.23148 |  | N/A
| Pumping handling system store; pipe module handing system collected; Pipe Module handling System Moved to Lower Port | Total | 0 | 1.8059 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB pipe module stored; Pipe Module handling System Moved to Lower Port | Remove ROB pipe module from the port | Trigger | 0 | 27.7359 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 28.4304 |  | N/A | hardware transporter (Loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 29.3104 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.23148 | 29.5419 |  | N/A | hardware transporter (Empty Stillage) | AMF Equipment Issue | Divertor Port | 50 | 0.06 | 0.23148 |  | N/A
| LOB pipe module stored; Pipe Module handling System Moved to Lower Port | Total | 0 | 29.5419 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB pipe module stored; Pipe Module handling System Moved to Lower Port | Remove LIB pipe module from the port | Trigger | 0 | 41.7389 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 42.4333 |  | N/A | hardware transporter (Loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 43.3133 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.23148 | 43.5448 |  | N/A | hardware transporter (Empty Stillage) | AMF Equipment Issue | Divertor Port | 50 | 0.06 | 0.23148 |  | N/A
| ROB pipe module stored; Pipe Module handling System Moved to Lower Port | Total | 0 | 43.5448 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB pipe module stored; Pipe Module handling System Moved to Lower Port | Remove RIB pipe module from the port | Trigger | 0 | 55.4719 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 56.1663 |  | N/A | hardware transporter (Loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 57.0463 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.23148 | 57.2778 |  | N/A | hardware transporter (Empty Stillage) | AMF Equipment Issue | Divertor Port | 50 | 0.06 | 0.23148 |  | N/A
| LIB pipe module stored; Pipe Module handling System Moved to Lower Port | Total | 0 | 57.2778 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB pipe module stored; Blanket Pipe Module handling System Stored | Remove RIB pipe module from the port | Trigger | 0 | 55.4719 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 56.1663 |  | N/A | hardware transporter (Loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 57.0463 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.23148 | 57.2778 |  | N/A | hardware transporter (Empty Stillage) | AMF Equipment Issue | Divertor Port | 50 | 0.06 | 0.23148 |  | N/A
| RIB pipe module stored; Blanket Pipe Module handling System Stored | Total | 0 | 57.2778 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Inner pipe module stored; Replacement RIB Inner Port Pipe Module collected; Transporter moved to port | Remove Inner RIB Pipe Module from port | Trigger | 0 | 79.2708 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move to AMF equipment reciept | Movement | 0.69444 | 79.9652 |  | N/A | hardware transporter (Loaded) | Divertor Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Inner Port Pipe Module | Logistics | 0.88 | 80.8452 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| move to AMF hardware issue | Movement | 0.092593 | 80.9378 |  | N/A | hardware transporter (empty stillage) | AMF Equipment Issue | AMF hardware issue | 20 | 0.06 | 0.092593 |  | N/A
| Collect RIB inner pipe module | Logistics | 0.68 | 81.6178 |  | N/A |  |  |  | N/A | N/A | N/A | Collect hardware from the AMF | 0.68
| Move hardware transporter to divertor port | Movement | 0.69444 | 82.3122 |  | N/A | hardware transporter (loaded) | AMF hardware issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| LIB Inner pipe module stored; Replacement RIB Inner Port Pipe Module collected; Transporter moved to port | Total | 0 | 82.3122 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Inner LIB pipe module collected; Pipe Module handling System Moved to Lower Port | Connect RIB inner pipe module | Trigger | 0 | 73.5908 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware issue | Movement | 0.23148 | 73.8222 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Hardware issue | 50 | 0.06 | 0.23148 |  | N/A
| Collect blanket Pipe Module | Logistics | 0.68 | 74.5022 |  | N/A |  |  |  | N/A | N/A | N/A | Collect hardware from the AMF | 0.68
| Move hardware transporter to Divertor Port | Movement | 0.69444 | 75.1967 |  | N/A | hardware transporter (loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Inner LIB pipe module collected; Pipe Module handling System Moved to Lower Port | Total | 0 | 75.1967 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB pipe module collected; Pipe Module handling System Moved to Lower Port | Connect LIB Inner Pipe Module | Trigger | 0 | 134.6576 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware issue | Movement | 0.23148 | 134.8891 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Hardware issue | 50 | 0.06 | 0.23148 |  | N/A
| Collect blanket Pipe Module | Logistics | 0.88 | 135.7691 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.69444 | 136.4635 |  | N/A | hardware transporter (loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| RIB pipe module collected; Pipe Module handling System Moved to Lower Port | Total | 0 | 136.4635 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB pipe module collected; Pipe Module handling System Moved to Lower Port | Connect LIB Inner Pipe Module | Trigger | 0 | 134.6576 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware issue | Movement | 0.23148 | 134.8891 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Hardware issue | 50 | 0.06 | 0.23148 |  | N/A
| Collect blanket Pipe Module | Logistics | 0.88 | 135.7691 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.69444 | 136.4635 |  | N/A | hardware transporter (loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| LIB pipe module collected; Pipe Module handling System Moved to Lower Port | Total | 0 | 136.4635 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB pipe module collected; Pipe Module handling System Moved to Lower Port | Connect RIB pipe module | Trigger | 0 | 154.8862 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware issue | Movement | 0.23148 | 155.1177 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Hardware issue | 50 | 0.06 | 0.23148 |  | N/A
| Collect blanket Pipe Module | Logistics | 0.88 | 155.9977 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.69444 | 156.6921 |  | N/A | hardware transporter (loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| ROB pipe module collected; Pipe Module handling System Moved to Lower Port | Total | 0 | 156.6921 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB pipe module collected; Pipe Module handling System Moved to Lower Port | Connect LIB Pipe Module | Trigger | 0 | 174.1088 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware issue | Movement | 0.23148 | 174.3403 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Hardware issue | 50 | 0.06 | 0.23148 |  | N/A
| Collect blanket Pipe Module | Logistics | 0.88 | 175.2203 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.69444 | 175.9148 |  | N/A | hardware transporter (loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| LOB pipe module collected; Pipe Module handling System Moved to Lower Port | Total | 0 | 175.9148 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Blanket segment installed | Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 161.0721 | 161.0721 | Install LOB Blanket Segment | 161.0721 |  |  |  | N/A | N/A | N/A |  | N/A
| LOB Blanket segment installed | Total | 0 | 161.0721 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Upper Port Pipe Module installed | Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 337.5611 | 337.5611 | Insert LOB Pipe Module | 337.5611 |  |  |  | N/A | N/A | N/A |  | N/A
| LOB Upper Port Pipe Module installed | Total | 0 | 337.5611 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Blanket segment installed | Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 155.296 | 155.296 | Install ROB Blanket Segment | 155.296 |  |  |  | N/A | N/A | N/A |  | N/A
| ROB Blanket segment installed | Total | 0 | 155.296 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Upper Port Pipe Module installed | Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 282.7383 | 282.7383 | Insert ROB Pipe Module | 282.7383 |  |  |  | N/A | N/A | N/A |  | N/A
| ROB Upper Port Pipe Module installed | Total | 0 | 282.7383 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Blanket segment installed | Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 150.3965 | 150.3965 | Install LIB Blanket Segment | 150.3965 |  |  |  | N/A | N/A | N/A |  | N/A
| LIB Blanket segment installed | Total | 0 | 150.3965 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Upper Port Pipe Module installed | Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 227.9154 | 227.9154 | Insert LIB Pipe Module | 227.9154 |  |  |  | N/A | N/A | N/A |  | N/A
| LIB Upper Port Pipe Module installed | Total | 0 | 227.9154 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Blanket segment installed | Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 145.4971 | 145.4971 | Install RIB Blanket Segment | 145.4971 |  |  |  | N/A | N/A | N/A |  | N/A
| RIB Blanket segment installed | Total | 0 | 145.4971 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Upper Port Pipe Module installed | Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 173.0926 | 173.0926 | Insert RIB Pipe Module | 173.0926 |  |  |  | N/A | N/A | N/A |  | N/A
| RIB Upper Port Pipe Module installed | Total | 0 | 173.0926 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Divertor Port Pipe ROB Weld Failure
Pumping handling system store; pipe module handing system collected; Pipe Module handling System Moved to Lower Port | Lower Port ROB weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 0.69444 |  | N/A | hardware transporter (Loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 1.5744 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.23148 | 1.8059 |  | N/A | hardware transporter (Empty Stillage) | AMF Equipment Issue | Divertor Port | 50 | 0.06 | 0.23148 |  | N/A
| Pumping handling system store; pipe module handing system collected; Pipe Module handling System Moved to Lower Port | Total | 0 | 1.8059 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB pipe module stored; Pipe Module handling System Moved to Lower Port | Remove ROB pipe module from the port | Trigger | 0 | 49.1289 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 49.8233 |  | N/A | hardware transporter (Loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 50.7033 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.23148 | 50.9348 |  | N/A | hardware transporter (Empty Stillage) | AMF Equipment Issue | Divertor Port | 50 | 0.06 | 0.23148 |  | N/A
| ROB pipe module stored; Pipe Module handling System Moved to Lower Port | Total | 0 | 50.9348 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB pipe module stored; Pipe Module handling System Moved to Lower Port | Remove RIB pipe module from the port | Trigger | 0 | 51.5348 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 52.2293 |  | N/A | hardware transporter (Loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 53.1093 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.23148 | 53.3408 |  | N/A | hardware transporter (Empty Stillage) | AMF Equipment Issue | Divertor Port | 50 | 0.06 | 0.23148 |  | N/A
| LIB pipe module stored; Pipe Module handling System Moved to Lower Port | Total | 0 | 53.3408 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB pipe module stored; Blanket Pipe Module handling System Stored | Remove RIB pipe module from the port | Trigger | 0 | 51.5348 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 52.2293 |  | N/A | hardware transporter (Loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 53.1093 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.23148 | 53.3408 |  | N/A | hardware transporter (Empty Stillage) | AMF Equipment Issue | Divertor Port | 50 | 0.06 | 0.23148 |  | N/A
| RIB pipe module stored; Blanket Pipe Module handling System Stored | Total | 0 | 53.3408 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Inner pipe module stored; Replacement RIB Inner Port Pipe Module collected; Transporter moved to port | Remove Inner RIB Pipe Module from port | Trigger | 0 | 68.9108 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move to AMF equipment reciept | Movement | 0.69444 | 69.6052 |  | N/A | hardware transporter (Loaded) | Divertor Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Inner Port Pipe Module | Logistics | 0.88 | 70.4852 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| move to AMF hardware issue | Movement | 0.092593 | 70.5778 |  | N/A | hardware transporter (empty stillage) | AMF Equipment Issue | AMF hardware issue | 20 | 0.06 | 0.092593 |  | N/A
| Collect RIB inner pipe module | Logistics | 0.68 | 71.2578 |  | N/A |  |  |  | N/A | N/A | N/A | Collect hardware from the AMF | 0.68
| Move hardware transporter to divertor port | Movement | 0.69444 | 71.9522 |  | N/A | hardware transporter (loaded) | AMF hardware issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| LIB Inner pipe module stored; Replacement RIB Inner Port Pipe Module collected; Transporter moved to port | Total | 0 | 71.9522 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Inner LIB pipe module collected; Pipe Module handling System Moved to Lower Port | Connect RIB inner pipe module | Trigger | 0 | 68.3108 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware issue | Movement | 0.23148 | 68.5422 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Hardware issue | 50 | 0.06 | 0.23148 |  | N/A
| Collect blanket Pipe Module | Logistics | 0.68 | 69.2222 |  | N/A |  |  |  | N/A | N/A | N/A | Collect hardware from the AMF | 0.68
| Move hardware transporter to Divertor Port | Movement | 0.69444 | 69.9167 |  | N/A | hardware transporter (loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Inner LIB pipe module collected; Pipe Module handling System Moved to Lower Port | Total | 0 | 69.9167 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB pipe module collected; Pipe Module handling System Moved to Lower Port | Connect LIB Inner Pipe Module | Trigger | 0 | 109.3276 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware issue | Movement | 0.23148 | 109.5591 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Hardware issue | 50 | 0.06 | 0.23148 |  | N/A
| Collect blanket Pipe Module | Logistics | 0.88 | 110.4391 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.69444 | 111.1335 |  | N/A | hardware transporter (loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| RIB pipe module collected; Pipe Module handling System Moved to Lower Port | Total | 0 | 111.1335 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB pipe module collected; Pipe Module handling System Moved to Lower Port | Connect LIB Inner Pipe Module | Trigger | 0 | 109.3276 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware issue | Movement | 0.23148 | 109.5591 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Hardware issue | 50 | 0.06 | 0.23148 |  | N/A
| Collect blanket Pipe Module | Logistics | 0.88 | 110.4391 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.69444 | 111.1335 |  | N/A | hardware transporter (loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| LIB pipe module collected; Pipe Module handling System Moved to Lower Port | Total | 0 | 111.1335 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB pipe module collected; Pipe Module handling System Moved to Lower Port | Connect RIB pipe module | Trigger | 0 | 129.5562 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware issue | Movement | 0.23148 | 129.7876 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Hardware issue | 50 | 0.06 | 0.23148 |  | N/A
| Collect blanket Pipe Module | Logistics | 0.88 | 130.6676 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.69444 | 131.3621 |  | N/A | hardware transporter (loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| ROB pipe module collected; Pipe Module handling System Moved to Lower Port | Total | 0 | 131.3621 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Blanket segment installed | Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 125.6908 | 125.6908 | Install ROB Blanket Segment | 125.6908 |  |  |  | N/A | N/A | N/A |  | N/A
| ROB Blanket segment installed | Total | 0 | 125.6908 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Upper Port Pipe Module installed | Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 253.1331 | 253.1331 | Insert ROB Pipe Module | 253.1331 |  |  |  | N/A | N/A | N/A |  | N/A
| ROB Upper Port Pipe Module installed | Total | 0 | 253.1331 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Blanket segment installed | Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 120.7913 | 120.7913 | Install LIB Blanket Segment | 120.7913 |  |  |  | N/A | N/A | N/A |  | N/A
| LIB Blanket segment installed | Total | 0 | 120.7913 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Upper Port Pipe Module installed | Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 198.3103 | 198.3103 | Insert LIB Pipe Module | 198.3103 |  |  |  | N/A | N/A | N/A |  | N/A
| LIB Upper Port Pipe Module installed | Total | 0 | 198.3103 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Blanket segment installed | Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 115.8919 | 115.8919 | Install RIB Blanket Segment | 115.8919 |  |  |  | N/A | N/A | N/A |  | N/A
| RIB Blanket segment installed | Total | 0 | 115.8919 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Upper Port Pipe Module installed | Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 143.4874 | 143.4874 | Insert RIB Pipe Module | 143.4874 |  |  |  | N/A | N/A | N/A |  | N/A
| RIB Upper Port Pipe Module installed | Total | 0 | 143.4874 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Divertor Port Pipe LIB Weld Failure
New ROB pipe module stored; Pipe Module handling System Moved to Lower Port | Weld Failure identified at LIB Module joint | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 0.69444 |  | N/A | hardware transporter (Loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 1.5744 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.23148 | 1.8059 |  | N/A | hardware transporter (Empty Stillage) | AMF Equipment Issue | Divertor Port | 50 | 0.06 | 0.23148 |  | N/A
| New ROB pipe module stored; Pipe Module handling System Moved to Lower Port | Total | 0 | 1.8059 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB pipe module stored; Pipe Module handling System Moved to Lower Port | Remove LIB Pipe Module from the port | Trigger | 0 | 13.203 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 13.8974 |  | N/A | hardware transporter (Loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 14.7774 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.23148 | 15.0089 |  | N/A | hardware transporter (Empty Stillage) | AMF Equipment Issue | Divertor Port | 50 | 0.06 | 0.23148 |  | N/A
| LIB pipe module stored; Pipe Module handling System Moved to Lower Port | Total | 0 | 15.0089 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB pipe module stored; Blanket Pipe Module handling System Stored | Remove RIB Pipe Module from the port | Trigger | 0 | 27.6119 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 28.3063 |  | N/A | hardware transporter (Loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 29.1863 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.23148 | 29.4178 |  | N/A | hardware transporter (Empty Stillage) | AMF Equipment Issue | Divertor Port | 50 | 0.06 | 0.23148 |  | N/A
| RIB pipe module stored; Blanket Pipe Module handling System Stored | Total | 0 | 29.4178 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Inner pipe module stored; Replacement RIB Inner Port Pipe Module collected; Transporter moved to port | Remove LIB Inner Pipework module from the port | Trigger | 0 | 42.2148 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move to AMF equipment reciept | Movement | 0.69444 | 42.9093 |  | N/A | hardware transporter (Loaded) | Divertor Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Inner Port Pipe Module | Logistics | 0.88 | 43.7893 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| move to AMF hardware issue | Movement | 0.092593 | 43.8819 |  | N/A | hardware transporter (empty stillage) | AMF Equipment Issue | AMF hardware issue | 20 | 0.06 | 0.092593 |  | N/A
| Collect RIB inner pipe module | Logistics | 0.68 | 44.5619 |  | N/A |  |  |  | N/A | N/A | N/A | Collect hardware from the AMF | 0.68
| Move hardware transporter to divertor port | Movement | 0.69444 | 45.2563 |  | N/A | hardware transporter (loaded) | AMF hardware issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| LIB Inner pipe module stored; Replacement RIB Inner Port Pipe Module collected; Transporter moved to port | Total | 0 | 45.2563 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Inner LIB pipe module collected; Pipe Module handling System Moved to Lower Port | Remove RIB Inner Pipework module from the port | Trigger | 0 | 55.9478 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware issue | Movement | 0.23148 | 56.1793 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Hardware issue | 50 | 0.06 | 0.23148 |  | N/A
| Collect blanket Pipe Module | Logistics | 0.68 | 56.8593 |  | N/A |  |  |  | N/A | N/A | N/A | Collect hardware from the AMF | 0.68
| Move hardware transporter to Divertor Port | Movement | 0.69444 | 57.5537 |  | N/A | hardware transporter (loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Inner LIB pipe module collected; Pipe Module handling System Moved to Lower Port | Total | 0 | 57.5537 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB pipe module collected; Pipe Module handling System Moved to Lower Port | Connect RIB Inner Pipe Module | Trigger | 0 | 126.3426 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware issue | Movement | 0.23148 | 126.5741 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Hardware issue | 50 | 0.06 | 0.23148 |  | N/A
| Collect blanket Pipe Module | Logistics | 0.88 | 127.4541 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.69444 | 128.1485 |  | N/A | hardware transporter (loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| RIB pipe module collected; Pipe Module handling System Moved to Lower Port | Total | 0 | 128.1485 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB pipe module collected; Pipe Module handling System Moved to Lower Port | Connect LIB Inner Pipe Module | Trigger | 0 | 144.7653 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware issue | Movement | 0.23148 | 144.9968 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Hardware issue | 50 | 0.06 | 0.23148 |  | N/A
| Collect blanket Pipe Module | Logistics | 0.88 | 145.8768 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.69444 | 146.5712 |  | N/A | hardware transporter (loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| LIB pipe module collected; Pipe Module handling System Moved to Lower Port | Total | 0 | 146.5712 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Blanket segment installed | Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 91.0973 | 91.0973 | Install LIB Blanket Segment | 91.0973 |  |  |  | N/A | N/A | N/A |  | N/A
| LIB Blanket segment installed | Total | 0 | 91.0973 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Upper Port Pipe Module installed | Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 168.6162 | 168.6162 | Insert LIB Pipe Module | 168.6162 |  |  |  | N/A | N/A | N/A |  | N/A
| LIB Upper Port Pipe Module installed | Total | 0 | 168.6162 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Blanket segment installed | Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 86.1978 | 86.1978 | Install RIB Blanket Segment | 86.1978 |  |  |  | N/A | N/A | N/A |  | N/A
| RIB Blanket segment installed | Total | 0 | 86.1978 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Upper Port Pipe Module installed | Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 113.7934 | 113.7934 | Insert RIB Pipe Module | 113.7934 |  |  |  | N/A | N/A | N/A |  | N/A
| RIB Upper Port Pipe Module installed | Total | 0 | 113.7934 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Divertor Port Pipe RIB Weld Failure
New LIB pipe module stored; Pipe Module handling System Moved to Lower Port | Weld Failure identified at RIB Module joint | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 0.69444 |  | N/A | hardware transporter (Loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 1.5744 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.23148 | 1.8059 |  | N/A | hardware transporter (Empty Stillage) | AMF Equipment Issue | Divertor Port | 50 | 0.06 | 0.23148 |  | N/A
| New LIB pipe module stored; Pipe Module handling System Moved to Lower Port | Total | 0 | 1.8059 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB pipe module stored; Pipe Module handling System Moved to Lower Port | Remove RIB pipe module from the port | Trigger | 0 | 13.203 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 13.8974 |  | N/A | hardware transporter (Loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 14.7774 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.23148 | 15.0089 |  | N/A | hardware transporter (Empty Stillage) | AMF Equipment Issue | Divertor Port | 50 | 0.06 | 0.23148 |  | N/A
| RIB pipe module stored; Pipe Module handling System Moved to Lower Port | Total | 0 | 15.0089 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Inner pipe module stored; Replacement RIB Inner Port Pipe Module collected; Transporter moved to port | Remove Inner RIB Pipe Module from port | Trigger | 0 | 29.4359 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move to AMF equipment reciept | Movement | 0.69444 | 30.1304 |  | N/A | hardware transporter (Loaded) | Divertor Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Inner Port Pipe Module | Logistics | 0.88 | 31.0104 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| move to AMF hardware issue | Movement | 0.092593 | 31.103 |  | N/A | hardware transporter (empty stillage) | AMF Equipment Issue | AMF hardware issue | 20 | 0.06 | 0.092593 |  | N/A
| Collect RIB inner pipe module | Logistics | 0.68 | 31.783 |  | N/A |  |  |  | N/A | N/A | N/A | Collect hardware from the AMF | 0.68
| Move hardware transporter to divertor port | Movement | 0.69444 | 32.4774 |  | N/A | hardware transporter (loaded) | AMF hardware issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| LIB Inner pipe module stored; Replacement RIB Inner Port Pipe Module collected; Transporter moved to port | Total | 0 | 32.4774 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Inner LIB pipe module collected; Pipe Module handling System Moved to Lower Port | Connect RIB inner pipe module | Trigger | 0 | 74.1264 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware issue | Movement | 0.23148 | 74.3579 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Hardware issue | 50 | 0.06 | 0.23148 |  | N/A
| Collect blanket Pipe Module | Logistics | 0.68 | 75.0379 |  | N/A |  |  |  | N/A | N/A | N/A | Collect hardware from the AMF | 0.68
| Move hardware transporter to Divertor Port | Movement | 0.69444 | 75.7324 |  | N/A | hardware transporter (loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Inner LIB pipe module collected; Pipe Module handling System Moved to Lower Port | Total | 0 | 75.7324 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB pipe module collected; Pipe Module handling System Moved to Lower Port | Connect LIB Inner Pipe Module | Trigger | 0 | 108.7199 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware issue | Movement | 0.23148 | 108.9514 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Hardware issue | 50 | 0.06 | 0.23148 |  | N/A
| Collect blanket Pipe Module | Logistics | 0.88 | 109.8314 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.69444 | 110.5259 |  | N/A | hardware transporter (loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| RIB pipe module collected; Pipe Module handling System Moved to Lower Port | Total | 0 | 110.5259 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Blanket segment installed | Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 56.5038 | 56.5038 | Install RIB Blanket Segment | 56.5038 |  |  |  | N/A | N/A | N/A |  | N/A
| RIB Blanket segment installed | Total | 0 | 56.5038 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Upper Port Pipe Module installed | Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 84.0993 | 84.0993 | Insert RIB Pipe Module | 84.0993 |  |  |  | N/A | N/A | N/A |  | N/A
| RIB Upper Port Pipe Module installed | Total | 0 | 84.0993 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Blanket segment installed | Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 91.0973 | 91.0973 | Install LIB Blanket Segment | 91.0973 |  |  |  | N/A | N/A | N/A |  | N/A
| LIB Blanket segment installed | Total | 0 | 91.0973 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Upper Port Pipe Module installed | Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 168.6162 | 168.6162 | Insert LIB Pipe Module | 168.6162 |  |  |  | N/A | N/A | N/A |  | N/A
| LIB Upper Port Pipe Module installed | Total | 0 | 168.6162 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Divertor Port Pipe LIB Inner Port Weld Failure
New RIB pipe module stored; Pipe Module handling System Moved to Lower Port | Weld Failure identified at LIB Inner Port Module joint | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 0.69444 |  | N/A | hardware transporter (Loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 1.5744 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.23148 | 1.8059 |  | N/A | hardware transporter (Empty Stillage) | AMF Equipment Issue | Divertor Port | 50 | 0.06 | 0.23148 |  | N/A
| New RIB pipe module stored; Pipe Module handling System Moved to Lower Port | Total | 0 | 1.8059 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Inner Port pipe module stored; Pipe Module handling System Moved to Lower Port | Remove RIB Inner Pipework module from the port | Trigger | 0 | 26.9359 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 27.6304 |  | N/A | hardware transporter (Loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 28.5104 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.23148 | 28.7419 |  | N/A | hardware transporter (Empty Stillage) | AMF Equipment Issue | Divertor Port | 50 | 0.06 | 0.23148 |  | N/A
| RIB Inner Port pipe module stored; Pipe Module handling System Moved to Lower Port | Total | 0 | 28.7419 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Inner pipe module stored; Replacement RIB Inner Port Pipe Module collected; Transporter moved to port | Remove RIB Inner Pipework module from the port | Trigger | 0 | 26.9359 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move to AMF equipment reciept | Movement | 0.69444 | 27.6304 |  | N/A | hardware transporter (Loaded) | Divertor Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Inner Port Pipe Module | Logistics | 0.88 | 28.5104 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| move to AMF hardware issue | Movement | 0.092593 | 28.603 |  | N/A | hardware transporter (empty stillage) | AMF Equipment Issue | AMF hardware issue | 20 | 0.06 | 0.092593 |  | N/A
| Collect RIB inner pipe module | Logistics | 0.68 | 29.283 |  | N/A |  |  |  | N/A | N/A | N/A | Collect hardware from the AMF | 0.68
| Move hardware transporter to divertor port | Movement | 0.69444 | 29.9774 |  | N/A | hardware transporter (loaded) | AMF hardware issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| LIB Inner pipe module stored; Replacement RIB Inner Port Pipe Module collected; Transporter moved to port | Total | 0 | 29.9774 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Inner pipe module module collected; Pipe Module handling System Moved to Lower Port | Connect RIB inner pipe module | Trigger | 0 | 126.3426 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware issue | Movement | 0.23148 | 126.5741 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Hardware issue | 50 | 0.06 | 0.23148 |  | N/A
| Collect blanket Pipe Module | Logistics | 0.68 | 127.2541 |  | N/A |  |  |  | N/A | N/A | N/A | Collect hardware from the AMF | 0.68
| Move hardware transporter to Divertor Port | Movement | 0.69444 | 127.9485 |  | N/A | hardware transporter (loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| LIB Inner pipe module module collected; Pipe Module handling System Moved to Lower Port | Total | 0 | 127.9485 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Blanket segment installed | Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 56.5038 | 56.5038 | Install RIB Blanket Segment | 56.5038 |  |  |  | N/A | N/A | N/A |  | N/A
| RIB Blanket segment installed | Total | 0 | 56.5038 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Upper Port Pipe Module installed | Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 84.0993 | 84.0993 | Insert RIB Pipe Module | 84.0993 |  |  |  | N/A | N/A | N/A |  | N/A
| RIB Upper Port Pipe Module installed | Total | 0 | 84.0993 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Blanket segment installed | Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 91.0973 | 91.0973 | Install LIB Blanket Segment | 91.0973 |  |  |  | N/A | N/A | N/A |  | N/A
| LIB Blanket segment installed | Total | 0 | 91.0973 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Upper Port Pipe Module installed | Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 168.6162 | 168.6162 | Insert LIB Pipe Module | 168.6162 |  |  |  | N/A | N/A | N/A |  | N/A
| LIB Upper Port Pipe Module installed | Total | 0 | 168.6162 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Divertor Port Pipe RIB Inner Port Weld Failure
New LIB Inner Port pipe module stored; Replacement RIB Inner Port Pipe collected; Hardware transporter moved to Lower Port | Weld Failure identified at RIB Module joint | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 0.69444 |  | N/A | hardware transporter (Loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 1.5744 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.23148 | 1.8059 |  | N/A | hardware transporter (Empty Stillage) | AMF Equipment Issue | Divertor Port | 50 | 0.06 | 0.23148 |  | N/A
| New LIB Inner Port pipe module stored; Replacement RIB Inner Port Pipe collected; Hardware transporter moved to Lower Port | Total | 0 | 1.8059 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Blanket segment installed | Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 56.5038 | 56.5038 | Install RIB Blanket Segment | 56.5038 |  |  |  | N/A | N/A | N/A |  | N/A
| RIB Blanket segment installed | Total | 0 | 56.5038 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Upper Port Pipe Module installed | Failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to upper port operations | Operation | 84.0993 | 84.0993 | Insert RIB Pipe Module | 84.0993 |  |  |  | N/A | N/A | N/A |  | N/A
| RIB Upper Port Pipe Module installed | Total | 0 | 84.0993 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Central Divertor cooling Weld Failure
Current payload stored; Divertor pipe module transporter collected; transporter moved to Divertor Port | Weld Failure identified at central divertor pipe module joint | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move transporter to AMF hardware receipt | Movement | 0.69444 | 0.69444 |  | N/A | Hardware Transporter (loaded) | Divertor Port | AMF hardware issue | 50 | 0.02 | 0.69444 |  | N/A
| Store current hardware | Logistics | 0.88 | 1.5744 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Store current transporter | Logistics | 0.88 | 2.4544 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Collect divertor pipe module transporter | Logistics | 0.68 | 3.1344 |  | N/A |  |  |  | N/A | N/A | N/A | Collect hardware from the AMF | 0.68
| Move transporter to Divertor Port | Movement | 0.23148 | 3.3659 |  | N/A | Hardware Transporter (Empty Stillage) | AMF equipment issue | Divertor Port | 50 | 0.06 | 0.23148 |  | N/A
| Current payload stored; Divertor pipe module transporter collected; transporter moved to Divertor Port | Total | 0 | 3.3659 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Central Divertor pipe module stored and transporter moved to divertor Port | remove central divertor cassette pipe module from port | Trigger | 0 | 13.203 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 13.8974 |  | N/A | hardware transporter (loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor cassette | Logistics | 0.88 | 14.7774 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move cassette transporter to Divertor Port | Movement | 0.69444 | 15.4719 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Central Divertor pipe module stored and transporter moved to divertor Port | Total | 0 | 15.4719 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Left Divertor Pipework Module Stored; pipe module handling system stored; Divertor cassette transporter collected and moved to Lower Port | Remove Left Divertor Pipework module | Trigger | 0 | 26.3359 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.23148 | 26.5674 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF hardware Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 27.4474 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Receipt | Movement | 0.027778 | 27.4752 |  | N/A | Hardware transporter (No load) | AMF hardware Receipt | AMF Equipment Receipt | 20 | 0.2 | 0.027778 |  | N/A
| Store Pipe module handling system | Logistics | 0.88 | 28.3552 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Issue | Movement | 0.027778 | 28.383 |  | N/A | hardware transporter (no load) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect port cleaning and maintenance system | Logistics | 0.68 | 29.063 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Hardware from the AMF | 0.68
| Move cassette transporter to Divertor Port | Movement | 0.69444 | 29.7574 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Left Divertor Pipework Module Stored; pipe module handling system stored; Divertor cassette transporter collected and moved to Lower Port | Total | 0 | 29.7574 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Right Divertor Pipework Module Stored; pipe module handling system stored; Divertor cassette transporter collected and moved to Lower Port | Remove Left Divertor Pipework module | Trigger | 0 | 26.3359 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.23148 | 26.5674 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF hardware Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 27.4474 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Receipt | Movement | 0.027778 | 27.4752 |  | N/A | Hardware transporter (No load) | AMF hardware Receipt | AMF Equipment Receipt | 20 | 0.2 | 0.027778 |  | N/A
| Store Pipe module handling system | Logistics | 0.88 | 28.3552 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Issue | Movement | 0.027778 | 28.383 |  | N/A | hardware transporter (no load) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect port cleaning and maintenance system | Logistics | 0.68 | 29.063 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Hardware from the AMF | 0.68
| Move cassette transporter to Divertor Port | Movement | 0.69444 | 29.7574 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Right Divertor Pipework Module Stored; pipe module handling system stored; Divertor cassette transporter collected and moved to Lower Port | Total | 0 | 29.7574 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Central Divertor cassette stored and transporter moved to divertor Port | remove central divertor cassette from the port | Trigger | 0 | 51.5689 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 52.2633 |  | N/A | hardware transporter (loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor cassette | Logistics | 0.88 | 53.1433 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move cassette transporter to Divertor Port | Movement | 0.69444 | 53.8378 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Central Divertor cassette stored and transporter moved to divertor Port | Total | 0 | 53.8378 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Left Divertor cassette stored; replacement right divertor cassette collected; transporter moved to divertor Port | remove left cassette from the port | Trigger | 0 | 54.3489 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 55.0433 |  | N/A | hardware transporter (loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor cassette | Logistics | 0.88 | 55.9233 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to AMF Hardware Issue | Movement | 0.046296 | 55.9696 |  | N/A | hardware transporter (empty stillage) | AMF Hardware Receipt | AMF Hardware Issue | 10 | 0.06 | 0.046296 |  | N/A
| Collect Divertor cassette | Logistics | 0.68 | 56.6496 |  | N/A |  |  |  | N/A | N/A | N/A | Collect hardware from the AMF | 0.68
| Move cassette transporter to Divertor Port | Movement | 0.69444 | 57.3441 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Left Divertor cassette stored; replacement right divertor cassette collected; transporter moved to divertor Port | Total | 0 | 57.3441 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Right Divertor cassette stored; replacement Left divertor cassette collected; transporter moved to divertor Port | Remove Right Cassette from the port | Trigger | 0 | 56.5289 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 57.2233 |  | N/A | hardware transporter (loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor cassette | Logistics | 0.88 | 58.1033 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to AMF Hardware Issue | Movement | 0.046296 | 58.1496 |  | N/A | hardware transporter (empty stillage) | AMF Hardware Receipt | AMF Hardware Issue | 10 | 0.06 | 0.046296 |  | N/A
| Collect Divertor cassette | Logistics | 0.68 | 58.8296 |  | N/A |  |  |  | N/A | N/A | N/A | Collect hardware from the AMF | 0.68
| Move cassette transporter to Divertor Port | Movement | 0.69444 | 59.5241 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Right Divertor cassette stored; replacement Left divertor cassette collected; transporter moved to divertor Port | Total | 0 | 59.5241 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Replacement Central Divertor cassette collected and transporter moved to divertor Port | Retract right cassette handling equipment | Trigger | 0 | 59.5241 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 60.2185 |  | N/A | hardware transporter (loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor cassette | Logistics | 0.88 | 61.0985 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move cassette transporter to Divertor Port | Movement | 0.69444 | 61.793 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Replacement Central Divertor cassette collected and transporter moved to divertor Port | Total | 0 | 61.793 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Divertor handling system stored; pipe module handling system collected; Replacement right divertor cassette pipe module collected and moved to Lower Port | Retract left cassette handling equipment | Trigger | 0 | 61.7041 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.23148 | 61.9356 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF hardware Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 62.8156 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Receipt | Movement | 0.027778 | 62.8433 |  | N/A | Hardware transporter (No load) | AMF hardware Receipt | AMF Equipment Receipt | 20 | 0.2 | 0.027778 |  | N/A
| Store Pipe module handling system | Logistics | 0.88 | 63.7233 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Issue | Movement | 0.027778 | 63.7511 |  | N/A | hardware transporter (no load) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect port cleaning and maintenance system | Logistics | 0.68 | 64.4311 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Hardware from the AMF | 0.68
| Move cassette transporter to Divertor Port | Movement | 0.69444 | 65.1256 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Divertor handling system stored; pipe module handling system collected; Replacement right divertor cassette pipe module collected and moved to Lower Port | Total | 0 | 65.1256 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Divertor handling system stored; pipe module handling system collected; Replacement left divertor cassette pipe module collected and moved to Lower Port | Retract right cassette handling equipment | Trigger | 0 | 59.5241 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.23148 | 59.7556 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF hardware Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 60.6356 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Receipt | Movement | 0.027778 | 60.6633 |  | N/A | Hardware transporter (No load) | AMF hardware Receipt | AMF Equipment Receipt | 20 | 0.2 | 0.027778 |  | N/A
| Store Pipe module handling system | Logistics | 0.88 | 61.5433 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Issue | Movement | 0.027778 | 61.5711 |  | N/A | hardware transporter (no load) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect port cleaning and maintenance system | Logistics | 0.68 | 62.2511 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Hardware from the AMF | 0.68
| Move cassette transporter to Divertor Port | Movement | 0.69444 | 62.9456 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Divertor handling system stored; pipe module handling system collected; Replacement left divertor cassette pipe module collected and moved to Lower Port | Total | 0 | 62.9456 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Replacement Central Divertor pipe module collected and transporter moved to divertor Port | Connect right divertor pipe module | Trigger | 0 | 73.7877 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 74.4822 |  | N/A | hardware transporter (loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor cassette | Logistics | 0.88 | 75.3622 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move cassette transporter to Divertor Port | Movement | 0.69444 | 76.0566 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Replacement Central Divertor pipe module collected and transporter moved to divertor Port | Total | 0 | 76.0566 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Left Divertor cooling Weld Failure
Current payload stored; Divertor pipe module transporter collected; transporter moved to Divertor Port | Weld Failure identified at left divertor pipe module joint | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move transporter to AMF hardware receipt | Movement | 0.69444 | 0.69444 |  | N/A | Hardware Transporter (loaded) | Divertor Port | AMF hardware issue | 50 | 0.02 | 0.69444 |  | N/A
| Store current hardware | Logistics | 0.88 | 1.5744 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Store current transporter | Logistics | 0.88 | 2.4544 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Collect divertor transporter | Logistics | 0.68 | 3.1344 |  | N/A |  |  |  | N/A | N/A | N/A | Collect hardware from the AMF | 0.68
| Move transporter to Divertor Port | Movement | 0.23148 | 3.3659 |  | N/A | Hardware Transporter (Empty Stillage) | AMF equipment issue | Divertor Port | 50 | 0.06 | 0.23148 |  | N/A
| Current payload stored; Divertor pipe module transporter collected; transporter moved to Divertor Port | Total | 0 | 3.3659 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Left Divertor Pipework Module Stored; pipe module handling system stored; Divertor cassette transporter collected and moved to Lower Port | Remove left divertor pipe module from the port | Trigger | 0 | 13.203 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.23148 | 13.4344 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF hardware Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 14.3144 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Receipt | Movement | 0.027778 | 14.3422 |  | N/A | Hardware transporter (No load) | AMF hardware Receipt | AMF Equipment Receipt | 20 | 0.2 | 0.027778 |  | N/A
| Store Pipe module handling system | Logistics | 0.88 | 15.2222 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Issue | Movement | 0.027778 | 15.25 |  | N/A | hardware transporter (no load) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect port cleaning and maintenance system | Logistics | 0.68 | 15.93 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Hardware from the AMF | 0.68
| Move cassette transporter to Divertor Port | Movement | 0.69444 | 16.6244 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Left Divertor Pipework Module Stored; pipe module handling system stored; Divertor cassette transporter collected and moved to Lower Port | Total | 0 | 16.6244 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Right Divertor Pipework Module Stored; pipe module handling system stored; Divertor cassette transporter collected and moved to Lower Port | Remove right divertor pipe module from the port | Trigger | 0 | 26.9359 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.23148 | 27.1674 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF hardware Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 28.0474 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Receipt | Movement | 0.027778 | 28.0752 |  | N/A | Hardware transporter (No load) | AMF hardware Receipt | AMF Equipment Receipt | 20 | 0.2 | 0.027778 |  | N/A
| Store Pipe module handling system | Logistics | 0.88 | 28.9552 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Issue | Movement | 0.027778 | 28.983 |  | N/A | hardware transporter (no load) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect port cleaning and maintenance system | Logistics | 0.68 | 29.663 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Hardware from the AMF | 0.68
| Move cassette transporter to Divertor Port | Movement | 0.69444 | 30.3574 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Right Divertor Pipework Module Stored; pipe module handling system stored; Divertor cassette transporter collected and moved to Lower Port | Total | 0 | 30.3574 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Central Divertor cassette stored and transporter moved to divertor Port | remove central divertor cassette from the port | Trigger | 0 | 38.4359 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 39.1304 |  | N/A | hardware transporter (loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor cassette | Logistics | 0.88 | 40.0104 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move cassette transporter to Divertor Port | Movement | 0.69444 | 40.7048 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Central Divertor cassette stored and transporter moved to divertor Port | Total | 0 | 40.7048 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Left Divertor cassette stored; replacement right divertor cassette collected; transporter moved to divertor Port | remove left cassette from the port | Trigger | 0 | 41.2159 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 41.9104 |  | N/A | hardware transporter (loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor cassette | Logistics | 0.88 | 42.7904 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to AMF Hardware Issue | Movement | 0.046296 | 42.8367 |  | N/A | hardware transporter (empty stillage) | AMF Hardware Receipt | AMF Hardware Issue | 10 | 0.06 | 0.046296 |  | N/A
| Collect Divertor cassette | Logistics | 0.68 | 43.5167 |  | N/A |  |  |  | N/A | N/A | N/A | Collect hardware from the AMF | 0.68
| Move cassette transporter to Divertor Port | Movement | 0.69444 | 44.2111 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Left Divertor cassette stored; replacement right divertor cassette collected; transporter moved to divertor Port | Total | 0 | 44.2111 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Right Divertor cassette stored; replacement Left divertor cassette collected; transporter moved to divertor Port | Remove Right Cassette from the port | Trigger | 0 | 43.3959 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 44.0904 |  | N/A | hardware transporter (loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor cassette | Logistics | 0.88 | 44.9704 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to AMF Hardware Issue | Movement | 0.046296 | 45.0167 |  | N/A | hardware transporter (empty stillage) | AMF Hardware Receipt | AMF Hardware Issue | 10 | 0.06 | 0.046296 |  | N/A
| Collect Divertor cassette | Logistics | 0.68 | 45.6967 |  | N/A |  |  |  | N/A | N/A | N/A | Collect hardware from the AMF | 0.68
| Move cassette transporter to Divertor Port | Movement | 0.69444 | 46.3911 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Right Divertor cassette stored; replacement Left divertor cassette collected; transporter moved to divertor Port | Total | 0 | 46.3911 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Replacement Central Divertor cassette collected and transporter moved to divertor Port | Retract right cassette handling equipment | Trigger | 0 | 46.3911 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 47.0856 |  | N/A | hardware transporter (loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor cassette | Logistics | 0.88 | 47.9656 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move cassette transporter to Divertor Port | Movement | 0.69444 | 48.66 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Replacement Central Divertor cassette collected and transporter moved to divertor Port | Total | 0 | 48.66 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Divertor handling system stored; pipe module handling system collected; Replacement right divertor cassette pipe module collected and moved to Lower Port | Retract left cassette handling equipment | Trigger | 0 | 48.5711 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.23148 | 48.8026 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF hardware Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 49.6826 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Receipt | Movement | 0.027778 | 49.7104 |  | N/A | Hardware transporter (No load) | AMF hardware Receipt | AMF Equipment Receipt | 20 | 0.2 | 0.027778 |  | N/A
| Store Pipe module handling system | Logistics | 0.88 | 50.5904 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Issue | Movement | 0.027778 | 50.6182 |  | N/A | hardware transporter (no load) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect port cleaning and maintenance system | Logistics | 0.68 | 51.2982 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Hardware from the AMF | 0.68
| Move cassette transporter to Divertor Port | Movement | 0.69444 | 51.9926 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Divertor handling system stored; pipe module handling system collected; Replacement right divertor cassette pipe module collected and moved to Lower Port | Total | 0 | 51.9926 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Divertor handling system stored; pipe module handling system collected; Replacement left divertor cassette pipe module collected and moved to Lower Port | Retract right cassette handling equipment | Trigger | 0 | 46.3911 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.23148 | 46.6226 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF hardware Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 47.5026 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Receipt | Movement | 0.027778 | 47.5304 |  | N/A | Hardware transporter (No load) | AMF hardware Receipt | AMF Equipment Receipt | 20 | 0.2 | 0.027778 |  | N/A
| Store Pipe module handling system | Logistics | 0.88 | 48.4104 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Issue | Movement | 0.027778 | 48.4382 |  | N/A | hardware transporter (no load) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect port cleaning and maintenance system | Logistics | 0.68 | 49.1182 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Hardware from the AMF | 0.68
| Move cassette transporter to Divertor Port | Movement | 0.69444 | 49.8126 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Divertor handling system stored; pipe module handling system collected; Replacement left divertor cassette pipe module collected and moved to Lower Port | Total | 0 | 49.8126 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Right Divertor cooling Weld Failure
Current payload stored; Divertor cassette transporter collected; transporter moved to Divertor Port | Weld Failure identified at left divertor pipe module joint | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move transporter to AMF hardware receipt | Movement | 0.69444 | 0.69444 |  | N/A | Hardware Transporter (loaded) | Divertor Port | AMF hardware issue | 50 | 0.02 | 0.69444 |  | N/A
| Store current hardware | Logistics | 0.88 | 1.5744 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Store current transporter | Logistics | 0.88 | 2.4544 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Collect divertor transporter | Logistics | 0.68 | 3.1344 |  | N/A |  |  |  | N/A | N/A | N/A | Collect hardware from the AMF | 0.68
| Move transporter to Divertor Port | Movement | 0.23148 | 3.3659 |  | N/A | Hardware Transporter (Empty Stillage) | AMF equipment issue | Divertor Port | 50 | 0.06 | 0.23148 |  | N/A
| Current payload stored; Divertor cassette transporter collected; transporter moved to Divertor Port | Total | 0 | 3.3659 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Right Divertor Pipework Module Stored; pipe module handling system stored; Divertor cassette transporter collected and moved to Lower Port | Remove right divertor pipe module from the port | Trigger | 0 | 13.203 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.23148 | 13.4344 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF hardware Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 14.3144 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Receipt | Movement | 0.027778 | 14.3422 |  | N/A | Hardware transporter (No load) | AMF hardware Receipt | AMF Equipment Receipt | 20 | 0.2 | 0.027778 |  | N/A
| Store Pipe module handling system | Logistics | 0.88 | 15.2222 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Issue | Movement | 0.027778 | 15.25 |  | N/A | hardware transporter (no load) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect port cleaning and maintenance system | Logistics | 0.68 | 15.93 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Hardware from the AMF | 0.68
| Move cassette transporter to Divertor Port | Movement | 0.69444 | 16.6244 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Right Divertor Pipework Module Stored; pipe module handling system stored; Divertor cassette transporter collected and moved to Lower Port | Total | 0 | 16.6244 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Central Divertor cassette stored and transporter moved to divertor Port | remove central divertor cassette from the port | Trigger | 0 | 24.703 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 25.3974 |  | N/A | hardware transporter (loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor cassette | Logistics | 0.88 | 26.2774 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move cassette transporter to Divertor Port | Movement | 0.69444 | 26.9719 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Central Divertor cassette stored and transporter moved to divertor Port | Total | 0 | 26.9719 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Left Divertor cassette stored; replacement right divertor cassette collected; transporter moved to divertor Port | remove left cassette from the port | Trigger | 0 | 27.483 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 28.1774 |  | N/A | hardware transporter (loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor cassette | Logistics | 0.88 | 29.0574 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to AMF Hardware Issue | Movement | 0.046296 | 29.1037 |  | N/A | hardware transporter (empty stillage) | AMF Hardware Receipt | AMF Hardware Issue | 10 | 0.06 | 0.046296 |  | N/A
| Collect Divertor cassette | Logistics | 0.68 | 29.7837 |  | N/A |  |  |  | N/A | N/A | N/A | Collect hardware from the AMF | 0.68
| Move cassette transporter to Divertor Port | Movement | 0.69444 | 30.4782 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Left Divertor cassette stored; replacement right divertor cassette collected; transporter moved to divertor Port | Total | 0 | 30.4782 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Right Divertor cassette stored; replacement Left divertor cassette collected; transporter moved to divertor Port | Remove Right Cassette from the port | Trigger | 0 | 29.663 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 30.3574 |  | N/A | hardware transporter (loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor cassette | Logistics | 0.88 | 31.2374 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to AMF Hardware Issue | Movement | 0.046296 | 31.2837 |  | N/A | hardware transporter (empty stillage) | AMF Hardware Receipt | AMF Hardware Issue | 10 | 0.06 | 0.046296 |  | N/A
| Collect Divertor cassette | Logistics | 0.68 | 31.9637 |  | N/A |  |  |  | N/A | N/A | N/A | Collect hardware from the AMF | 0.68
| Move cassette transporter to Divertor Port | Movement | 0.69444 | 32.6582 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Right Divertor cassette stored; replacement Left divertor cassette collected; transporter moved to divertor Port | Total | 0 | 32.6582 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Replacement Central Divertor cassette collected and transporter moved to divertor Port | Retract right cassette handling equipment | Trigger | 0 | 32.6582 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 33.3526 |  | N/A | hardware transporter (loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor cassette | Logistics | 0.88 | 34.2326 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move cassette transporter to Divertor Port | Movement | 0.69444 | 34.927 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Replacement Central Divertor cassette collected and transporter moved to divertor Port | Total | 0 | 34.927 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Divertor handling system stored; pipe module handling system collected; Replacement right divertor cassette pipe module collected and moved to Lower Port | Retract left cassette handling equipment | Trigger | 0 | 34.8382 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.23148 | 35.0696 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF hardware Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 35.9496 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Receipt | Movement | 0.027778 | 35.9774 |  | N/A | Hardware transporter (No load) | AMF hardware Receipt | AMF Equipment Receipt | 20 | 0.2 | 0.027778 |  | N/A
| Store Pipe module handling system | Logistics | 0.88 | 36.8574 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Issue | Movement | 0.027778 | 36.8852 |  | N/A | hardware transporter (no load) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect port cleaning and maintenance system | Logistics | 0.68 | 37.5652 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Hardware from the AMF | 0.68
| Move cassette transporter to Divertor Port | Movement | 0.69444 | 38.2596 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Divertor handling system stored; pipe module handling system collected; Replacement right divertor cassette pipe module collected and moved to Lower Port | Total | 0 | 38.2596 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Hardware Transporter failure at the divertor port
Replacement transporter commissioned; moved to port to collect abandoned payload | Hardware transporter failure detected during maintenance operations | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Hardware transporter exported from the AMF | Logistics | 0.68 | 0.68 |  | N/A |  |  |  | N/A | N/A | N/A | Collect hardware from the AMF | 0.68
| Hardware transporter moved to AMF equipment issue | movement | 0.027778 | 0.70778 |  | N/A | Hardware Transporter (no load) | AMF hardware issue | AMF equipment issue | 20 | 0.2 | 0.027778 |  | N/A
| Hardware stillage or handling system collected | Logistics | 0.68 | 1.3878 |  | N/A |  |  |  | N/A | N/A | N/A | Collect hardware from the AMF | 0.68
| Transporter moved to Divertor port to collect abandoned load | movement | 0.23148 | 1.6193 |  | N/A | Hardware Transporter (Empty Stillage) | AMF equipment issue | Divertor port | 50 | 0.06 | 0.23148 |  | N/A
| Replacement transporter commissioned; moved to port to collect abandoned payload | Total | 0 | 1.6193 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Multifunction Manipulator failure at the divertor port
Hardware transporter moved to the AMF; Replacement MFM issued; MFM moved to port | mfm failure detected during maintenance operations | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Hardware transporter moved to the AMF equipment reciept | movement | 0.69444 | 0.69444 |  | N/A | hardware transporter (loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Current hardware stored in the AMF | Logistics | 0.88 | 1.5744 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in the AMF | 0.88
| Hardware transporter moved to the AMF equipment issue | Movement | 0.027778 | 1.6022 |  | N/A | hardware transporter (no load) | AMF Hardware Receipt | AMF equipment issue | 20 | 0.2 | 0.027778 |  | N/A
| Replacement MFM collected from AMF | Logistics | 0.68 | 2.2822 |  | N/A |  |  |  | N/A | N/A | N/A | Collect hardware from the AMF | 0.68
| Move replacement MFM to the port | movement | 0.69444 | 2.9767 |  | N/A | hardware transporter (loaded) | AMF equipment issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Hardware transporter moved to the AMF; Replacement MFM issued; MFM moved to port | Total | 0 | 2.2822 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Cassette Handling system failure at the divertor port
Hardware transporter moved to the AMF; Replacement MFM issued; MFM moved to port | mfm failure detected during maintenance operations | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Hardware transporter moved to the AMF equipment reciept | movement | 0.69444 | 0.69444 |  | N/A | hardware transporter (loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Current hardware stored in the AMF | Logistics | 0.88 | 1.5744 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in the AMF | 0.88
| Hardware transporter moved to the AMF equipment issue | Movement | 0.027778 | 1.6022 |  | N/A | hardware transporter (no load) | AMF Hardware Receipt | AMF equipment issue | 20 | 0.2 | 0.027778 |  | N/A
| Replacement MFM collected from AMF | Logistics | 0.68 | 2.2822 |  | N/A |  |  |  | N/A | N/A | N/A | Collect hardware from the AMF | 0.68
| Move replacement MFM to the port | movement | 0.69444 | 2.9767 |  | N/A | hardware transporter (loaded) | AMF equipment issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Hardware transporter moved to the AMF; Replacement MFM issued; MFM moved to port | Total | 0 | 2.2822 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A

## Lower Hot Cell Dependencies (hidden)
[5 empty] | Operations |  | Movement | [5 empty] | Logistics
Group | Activity | Activity Type | Time (h) | Cumulative | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h)
Contamination Control System Prepared; Contamination Control System Moved to Lower Port | Cassette Removal Required | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Collect Port Plate | Logistics | 0.68 | 0.68 |  | N/A |  |  |  | N/A | N/A | N/A | Collect hardware from the AMF | 0.68
| Move Port Plate to Divertor Port | Movement | 0.69444 | 1.3744 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Contamination Control System Prepared; Contamination Control System Moved to Lower Port | Total | 0 | 1.3744 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Bioshield interface hardware stored; Port Inspection System collected; Transport Moved to Lower Port | Store Bioshield | Trigger | 0 | 2.7081 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.13889 | 2.847 |  | N/A | hardware transporter (empty stillage) | Divertor Port | Hardware Stillage | 30 | 0.06 | 0.13889 |  | N/A
| Store Biosheild interface hardware | Logistics | 0.88 | 3.727 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Issue | Movement | 0.027778 | 3.7548 |  | N/A | hardware transporter (no load) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Port Inspection System | Logistics | 0.68 | 4.4348 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Hardware from the AMF | 0.68
| Move transporter to Divertor Port | Movement | 0.69444 | 5.1293 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Bioshield interface hardware stored; Port Inspection System collected; Transport Moved to Lower Port | Total | 0 | 5.1293 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Contamination Control System Interface stored; Vacuum Closure Plate Interface collected; Transport Moved to Lower Port | recover CCS lifting interface | Trigger | 0 | 4.6081 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.13889 | 4.747 |  | N/A | hardware transporter (empty stillage) | Divertor Port | Hardware Stillage | 30 | 0.06 | 0.13889 |  | N/A
| Store CCS | Logistics | 0.88 | 5.627 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Issue | Movement | 0.027778 | 5.6548 |  | N/A | hardware transporter (no load) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Vacuum Closure Plate Handling System | Logistics | 0.68 | 6.3348 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Hardware from the AMF | 0.68
| Move transporter to Divertor Port | Movement | 0.69444 | 7.0293 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Contamination Control System Interface stored; Vacuum Closure Plate Interface collected; Transport Moved to Lower Port | Total | 0 | 7.0293 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Port Plate Equipment Stored; Threshold rail hardware collected; Transport Moved to Lower Port | Retract Vacuum Closure Plate Equipment | Trigger | 0 | 47.4326 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.23148 | 47.6641 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Port Plate interface hardware | Logistics | 0.88 | 48.5441 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Issue | Movement | 0.027778 | 48.5719 |  | N/A | hardware transporter (no load) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Threshold rail hardware system | Logistics | 0.68 | 49.2519 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Hardware from the AMF | 0.68
| Move Transporter to Divertor Port | Movement | 0.69444 | 49.9463 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Port Plate Equipment Stored; Threshold rail hardware collected; Transport Moved to Lower Port | Total | 0 | 49.9463 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Vacuum closure plate Stored; Diagnostic maintenance hardware collected; Transport Moved to Lower Port | Retract Vacuum Closure Plate Equipment | Trigger | 0 | 47.4326 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.23148 | 47.6641 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Port Plate interface hardware | Logistics | 0.88 | 48.5441 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Issue | Movement | 0.027778 | 48.5719 |  | N/A | hardware transporter (no load) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Threshold rail hardware system | Logistics | 0.68 | 49.2519 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Hardware from the AMF | 0.68
| Move Transporter to Divertor Port | Movement | 0.69444 | 49.9463 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Vacuum closure plate Stored; Diagnostic maintenance hardware collected; Transport Moved to Lower Port | Total | 0 | 49.9463 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Threshold rail handling system Stored; vacuum pumping interface hardware collected; Transport Moved to Lower Port | Retract Vacuum Closure Plate Equipment | Trigger | 0 | 47.4326 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.23148 | 47.6641 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Threshold Rail interface hardware | Logistics | 0.88 | 48.5441 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Issue | Movement | 0.027778 | 48.5719 |  | N/A | hardware transporter (no load) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Vacuum pumping hardware interface | Logistics | 0.68 | 49.2519 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Hardware from the AMF | 0.68
| Move Transporter to Divertor Port | Movement | 0.69444 | 49.9463 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Threshold rail handling system Stored; vacuum pumping interface hardware collected; Transport Moved to Lower Port | Total | 0 | 49.9463 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Diagnostic maintenance system stored; shielding module hardware collected; Transport Moved to Lower Port | Retract diagnostic system and store in the AMF | Trigger | 0 | 79.0206 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.23148 | 79.2521 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store diagnostic system | Logistics | 0.88 | 80.1321 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Issue | Movement | 0.027778 | 80.1599 |  | N/A | hardware transporter (no load) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Shielding module lifting hardware interface | Logistics | 0.68 | 80.8399 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Hardware from the AMF | 0.68
| Move Transporter to Divertor Port | Movement | 0.69444 | 81.5344 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Diagnostic maintenance system stored; shielding module hardware collected; Transport Moved to Lower Port | Total | 0 | 81.5344 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Vacuum pumping hardware stored; Divertor pipework maintenance system collected; Transport Moved to Lower Port | Remove vacuum pumping system assembly from the port | Trigger | 0 | 93.0651 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.23148 | 93.2966 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store diagnostic system | Logistics | 0.88 | 94.1766 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Issue | Movement | 0.027778 | 94.2044 |  | N/A | hardware transporter (no load) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Shielding module lifting hardware interface | Logistics | 0.68 | 94.8844 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Hardware from the AMF | 0.68
| Move Transporter to Divertor Port | Movement | 0.69444 | 95.5788 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Vacuum pumping hardware stored; Divertor pipework maintenance system collected; Transport Moved to Lower Port | Total | 0 | 95.5788 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Sheilding Modules stored; Divertor pipework maintenance system collected; Transport Moved to Lower Port | Retract sheild modules and store in cask | Trigger | 0 | 97.5951 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.23148 | 97.8266 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Port Plate interface hardware | Logistics | 0.88 | 98.7066 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Issue | Movement | 0.027778 | 98.7344 |  | N/A | hardware transporter (no load) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect divertor pipework maintenance system | Logistics | 0.68 | 99.4144 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Hardware from the AMF | 0.68
| Move Transporter to Divertor Port | Movement | 0.69444 | 100.1088 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Sheilding Modules stored; Divertor pipework maintenance system collected; Transport Moved to Lower Port | Total | 0 | 100.1088 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Central Divertor Pipework Module Stored; Pipe Module handling System Moved to Lower Port | Remove Central Divertor Pipework module | Trigger | 0 | 112.3106 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.23148 | 112.5421 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Hardware Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 113.4221 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move cassette transporter to Divertor Port | Movement | 0.69444 | 114.1165 |  | N/A | hardware transporter (Loaded) | AMF Hardware Receipt | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Central Divertor Pipework Module Stored; Pipe Module handling System Moved to Lower Port | Total | 0 | 114.1165 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Left Divertor Pipework Module Stored; Pipe Module handling System stored; Central divertor system and maintenance system collected and moved to Lower Port | Remove Left Divertor Pipework module | Trigger | 0 | 113.8661 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.23148 | 114.0975 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF hardware Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 114.9775 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Receipt | Movement | 0.027778 | 115.0053 |  | N/A | Hardware transporter (No load) | AMF hardware Receipt | AMF Equipment Receipt | 20 | 0.2 | 0.027778 |  | N/A
| Store Pipe module handling system | Logistics | 0.88 | 115.8853 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Issue | Movement | 0.027778 | 115.9131 |  | N/A | hardware transporter (no load) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect port cleaning and maintenance system | Logistics | 0.68 | 116.5931 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Hardware from the AMF | 0.68
| Move cassette transporter to Divertor Port | Movement | 0.69444 | 117.2875 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Left Divertor Pipework Module Stored; Pipe Module handling System stored; Central divertor system and maintenance system collected and moved to Lower Port | Total | 0 | 117.2875 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Right Divertor Pipework Module Stored; Pipe Module handling System stored; Divertor handling system collected and moved to Lower Port | Remove Right Divertor Pipework module | Trigger | 0 | 115.4215 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 116.116 |  | N/A | hardware transporter (loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 116.996 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move transporter to AMF equipment reciept | Movement | 0.092593 | 117.0886 |  | N/A | hardware transporter (empty stillage) | AMF Hardware Receipt | AMF Equipment Receipt | 20 | 0.06 | 0.092593 |  | N/A
| Store divertor pipe module handling system | Logistics | 0.88 | 117.9686 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Issue | Movement | 0.027778 | 117.9964 |  | N/A | hardware transporter (no load) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Divertor cassette handling system | Logistics | 0.68 | 118.6764 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Hardware from the AMF | 0.68
| Move cassette transporter to Divertor Port | Movement | 0.69444 | 119.3708 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Right Divertor Pipework Module Stored; Pipe Module handling System stored; Divertor handling system collected and moved to Lower Port | Total | 0 | 119.3708 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Central Cassette Stored; Cassette Transport Cask Moved to Lower Port | Remove Central cassette from the port | Trigger | 0 | 128.6042 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 129.2987 |  | N/A | hardware transporter (Loaded) | Divertor Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Central Cassette | Logistics | 0.88 | 130.1787 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Issue | Movement | 0.027778 | 130.2064 |  | N/A | hardware transporter (no load) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect cassette transporterer | Logistics | 0.68 | 130.8864 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Hardware from the AMF | 0.68
| Move cassette transporter to Divertor Port | Movement | 0.23148 | 131.1179 |  | N/A | hardware transporter (empty stillage) | AMF Equipment Issue | Divertor Port | 50 | 0.06 | 0.23148 |  | N/A
| Central Cassette Stored; Cassette Transport Cask Moved to Lower Port | Total | 0 | 131.1179 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Left Divertor Cassette Stored; Cassette Handling system Stored; Blanket Pipe Module Interface hardware Prepared; Blanket Pipe Module Interface hardware moved to Lower Port | Remove Left cassette from the port | Trigger | 0 | 130.8542 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.23148 | 131.0857 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Hardware Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Left Divertor Cassette | Logistics | 0.88 | 131.9657 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Receipt | Movement | 0.027778 | 131.9935 |  | N/A | hardware transporter (no load) | AMF Hardware Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Store Divertor Cassette Handling System | Logistics | 0.68 | 132.6735 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Hardware from the AMF | 0.68
| Move hardware transporter to AMF Equipment Issue | Movement | 0.092593 | 132.7661 |  | N/A | hardware transporter (empty stillage) | AMF Equipment Issue | AMF Hardware Receipt | 20 | 0.06 | 0.092593 |  | N/A
| Collect Outboard Pipework Maintenance System | Logistics | 0.68 | 133.4461 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Hardware from the AMF | 0.68
| Move Outboard Pipework to Divertor Port | Movement | 0.69444 | 134.1405 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Left Divertor Cassette Stored; Cassette Handling system Stored; Blanket Pipe Module Interface hardware Prepared; Blanket Pipe Module Interface hardware moved to Lower Port | Total | 0 | 134.1405 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Right Divertor Cassette Stored; Cassette Transport Cask Stored; Blanket Pipe Module Interface hardware Prepared; Blanket Pipe Module Interface hardware moved to Lower Port | Remove Right cassette from the port | Trigger | 0 | 133.3679 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.23148 | 133.5994 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store cassette transporter | Logistics | 0.88 | 134.4794 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Issue | Movement | 0.027778 | 134.5072 |  | N/A | hardware transporter (no load) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Inboard Pipework | Logistics | 0.68 | 135.1872 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Hardware from the AMF | 0.68
| Move Inboard Pipework to Divertor Port | Movement | 0.69444 | 135.8816 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Right Divertor Cassette Stored; Cassette Transport Cask Stored; Blanket Pipe Module Interface hardware Prepared; Blanket Pipe Module Interface hardware moved to Lower Port | Total | 0 | 135.8816 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Divertor pipe module handling system stored; blanket pipework handling system collected; blanket pipework handling system moved to the port | Remove divertor pipework handling system from the port | Trigger | 0 | 116.0215 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.23148 | 116.253 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF hardware Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 117.133 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Issue | Movement | 0.027778 | 117.1608 |  | N/A | hardware transporter (no load) | AMF Hardware Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Vacuum pumping interface hardware | Logistics | 0.68 | 117.8408 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Hardware from the AMF | 0.68
| Move Transporter to Divertor Port | Movement | 0.69444 | 118.5353 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Divertor pipe module handling system stored; blanket pipework handling system collected; blanket pipework handling system moved to the port | Total | 0 | 118.5353 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
COB pipe module stored; Pipe Module handling System Moved to Lower Port | Remove COB pipe module from the port | Trigger | 0 | 140.9305 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 141.625 |  | N/A | hardware transporter (Loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 142.505 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.23148 | 142.7365 |  | N/A | hardware transporter (Empty Stillage) | AMF Equipment Issue | Divertor Port | 50 | 0.06 | 0.23148 |  | N/A
| COB pipe module stored; Pipe Module handling System Moved to Lower Port | Total | 0 | 142.7365 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB pipe module stored; Pipe Module handling System Moved to Lower Port | Remove LOB pipe module from the port | Trigger | 0 | 151.8805 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 152.575 |  | N/A | hardware transporter (Loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 153.455 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.23148 | 153.6865 |  | N/A | hardware transporter (Empty Stillage) | AMF Equipment Issue | Divertor Port | 50 | 0.06 | 0.23148 |  | N/A
| LOB pipe module stored; Pipe Module handling System Moved to Lower Port | Total | 0 | 153.6865 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB pipe module stored; Pipe Module handling System Moved to Lower Port | Remove COB pipe module from the port | Trigger | 0 | 140.9305 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 141.625 |  | N/A | hardware transporter (Loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 142.505 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.23148 | 142.7365 |  | N/A | hardware transporter (Empty Stillage) | AMF Equipment Issue | Divertor Port | 50 | 0.06 | 0.23148 |  | N/A
| ROB pipe module stored; Pipe Module handling System Moved to Lower Port | Total | 0 | 142.7365 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB pipe module stored; Pipe Module handling System Moved to Lower Port | Remove LIB pipe module from the port | Trigger | 0 | 155.9306 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 156.625 |  | N/A | hardware transporter (Loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 157.505 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.23148 | 157.7365 |  | N/A | hardware transporter (Empty Stillage) | AMF Equipment Issue | Divertor Port | 50 | 0.06 | 0.23148 |  | N/A
| LIB pipe module stored; Pipe Module handling System Moved to Lower Port | Total | 0 | 157.7365 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB pipe module stored; Pipe Module handling System Moved to Lower Port | Remove RIB pipe module from the port | Trigger | 0 | 157.8206 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 158.5151 |  | N/A | hardware transporter (Loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 159.3951 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.23148 | 159.6265 |  | N/A | hardware transporter (Empty Stillage) | AMF Equipment Issue | Divertor Port | 50 | 0.06 | 0.23148 |  | N/A
| RIB pipe module stored; Pipe Module handling System Moved to Lower Port | Total | 0 | 159.6265 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Inner pipe module stored; Blanket Pipe Module handling System Stored | Remove COB pipe module from the port | Trigger | 0 | 140.9305 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.69444 | 141.625 |  | N/A | hardware transporter (Loaded) | Divertor Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 142.505 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.23148 | 142.7365 |  | N/A | hardware transporter (Empty Stillage) | AMF Equipment Issue | Divertor Port | 50 | 0.06 | 0.23148 |  | N/A
| LIB Inner pipe module stored; Blanket Pipe Module handling System Stored | Total | 0 | 142.7365 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Inner pipe module stored; Blanket Pipe Module handling System Stored | Retract Blanket Pipe Module Handling System from port | Trigger | 0 | 164.2947 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware Receipt | Movement | 0.23148 | 164.5262 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Divertor Pipework Modules | Logistics | 0.88 | 165.4062 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Issue | Movement | 0.027778 | 165.4339 |  | N/A | hardware transporter (no load) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect cassette transporter | Logistics | 0.68 | 166.1139 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Hardware from the AMF | 0.68
| Move cassette transporter to Divertor Port | Movement | 0.69444 | 166.8084 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| RIB Inner pipe module stored; Blanket Pipe Module handling System Stored | Total | 0 | 166.8084 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
N/A
N/A
N/A
N/A
COB Installed | Cassette Installation Required | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Divertor Port COB pipework joint cut and pipework removed | Operation | 43.9661 | 43.9661 | Install COB Blanket Segment | 43.9661 |  |  |  | N/A | N/A | N/A |  | N/A
| COB Installed | Total | 0 | 43.9661 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Installed | Cassette Installation Required | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Divertor Port LOB pipework joint cut and pipework removed | Operation | 38.9417 | 38.9417 | Install LOB Blanket Segment | 38.9417 |  |  |  | N/A | N/A | N/A |  | N/A
| LOB Installed | Total | 0 | 38.9417 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Installed | Cassette Installation Required | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Divertor Port ROB pipework joint cut and pipework removed | Operation | 33.9172 | 33.9172 | Install ROB Blanket Segment | 33.9172 |  |  |  | N/A | N/A | N/A |  | N/A
| ROB Installed | Total | 0 | 33.9172 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Installed | Cassette Installation Required | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Divertor Port LIB pipework joint cut and pipework removed | Operation | 28.8928 | 28.8928 | Install LIB Blanket Segment | 28.8928 |  |  |  | N/A | N/A | N/A |  | N/A
| LIB Installed | Total | 0 | 28.8928 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Installed | Cassette Installation Required | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Divertor Port RIB pipework joint cut and pipework removed | Operation | 23.8683 | 23.8683 | Install RIB Blanket Segment | 23.8683 |  |  |  | N/A | N/A | N/A |  | N/A
| RIB Installed | Total | 0 | 23.8683 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Inner Port Pipework Collected and Prepared; RIB inner pipe module collected; Inner Port Pipework Cask Moved to Lower Port | Cassette Installation Required | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Collect Blanket Pipe Module handling system | Logistics | 0.68 | 0.68 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Hardware from the AMF | 0.68
| Move to AMF Hardware issue | Movement | 0.092593 | 0.77259 |  | N/A | hardware transporter (Empty Stillage) | AMF Equipment Issue | AMF hardware issue | 20 | 0.06 | 0.092593 |  | N/A
| Collect new Inner Port Pipe Modules | Logistics | 0.68 | 1.4526 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Hardware from the AMF | 0.68
| Move Port Plate & Pipework to Divertor Port | Movement | 0.69444 | 2.147 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Inner Port Pipework Collected and Prepared; RIB inner pipe module collected; Inner Port Pipework Cask Moved to Lower Port | Total | 0 | 2.147 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Inspection Cask Stored; Blanket Pipe Module handling system collected; LIB Inner Pipe Module collected; hardware transporter moved to Lower Port | Retract port maintenance system | Trigger | 0 | 18.1333 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move to AMF equipment reciept | Movement | 0.69444 | 18.8278 |  | N/A | hardware transporter (Loaded) | Divertor Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Port maintenance system | Logistics | 0.88 | 19.7078 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Issue | Movement | 0.027778 | 19.7356 |  | N/A | hardware transporter (no load) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Blanket Pipe Module handling system | Logistics | 0.68 | 20.4156 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Hardware from the AMF | 0.68
| move to AMF hardware issue | Movement | 0.092593 | 20.5081 |  | N/A | hardware transporter (empty stillage) | AMF Equipment Issue | AMF hardware issue | 20 | 0.06 | 0.092593 |  | N/A
| Collect RIB inner pipe module | Logistics | 0.68 | 21.1881 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Hardware from the AMF | 0.68
| Move hardware transporter to divertor port | Movement | 0.69444 | 21.8826 |  | N/A | hardware transporter (loaded) | AMF hardware issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Inspection Cask Stored; Blanket Pipe Module handling system collected; LIB Inner Pipe Module collected; hardware transporter moved to Lower Port | Total | 0 | 21.8826 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB pipe module collected; Pipe Module handling System Moved to Lower Port | Connect RIB inner pipe module | Trigger | 0 | 73.518 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware issue | Movement | 0.23148 | 73.7495 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Hardware issue | 50 | 0.06 | 0.23148 |  | N/A
| Collect blanket Pipe Module | Logistics | 0.68 | 74.4295 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Hardware from the AMF | 0.68
| Move hardware transporter to Divertor Port | Movement | 0.69444 | 75.1239 |  | N/A | hardware transporter (loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| RIB pipe module collected; Pipe Module handling System Moved to Lower Port | Total | 0 | 75.1239 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB pipe module collected; Pipe Module handling System Moved to Lower Port | Connect LIB Inner Pipe Module | Trigger | 0 | 128.6326 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware issue | Movement | 0.23148 | 128.8641 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Hardware issue | 50 | 0.06 | 0.23148 |  | N/A
| Collect blanket Pipe Module | Logistics | 0.88 | 129.7441 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.69444 | 130.4385 |  | N/A | hardware transporter (loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| LIB pipe module collected; Pipe Module handling System Moved to Lower Port | Total | 0 | 130.4385 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB pipe module collected; Pipe Module handling System Moved to Lower Port | Connect RIB pipe module | Trigger | 0 | 184.4172 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware issue | Movement | 0.23148 | 184.6487 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Hardware issue | 50 | 0.06 | 0.23148 |  | N/A
| Collect blanket Pipe Module | Logistics | 0.88 | 185.5287 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.69444 | 186.2232 |  | N/A | hardware transporter (loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| ROB pipe module collected; Pipe Module handling System Moved to Lower Port | Total | 0 | 186.2232 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB pipe module collected; Pipe Module handling System Moved to Lower Port | Connect LIB Pipe Module | Trigger | 0 | 239.8019 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware issue | Movement | 0.23148 | 240.0334 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Hardware issue | 50 | 0.06 | 0.23148 |  | N/A
| Collect blanket Pipe Module | Logistics | 0.88 | 240.9134 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.69444 | 241.6078 |  | N/A | hardware transporter (loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| LOB pipe module collected; Pipe Module handling System Moved to Lower Port | Total | 0 | 241.6078 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
COB pipe module collected; Pipe Module handling System Moved to Lower Port | Connect ROB Pipe Module | Trigger | 0 | 267.3752 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware issue | Movement | 0.23148 | 267.6066 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Hardware issue | 50 | 0.06 | 0.23148 |  | N/A
| Collect blanket Pipe Module | Logistics | 0.88 | 268.4866 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.69444 | 269.1811 |  | N/A | hardware transporter (loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| COB pipe module collected; Pipe Module handling System Moved to Lower Port | Total | 0 | 269.1811 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Blanket pipe module handling system stored; divertor cassette handling system collect; Divertor cassette collected; hardware transporter moved to port | Connect LOB Pipe Module | Trigger | 0 | 295.4784 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move blanket pipework handling system to AMF Equipment Receipt | Movement | 0.23148 | 295.7099 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store blanket pipework handling system | Logistics | 0.88 | 296.5899 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Issue | Movement | 0.027778 | 296.6177 |  | N/A | hardware transporter (no load) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Divertor cassette handling system | Logistics | 0.68 | 297.2977 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Hardware from the AMF | 0.68
| Move hardware transport to AMF hardware issue | Movement | 0.092593 | 297.3903 |  | N/A | hardware transporter (Empty Stillage) | AMF Equipment issue | AMF Hardware issue | 20 | 0.06 | 0.092593 |  | N/A
| Collect Right Divertor Cassette | Logistics | 0.68 | 298.0703 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Hardware from the AMF | 0.68
| Move hardware transporter to Divertor port | Movement | 0.69444 | 298.7647 |  | N/A | hardware transporter (Loaded) | AMF Hardware issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Blanket pipe module handling system stored; divertor cassette handling system collect; Divertor cassette collected; hardware transporter moved to port | Total | 0 | 298.7647 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Blanket pipe module handling system stored; second divertor cassette handling system collect; Divertor cassette collected; hardware transporter moved to port | Remove blanket pipe module handling system from port | Trigger | 0 | 343.8617 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move blanket pipework handling system to AMF Equipment Receipt | Movement | 0.23148 | 344.0932 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store blanket pipework handling system | Logistics | 0.88 | 344.9732 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Issue | Movement | 0.027778 | 345.001 |  | N/A | hardware transporter (no load) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Divertor cassette handling system | Logistics | 0.68 | 345.681 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Hardware from the AMF | 0.68
| Move hardware transport to AMF hardware issue | Movement | 0.092593 | 345.7735 |  | N/A | hardware transporter (Empty Stillage) | AMF Equipment issue | AMF Hardware issue | 20 | 0.06 | 0.092593 |  | N/A
| Collect Right Divertor Cassette | Logistics | 0.68 | 346.4535 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Hardware from the AMF | 0.68
| Move hardware transporter to Divertor port | Movement | 0.69444 | 347.148 |  | N/A | hardware transporter (Loaded) | AMF Hardware issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Blanket pipe module handling system stored; second divertor cassette handling system collect; Divertor cassette collected; hardware transporter moved to port | Total | 0 | 347.148 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Divertor cassette collected; Divertor cassette handling System Moved to Lower Port | Retract Right cassette handling equipment | Trigger | 0 | 345.9917 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware issue | Movement | 0.23148 | 346.2232 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Hardware issue | 50 | 0.06 | 0.23148 |  | N/A
| Collect blanket Pipe Module | Logistics | 0.88 | 347.1032 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.69444 | 347.7976 |  | N/A | hardware transporter (loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Divertor cassette collected; Divertor cassette handling System Moved to Lower Port | Total | 0 | 347.7976 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Divertor Handling system Stored; Divertor Pipework handling system collected; Right Divertor pipe module collected; Transport Moved to Lower Port | Retract Left Cassette Handling Equipment | Trigger | 0 | 349.278 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Inboard Pipework to AMF Equipment Receipt | Movement | 0.23148 | 349.5095 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Equipment Issue | 50 | 0.06 | 0.23148 |  | N/A
| Store Inboard Pipework | Logistics | 0.88 | 350.3895 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in the AMF | 0.88
| Move hardware transporter to AMF equipment Issue | Movement | 0.027778 | 350.4173 |  | N/A | hardware transporter (no load) | AMF equipment Receipt | AMF equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Right cassette transporter | Logistics | 0.68 | 351.0973 |  | N/A |  |  |  | N/A | N/A | N/A | Collect hardware from the AMF | 0.68
| Move Pipework to Divertor Port | Movement | 0.69444 | 351.7917 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Divertor Handling system Stored; Divertor Pipework handling system collected; Right Divertor pipe module collected; Transport Moved to Lower Port | Total | 0 | 351.7917 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Divertor Handling system Stored; Divertor Pipework handling system collected; Left Divertor pipe module collected; Transport Moved to Lower Port | Retract Left Cassette Handling Equipment | Trigger | 0 | 349.278 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Inboard Pipework to AMF Equipment Receipt | Movement | 0.23148 | 349.5095 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Equipment Issue | 50 | 0.06 | 0.23148 |  | N/A
| Store Inboard Pipework | Logistics | 0.88 | 350.3895 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in the AMF | 0.88
| Move hardware transporter to AMF equipment Issue | Movement | 0.027778 | 350.4173 |  | N/A | hardware transporter (no load) | AMF equipment Receipt | AMF equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Right cassette transporter | Logistics | 0.68 | 351.0973 |  | N/A |  |  |  | N/A | N/A | N/A | Collect hardware from the AMF | 0.68
| Move Pipework to Divertor Port | Movement | 0.69444 | 351.7917 |  | N/A | hardware transporter (Loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Divertor Handling system Stored; Divertor Pipework handling system collected; Left Divertor pipe module collected; Transport Moved to Lower Port | Total | 0 | 351.7917 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Divertor pipe module collected; Divertor cassette handling System Moved to Lower Port | Connect Right divertor pipe module | Trigger | 0 | 370.3568 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Hardware issue | Movement | 0.23148 | 370.5882 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Hardware issue | 50 | 0.06 | 0.23148 |  | N/A
| Collect blanket Pipe Module | Logistics | 0.88 | 371.4682 |  | N/A |  |  |  | N/A | N/A | N/A | Store hardware in the AMF | 0.88
| Move hardware transporter to Divertor Port | Movement | 0.69444 | 372.1627 |  | N/A | hardware transporter (loaded) | AMF Equipment Issue | Divertor Port | 50 | 0.02 | 0.69444 |  | N/A
| Divertor pipe module collected; Divertor cassette handling System Moved to Lower Port | Total | 0 | 372.1627 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Store Divertor pipework handling system; Collect Shield module handling system & shield modules; Move to Lower Port | Connect Left divertor pipe module | Trigger | 0 | 388.6518 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Equipment Receipt | Movement | 0.23148 | 388.8833 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store cassette transporter | Logistics | 0.88 | 389.7633 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Issue | Movement | 0.027778 | 389.7911 |  | N/A | hardware transporter (no load) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect shield module handling system | Logistics | 0.58 | 390.3711 |  | N/A |  |  |  | N/A | N/A | N/A | Collect interface hardware | 0.58
| Move shield modules to Divertor Port | Movement | 0.41667 | 390.7877 |  | N/A | hardware transporter (loaded) | Hardware Stillage | Divertor Port | 30 | 0.02 | 0.41667 |  | N/A
| Store Divertor pipework handling system; Collect Shield module handling system & shield modules; Move to Lower Port | Total | 0 | 390.7877 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Store Divertor pipework handling system; Collect Vacuum Plumping system handling system & vaccum pumping sled; move to port | Connect Central divertor pipe module | Trigger | 0 | 406.9469 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Equipment Receipt | Movement | 0.23148 | 407.1783 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store cassette transporter | Logistics | 0.88 | 408.0583 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Issue | Movement | 0.027778 | 408.0861 |  | N/A | hardware transporter (no load) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect vacuum pumping interface and pumping hardware | Logistics | 0.58 | 408.6661 |  | N/A |  |  |  | N/A | N/A | N/A | Collect interface hardware | 0.58
| Move pumping equipment to Divertor Port | Movement | 0.41667 | 409.0828 |  | N/A | hardware transporter (loaded) | Hardware Stillage | Divertor Port | 30 | 0.02 | 0.41667 |  | N/A
| Store Divertor pipework handling system; Collect Vacuum Plumping system handling system & vaccum pumping sled; move to port | Total | 0 | 409.0828 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Store Shield Module handling system; Collect in-port diagnostic system; move to port | Retract sheild module handling system | Trigger | 0 | 429.9569 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Equipment Receipt | Movement | 0.23148 | 430.1883 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store cassette transporter | Logistics | 0.88 | 431.0683 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Issue | Movement | 0.027778 | 431.0961 |  | N/A | hardware transporter (no load) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect vacuum pumping interface and pumping hardware | Logistics | 0.58 | 431.6761 |  | N/A |  |  |  | N/A | N/A | N/A | Collect interface hardware | 0.58
| Move pumping equipment to Divertor Port | Movement | 0.41667 | 432.0928 |  | N/A | hardware transporter (loaded) | Hardware Stillage | Divertor Port | 30 | 0.02 | 0.41667 |  | N/A
| Store Shield Module handling system; Collect in-port diagnostic system; move to port | Total | 0 | 432.0928 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Store Pumping system handling system; Collect threshold rail lifting interface; Move to Lower Port | Retract pumping sled handling system | Trigger | 0 | 444.6013 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Equipment Receipt | Movement | 0.23148 | 444.8328 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store cassette transporter | Logistics | 0.88 | 445.7128 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Issue | Movement | 0.027778 | 445.7406 |  | N/A | hardware transporter (no load) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Port Plate & Pipework | Logistics | 0.58 | 446.3206 |  | N/A |  |  |  | N/A | N/A | N/A | Collect interface hardware | 0.58
| Move Port Plate to Divertor Port | Movement | 0.41667 | 446.7372 |  | N/A | hardware transporter (loaded) | Hardware Stillage | Divertor Port | 30 | 0.02 | 0.41667 |  | N/A
| Store Pumping system handling system; Collect threshold rail lifting interface; Move to Lower Port | Total | 0 | 446.7372 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Store diagnostic handling system; Collect port inspection system; Move to Lower Port | Recover diagnostic handling system | Trigger | 0 | 454.5952 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Equipment Receipt | Movement | 0.23148 | 454.8267 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store cassette transporter | Logistics | 0.88 | 455.7067 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Issue | Movement | 0.027778 | 455.7345 |  | N/A | hardware transporter (no load) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Port Inspection System | Logistics | 0.58 | 456.3145 |  | N/A |  |  |  | N/A | N/A | N/A | Collect interface hardware | 0.58
| Move Port Plate to Divertor Port | Movement | 0.41667 | 456.7311 |  | N/A | hardware transporter (loaded) | Hardware Stillage | Divertor Port | 30 | 0.02 | 0.41667 |  | N/A
| Store diagnostic handling system; Collect port inspection system; Move to Lower Port | Total | 0 | 456.7311 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Store threshold rail handling system; Collect vacuum closure plate & handling system; Move to Lower Port | Recover Rails from the port | Trigger | 0 | 465.5091 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Equipment Receipt | Movement | 0.23148 | 465.7406 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store cassette transporter | Logistics | 0.88 | 466.6206 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Issue | Movement | 0.027778 | 466.6483 |  | N/A | hardware transporter (no load) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Port Plate & Pipework | Logistics | 0.58 | 467.2283 |  | N/A |  |  |  | N/A | N/A | N/A | Collect interface hardware | 0.58
| Move Port Plate to Divertor Port | Movement | 0.41667 | 467.645 |  | N/A | hardware transporter (loaded) | Hardware Stillage | Divertor Port | 30 | 0.02 | 0.41667 |  | N/A
| Store threshold rail handling system; Collect vacuum closure plate & handling system; Move to Lower Port | Total | 0 | 467.645 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Store vacuum closure plate handling system; Collect CCS handling system; Move to Lower Port | Retract Vaccum closure plate lifting interface | Trigger | 0 | 484.3646 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Equipment Receipt | Movement | 0.23148 | 484.5961 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store cassette transporter | Logistics | 0.88 | 485.4761 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Issue | Movement | 0.027778 | 485.5039 |  | N/A | hardware transporter (no load) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Port Plate & Pipework | Logistics | 0.58 | 486.0839 |  | N/A |  |  |  | N/A | N/A | N/A | Collect interface hardware | 0.58
| Move Port Plate to Divertor Port | Movement | 0.41667 | 486.5006 |  | N/A | hardware transporter (loaded) | Hardware Stillage | Divertor Port | 30 | 0.02 | 0.41667 |  | N/A
| Store vacuum closure plate handling system; Collect CCS handling system; Move to Lower Port | Total | 0 | 486.5006 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Store Port Inspection system; Collect Bioshield plug handling system; collect bioshield plug; move to port | Recovery Port Inspection System and store in the AMF | Trigger | 0 | 492.5369 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move hardware transporter to AMF Equipment Receipt | Movement | 0.23148 | 492.7683 |  | N/A | hardware transporter (empty stillage) | Divertor Port | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store port inspection system | Logistics | 0.88 | 493.6483 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in the AMF | 0.88
| Move hardware transporter to AMF Equipment Issue | Movement | 0.027778 | 493.6761 |  | N/A | hardware transporter (no load) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Bioshield interface hardware | Logistics | 0.58 | 494.2561 |  | N/A |  |  |  | N/A | N/A | N/A | Collect interface hardware | 0.58
| Move Divertor Port Pipework to bioshield stillage | Movement | 0.23148 | 494.4876 |  | N/A | hardware transporter (empty stillage) | AMF Equipment Issue | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Collect Bioshield plug | Logistics | 0.58 | 495.0676 |  | N/A |  |  |  | N/A | N/A | N/A | Collect interface hardware | 0.58
| Move Bioshield Plug to Divertor Port | Movement | 0.41667 | 495.4843 |  | N/A | hardware transporter (loaded) | Hardware Stillage | Divertor Port | 30 | 0.02 | 0.41667 |  | N/A
| Store Port Inspection system; Collect Bioshield plug handling system; collect bioshield plug; move to port | Total | 0 | 495.4843 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A

## Upper Cask Summary
|  |  | Cask Vertical Port Maintenance Interval |  |  |  |  | Impact of | Duration of a Long
|  |  | Blanket Maintenance |  | Failures |  | Total
|  |  | Blanket Removal | Blanket Installation | RM Equipment | Welding Operations | Maintenance Cycle | Lower Port Hot Cell Ops | Maintenance Interval
Single Port | Operations | hrs | 151.819 | 300.632 | 35.9214 | 225.8333 | 714.2057 | 906.8095
|  | %age | 71.43% | 82.76% | 36.06% | 71.61% | 72.08% | 77.97%
| Logistics | hrs | 51.3867 | 52.1211 | 63.6897 | 42.6817 | 209.8791 | 134.4096
|  | %age | 24.18% | 14.35% | 63.94% | 13.53% | 21.18% | 11.56%
|  | Idle time | 9.3348 | 10.5106 | 0 | 46.8636 | 66.7089 | 121.8332
|  | %age | 4.392% | 2.893% | 0% | 14.86% | 6.733% | 10.48%
| Total Time | hrs | 212.5405 | 363.2637 | 99.6111 | 315.3786 | 990.7938 | 1163.0523 | 1163.0523
|  | days | 8.8559 | 15.136 | 4.1505 | 13.1408 | 41.2831 | 48.4605 | 48.4605
| Elapsed Time | hrs | 350.6918 | 599.385 | 164.3583 | 520.3746 | 1634.8097 | 1919.0363 | 1919.0363
|  | Days | 14.6122 | 24.9744 | 6.8483 | 21.6823 | 68.1171 | 79.9598 | 79.9598
|  | Months | 0.48707 | 0.83248 | 0.22828 | 0.72274 | 2.2706 | 2.6653 | 2.6653
|  | % | 21.45% | 36.66% | 10.05% | 31.83% | 100% | 100% | 100%
All 18 Ports in series | Operations | hrs | 2732.7424 | 5411.3759 | 646.5855 | 3305.2016 | 12095.9054 | 11513.0551
|  | days | 113.8643 | 225.474 | 26.9411 | 137.7167 | 503.9961 | 479.7106
| Logistics | hrs | 924.96 | 938.18 | 1146.4141 | 596.4467 | 3606.0009 | 1829.9472
|  | days | 38.54 | 39.0908 | 47.7673 | 24.8519 | 150.25 | 76.2478
|  | Idle time | 168.0262 | 189.19 | 0 | 545.2934 | 902.5096 | 200.8735
| Total Time | hrs | 3825.7286 | 6538.7459 | 1792.9996 | 4446.9417 | 16604.4158 | 13543.8758 | 16604.4158
|  | days | 159.4054 | 272.4477 | 74.7083 | 185.2892 | 691.8507 | 564.3282 | 691.8507
| Elapsed Time | hrs | 6312.4521 | 10788.9308 | 2958.4494 | 7337.4538 | 27397.2861 | 22347.3951 | 27397.2861
|  | Days | 263.0188 | 449.5388 | 123.2687 | 305.7272 | 1141.5536 | 931.1415 | 1141.5536
|  | Months | 8.7673 | 14.9846 | 4.109 | 10.1909 | 38.0518 | 31.038 | 38.0518
|  | % | 23.04% | 39.38% | 10.8% | 26.78% | 100% | 100% | 100%
|  |  | -1366.3712 | -2705.688
All 18 Ports with 2 Systems | Operations | hrs | 1366.3712 | 2705.688 | 323.2927 | 1652.6008 | 6047.9527 | 8161.2854
|  | days | 56.9321 | 112.737 | 13.4705 | 68.8584 | 251.998 | 340.0536
| Logistics | hrs | 462.48 | 469.09 | 573.2071 | 298.2234 | 1803.0004 | 1209.6863
|  | days | 19.27 | 19.5454 | 23.8836 | 12.426 | 75.125 | 50.4036
|  | Idle time | 84.0131 | 94.595 | 0 | 272.6467 | 451.2548 | 1096.499
| Total Time | hrs | 1912.8643 | 3269.373 | 896.4998 | 2223.4709 | 8302.2079 | 10467.4708 | 10467.4708
|  | days | 79.7027 | 136.2239 | 37.3542 | 92.6446 | 345.9253 | 436.1446 | 436.1446
| Elapsed Time | hrs | 3156.2261 | 5394.4654 | 1479.2247 | 3668.7269 | 13698.6431 | 17271.3268 | 17271.3268
|  | Days | 131.5094 | 224.7694 | 61.6344 | 152.8636 | 570.7768 | 719.6386 | 719.6386
|  | Months | 6.5755 | 11.2385 | 3.0817 | 7.6432 | 28.5388 | 23.988 | 28.5388
|  | % | 23.04% | 39.38% | 10.8% | 26.78% | 100% | 100% | 100%
[7 empty] | 0.05967 | 0 | 0.05967
All 18 Ports with 3 Systems | Operations | hrs | 910.9141 | 1803.792 | 215.5285 | 1101.7339 | 4031.9685 | 5440.8569
|  | days | 37.9548 | 75.158 | 8.9804 | 45.9056 | 167.9987 | 181.2389
| Logistics | hrs | 308.32 | 312.7267 | 382.138 | 198.8156 | 1202.0003 | 806.4575
|  | days | 12.8467 | 13.0303 | 15.9224 | 8.284 | 50.0833 | 27.3014
|  | Idle time | 56.0087 | 63.0633 | 0 | 181.7645 | 300.8365 | 730.9994
| Total Time | hrs | 1275.2429 | 2179.582 | 597.6665 | 1482.3139 | 5534.8053 | 6978.3138 | 6978.3138
|  | days | 53.1351 | 90.8159 | 24.9028 | 61.7631 | 230.6169 | 238.7161 | 238.7161
| Elapsed Time | hrs | 2104.1507 | 3596.3103 | 986.1498 | 2445.8179 | 9132.4287 | 11514.2178 | 11514.2178
|  | Days | 87.6729 | 149.8463 | 41.0896 | 101.9091 | 380.5179 | 479.7591 | 479.7591
|  | Months | 2.9224 | 4.9949 | 1.3697 | 3.397 | 12.6839 | 15.992 | 15.992
|  | % | 15.36% | 26.25% | 7.199% | 17.85% | 66.67% | 100% | 100%
All 18 Ports with 4 Systems | Operations | hrs | 759.0951 | 1503.16 | 179.6071 | 918.1116 | 3359.9737 | 4534.0474
|  | days | 31.629 | 62.6317 | 7.4836 | 38.2546 | 139.9989 | 130.3673
| Logistics | hrs | 256.9333 | 260.6056 | 318.4484 | 165.6796 | 1001.6669 | 672.048
|  | days | 10.7056 | 10.8586 | 13.2687 | 6.9033 | 41.7361 | 19.887
|  | Idle time | 46.6739 | 52.5528 | 0 | 151.4704 | 250.6971 | 609.1661
| Total Time | hrs | 1062.7024 | 1816.3183 | 498.0555 | 1235.2616 | 4612.3377 | 5815.2615 | 5815.2615
|  | days | 44.2793 | 75.6799 | 20.7523 | 51.4692 | 192.1807 | 175.2724 | 192.1807
| Elapsed Time | hrs | 1753.4589 | 2996.9252 | 821.7915 | 2038.1816 | 7610.3573 | 9595.1815 | 9595.1815
|  | Days | 73.0608 | 124.8719 | 34.2413 | 84.9242 | 317.0982 | 399.7992 | 399.7992
|  | Months | 2.4354 | 4.1624 | 1.1414 | 2.8308 | 10.5699 | 13.3266 | 13.3266
|  | % | 12.8% | 21.88% | 5.999% | 14.88% | 55.56% | 100% | 100%
All 18 Ports with 6 Systems | Operations | hrs | 455.4571 | 901.896 | 107.7642 | 550.8669 | 2015.9842 | 2720.4285
|  | days | 18.9774 | 37.579 | 4.4902 | 22.9528 | 83.9993 | 65.0463
| Logistics | hrs | 154.16 | 156.3633 | 191.069 | 99.4078 | 601.0001 | 403.2288
|  | days | 6.4233 | 6.5151 | 0.63938 | 0.13413 | 25.0417 | 10.1063
|  | Idle time | 28.0044 | 31.5317 | 0 | 90.8822 | 150.4183 | 365.4997
| Total Time | hrs | 637.6214 | 1089.791 | 298.8333 | 741.157 | 2767.4026 | 3489.1569 | 3489.1569
|  | days | 26.5676 | 45.408 | 12.4514 | 30.8815 | 115.3084 | 90.0816 | 115.3084
| Elapsed Time | hrs | 1052.0754 | 1798.1551 | 493.0749 | 1222.909 | 4566.2144 | 5757.1089 | 5757.1089
|  | Days | 43.8365 | 74.9231 | 20.5448 | 50.9545 | 190.2589 | 239.8795 | 239.8795
|  | Months | 1.4612 | 2.4974 | 0.68483 | 1.6985 | 6.342 | 7.996 | 7.996
|  | % | 23.04% | 39.38% | 10.8% | 26.78% | 100% | 100% | 100%
Note on C13: Farquhar, Iain: Calculated by factoring a efficiently factor of 0.67, as well as an allowance for both un-planned maintenance and logistics tasks, equal to an additional 10%.
Note on C25: Farquhar, Iain: Calculated by factoring a efficiently factor of 0.67, as well as an allowance for both un-planned maintenance and logistics tasks equal to an additional 10%.
Note on C37: Farquhar, Iain: Calculated by factoring a efficiently factor of 0.67, as well as an allowance for both un-planned maintenance and logistics tasks equal to an additional 10%.
Note on C49: Farquhar, Iain: Calculated by factoring a efficiently factor of 0.67, as well as an allowance for both un-planned maintenance and logistics tasks equal to an additional 10%.
Note on C61: Farquhar, Iain: Calculated by factoring a efficiently factor of 0.67, as well as an allowance for both un-planned maintenance and logistics tasks equal to an additional 10%.
Note on C73: Farquhar, Iain: Calculated by factoring a efficiently factor of 0.67, as well as an allowance for both un-planned maintenance and logistics tasks equal to an additional 10%.

## Upper Cask Critical Path (hidden)
[5 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies
Group | Activity | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack
bioshield and CCD Removal | Blanket Removal Required | Operation | 0 | 0 | Blanket Removal Required | 0 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Deploy Overhead Crane | Logistics | 0.5 | 0.5 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Equipment from Store | 0.5 |  | N/A | N/A
| Move Overhead Crane to Upper Port | Movement | 0.069444 | 0.56944 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A
| Open bioshield | Operation | 0.56667 | 1.1361 | Open Bioshield | 0.56667 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move Overhead Crane to bioshield Stillage | Movement | 0.41667 | 1.5528 |  | N/A | Overhead Crane (Loaded) | Vertical Port | bioshield Stillage | 30 | 0.02 | 0.41667 |  | N/A |  | N/A | N/A
| Store bioshield | Logistics | 0.68 | 2.2328 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68 |  | N/A | N/A
| Move Overhead Crane to AMF Equipment Issue | Movement | 0.027778 | 2.2606 |  | N/A | Overhead Crane (Unloaded) | bioshield Stillage | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A |  | N/A | N/A
| Collect Maintenance Cask | Logistics | 0.68 | 2.9406 |  | N/A |  |  |  | N/A | N/A | N/A | Collect bioshield / Equipment Platform | 0.68 |  | N/A | N/A
| Move Overhead Crane to Upper Port | Movement | 0.69444 | 3.635 |  | N/A | Overhead Crane (Loaded) | AMF Equipment Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A
| Install Maintenance Cask | Logistics | 3.9 | 7.535 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Maintenance Cask | 3.9 |  | N/A | N/A
| Move Overhead Crane to AMF Equipment Issue | Movement | 0.069444 | 7.6044 |  | N/A | Overhead Crane (Unloaded) | Vertical Port | AMF Equipment Issue | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A
| Collect Equipment Cask Platform | Logistics | 0.68 | 8.2844 |  | N/A |  |  |  | N/A | N/A | N/A | Collect bioshield / Equipment Platform | 0.68 |  | N/A | N/A
| Move Overhead Crane to Equipment Stillage | Movement | 0.69444 | 8.9789 |  | N/A | Overhead Crane (Loaded) | AMF Equipment Issue | Equipment Stillage | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A
| Install Equipment Platform | Logistics | 0.68 | 9.6589 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68 |  | N/A | N/A
| Move Cask Transporter A to Equipment Stillage | Movement | 0.69444 | 10.3533 |  | N/A | Cask Transporter (loaded) | AMF Equipment Issue | Equipment Stillage | 50 | 0.02 | 0.69444 |  | N/A | Equipment Cask 1 collected | 0.48 | 9.1789
| Dock Equipment Cask 1 | Logistics | 1.64 | 11.9933 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Equipment Cask | 1.64 |  | N/A | N/A
| Deploy health physics system | Logistics | 1.64 | 13.6333 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Equipment Cask | 1.64 |  | N/A | N/A
| Perform health physics checks | Operation | 6.7722 | 20.4056 | Perform Health Physics Checks | 6.7722 |  |  |  | N/A | N/A | N/A | Dock Equipment Cask | N/A |  | N/A | N/A
| Recovery health physics system | Logistics | 1.64 | 22.0456 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Equipment Cask | 1.64 |  | N/A | N/A
| Deploy CCD Equipment | Logistics | 0.38 | 22.4256 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Open Contamination Control Door | Operation | 0.6 | 23.0256 | Open Contamination Control Door | 0.6 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store CCD in Maintenance Cask | Logistics | 0.63 | 23.6556 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 |  | N/A | N/A
| Store CCD Equipment in Equipment Cask 1 | Logistics | 0.38 | 24.0356 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
ECH Removal | Deploy port inspection system | Logistics | 0.38 | 24.4156 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Perform port inspection survey | Operation | 5.7722 | 30.1878 | Perform engineering checks | 5.7722 |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | N/A |  | N/A | N/A
| Retract port inspection system | Logistics | 0.38 | 30.5678 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Deploy Multifunction Manipulator for ECH | Logistics | 0.38 | 30.9478 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Disconnect ECH using Multifunction Manipulator | Operation | 9.425 | 40.3728 | Disconnect ECH | 9.425 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Multifunction Manipulator in Equipment Cask 1 | Logistics | 0.38 | 40.7528 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Deploy Component Carrier | Logistics | 0.38 | 41.1328 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Extract ECH | Operation | 2.175 | 43.3078 | Extract ECH | 2.175 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store ECH in Hardware Cask 1 | Logistics | 0.63 | 43.9378 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | Hardware Cask 1 collected & docked | 14.7993 | 28.5085
| Store Component Carrier in Equipment Cask 1 | Logistics | 0.38 | 44.3178 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Deploy port inspection system | Logistics | 0.38 | 44.6978 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Perform port inspection survey | Operation | 5.7722 | 50.47 | Perform engineering checks | 5.7722 |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | N/A |  | N/A | N/A
| Retract port inspection system | Logistics | 0.38 | 50.85 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
Closure Plate Removal | Deploy Multifunction Manipulator with Closure Equipment | Logistics | 0.38 | 51.23 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Disconnect Port Closure Plate using Multifunction Manipulator | Operation | 29.3333 | 80.5633 | Disconnect Port Closure Plate | 29.3333 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Multifunction Manipulator & Closure Equipment in Equipment Cask 1 | Logistics | 0.38 | 80.9433 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Deploy Component Carrier | Logistics | 0.38 | 81.3233 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Extract Port Closure Plate | Operation | 0.375 | 81.6983 | Extract Port Closure Plate | 0.375 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Closure Plate in Hardware Cask 2 | Logistics | 0.63 | 82.3283 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | ECH & Hardware Cask 1 stored; Hardware Cask 2 collected; Hardware Cask 2 docked | 50.7593 | 30.9391
| Store Component Carrier in Equipment Cask 1 | Logistics | 0.38 | 82.7083 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
Shield Plug & Fixations Removal | Deploy port inspection system | Logistics | 0.38 | 83.0883 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Perform port inspection survey | Operation | 5.7722 | 88.8606 | Perform engineering checks | 5.7722 |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | N/A |  | N/A | N/A
| Retract port inspection system | Logistics | 0.38 | 89.2406 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Deploy Multifunction Manipulator for Shield Plug Flange | Logistics | 0.38 | 89.6206 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Disconnect Shield Plug Pipe Flange using Multifunction Manipulator | Operation | 3.8333 | 93.4539 | Disconnect Shield Plug Pipe Flange | 3.8333 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Multifunction Manipulator in Equipment Cask 1 | Logistics | 0.38 | 93.8339 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Deploy Shield Plug & Fixations Equip | Logistics | 0.38 | 94.2139 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Disconnect & extract Shield Plug and Fixations | Operation | 3.925 | 98.1389 | Disconnect & extract Shield Plug and Fixations | 3.925 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Shield Plug & Fixations in Hardware Cask 3 | Logistics | 0.63 | 98.7689 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | Closure Plate & Hardware Cask 2 stored; Hardware Cask 3 collected; Hardware Cask 3 docked | 89.1776 | 8.9613
| Store Shield Plug & Fixations Equip. in Equipment Cask 1 | Logistics | 0.38 | 99.1489 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Deploy engineering survey equipment | Logistics | 0 | 99.1489 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask
| perfrom engineering survey | Operation | 5.7722 | 104.9211 | Perform engineering checks | 5.7722 |  |  |  | N/A | N/A | N/A
| Recover engineering survey equipment | Logistics | 0 | 104.9211 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask
COB Blanket Pipework Disconnection | Deploy Multifunction Manipulator for Multipipe Flange 1 | Logistics | 0.38 | 105.3011 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Disconnect Multipipe Flange 1 using Multifunction Manipulator | Operation | 6.83 | 112.1311 | Disconnect Multipipe Flange & Access Lid | 6.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Multifunction Manipulator in Equipment Cask 2 | Logistics | 0.38 | 112.5111 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 | Shield Plug & Fixations & Hardware Cask 3 stored; Equipment Cask 2 collected; Equipment cask 2 docked | 105.8581 | 6.273
| Deploy Service Joint System | Logistics | 0.38 | 112.8911 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Cut COB Pipe joint | Operation | 1.0499 | 113.941 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Service Joint System in Equipment Cask 2 | Logistics | 0.38 | 114.321 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
COB Blanket Pipework Removal | Deploy Pipe module lifting attachment | Logistics | 0.38 | 114.701 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Extract COB Pipe Module | Operation | 0.725 | 115.426 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store COB Pipe Module In Hardware Cask 4 | Logistics | 0.63 | 116.056 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | Equipment Cask 1 stored; Hardware Cask 4 collected; Hardware Cask 4 docked | 111.6826 | 3.7434
| Store Pipe Lifter in Equipment Cask 2 | Logistics | 0.38 | 116.436 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
LOB Blanket Pipework Disconnection | Deploy Multifunction Manipulator | Logistics | 0.38 | 116.816 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Disconnect Multipipe Flange 2 using Multifunction Manipulator | Operation | 6.83 | 123.646 | Disconnect Multipipe Flange & Access Lid | 6.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Multifunction Manipulator in Equipment Cask 2 | Logistics | 0.38 | 124.026 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Deploy Service Joint System | Logistics | 0.38 | 124.406 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Cut LOB Pipe joint | Operation | 1.0499 | 125.4559 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Service Joint System in Equipment Cask 2 | Logistics | 0.38 | 125.8359 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
LOB Blanket Pipework Removal | Deploy Pipe module lifting attachment | Logistics | 0.38 | 126.2159 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Extract LOB Pipe Module | Operation | 0.725 | 126.9409 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store LOB Pipe Module In Hardware Cask 4 | Logistics | 0.63 | 127.5709 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | COB Pipe Module stored; Hardware Cask 4 docked | 121.362 | 5.579
| Store Pipe Lifter in Equipment Cask 2 | Logistics | 0.38 | 127.9509 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
ROB Blanket Pipework Disconnection | Deploy Multifunction Manipulator | Logistics | 0.38 | 128.3309 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Disconnect Multipipe Flange 3 using Multifunction Manipulator | Operation | 6.83 | 135.1609 | Disconnect Multipipe Flange & Access Lid | 6.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Multifunction Manipulator in Equipment Cask 2 | Logistics | 0.38 | 135.5409 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Deploy Service Joint System | Logistics | 0.38 | 135.9209 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Cut ROB Pipe joint | Operation | 1.0499 | 136.9709 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Service Joint System in Equipment Cask 2 | Logistics | 0.38 | 137.3509 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
ROB Blanket Pipework Removal | Deploy Pipe module lifting attachment | Logistics | 0.38 | 137.7309 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Extract ROB Pipe Module | Operation | 0.725 | 138.4559 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store ROB Pipe Module In Hardware Cask 4 | Logistics | 0.63 | 139.0859 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | LOB Pipe Module stored; Hardware Cask 4 docked | 132.8769 | 5.579
| Store Pipe Lifter in Equipment Cask 2 | Logistics | 0.38 | 139.4659 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
LIB Blanket Pipework Disconnection | Deploy Multifunction Manipulator | Logistics | 0.38 | 139.8459 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Disconnect Multipipe Flange 4 using Multifunction Manipulator | Operation | 6.83 | 146.6759 | Disconnect Multipipe Flange & Access Lid | 6.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Multifunction Manipulator in Equipment Cask 2 | Logistics | 0.38 | 147.0559 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Deploy Service Joint System | Logistics | 0.38 | 147.4359 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Cut LIB Pipe joint | Operation | 1.0499 | 148.4858 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Service Joint System in Equipment Cask 2 | Logistics | 0.38 | 148.8658 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
LIB Blanket Pipework Removal | Deploy Pipe module lifting attachment | Logistics | 0.38 | 149.2458 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Extract LIB Pipe Module | Operation | 0.725 | 149.9708 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store LIB Pipe Module In Hardware Cask 4 | Logistics | 0.63 | 150.6008 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | ROB Pipe Module stored; Hardware Cask 4 docked | 144.3918 | 5.579
| Store Pipe Lifter in Equipment Cask 2 | Logistics | 0.38 | 150.9808 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
RIB Blanket Pipework Disconnection | Deploy Multifunction Manipulator | Logistics | 0.38 | 151.3608 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Disconnect Multipipe Flange 5 using Multifunction Manipulator | Operation | 6.83 | 158.1908 | Disconnect Multipipe Flange & Access Lid | 6.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Multifunction Manipulator in Equipment Cask 2 | Logistics | 0.38 | 158.5708 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Deploy Service Joint System | Logistics | 0.38 | 158.9508 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Cut RIB Pipe joint | Operation | 1.0499 | 160.0007 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Service Joint System in Equipment Cask 2 | Logistics | 0.38 | 160.3807 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
RIB Blanket Pipework Removal | Deploy Pipe module lifting attachment | Logistics | 0.38 | 160.7607 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Extract RIB Pipe Module | Operation | 0.725 | 161.4857 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store RIB Pipe Module In Hardware Cask 4 | Logistics | 0.63 | 162.1157 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | LIB Pipe Module stored; Hardware Cask 4 docked | 155.9067 | 5.579
| Store Pipe Lifter in Equipment Cask 2 | Logistics | 0.38 | 162.4957 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Un-Dock Equipment Cask 2 | Logistics | 2.54 | 165.0357 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Equipment Cask | 2.54 |  | N/A | N/A
Blanket Removal | Dock Equipment Cask 3 | Logistics | 1.64 | 168.3501 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Equipment Cask | 1.64 | Equipment Cask 3 collected; Equipment Cask 3 moved to equipment stillage | 166.7101 | -1.6744
| Deploy Blanket Transporter | Logistics | 0.38 | 168.7301 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Extract COB Blanket Segment | Operation | 5.74 | 178.9105 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A | Lower Port COB Pipe Module Removed | 173.1705 | -4.4403
| Store COB Blanket Segment in Hardware Cask 5 | Logistics | 0.63 | 179.5405 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | RIB Pipe Module stored; Hardware Cask 4 stored; Hardware Cask 5 collected; Hardware Cask 5 docked | 168.502 | 10.4085
| Deploy Blanket Transporter | Logistics | 0.5 | 180.0405 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Equipment from Store | 0.5 |  | N/A | N/A
| Extract LOB Blanket Segment | Operation | 5.74 | 189.0005 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A | Lower Port LOB Pipe Module Removed | 183.2605 | -3.22
| Store LOB Blanket Segment in Hardware Cask 6 | Logistics | 0.63 | 189.6305 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | Equipment Cask 2 stored; Hardware Cask 6 Collected; Hardware Cask 6 docked | 168.8772 | 20.1233
| Deploy Blanket Transporter | Logistics | 0.5 | 190.1305 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Equipment from Store | 0.5 |  | N/A | N/A
| Extract ROB Blanket Segment | Operation | 5.74 | 195.8705 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A | Lower Port ROB Pipe Module Removed | 184.9305 | 5.2
| Store ROB Blanket Segment in Hardware Cask 5 | Logistics | 0.63 | 196.5005 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | COB Blanket Segment stored; Hardware Cask 5 docked | 184.8464 | 11.0241
| Deploy Blanket Transporter | Logistics | 0.5 | 197.0005 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Equipment from Store | 0.5 |  | N/A | N/A
| Extract LIB Blanket Segment | Operation | 5.74 | 202.7405 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A | Lower Port LIB Pipe Module Removed | 191.0305 | 5.97
| Store LIB Blanket Segment in Hardware Cask 6 | Logistics | 0.63 | 203.3705 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | LOB Blanket Segment stored; Hardware Cask 6 docked | 194.9364 | 7.8041
| Deploy Blanket Transporter | Logistics | 0.5 | 203.8705 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Equipment from Store | 0.5 |  | N/A | N/A
| Extract RIB Blanket Segment | Operation | 5.74 | 209.6105 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A | Lower Port RIB Pipe Module Removed | 192.7005 | 11.1699
| Store RIB Blanket Segment in Hardware Cask 5 | Logistics | 0.63 | 210.2405 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | ROB Blanket Segment stored; Hardware Cask 5 docked | 201.8064 | 7.8041
| Un-Dock Hardware Cask 5 | Logistics | 2.3 | 212.5405 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3 |  | N/A | N/A
Blanket Removal Complete | End Time |  | 212.5405
| Operational Time |  | 151.819 |  | 71.43%
| Logistical Time |  | 48.72 |  | 32.09%
| Movements |  | 2.6667 |  | 5.473%
Inspect and re-condition Upper Port | Blanket Installation Required | Operation | 0 | 0 | Blanket Removal Required | 0 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Deploy inspection system | Movement | 0.69444 | 5.8346 |  | N/A | Overhead Crane (loaded) | AMF Equipment Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A | Port Inspection System Collected; Hardware Cask 7 docked | 5.1402 | -5.1402
| Inspect the port | Operation | 8.5 | 14.3346 | Inspect the port | 8.5 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Re-condition IVC hardware/fixations | Operation | 8.5 | 22.8346 | Clean/re-condition port hardware | 8.5 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Inspection system in equipment cask | Logistics | 0.38 | 23.2146 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| un-dock inspection cask | Logistics | 2.54 | 25.7546 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Equipment Cask | 2.54 |  | N/A | N/A
Blanket Installation | Dock equipment cask | Logistics | 1.4 | 27.1546 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4 |  | N/A | N/A
| Collect Blanket Segment 5 from Hardware Cask 6 | Logistics | 0.6 | 27.7546 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 |  | N/A | N/A
| Deploy Blanket Transporter | Logistics | 0.38 | 28.1346 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Install RIB Blanket Segment | Operation | 4.33 | 32.4646 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A | RIB Blanket Segment Collected; Hardware Cask 6 docked | 5.1402 | 22.9944
| Collect Blanket Segment 4 from Hardware Cask 5 | Logistics | 0.6 | 33.0646 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 |  | N/A | N/A
| Deploy Blanket Transporter | Logistics | 0.38 | 33.4446 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Install LIB Blanket Segment | Operation | 4.33 | 37.7746 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A | LIB Blanket Segment Collected; Hardware Cask 5 docked | 32.8948 | 0.54981
| Collect Blanket Segment 3 from Hardware Cask 6 | Logistics | 0.6 | 38.3746 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 |  | N/A | N/A
| Deploy Blanket Transporter | Logistics | 0.38 | 38.7546 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Install ROB Blanket Segment | Operation | 4.33 | 43.0846 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A | ROB Blanket Segment Collected; Hardware Cask 6 docked | 37.6048 | 1.1498
| Collect Blanket Segment 2 from Hardware Cask 5 | Logistics | 0.6 | 43.6846 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 |  | N/A | N/A
| Deploy Blanket Transporter | Logistics | 0.38 | 44.0646 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Install LOB Blanket Segment | Operation | 4.33 | 48.3946 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A | LOB Blanket Segment Collected; Hardware Cask 5 docked | 42.9148 | 1.1498
| Collect Blanket Segment 1 from Hardware Cask 6 | Logistics | 0.6 | 48.9946 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 |  | N/A | N/A
| Deploy Blanket Transporter | Logistics | 0.38 | 49.3746 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Install COB Blanket Segment | Operation | 4.33 | 53.7046 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A | COB Blanket Segment Collected; Hardware Cask 6 docked | 48.2248 | 1.1498
| Store Blanket transporter in equipment cask | Logistics | 0.38 | 54.0846 | Install Blanket Segment | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Un-dock equipment cask 6 | Logistics | 2.54 | 56.6246 | Install Blanket Segment | N/A |  |  |  | N/A | N/A | N/A | Un-dock equipment cask | 2.54 |  | N/A | N/A
Install RIB Pipe Module | Dock Equipment Cask | Logistics | 1.64 | 58.2646 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Equipment Cask | 1.64 |  | N/A | N/A
| Collect RIB Pipe Module from Hardware Cask 3 | Logistics | 0.6 | 58.8646 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 |  | N/A | N/A
| Collect RIB Pipe Module from Hardware Cask 4 | Logistics | 0.6 | 59.4646 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 | Equipment Cask 6 stored; Equipment Cask 2 Collected; Hardware Cask 2 docked; RIB Pipe Module Collected | 33.9539 | 24.9107
| Deploy Pipe module lifting attachment | Logistics | 0.38 | 59.8446 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Install RIB Pipe Module | Operation | 4.095 | 63.9396 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Pipe Lifter in Equipment Cask 1 | Logistics | 0.38 | 64.3196 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Undock hardware cask 2 | Logistics | 2.3 | 66.6196 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock Hardware CAsk | 2.3 |  | N/A | N/A
Connect RIB Pipe Module | Deploy Service Joint System from Equipment Cask 2 | Logistics | 0.38 | 66.9996 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Weld RIB Pipe Module | Operation | 24.0227 | 91.0224 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Service Joint System in Equipment Cask 2 | Logistics | 0.38 | 91.4024 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Deploy Multifunction Manipulator | Logistics | 0.38 | 91.7824 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Connect Multipipe Flange 5 using Multifunction Manipulator | Operation | 7.83 | 99.6124 | Connect Multipipe Flange & Access Lid | 7.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Multifunction Manipulator in Equipment Cask 2 | Logistics | 0.38 | 99.9924 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
Install LIB Pipe Module | Collect LIB Pipe Module from Hardware Cask 4 | Logistics | 0.6 | 100.5924 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 | Hardware Cask 2 Un-Docked; LIB pipe module Collected; Hardware Cask 4 docked | 69.2456 | 30.7468
| Deploy Pipe module lifting attachment | Logistics | 0.38 | 100.9724 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Install LIB Pipe Module | Operation | 4.095 | 105.0674 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Pipe Lifter in Equipment Cask 3 | Logistics | 0.38 | 105.4474 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
Connect LIB Pipe Module | Deploy Service Joint System from Equipment Cask 2 | Logistics | 0.38 | 105.8274 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Weld LIB Pipe Module | Operation | 24.0227 | 129.8501 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Service Joint System in Equipment Cask 2 | Logistics | 0.38 | 130.2301 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Deploy Multifunction Manipulator | Logistics | 0.38 | 130.6101 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Connect Multipipe Flange 4 using Multifunction Manipulator | Operation | 7.83 | 138.4401 | Connect Multipipe Flange & Access Lid | 7.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Multifunction Manipulator in Equipment Cask 2 | Logistics | 0.38 | 138.8201 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
Install ROB Pipe Module | Collect ROB Pipe Module from Hardware Cask 2 | Logistics | 0.6 | 139.4201 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 | Hardware Cask 4 Un-Docked; ROB pipe module Collected; Hardware Cask 2 docked | 110.3733 | 28.4468
| Deploy Pipe module lifting attachment | Logistics | 0.38 | 139.8001 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Install ROB Pipe Module | Operation | 4.095 | 143.8951 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Pipe Lifter in Equipment Cask 2 | Logistics | 0.38 | 144.2751 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
Connect ROB Pipe Module | Deploy Service Joint System from Equipment Cask 2 | Logistics | 0.38 | 144.6551 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Weld ROB Pipe Module | Operation | 24.0227 | 168.6778 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Service Joint System in Equipment Cask 2 | Logistics | 0.38 | 169.0578 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Deploy Multifunction Manipulator | Logistics | 0.38 | 169.4378 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Connect Multipipe Flange 3 using Multifunction Manipulator | Operation | 7.83 | 177.2678 | Connect Multipipe Flange & Access Lid | 7.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Multifunction Manipulator in Equipment Cask 2 | Logistics | 0.38 | 177.6478 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
Install LOB Pipe Module | Collect LOB Pipe Module from Hardware Cask 4 | Logistics | 0.6 | 178.2478 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 | Hardware Cask 2 Un-Docked; LOB pipe module Collected; Hardware Cask 4 docked | 149.201 | 28.4468
| Deploy Pipe module lifting attachment | Logistics | 0.38 | 178.6278 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Install LOB Pipe Module | Operation | 4.095 | 182.7228 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Pipe Lifter in Equipment Cask 2 | Logistics | 0.38 | 183.1028 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
Connect LOB Pipe Module | Deploy Service Joint System from Equipment Cask 2 | Logistics | 0.38 | 183.4828 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Weld LOB Pipe Module | Operation | 24.0227 | 207.5056 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Service Joint System in Equipment Cask 2 | Logistics | 0.38 | 207.8856 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Deploy Multifunction Manipulator | Logistics | 0.38 | 208.2656 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Connect Multipipe Flange 2 using Multifunction Manipulator | Operation | 7.83 | 216.0956 | Connect Multipipe Flange & Access Lid | 7.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Multifunction Manipulator in Equipment Cask 2 | Logistics | 0.38 | 216.4756 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
Install COB Pipe Module | Collect COB Pipe Module from Hardware Cask 2 | Logistics | 0.6 | 217.0756 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 | Hardware Cask 4 Un-Docked; COB pipe module Collected; Hardware Cask 2 docked | 188.0288 | 28.4468
| Deploy Pipe module lifting attachment | Logistics | 0.38 | 217.4556 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Install COB Pipe Module | Operation | 4.095 | 221.5506 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Pipe Lifter in Equipment Cask 2 | Logistics | 0.38 | 221.9306 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
Connect COB Pipe Module | Deploy Service Joint System from Equipment Cask 2 | Logistics | 0.38 | 222.3106 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Weld COB Pipe Module | Operation | 24.0227 | 246.3333 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Service Joint System in Equipment Cask 2 | Logistics | 0.38 | 246.7133 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Deploy Multifunction Manipulator | Logistics | 0.38 | 247.0933 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Connect Multipipe Flange 1 using Multifunction Manipulator | Operation | 7.83 | 254.9233 | Connect Multipipe Flange & Access Lid | 7.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Multifunction Manipulator in Equipment Cask 2 | Logistics | 0.38 | 255.3033 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Un-Dock Equipment Cask 2 | Logistics | 2.54 | 257.8433 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Equipment Cask | 2.54 |  | N/A | N/A
Install Shield Plug & Fixations | Deploy Shield Plug & Fixations Equip from Equipment Cask 1 | Logistics | 0.38 | 261.52 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 | Equipment Cask 2 stored; Equipment Cask 1 collected; Equipment Cask 1 Docked | 261.14 | -3.2967
| Collect Shield Plug & Fixations from Hardware Cask | Logistics | 0.6 | 262.12 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 | Hardware Cask 4 stored; Hardware Cask 3 collected; Hardware Cask 3 docked | 188.3088 | 73.2112
| Install and Connect Shield Plug & Fixations | Operation | 3.695 | 265.815 | Insert and Connect Shield Plug and Fixations | 3.695 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Shield Plug & Fixations Equip. in Equipment Cask 1 | Logistics | 0.38 | 266.195 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Deploy Multifunction Manipulator | Logistics | 0.38 | 266.575 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Connect Shield Plug Pipe Flange using Multifunction Manipulator | Operation | 4.105 | 270.68 | Connect Shield Plug Pipe Flange | 4.105 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Multifunction Manipulator in Equipment Cask 1 | Logistics | 0.38 | 271.06 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Deploy port inspection system | Logistics | 0.38 | 271.44 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Perform port inspection survey | Operation | 5.7722 | 277.2122 | Perform engineering checks | 5.7722 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract port inspection system | Logistics | 0.38 | 277.5922 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
Install Closure Plate | Deploy Closure Plate Equip from Equipment Cask 1 | Logistics | 0.38 | 277.9722 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Collect Closure Plate from Hardware Cask 2 | Logistics | 0.6 | 278.5722 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 | Hardware Cask 3 stored; Hardware Cask 2 Collected; Hardware Cask 2 Docked | 269.5087 | 8.4635
| Install Port Closure Plate | Operation | 0.375 | 278.9472 | Insert Port Closure Plate | 0.375 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Closure Plate Equipment in Equipment Cask 1 | Logistics | 0.38 | 279.3272 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Deploy Multifunction Manipulator | Logistics | 0.38 | 279.7072 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Connect Port Closure Plate using Multifunction Manipulator | Operation | 34.32 | 314.0272 | Connect Port Closure Plate | 34.32 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Multifunction Manipulator in Equipment Cask 1 | Logistics | 0.38 | 314.4072 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
Install and Connect ECH | Deploy Component Carrier from Equipment Cask 1 | Logistics | 0.38 | 314.7872 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Collect ECH from Hardware Cask 1 | Logistics | 0.6 | 317.4609 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 | Hardware Cask 2 Stored; Hardware Cask 1 Collected; Hardware Cask 1 Docked | 316.8609 | -2.0737
| Install ECH | Operation | 0.16667 | 317.6276 | Insert ECH | 0.16667 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Component Carrier in Equipment Cask 1 | Logistics | 0.38 | 318.0076 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Deploy Multifunction Manipulator | Logistics | 0.38 | 318.3876 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Connect ECH Services using Multifunction Manipulator | Operation | 14.565 | 332.9526 | Connect ECH | 14.565 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store Multifunction Manipulator in Equipment Cask 1 | Logistics | 0.38 | 333.3326 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Deploy port inspection system | Logistics | 0.38 | 333.7126 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Perform port inspection survey | Operation | 5.7722 | 339.4848 | Perform engineering checks | 5.7722 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract port inspection system | Logistics | 0.38 | 339.8648 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
Install CCD and Bioshield | Deploy CCD Equipment from Equipment Cask 1 | Logistics | 0.38 | 340.2448 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Collect CCD from Maintenance Cask | Logistics | 0.6 | 340.8448 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 |  | N/A | N/A
| Install CCD | Operation | 5.6 | 346.4448 | Close Contamination Control Door | 5.6 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store CCD Equipment in Equipment Cask 1 | Logistics | 0.38 | 346.8248 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool in Equipment Cask | 0.38 |  | N/A | N/A
| Deploy health physics system | Logistics | 0.38 | 347.2048 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
| Perform health physics checks | Operation | 6.7722 | 353.977 | Perform Health Physics Checks | 6.7722 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Recover health physics system | Logistics | 0.38 | 354.357 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool in Equipment Cask | 0.38 |  | N/A | N/A
| Un-dock Equipment Cask 1 | Logistics | 2.54 | 356.897 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock Equipment Cask | 2.54 |  | N/A | N/A
| Move Overhead Crane to Equipment Stillage | Movement | 0.069444 | 356.9664 |  | N/A | Overhead crane (unloaded) | AMF equipment issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A
| Remove Equipment Platform | Logistics | 0.68 | 357.6464 |  | N/A |  |  |  | N/A | N/A | N/A | Collect bioshield / Equipment Platform | 0.68 |  | N/A | N/A
| Move Overhead Crane to AMF Equipment Receipt | Movement | 0.69444 | 358.3409 |  | N/A | Overhead Crane (Loaded) | Equipment Stillage | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A
| Store Equipment Platform | Logistics | 0.48 | 358.8209 |  | N/A |  |  |  | N/A | N/A | N/A | Store Cask | 0.48 |  | N/A | N/A
| Move Overhead Crane to Upper Port | Movement | 0.069444 | 358.8903 |  | N/A | Overhead Crane (unloaded) | AMF Equipment Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A
| Collect Maintenance Cask | Logistics | 0.48 | 359.3703 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48 |  | N/A | N/A
| Move Overhead Crane to AMF Equipment Issue | Movement | 0.69444 | 360.0648 |  | N/A | Overhead Crane (Loaded) | Equipment Stillage | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A
| Store Maintenance Cask | Logistics | 0.48 | 360.5448 |  | N/A |  |  |  | N/A | N/A | N/A | Store Cask | 0.48 |  | N/A | N/A
| Move Overhead Crane to bioshield Stillage | Movement | 0.027778 | 360.5726 |  | N/A | Overhead Crane (unloaded) | AMF Equipment Receipt | bioshield Stillage | 20 | 0.2 | 0.027778 |  | N/A |  | N/A | N/A
| Collect bioshield | Logistics | 0.48 | 361.0526 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48 |  | N/A | N/A
| Move Overhead Crane to Upper Port | Movement | 0.41667 | 361.4692 |  | N/A | Overhead Crane (loaded) | bioshield Stillage | Vertical Port | 30 | 0.02 | 0.41667 |  | N/A |  | N/A | N/A
| Seal bioshield | Operation | 1.1 | 362.5692 | Seal bioshield | 1.1 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move Overhead Crane to AMF Equipment Receipt | Movement | 0.69444 | 363.2637 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A
Blanket Installation Complete | End Time |  |  | 363.2637
| Operational Time |  |  | 300.632 | 82.76%
| Logistical Time |  |  | 48.76 | 16.22%
| Movements |  |  | 3.3611 | 6.893%
Maintenance Cycle Complete | End Time |  |  | 575.8041
| Operational Time |  |  | 452.451 | 78.58%
| Logistical Time |  |  | 97.48 | 21.54%
| Movements |  |  | 6.0278 | 6.184%
632.1299
| 181.0417 | 181.0417

## Upper Cask Dependencies (hidden)
[5 empty] | Operations |  | Movement | [5 empty] | Logistics
Group | Activity | Activity Type | Time (h) | Cumulative | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h)
Equipment Cask 1 collected | Blanket Removal Required | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Collect Equipment Cask 1 | Logistics | 0.48 | 0.48 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48
| Equipment Cask 1 collected | Total | 0 | 0.48 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Hardware Cask 1 collected & docked | Dock Equipment Cask 1 | Trigger | 0 | 11.9933 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter A to AMF Equipment Issue | Movement | 0.23148 | 12.2248 |  | N/A | Cask Transporter (empty) | Equipment Stillage | AMF Equipment Issue | 50 | 0.06 | 0.23148 |  | N/A
| Collect Hardware Cask 1 | Logistics | 0.48 | 12.7048 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48
| Move Cask Transporter A to Hardware Stillage | Movement | 0.69444 | 13.3993 |  | N/A | Cask Transporter (loaded) | AMF Equipment Issue | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 1 | Logistics | 1.4 | 14.7993 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Hardware Cask 1 collected & docked | Total | 0 | 14.7993 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ECH & Hardware Cask 1 stored; Hardware Cask 2 collected; Hardware Cask 2 docked | Store ECH in Hardware Cask 1 | Trigger | 0 | 43.9378 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 1 | Logistics | 2.3 | 46.2378 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Receipt | Movement | 0.69444 | 46.9322 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store ECH | Logistics | 0.68 | 47.6122 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter A to AMF Equipment Receipt | Movement | 0.092593 | 47.7048 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | AMF Equipment Receipt | 20 | 0.06 | 0.092593 |  | N/A
| Store Hardware Cask 1 | Logistics | 0.48 | 48.1848 |  | N/A |  |  |  | N/A | N/A | N/A | Store Cask | 0.48
| Move Cask Transporter A to AMF Equipment Issue | Movement | 0 | 48.1848 |  | N/A | Cask transporer (unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | N/A | Error |  | N/A
| Collect Hardware Cask 2 | Logistics | 0.48 | 48.6648 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48
| Move Cask Transporter A to Hardware Stillage | Movement | 0.69444 | 49.3593 |  | N/A | Cask Transporter (loaded) | AMF Equipment Issue | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 2 | Logistics | 1.4 | 50.7593 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| ECH & Hardware Cask 1 stored; Hardware Cask 2 collected; Hardware Cask 2 docked | Total | 0 | 50.7593 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Closure Plate & Hardware Cask 2 stored; Hardware Cask 3 collected; Hardware Cask 3 docked | Store Closure Plate in Hardware Cask 2 | Trigger | 0 | 82.3283 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 2 | Logistics | 2.3 | 84.6283 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Receipt | Movement | 0.69444 | 85.3228 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Closure Plate | Logistics | 0.68 | 86.0028 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter A to AMF Equipment Receipt | Movement | 0.092593 | 86.0954 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | AMF Equipment Receipt | 20 | 0.06 | 0.092593 |  | N/A
| Store Hardware Cask 2 | Logistics | 0.48 | 86.5754 |  | N/A |  |  |  | N/A | N/A | N/A | Store Cask | 0.48
| Move Cask Transporter A to AMF Equipment Issue | Movement | 0.027778 | 86.6031 |  | N/A | Cask Transporter (unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Hardware Cask 3 | Logistics | 0.48 | 87.0831 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48
| Move Cask Transporter A to Hardware Stillage | Movement | 0.69444 | 87.7776 |  | N/A | Cask Transporter (loaded) | AMF Equipment Issue | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 3 | Logistics | 1.4 | 89.1776 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Closure Plate & Hardware Cask 2 stored; Hardware Cask 3 collected; Hardware Cask 3 docked | Total | 0 | 89.1776 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Shield Plug & Fixations & Hardware Cask 3 stored; Equipment Cask 2 collected; Equipment cask 2 docked | Store Shield Plug & Fixations in Hardware Cask 3 | Trigger | 0 | 98.7689 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 3 | Logistics | 2.3 | 101.0689 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Receipt | Movement | 0.69444 | 101.7633 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Shield Plug & Fixations | Logistics | 0.68 | 102.4433 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter A to AMF Equipment Receipt | Movement | 0.092593 | 102.5359 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | AMF Equipment Receipt | 20 | 0.06 | 0.092593 |  | N/A
| Store Hardware Cask 3 | Logistics | 0.48 | 103.0159 |  | N/A |  |  |  | N/A | N/A | N/A | Store Cask | 0.48
| Move Cask Transporter A to AMF Equipment Issue | Movement | 0.027778 | 103.0437 |  | N/A | Cask Transporter (unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Equipment Cask 2 | Logistics | 0.48 | 103.5237 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48
| Move Cask Transporter A to Equipment Stillage | Movement | 0.69444 | 104.2181 |  | N/A | Cask Transporter (loaded) | AMF Equipment Issue | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Equipment Cask 2 | Logistics | 1.64 | 105.8581 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Equipment Cask | 1.64
| Shield Plug & Fixations & Hardware Cask 3 stored; Equipment Cask 2 collected; Equipment cask 2 docked | Total | 0 | 105.8581 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Equipment Cask 1 stored; Hardware Cask 4 collected; Hardware Cask 4 docked | Deploy Multifunction Manipulator for Multipipe Flange 1 | Trigger | 0 | 105.3011 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Equipment Cask 1 | Logistics | 2.54 | 107.8411 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Equipment Cask | 2.54
| Move Cask Transporter B to AMF Equipment Receipt | Movement | 0.69444 | 108.5356 |  | N/A | Cask Transporter (loaded) | Equipment Stillage | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Equipment Cask 1 | Logistics | 0.48 | 109.0156 |  | N/A |  |  |  | N/A | N/A | N/A | Store Cask | 0.48
| Move Cask Transporter B to AMF Equipment Issue | Movement | 0.092593 | 109.1081 |  | N/A | Cask Transporter (empty) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.06 | 0.092593 |  | N/A
| Collect Hardware Cask 4 | Logistics | 0.48 | 109.5881 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48
| Move Cask Transporter B to Hardware Stillage | Movement | 0.69444 | 110.2826 |  | N/A | Cask Transporter (loaded) | AMF Equipment Issue | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 4 | Logistics | 1.4 | 111.6826 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Equipment Cask 1 stored; Hardware Cask 4 collected; Hardware Cask 4 docked | Total | 0 | 111.6826 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
COB Pipe Module stored; Hardware Cask 4 docked | Store COB Pipe Module In Hardware Cask 4 | Trigger | 0 | 116.056 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 4 | Logistics | 2.3 | 118.356 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Receipt | Movement | 0.69444 | 119.0505 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store COB Pipe Module | Logistics | 0.68 | 119.7305 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.23148 | 119.962 |  | N/A | Cask Transporter (Empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 4 | Logistics | 1.4 | 121.362 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| COB Pipe Module stored; Hardware Cask 4 docked | Total | 0 | 121.362 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Pipe Module stored; Hardware Cask 4 docked | Store LOB Pipe Module In Hardware Cask 4 | Trigger | 0 | 127.5709 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 4 | Logistics | 2.3 | 129.8709 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Receipt | Movement | 0.69444 | 130.5654 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store LOB Pipe Module | Logistics | 0.68 | 131.2454 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.23148 | 131.4769 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 4 | Logistics | 1.4 | 132.8769 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| LOB Pipe Module stored; Hardware Cask 4 docked | Total | 0 | 132.8769 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Pipe Module stored; Hardware Cask 4 docked | Store ROB Pipe Module In Hardware Cask 4 | Trigger | 0 | 139.0859 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 4 | Logistics | 2.3 | 141.3859 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Receipt | Movement | 0.69444 | 142.0803 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store ROB Pipe Module | Logistics | 0.68 | 142.7603 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.23148 | 142.9918 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 4 | Logistics | 1.4 | 144.3918 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| ROB Pipe Module stored; Hardware Cask 4 docked | Total | 0 | 144.3918 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Pipe Module stored; Hardware Cask 4 docked | Store LIB Pipe Module In Hardware Cask 4 | Trigger | 0 | 150.6008 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-dock Hardware Cask 4 | Logistics | 2.3 | 152.9008 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Receipt | Movement | 0.69444 | 153.5952 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store LIB Pipe Module | Logistics | 0.68 | 154.2752 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.23148 | 154.5067 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 4 | Logistics | 1.4 | 155.9067 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| LIB Pipe Module stored; Hardware Cask 4 docked | Total | 0 | 155.9067 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Pipe Module stored; Hardware Cask 4 stored; Hardware Cask 5 collected; Hardware Cask 5 docked | Store RIB Pipe Module In Hardware Cask 4 | Trigger | 0 | 162.1157 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 4 | Logistics | 2.3 | 164.4157 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Receipt | Movement | 0.69444 | 165.1101 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store ROB Pipe Module | Logistics | 0.68 | 165.7901 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to AMF Equipment Receipt | Movement | 0.092593 | 165.8827 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | AMF Equipment Receipt | 20 | 0.06 | 0.092593 |  | N/A
| Store Hardware Cask 4 | Logistics | 0.48 | 166.3627 |  | N/A |  |  |  | N/A | N/A | N/A | Store Cask | 0.48
| Move to Cask Transporter B to AMF Equipment Issue | Movement | 0.027778 | 166.3905 |  | N/A | Cask Transporter (unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Hardware Cask 5 | Logistics | 0.48 | 166.8705 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48
| Move Cask Transporter B to Hardware Stillage | Movement | 0.23148 | 167.102 |  | N/A | Cask Transporter (empty) | AMF Equipment Issue | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 5 | Logistics | 1.4 | 168.502 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| RIB Pipe Module stored; Hardware Cask 4 stored; Hardware Cask 5 collected; Hardware Cask 5 docked | Total | 0 | 168.502 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Equipment Cask 3 collected; Equipment Cask 3 moved to equipment stillage | Un-Dock Equipment Cask 2 | Trigger | 0 | 165.0357 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Deploy Cask Transporter C | Logistics | 0.5 | 165.5357 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Equipment from Store | 0.5
| Collect Equipment Cask 3 | Logistics | 0.48 | 166.0157 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48
| Move Cask Transporter C to Equipment Stillage | Movement | 0.69444 | 166.7101 |  | N/A | Cask Transporter (loaded) | AMF Equipment Issue | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Equipment Cask 3 collected; Equipment Cask 3 moved to equipment stillage | Total | 0 | 166.7101 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Equipment Cask 2 stored; Hardware Cask 6 Collected; Hardware Cask 6 docked | Un-Dock Equipment Cask 2 | Trigger | 0 | 165.0357 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter A to AMF Equipment Receipt | Movement | 0.69444 | 165.7301 |  | N/A | Cask Transporter (loaded) | Equipment Stillage | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Equipment Cask 2 | Logistics | 0.48 | 166.2101 |  | N/A |  |  |  | N/A | N/A | N/A | Store Cask | 0.48
| Move Cask Transporter A to AMF Equipment Issue | Movement | 0.092593 | 166.3027 |  | N/A | Cask Transporter (Empty) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.06 | 0.092593 |  | N/A
| Collect Hardware Cask 6 | Logistics | 0.48 | 166.7827 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48
| Move Cask Transporter A to Hardware Stillage | Movement | 0.69444 | 167.4772 |  | N/A | Cask Transporter (loaded) | AMF Equipment Issue | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 168.8772 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Equipment Cask 2 stored; Hardware Cask 6 Collected; Hardware Cask 6 docked | Total | 0 | 168.8772 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Lower Port COB Pipe Module Removed | Blanket Removal Required | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Lower Port COB pipework joint cut and pipework removed | Operation | 173.1705 | 173.1705 | Remove COB blanket pipework module | 173.1705 |  |  |  | N/A | N/A | N/A |  | N/A
| Lower Port COB Pipe Module Removed | Total | 0 | 173.1705 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Lower Port LOB Pipe Module Removed | Blanket Removal Required | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Lower Port LOB pipework joint cut and pipework removed | Operation | 183.2605 | 183.2605 | Remove LOB blanket pipework module | 183.2605 |  |  |  | N/A | N/A | N/A |  | N/A
| Lower Port LOB Pipe Module Removed | Total | 0 | 183.2605 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Lower Port ROB Pipe Module Removed | Blanket Removal Required | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Lower Port ROB pipework joint cut and pipework removed | Operation | 184.9305 | 184.9305 | Remove ROB blanket pipework module | 184.9305 |  |  |  | N/A | N/A | N/A |  | N/A
| Lower Port ROB Pipe Module Removed | Total | 0 | 184.9305 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Lower Port LIB Pipe Module Removed | Blanket Removal Required | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Lower Port LIB pipework joint cut and pipework removed | Operation | 191.0305 | 191.0305 | Remove LIB blanket pipework module | 191.0305 |  |  |  | N/A | N/A | N/A |  | N/A
| Lower Port LIB Pipe Module Removed | Total | 0 | 191.0305 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Lower Port RIB Pipe Module Removed | Blanket Removal Required | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Lower Port RIB pipework joint cut and pipework removed | Operation | 192.7005 | 192.7005 | Remove RIB blanket pipework module | 192.7005 |  |  |  | N/A | N/A | N/A |  | N/A
| Lower Port RIB Pipe Module Removed | Total | 0 | 192.7005 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
COB Blanket Segment stored; Hardware Cask 5 docked | Store COB Blanket Segment in Hardware Cask 5 | Trigger | 0 | 179.5405 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 5 | Logistics | 2.3 | 181.8405 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Receipt | Movement | 0.69444 | 182.5349 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store COB Blanket Segment | Logistics | 0.68 | 183.2149 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.23148 | 183.4464 |  | N/A | Cask Transporter (Empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 5 | Logistics | 1.4 | 184.8464 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| COB Blanket Segment stored; Hardware Cask 5 docked | Total | 0 | 184.8464 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Blanket Segment stored; Hardware Cask 6 docked | Store LOB Blanket Segment in Hardware Cask 6 | Trigger | 0 | 189.6305 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 6 | Logistics | 2.3 | 191.9305 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Receipt | Movement | 0.69444 | 192.6249 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store LOB Blanket Segment | Logistics | 0.68 | 193.3049 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter A to Hardware Stillage | Movement | 0.23148 | 193.5364 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 194.9364 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| LOB Blanket Segment stored; Hardware Cask 6 docked | Total | 0 | 194.9364 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Blanket Segment stored; Hardware Cask 5 docked | Store ROB Blanket Segment in Hardware Cask 5 | Trigger | 0 | 196.5005 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 5 | Logistics | 2.3 | 198.8005 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Receipt | Movement | 0.69444 | 199.4949 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store ROB Blanket Segment | Logistics | 0.68 | 200.1749 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.23148 | 200.4064 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 5 | Logistics | 1.4 | 201.8064 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| ROB Blanket Segment stored; Hardware Cask 5 docked | Total | 0 | 201.8064 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Blanket Segment stored; Hardware Cask 6 docked | Collect Blanket Segment 5 from Hardware Cask 6 | Trigger | 0 | 27.7546 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 5 | Logistics | 2.3 | 30.0546 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Receipt | Movement | 0.34722 | 30.4019 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Issue | 25 | 0.02 | 0.34722 |  | N/A
| Store RIB Blanket Segment | Logistics | 0.68 | 31.0819 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter A to Hardware Stillage | Movement | 0.23148 | 31.3133 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 32.7133 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| LIB Blanket Segment stored; Hardware Cask 6 docked | Total | 0 | 32.7133 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Blanket Segment stored; Hardware Cask 5 docked | Collect Blanket Segment 4 from Hardware Cask 5 | Trigger | 0 | 33.0646 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 5 | Logistics | 2.3 | 35.3646 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Receipt | Movement | 0.69444 | 36.0591 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store RIB Blanket Segment | Logistics | 0.68 | 36.7391 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter A to Hardware Stillage | Movement | 0.23148 | 36.9706 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 38.3706 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| RIB Blanket Segment stored; Hardware Cask 5 docked | Total | 0 | 38.3706 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Port Inspection System Collected; Hardware Cask 7 docked | Blanket Installation Required | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 5 | Logistics | 2.3 | 2.3 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Issue | Movement | 0.11574 | 2.4157 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Issue | 25 | 0.06 | 0.11574 |  | N/A
| Export Port Inspection and Repair hardware | Logistics | 0.63 | 3.0457 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63
| Move Cask Transporter A to Hardware Stillage | Movement | 0.69444 | 3.7402 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 7 | Logistics | 1.4 | 5.1402 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Port Inspection System Collected; Hardware Cask 7 docked | Total | 0 | 5.1402 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Blanket Segment Collected; Hardware Cask 6 docked | Blanket Installation Required | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 7 | Logistics | 2.3 | 2.3 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Issue | Movement | 0.11574 | 2.4157 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Issue | 25 | 0.06 | 0.11574 |  | N/A
| Export RIB Blanket Segment | Logistics | 0.63 | 3.0457 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63
| Move Cask Transporter A to Hardware Stillage | Movement | 0.69444 | 3.7402 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 5.1402 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| RIB Blanket Segment Collected; Hardware Cask 6 docked | Total | 0 | 5.1402 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Blanket Segment Collected; Hardware Cask 5 docked | Collect Blanket Segment 5 from Hardware Cask 6 | Trigger | 0 | 27.7546 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 6 | Logistics | 2.3 | 30.0546 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Issue | Movement | 0.11574 | 30.1704 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Issue | 25 | 0.06 | 0.11574 |  | N/A
| Export LIB Blanket Segment | Logistics | 0.63 | 30.8004 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63
| Move Cask Transporter A to Hardware Stillage | Movement | 0.69444 | 31.4948 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 32.8948 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| LIB Blanket Segment Collected; Hardware Cask 5 docked | Total | 0 | 32.8948 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Blanket Segment Collected; Hardware Cask 6 docked | Install RIB Blanket Segment | Trigger | 0 | 32.4646 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 5 | Logistics | 2.3 | 34.7646 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Issue | Movement | 0.11574 | 34.8804 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Issue | 25 | 0.06 | 0.11574 |  | N/A
| Export ROB Blanket Segment | Logistics | 0.63 | 35.5104 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63
| Move Cask Transporter B to Hardware Stillage | Movement | 0.69444 | 36.2048 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 37.6048 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| ROB Blanket Segment Collected; Hardware Cask 6 docked | Total | 0 | 37.6048 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Blanket Segment Collected; Hardware Cask 5 docked | Install LIB Blanket Segment | Trigger | 0 | 37.7746 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 6 | Logistics | 2.3 | 40.0746 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Issue | Movement | 0.11574 | 40.1904 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Issue | 25 | 0.06 | 0.11574 |  | N/A
| Export LOB Blanket Segment | Logistics | 0.63 | 40.8204 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63
| Move Cask Transporter A to Hardware Stillage | Movement | 0.69444 | 41.5148 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 42.9148 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| LOB Blanket Segment Collected; Hardware Cask 5 docked | Total | 0 | 42.9148 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
COB Blanket Segment Collected; Hardware Cask 6 docked | Install ROB Blanket Segment | Trigger | 0 | 43.0846 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 5 | Logistics | 2.3 | 45.3846 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Issue | Movement | 0.11574 | 45.5004 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Issue | 25 | 0.06 | 0.11574 |  | N/A
| Export COB Blanket Segment | Logistics | 0.63 | 46.1304 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63
| Move Cask Transporter B to Hardware Stillage | Movement | 0.69444 | 46.8248 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 48.2248 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| COB Blanket Segment Collected; Hardware Cask 6 docked | Total | 0 | 48.2248 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Equipment Cask 6 stored; Equipment Cask 2 Collected; Hardware Cask 2 docked; RIB Pipe Module Collected | un-dock inspection cask | Trigger | 0 | 25.7546 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter A to AMF Equipment Receipt | Movement | 0.69444 | 26.4491 |  | N/A | Cask Transporter (loaded) | Equipment Stillage | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Equipment Cask 6 | Logistics | 0.48 | 26.9291 |  | N/A |  |  |  | N/A | N/A | N/A | Store Cask | 0.48
| Move Cask Transporter A to AMF Equipment Issue | Movement | 0.027778 | 26.9569 |  | N/A | Cask Transporter (unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Equipment Cask 2 | Logistics | 0.48 | 27.4369 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48
| Move Cask Transporter A to AMF Hardware issue | Movement | 0.092593 | 27.5294 |  | N/A | Cask Transporter (empty) | AMF Equipment Issue | AMF Hardware Issue | 20 | 0.06 | 0.092593 |  | N/A
| Dock Equipment Cask 2 | Logistics | 1.4 | 28.9294 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Collect RIB Pipe Module | Logistics | 0.63 | 29.5594 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63
| un-dock cask | Logistics | 2.3 | 31.8594 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to vertical port | Movement | 0.69444 | 32.5539 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 4 | Logistics | 1.4 | 33.9539 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Equipment Cask 6 stored; Equipment Cask 2 Collected; Hardware Cask 2 docked; RIB Pipe Module Collected | Total | 0 | 33.9539 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Hardware Cask 2 Un-Docked; LIB Pipe Module Collected; Hardware Cask 4 docked | Install RIB Pipe Module | Trigger | 0 | 63.9396 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-dock Hardware Cask 4 | Logistics | 2.3 | 66.2396 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Issue | Movement | 0.23148 | 66.4711 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Collect LIB Pipe Module | Logistics | 0.68 | 67.1511 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.69444 | 67.8456 |  | N/A | Cask transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 4 | Logistics | 1.4 | 69.2456 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Hardware Cask 2 Un-Docked; LIB Pipe Module Collected; Hardware Cask 4 docked | Total | 0 | 69.2456 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Hardware Cask 4 Un-Docked; ROB Pipe Module Collected; Hardware Cask 2 docked | Install LIB Pipe Module | Trigger | 0 | 105.0674 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-dock Hardware Cask 4 | Logistics | 2.3 | 107.3674 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Issue | Movement | 0.23148 | 107.5988 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Collect LIB Pipe Module | Logistics | 0.68 | 108.2788 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter A to Hardware Stillage | Movement | 0.69444 | 108.9733 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 4 | Logistics | 1.4 | 110.3733 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Hardware Cask 4 Un-Docked; ROB Pipe Module Collected; Hardware Cask 2 docked | Total | 0 | 110.3733 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Hardware Cask 2 Un-Docked; LOB Pipe Module Collected; Hardware Cask 4 docked | Install ROB Pipe Module | Trigger | 0 | 143.8951 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-dock Hardware Cask 4 | Logistics | 2.3 | 146.1951 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Issue | Movement | 0.23148 | 146.4266 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Collect LIB Pipe Module | Logistics | 0.68 | 147.1066 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.69444 | 147.801 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 4 | Logistics | 1.4 | 149.201 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Hardware Cask 2 Un-Docked; LOB Pipe Module Collected; Hardware Cask 4 docked | Total | 0 | 149.201 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Hardware Cask 4 Un-Docked; COB Pipe Module Collected; Hardware Cask 2 docked | Install LOB Pipe Module | Trigger | 0 | 182.7228 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-dock Hardware Cask 4 | Logistics | 2.3 | 185.0228 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Issue | Movement | 0.23148 | 185.2543 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Collect LOB Pipe Module | Logistics | 0.68 | 185.9343 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.69444 | 186.6288 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 4 | Logistics | 1.4 | 188.0288 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Hardware Cask 4 Un-Docked; COB Pipe Module Collected; Hardware Cask 2 docked | Total | 0 | 188.0288 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Hardware Cask 4 stored; Hardware Cask 3 collected; Hardware Cask 3 docked | Install LOB Pipe Module | Trigger | 0 | 182.7228 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 4 | Logistics | 2.3 | 185.0228 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Receipt | Movement | 0.23148 | 185.2543 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Hardware Cask 3 | Logistics | 0.48 | 185.7343 |  | N/A |  |  |  | N/A | N/A | N/A | Store Cask | 0.48
| Move Cask Transporter A to AMF Equipment Issue | Movement | 0 | 185.7343 |  | N/A | Cask Transporter (unloaded) | AMF Hardware Receipt | Issue | N/A | 0.2 | Error |  | N/A
| Collect Hardware Cask 3 | Logistics | 0.48 | 186.2143 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48
| Move Cask Transporter A to Hardware Stillage | Movement | 0.69444 | 186.9088 |  | N/A | Cask Transporter (loaded) | AMF Hardware Issue | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 3 | Logistics | 1.4 | 188.3088 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Hardware Cask 4 stored; Hardware Cask 3 collected; Hardware Cask 3 docked | Total | 0 | 188.3088 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Equipment Cask 2 stored; Equipment Cask 1 collected; Equipment Cask 1 Docked | Un-Dock Equipment Cask 2 | Trigger | 0 | 257.8433 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-dock Hardware Cask 2 | Logistics | 2.3 | 190.6088 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Equipment Receipt | Movement | 0.69444 | 258.5377 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Equipment Cask 2 | Logistics | 0.48 | 259.0177 |  | N/A |  |  |  | N/A | N/A | N/A | Store Cask | 0.48
| Move Transporter B to AMF Equipment Issue | Movement | 0.027778 | 259.0455 |  | N/A | Cask Transporter (unloaded) | AMF Hardware Receipt | AMF Hardware Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Equipment Cask 1 | Logistics | 0 | 259.0455 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | N/A
| Move Cask Transporter B to Hardware Stillage | Movement | 0.69444 | 259.74 |  | N/A | Cask Transporter (loaded) | AMF Hardware Issue | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 3 | Logistics | 1.4 | 261.14 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Equipment Cask 2 stored; Equipment Cask 1 collected; Equipment Cask 1 Docked | Total | 0 | 261.14 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Hardware Cask 3 stored; Hardware Cask 2 Collected; Hardware Cask 2 Docked | Store Shield Plug & Fixations Equip. in Equipment Cask 1 | Trigger | 0 | 266.195 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-dock Hardware Cask 3 | Logistics | 2.3 | 263.44 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Equipment Receipt | Movement | 0.23148 | 266.4264 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Hardware Cask 2 | Logistics | 0.48 | 266.9064 |  | N/A |  |  |  | N/A | N/A | N/A | Store Cask | 0.48
| Move Transporter B to AMF Equipment Issue | Movement | 0.027778 | 266.9342 |  | N/A | Cask Transporter (unloaded) | AMF Hardware Receipt | AMF Hardware Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Hardware Cask 2 | Logistics | 0.48 | 267.4142 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48
| Move Cask Transporter B to Hardware Stillage | Movement | 0.69444 | 268.1087 |  | N/A | Cask Transporter (loaded) | AMF Hardware Issue | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 3 | Logistics | 1.4 | 269.5087 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Hardware Cask 3 stored; Hardware Cask 2 Collected; Hardware Cask 2 Docked | Total | 0 | 269.5087 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Hardware Cask 2 Stored; Hardware Cask 1 Collected; Hardware Cask 1 Docked | Connect Port Closure Plate using Multifunction Manipulator | Trigger | 0 | 314.0272 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-dock Hardware Cask 2 | Logistics | 2.3 | 271.8087 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Equipment Receipt | Movement | 0.23148 | 314.2587 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Hardware Cask 2 | Logistics | 0.48 | 314.7387 |  | N/A |  |  |  | N/A | N/A | N/A | Store Cask | 0.48
| Move Transporter B to AMF Equipment Issue | Movement | 0.027778 | 314.7664 |  | N/A | Cask Transporter (unloaded) | AMF Hardware Receipt | AMF Hardware Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Equipment Cask 1 | Logistics | 0 | 314.7664 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | N/A
| Move Cask Transporter B to Hardware Stillage | Movement | 0.69444 | 315.4609 |  | N/A | Cask Transporter (loaded) | AMF Hardware Issue | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 3 | Logistics | 1.4 | 316.8609 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Hardware Cask 2 Stored; Hardware Cask 1 Collected; Hardware Cask 1 Docked | Total | 0 | 316.8609 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A

## Upper Cask Movement & Logistics (hidden)
Logistical Activities |  |  |  | Equipment Speed
Activity | Sub activity | Time |  | Equipment | Speed (m/s)
Deploy Equipment from Store | Deploy Equipment from Store | 0.5 |  | Overhead Crane (Loaded) | 0.02
Collect Bioshield / Equipment Platform | Position | 0.28 |  | Overhead Crane (Unloaded) | 0.2
| Attach crane to hardware | 0.2 |  | Cask transporter (empty) | 0.06
| Lift hardware | 0.2 |  | Cask Transporter (loaded) | 0.02
| Collect Bioshield / Equipment Platform | 0.68 |  | Cask transporter (unloaded) | 0.2
Collect Cask | Position | 0.28
| Attach to cask | 0.2
| Collect Cask | 0.48
Store Cask | Position | 0.28
| Detach from Cask | 0.2
| Store Cask | 0.48
Dock Maintenance Cask | Dock to bioshield | 0.2
| Connect double lidded door and frame | 0.3
| Disconnect door | 0.3
| Store door | 0.5
| Connect services | 0.1
| Software check | 1
| Hardware check | 1
| Install VMS rails | 0.5 |  | Distance Table
| Dock Maintenance Cask | 3.9 |  | To: From : | Equipment Stillage | Vertical Port | Hardware Stillage | AMF Equipment Issue | AMF Equipment Receipt | AMF Hardware Receipt | AMF Hardware Issue | Bioshield Stillage
Dock Equipment Cask | Dock to interface cask | 0.2 |  | Equipment Stillage |  | 5 | 5 | 50 | 50 | 50 | 50 | 25
| Connect double lidded door and frame | 0.3 |  | Vertical Port | 5 |  | 5 | 50 | 50 | 50 | 30 | 30
| Disconnect door | 0.3 |  | Hardware Stillage | 5 | 5 |  | 50 | 50 | 50 | 25 | 25
| Store door | 0.5 |  | AMF Equipment Issue | 50 | 50 | 50 |  | 20 | 20 | 20 | 20
| Connect services | 0.1 |  | AMF Equipment Receipt | 50 | 50 | 50 | 20 |  | 20 | 20 | 20
| Extend tool rail | 0.19 |  | AMF Hardware Receipt | 50 | 50 | 50 | 20 | 20 |  | 20 | 20
| Rotate to collection position | 0.05 |  | AMF Hardware Issue | 50 | 50 | 50 | 20 | 20 | 10 |  | 50
| Dock Equipment Cask | 1.64 |  | Bioshield Stillage | 25 | 30 | 25 | 20 | 20 | 20 | 50
Un-Dock Equipment Cask | Rotate rail to storage position | 0.05
| Retract rail | 0.19
| Replace door | 0.5
| Attach to frame | 0.3
| Disconnect door and frame | 0.3
| Disconnect Services | 0.1 | RM Equipment Cask Contents
| Demonstrate seals | 1 | Equipment Cask 1 | CCD Equipment | Multifunction Manipulator | Shield Plug & Fixations Equipment
| Undock from interface cask | 0.1 | Equipment Cask 2 | Pipe Cutting | Pipe Lifter | Pipe Welder
| Un-Dock Equipment Cask | 2.54 | Equipment Cask 3 | Blanket Transporter
Dock Hardware Cask | Dock to interface cask | 0.2
| Connect double lidded door and frame | 0.3
| Disconnect door | 0.3
| Store door | 0.5
| Connect services | 0.1
| Dock Hardware Cask | 1.4
Un-Dock Hardware Cask | Replace door | 0.5
| Attach to frame | 0.3
| Disconnect door and frame | 0.3
| Disconnect Services | 0.1
| Demonstrate seals | 1
| Undock from interface cask | 0.1
| Un-Dock Hardware Cask | 2.3
Un-dock Maintenance Cask | Rotate rail to storage position | 0.05
| Retract rail | 0.19
| Replace door | 0.5
| Attach to frame | 0.3
| Disconnect door and frame | 0.3
| Disconnect Services | 0.1
| Demonstrate seals | 1
| Undock from interface cask | 0.1
| Un-dock Maintenance Cask | 2.54
Deploy Tool From Equipment Cask | Position Vertical Crane | 0.28
| Make Connections/commission] | 0.1
| Deploy Tool From Equipment Cask | 0.38
Store Hardware in Storage Location | Position | 0.28
| Lower onto storage location | 0.2
| Release crane | 0.2
| Store Hardware in Storage Location | 0.68
Store Tool In Equipment Cask | Position in storage location | 0.28
| Break connections | 0.1
| Store Tool In Equipment Cask | 0.38
Store Hardware in Hardware Cask | Holding cradle deployed | 0.23
| Place on cradle | 0.2
| Retract VMS | 0.2
| Store Hardware in Hardware Cask | 0.63
Export Hardware from Hardware Cask | Holding cradle deployed | 0.2
| Extend VMS | 0.2
| Remove from the cradle | 0.2
| Export Hardware from Hardware Cask | 0.6

## Upper Cask Welding failures (hidden)
Delay caused by failure and recovery from failed welding operations
Welding Assumptions | [14 empty] | Estimated Delay
Operations Assumptions
TIG welding and laser cutting is the current worst case scenario
In-situ surface treatment is not possible, so all hardware must be removed and replaced/reconditioned before it can be re-welded
All other positioning, delivery and retrieval operations are of a similar length to nominal operations
Service Joint system is capable of cutting and pipes without tool change
No additional blanket modules will need to be removed to access impacted blanket module
RM Tooling is able to cut and weld all pipes within a pipe module simultaneously
No logistical bottlenecks occur during recovery operations
Both upper and lower port welding operations are carried out simultaneously for each blanket, to prevent unnecessary cutting of welds
Design Assumptions
Each Vertical Port pipe module contains 5 pipes
Each lower port pipe module contains 3 pipes
All other positioning, delivery and retrieval operations are of a similar length to nominal operations
Service Joint system is capable of cutting and pipes without tool change
|  | Single Port | Full DEMO Maintenance
| No. Systems | 1 | 1 | 2 | 3 | 4 | 6
| Vertical Port Maintenance | 1 Port | 18 Ports | 9 Ports | 6 Ports | 5 Ports | 3 Ports
| Operational contribution | 225.8333 | 3305.2016 | 1652.6008 | 1101.7339 | 918.1116 | 550.8669
| Logistical contribution | 42.6817 | 596.4467 | 298.2234 | 198.8156 | 165.6796 | 99.4078
| Idle time waiting for dependent operations | 46.8636 | 545.2934 | 272.6467 | 181.7645 | 151.4704 | 90.8822
| Estimated Delay (H) | 315.3786 | 4446.9417 | 2223.4709 | 1482.3139 | 1235.2616 | 741.157
Estimated Operational Durations (taken from Hotcell Critical Path)
Failure of COB Vertical Port Welds
Assumptions:
|  | TIG welding and laser cutting is the current worst case scenario | [14 empty] | Single Port | DEMO
|  | In-situ surface treatment is not possible, so all hardware must be removed and replaced/reconditioned before it can be re-welded | [13 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
|  | All other positioning, delivery and retrieval operations are of a similar length to nominal operations | [13 empty] | Duration of welding operations (h) | 24.0227 | 432.4092 | 216.2046 | 144.1364 | 120.1137 | 72.0682
|  | Service Joint system is capable of cutting and pipes without tool change | [13 empty] | Estimated number of failures, impacting all RM systems equally | 0.26425 | 4.7565 | 2.3783 | 1.5855 | 1.3213 | 0.79275
|  | No additional blanket modules will need to be removed to access impacted blanket module | [13 empty] | Operational contribution | 68.2963 | 1229.3331 | 614.6666 | 409.7777 | 341.4814 | 204.8889
[16 empty] | Logistical contribution | 11.516 | 207.2883 | 103.6442 | 69.0961 | 57.5801 | 34.5481
|  | Failure rate: | 1.1% | [12 empty] | Idle time waiting for dependent operations | 8.2189 | 147.9399 | 73.97 | 49.3133 | 41.0944 | 24.6567
|  | Assuming a weld failure rate of | 0.1% | [12 empty] | Total Duration of Recovery Operations | 88.0312 | 1584.5613 | 792.2807 | 528.1871 | 440.1559 | 264.0936
|  | Assuming a tool failure rate of | 1%
|  | Probability of Secondary Failure/hr or Event | 0.07063%
[6 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies
| Group | Pipe weld failure (Sub Tasks) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack
| Cut Failed Welds | Weld Failure identified at COB/Pipe Module joint | Operation | 0 | 0 | Hardware Recovery Required | 0 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Cut Failed COB Pipe Module Weld | Operation | 1.0499 | 1.0499 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| COB Blanket Pipework Removal | Deploy Pipe Lifter | Logistics | 0.38 | 1.4299 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Extract COB Pipe Module | Operation | 0.725 | 2.1549 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store COB Pipe Module In Hardware Cask 4 | Logistics | 0.63 | 4.23 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | Shield Plug & Fixations & Hardware Cask 3 stored; Equipment Cask 2 collected; Equipment cask 2 docked | 3.6 | -1.4451
|  | Store Pipe Lifter in Equipment Cask 2 | Logistics | 0.38 | 4.61 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| LOB Blanket Pipework Disconnection | Deploy Multifunction Manipulator | Logistics | 0.38 | 4.99 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Disconnect Multipipe Flange 2 | Operation | 6.83 | 11.82 | Disconnect Multipipe Flange & Access Lid | 6.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Multifunction Manipulator in Equipment Cask 2 | Logistics | 0.38 | 12.2 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
|  | Deploy Service Joint System | Logistics | 0.38 | 12.58 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Cut LOB Pipe joint | Operation | 1.0499 | 13.6299 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Service Joint System in Equipment Cask 2 | Logistics | 0.38 | 14.0099 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| LOB Blanket Pipework Removal | Deploy Pipe Lifter | Logistics | 0.38 | 14.3899 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Extract LOB Pipe Module | Operation | 0.725 | 15.1149 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store LOB Pipe Module In Hardware Cask 4 | Logistics | 0.63 | 15.7449 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | COB Pipe Module stored; Hardware Cask 4 docked | 7.4608 | 7.6541
|  | Store Pipe Lifter in Equipment Cask 2 | Logistics | 0.38 | 16.1249 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| ROB Blanket Pipework Disconnection | Deploy Multifunction Manipulator | Logistics | 0.38 | 16.5049 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Disconnect Multipipe Flange 3 | Operation | 6.83 | 23.3349 | Disconnect Multipipe Flange & Access Lid | 6.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Multifunction Manipulator in Equipment Cask 2 | Logistics | 0.38 | 23.7149 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
|  | Deploy Service Joint System | Logistics | 0.38 | 24.0949 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Cut ROB Pipe joint | Operation | 1.0499 | 25.1448 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Service Joint System in Equipment Cask 2 | Logistics | 0.38 | 25.5248 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| ROB Blanket Pipework Removal | Deploy Pipe Lifter | Logistics | 0.38 | 25.9048 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Extract ROB Pipe Module | Operation | 0.725 | 26.6298 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store ROB Pipe Module In Hardware Cask 4 | Logistics | 0.63 | 27.2598 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | LOB Pipe Module stored; Hardware Cask 4 docked | 20.4208 | 6.209
|  | Store Pipe Lifter in Equipment Cask 2 | Logistics | 0.38 | 27.6398 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| LIB Blanket Pipework Disconnection | Deploy Multifunction Manipulator | Logistics | 0.38 | 28.0198 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Disconnect Multipipe Flange 4 | Operation | 6.83 | 34.8498 | Disconnect Multipipe Flange & Access Lid | 6.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Multifunction Manipulator in Equipment Cask 2 | Logistics | 0.38 | 35.2298 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
|  | Deploy Service Joint System | Logistics | 0.38 | 35.6098 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Cut LIB Pipe joint | Operation | 1.0499 | 36.6597 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Service Joint System in Equipment Cask 2 | Logistics | 0.38 | 37.0397 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| LIB Blanket Pipework Removal | Deploy Pipe Lifter | Logistics | 0.38 | 37.4197 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Extract LIB Pipe Module | Operation | 0.725 | 38.1447 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store LIB Pipe Module In Hardware Cask 4 | Logistics | 0.63 | 38.7747 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | ROB Pipe Module stored; Hardware Cask 4 docked | 31.9358 | 6.209
|  | Store Pipe Lifter in Equipment Cask 2 | Logistics | 0.38 | 39.1547 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| RIB Blanket Pipework Disconnection | Deploy Multifunction Manipulator | Logistics | 0.38 | 39.5347 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Disconnect Multipipe Flange 5 | Operation | 6.83 | 46.3647 | Disconnect Multipipe Flange & Access Lid | 6.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Multifunction Manipulator in Equipment Cask 2 | Logistics | 0.38 | 46.7447 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
|  | Deploy Service Joint System | Logistics | 0.38 | 47.1247 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Cut RIB Pipe joint | Operation | 1.0499 | 48.1747 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Service Joint System in Equipment Cask 2 | Logistics | 0.38 | 48.5547 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| RIB Blanket Pipework Removal | Deploy Pipe Lifter | Logistics | 0.38 | 48.9347 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Extract RIB Pipe Module | Operation | 0.725 | 49.6597 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store RIB Pipe Module In Hardware Cask 4 | Logistics | 0.63 | 50.2897 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | LIB Pipe Module stored; Hardware Cask 4 docked | 43.4507 | 6.209
|  | Store Pipe Lifter in Equipment Cask 2 | Logistics | 0.38 | 50.6697 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Equipment Cask 2 | Logistics | 2.54 | 53.2097 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Equipment Cask | 2.54 |  | N/A | N/A
| Blanket Removal | Dock Equipment Cask 3 | Logistics | 1.64 | 54.8497 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Equipment Cask | 1.64 | Equipment Cask 3 collected; Equipment Cask 3 moved to equipment stillage | 6.2844 | 46.9252
|  | Deploy Blanket Transporter | Logistics | 0.38 | 55.2297 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Extract COB Blanket Segment | Operation | 5.74 | 60.9697 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A | Disconnect COB Divertor port pipe module | 12.603 | 42.6267
|  | Store COB Blanket Segment in Hardware Cask 5 | Logistics | 0.63 | 61.5997 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | RIB Pipe Module stored; Hardware Cask 4 stored; Hardware Cask 5 collected; Hardware Cask 5 docked | 56.5089 | 4.4607
|  | Deploy Blanket Transporter | Logistics | 0.5 | 62.0997 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Equipment from Store | 0.5 |  | N/A | N/A
|  | Extract LOB Blanket Segment | Operation | 5.74 | 67.8397 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store LOB Blanket Segment in Hardware Cask 6 | Logistics | 0.63 | 68.4697 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | Equipment Cask 2 stored; Hardware Cask 6 Collected; Hardware Cask 6 docked | 8.3867 | 59.453
|  | Deploy Blanket Transporter | Logistics | 0.5 | 68.9697 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Equipment from Store | 0.5 |  | N/A | N/A
|  | Extract ROB Blanket Segment | Operation | 5.74 | 74.7097 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store ROB Blanket Segment in Hardware Cask 5 | Logistics | 0.63 | 75.3397 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | COB Blanket Segment stored; Hardware Cask 5 docked | 66.9056 | 7.8041
|  | Deploy Blanket Transporter | Logistics | 0.5 | 75.8397 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Equipment from Store | 0.5 |  | N/A | N/A
|  | Extract LIB Blanket Segment | Operation | 5.74 | 81.5797 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store LIB Blanket Segment in Hardware Cask 6 | Logistics | 0.63 | 82.2097 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | LOB Blanket Segment stored; Hardware Cask 6 docked | 73.7756 | 7.8041
|  | Deploy Blanket Transporter | Logistics | 0.5 | 82.7097 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Equipment from Store | 0.5 |  | N/A | N/A
|  | Extract RIB Blanket Segment | Operation | 5.74 | 88.4497 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store RIB Blanket Segment in Hardware Cask 5 | Logistics | 0.63 | 89.0797 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | ROB Blanket Segment stored; Hardware Cask 5 docked | 80.6456 | 7.8041
|  | Un-Dock Hardware Cask 5 | Logistics | 2.3 | 91.3797 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3 |  | N/A | N/A
| Blanket Installation | Collect Blanket Segment 5 from Hardware Cask 6 | Logistics | 0.6 | 91.9797 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 |  | N/A | N/A
|  | Deploy Blanket Transporter | Logistics | 0.38 | 92.3597 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install RIB Blanket Segment | Operation | 4.33 | 101.4498 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A | RIB Blanket Segment Collected; Hardware Cask 6 docked | 97.1198 | -4.7602
|  | Collect Blanket Segment 4 from Hardware Cask 5 | Logistics | 0.6 | 102.0498 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 |  | N/A | N/A
|  | Deploy Blanket Transporter | Logistics | 0.38 | 102.4298 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install LIB Blanket Segment | Operation | 4.33 | 111.52 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A | LIB Blanket Segment Collected; Hardware Cask 5 docked | 107.19 | -4.7602
|  | Collect Blanket Segment 3 from Hardware Cask 6 | Logistics | 0.6 | 112.12 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 |  | N/A | N/A
|  | Deploy Blanket Transporter | Logistics | 0.38 | 112.5 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install ROB Blanket Segment | Operation | 4.33 | 121.5902 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A | ROB Blanket Segment Collected; Hardware Cask 6 docked | 117.2602 | -4.7602
|  | Collect Blanket Segment 2 from Hardware Cask 5 | Logistics | 0.6 | 122.1902 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 |  | N/A | N/A
|  | Deploy Blanket Transporter | Logistics | 0.38 | 122.5702 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install LOB Blanket Segment | Operation | 4.33 | 131.6604 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A | LOB Blanket Segment Collected; Hardware Cask 5 docked | 127.3304 | -4.7602
|  | Collect Blanket Segment 1 from Hardware Cask 6 | Logistics | 0.6 | 132.2604 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 |  | N/A | N/A
|  | Deploy Blanket Transporter | Logistics | 0.38 | 132.6404 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install COB Blanket Segment | Operation | 4.33 | 141.7306 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A | COB Blanket Segment Collected; Hardware Cask 6 docked | 137.4006 | -4.7602
| Install RIB Pipe Module | Collect RIB Pipe Module from Hardware Cask 2 | Logistics | 0.6 | 148.1873 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 | Equipment Cask 6 stored; Equipment Cask 2 Collected; Hardware Cask 2 docked; RIB Pipe Module Collected | 147.5873 | -5.8567
|  | Deploy Pipe Lifter | Logistics | 0.38 | 148.5673 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install RIB Pipe Module | Operation | 4.095 | 152.6623 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Pipe Lifter in Equipment Cask 2 | Logistics | 0.38 | 153.0423 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Connect RIB Pipe Module | Deploy Service Joint System from Equipment Cask 2 | Logistics | 0.38 | 153.4223 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Weld RIB Pipe Module | Operation | 24.0227 | 177.445 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Service Joint System in Equipment Cask 2 | Logistics | 0.38 | 177.825 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 | RIB Lower Port Pipe Module installed | N/A | N/A
|  | Deploy Multifunction Manipulator | Logistics | 0.38 | 178.205 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Connect Multipipe Flange 5 | Operation | 7.83 | 186.035 | Connect Multipipe Flange & Access Lid | 7.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Multifunction Manipulator in Equipment Cask 2 | Logistics | 0.38 | 186.415 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Install LIB Pipe Module | Collect LIB Pipe Module from Hardware Cask 4 | Logistics | 0.6 | 187.015 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 | Hardware Cask 2 Un-Docked; LIB Pipe Module Collected; Hardware Cask 4 docked | 157.9682 | 28.4468
|  | Deploy Pipe Lifter | Logistics | 0.38 | 187.395 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install LIB Pipe Module | Operation | 4.095 | 191.49 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Pipe Lifter in Equipment Cask 2 | Logistics | 0.38 | 191.87 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Connect LIB Pipe Module | Deploy Service Joint System from Equipment Cask 2 | Logistics | 0.38 | 192.25 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Weld LIB Pipe Module | Operation | 24.0227 | 216.2727 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Service Joint System in Equipment Cask 2 | Logistics | 0.38 | 216.6527 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 | LIB Lower Port Pipe Module installed | N/A | N/A
|  | Deploy Multifunction Manipulator | Logistics | 0.38 | 217.0327 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Connect Multipipe Flange 4 | Operation | 7.83 | 224.8627 | Connect Multipipe Flange & Access Lid | 7.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Multifunction Manipulator in Equipment Cask 2 | Logistics | 0.38 | 225.2427 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Install ROB Pipe Module | Collect ROB Pipe Module from Hardware Cask 2 | Logistics | 0.6 | 225.8427 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 | Hardware Cask 4 Un-Docked; ROB Pipe Module Collected; Hardware Cask 2 docked | 196.7959 | 28.4468
|  | Deploy Pipe Lifter | Logistics | 0.38 | 226.2227 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install ROB Pipe Module | Operation | 4.095 | 230.3177 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Pipe Lifter in Equipment Cask 2 | Logistics | 0.38 | 230.6977 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Connect ROB Pipe Module | Deploy Service Joint System from Equipment Cask 2 | Logistics | 0.38 | 231.0777 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Weld ROB Pipe Module | Operation | 24.0227 | 255.1005 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Service Joint System in Equipment Cask 2 | Logistics | 0.38 | 255.4805 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 | ROB Lower Port Pipe Module installed | N/A | N/A
|  | Deploy Multifunction Manipulator | Logistics | 0.38 | 255.8605 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Connect Multipipe Flange 4 | Operation | 7.83 | 263.6905 | Connect Multipipe Flange & Access Lid | 7.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Multifunction Manipulator in Equipment Cask 2 | Logistics | 0.38 | 264.0705 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Install LOB Pipe Module | Collect LOB Pipe Module from Hardware Cask 4 | Logistics | 0.6 | 264.6705 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 | Hardware Cask 2 Un-Docked; LOB Pipe Module Collected; Hardware Cask 4 docked | 235.6236 | 28.4468
|  | Deploy Pipe Lifter | Logistics | 0.38 | 265.0505 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install LOB Pipe Module | Operation | 4.095 | 269.1455 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Pipe Lifter in Equipment Cask 2 | Logistics | 0.38 | 269.5255 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Connect LOB Pipe Module | Deploy Service Joint System from Equipment Cask 2 | Logistics | 0.38 | 269.9055 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Weld LOB Pipe Module | Operation | 24.0227 | 293.9282 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Service Joint System in Equipment Cask 2 | Logistics | 0.38 | 294.3082 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 | LOB Lower Port Pipe Module installed | N/A | N/A
|  | Deploy Multifunction Manipulator | Logistics | 0.38 | 294.6882 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Connect Multipipe Flange 2 | Operation | 7.83 | 302.5182 | Connect Multipipe Flange & Access Lid | 7.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Multifunction Manipulator in Equipment Cask 2 | Logistics | 0.38 | 302.8982 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Install COB Pipe Module | Collect COB Pipe Module from Hardware Cask 2 | Logistics | 0.6 | 303.4982 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 | Hardware Cask 4 Un-Docked; COB Pipe Module Collected; Hardware Cask 2 docked | 274.4514 | 28.4468
|  | Deploy Pipe Lifter | Logistics | 0.38 | 303.8782 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install COB Pipe Module | Operation | 4.095 | 307.9732 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Pipe Lifter in Equipment Cask 2 | Logistics | 0.38 | 308.3532 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Connect COB Pipe Module | Deploy Service Joint System from Equipment Cask 2 | Logistics | 0.38 | 308.7332 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Weld ROB Pipe Module | Operation | 24.0227 | 332.7559 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Service Joint System in Equipment Cask 2 | Logistics | 0.38 | 333.1359 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 | COB Lower Port Pipe Module installed | N/A | N/A
|  |  | Total |  | 333.1359 | [12 empty] | 31.1027
Failure of LOB Vertical Port Welds
Assumptions:
|  | TIG welding and laser cutting is the current worst case scenario | [13 empty] | Bore Pipe Welds | Single Port | DEMO
|  | In-situ surface treatment is not possible, so all hardware must be removed and replaced/reconditioned before it can be re-welded | [13 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
|  | All other positioning, delivery and retrieval operations are of a similar length to nominal operations | [13 empty] | Duration of welding operations (h) | 24.0227 | 432.4092 | 216.2046 | 144.1364 | 120.1137 | 72.0682
|  | Service Joint system is capable of cutting and pipes without tool change | [13 empty] | Estimated number of failures, impacting all RM systems equally | 0.26425 | 4.7565 | 2.3783 | 1.5855 | 1.3213 | 0.79275
|  | No additional blanket modules will need to be removed to access impacted blanket module | [13 empty] | Operational contribution | 56.5232 | 1017.4184 | 508.7092 | 339.1395 | 282.6162 | 169.5697
[16 empty] | Logistical contribution | 9.986 | 179.7482 | 89.8741 | 59.9161 | 49.93 | 29.958
|  | Failure rate: | 1.1% | [12 empty] | Idle time waiting for dependent operations | 8.2795 | 149.0309 | 74.5154 | 49.677 | 41.3975 | 24.8385
|  | Assuming a weld failure rate of | 0.1% | [12 empty] | Total Duration of Recovery Operations | 74.7887 | 1346.1974 | 673.0987 | 448.7325 | 373.9437 | 224.3662
|  | Assuming a tool failure rate of | 1%
|  | Probability of Secondary Failure/hr or Event | 0.07063%
[6 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies
| Group | Pipe weld failure (Sub Tasks) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack
| Cut Failed Welds | Weld Failure identified at LOB/Pipe Module joint | Operation | 0 | 0 | Hardware Recovery Required | 0 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Cut Failed LOB Pipe Module Weld | Operation | 1.0499 | 1.0499 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| LOB Blanket Pipework Removal | Deploy Pipe Lifter | Logistics | 0.38 | 1.4299 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Extract LOB Pipe Module | Operation | 0.725 | 2.1549 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store LOB Pipe Module In Hardware Cask 4 | Logistics | 0.63 | 2.7849 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | COB Pipe Module stored; Hardware Cask 4 docked | N/A | N/A
|  | Store Pipe Lifter in Equipment Cask 2 | Logistics | 0.38 | 3.1649 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| ROB Blanket Pipework Disconnection | Deploy Multifunction Manipulator | Logistics | 0.38 | 3.5449 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Disconnect Multipipe Flange 3 | Operation | 6.83 | 10.3749 | Disconnect Multipipe Flange & Access Lid | 6.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Multifunction Manipulator in Equipment Cask 2 | Logistics | 0.38 | 10.7549 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
|  | Deploy Service Joint System | Logistics | 0.38 | 11.1349 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Cut ROB Pipe joint | Operation | 1.0499 | 12.1848 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Service Joint System in Equipment Cask 2 | Logistics | 0.38 | 12.5648 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| ROB Blanket Pipework Removal | Deploy Pipe Lifter | Logistics | 0.38 | 12.9448 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Extract ROB Pipe Module | Operation | 0.725 | 13.6698 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store ROB Pipe Module In Hardware Cask 4 | Logistics | 0.63 | 14.2998 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | LOB Pipe Module stored; Hardware Cask 4 docked | 7.4608 | 6.209
|  | Store Pipe Lifter in Equipment Cask 2 | Logistics | 0.38 | 14.6798 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| LIB Blanket Pipework Disconnection | Deploy Multifunction Manipulator | Logistics | 0.38 | 15.0598 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Disconnect Multipipe Flange 4 | Operation | 6.83 | 21.8898 | Disconnect Multipipe Flange & Access Lid | 6.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Multifunction Manipulator in Equipment Cask 2 | Logistics | 0.38 | 22.2698 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
|  | Deploy Service Joint System | Logistics | 0.38 | 22.6498 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Cut LIB Pipe joint | Operation | 1.0499 | 23.6997 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Service Joint System in Equipment Cask 2 | Logistics | 0.38 | 24.0797 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| LIB Blanket Pipework Removal | Deploy Pipe Lifter | Logistics | 0.38 | 24.4597 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Extract LIB Pipe Module | Operation | 0.725 | 25.1847 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store LIB Pipe Module In Hardware Cask 4 | Logistics | 0.63 | 25.8147 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | ROB Pipe Module stored; Hardware Cask 4 docked | 18.9758 | 6.209
|  | Store Pipe Lifter in Equipment Cask 2 | Logistics | 0.38 | 26.1947 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| RIB Blanket Pipework Disconnection | Deploy Multifunction Manipulator | Logistics | 0.38 | 26.5747 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Disconnect Multipipe Flange 5 | Operation | 6.83 | 33.4047 | Disconnect Multipipe Flange & Access Lid | 6.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Multifunction Manipulator in Equipment Cask 2 | Logistics | 0.38 | 33.7847 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
|  | Deploy Service Joint System | Logistics | 0.38 | 34.1647 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Cut RIB Pipe joint | Operation | 1.0499 | 35.2147 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Service Joint System in Equipment Cask 2 | Logistics | 0.38 | 35.5947 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| RIB Blanket Pipework Removal | Deploy Pipe Lifter | Logistics | 0.38 | 35.9747 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Extract RIB Pipe Module | Operation | 0.725 | 36.6997 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store RIB Pipe Module In Hardware Cask 4 | Logistics | 0.63 | 37.3297 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | LIB Pipe Module stored; Hardware Cask 4 docked | 30.4907 | 6.209
|  | Store Pipe Lifter in Equipment Cask 2 | Logistics | 0.38 | 37.7097 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Equipment Cask 2 | Logistics | 2.54 | 40.2497 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Equipment Cask | 2.54 |  | N/A | N/A
| Blanket Removal | Dock Equipment Cask 3 | Logistics | 1.64 | 43.5641 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Equipment Cask | 1.64 | Equipment Cask 3 collected; Equipment Cask 3 moved to equipment stillage | 41.9241 | -1.6744
|  | Deploy Blanket Transporter | Logistics | 0.38 | 43.9441 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Extract COB Blanket Segment | Operation | 5.74 | 49.6841 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store COB Blanket Segment in Hardware Cask 5 | Logistics | 0.63 | 50.3141 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | RIB Pipe Module stored; Hardware Cask 4 stored; Hardware Cask 5 collected; Hardware Cask 5 docked | 43.5489 | 6.1352
|  | Deploy Blanket Transporter | Logistics | 0.5 | 50.8141 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Equipment from Store | 0.5 |  | N/A | N/A
|  | Extract LOB Blanket Segment | Operation | 5.74 | 56.5541 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store LOB Blanket Segment in Hardware Cask 6 | Logistics | 0.63 | 57.1841 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | Equipment Cask 2 stored; Hardware Cask 6 Collected; Hardware Cask 6 docked | 44.0263 | 12.5278
|  | Deploy Blanket Transporter | Logistics | 0.5 | 57.6841 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Equipment from Store | 0.5 |  | N/A | N/A
|  | Extract ROB Blanket Segment | Operation | 5.74 | 63.4241 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store ROB Blanket Segment in Hardware Cask 5 | Logistics | 0.63 | 64.0541 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | COB Blanket Segment stored; Hardware Cask 5 docked | 55.62 | 7.8041
|  | Deploy Blanket Transporter | Logistics | 0.5 | 64.5541 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Equipment from Store | 0.5 |  | N/A | N/A
|  | Extract LIB Blanket Segment | Operation | 5.74 | 70.2941 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store LIB Blanket Segment in Hardware Cask 6 | Logistics | 0.63 | 70.9241 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | LOB Blanket Segment stored; Hardware Cask 6 docked | 62.49 | 7.8041
|  | Deploy Blanket Transporter | Logistics | 0.5 | 71.4241 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Equipment from Store | 0.5 |  | N/A | N/A
|  | Extract RIB Blanket Segment | Operation | 5.74 | 77.1641 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store RIB Blanket Segment in Hardware Cask 5 | Logistics | 0.63 | 77.7941 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | ROB Blanket Segment stored; Hardware Cask 5 docked | 69.36 | 7.8041
|  | Un-Dock Hardware Cask 5 | Logistics | 2.3 | 80.0941 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3 |  | N/A | N/A
| Blanket Installation | Collect Blanket Segment 5 from Hardware Cask 6 | Logistics | 0.6 | 80.6941 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 |  | N/A | N/A
|  | Deploy Blanket Transporter | Logistics | 0.38 | 81.0741 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install RIB Blanket Segment | Operation | 4.33 | 90.1643 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A | RIB Blanket Segment Collected; Hardware Cask 6 docked | 85.8343 | -4.7602
|  | Collect Blanket Segment 4 from Hardware Cask 5 | Logistics | 0.6 | 90.7643 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 |  | N/A | N/A
|  | Deploy Blanket Transporter | Logistics | 0.38 | 91.1443 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install LIB Blanket Segment | Operation | 4.33 | 100.2345 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A | LIB Blanket Segment Collected; Hardware Cask 5 docked | 95.9045 | -4.7602
|  | Collect Blanket Segment 3 from Hardware Cask 6 | Logistics | 0.6 | 100.8345 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 |  | N/A | N/A
|  | Deploy Blanket Transporter | Logistics | 0.38 | 101.2145 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install ROB Blanket Segment | Operation | 4.33 | 110.3047 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A | ROB Blanket Segment Collected; Hardware Cask 6 docked | 105.9747 | -4.7602
|  | Collect Blanket Segment 2 from Hardware Cask 5 | Logistics | 0.6 | 110.9047 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 |  | N/A | N/A
|  | Deploy Blanket Transporter | Logistics | 0.38 | 111.2847 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install LOB Blanket Segment | Operation | 4.33 | 120.3748 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A | LOB Blanket Segment Collected; Hardware Cask 5 docked | 116.0448 | -4.7602
|  | Collect Blanket Segment 1 from Hardware Cask 6 | Logistics | 0.6 | 120.9748 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 |  | N/A | N/A
|  | Deploy Blanket Transporter | Logistics | 0.38 | 121.3548 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install COB Blanket Segment | Operation | 4.33 | 130.445 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A | COB Blanket Segment Collected; Hardware Cask 6 docked | 126.115 | -4.7602
| Install RIB Pipe Module | Collect RIB Pipe Module from Hardware Cask 2 | Logistics | 0.6 | 136.9017 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 | Equipment Cask 6 stored; Equipment Cask 2 Collected; Hardware Cask 2 docked; RIB Pipe Module Collected | 136.3017 | -5.8567
|  | Deploy Pipe Lifter | Logistics | 0.38 | 137.2817 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install RIB Pipe Module | Operation | 4.095 | 141.3767 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Pipe Lifter in Equipment Cask 2 | Logistics | 0.38 | 141.7567 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Connect RIB Pipe Module | Deploy Service Joint System from Equipment Cask 2 | Logistics | 0.38 | 142.1367 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Weld RIB Pipe Module | Operation | 24.0227 | 166.1594 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Service Joint System in Equipment Cask 2 | Logistics | 0.38 | 166.5394 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 | RIB Lower Port Pipe Module installed | N/A | N/A
|  | Deploy Multifunction Manipulator | Logistics | 0.38 | 166.9194 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Connect Multipipe Flange 5 | Operation | 7.83 | 174.7494 | Connect Multipipe Flange & Access Lid | 7.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Multifunction Manipulator in Equipment Cask 2 | Logistics | 0.38 | 175.1294 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Install LIB Pipe Module | Collect LIB Pipe Module from Hardware Cask 4 | Logistics | 0.6 | 175.7294 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 | Hardware Cask 2 Un-Docked; LIB Pipe Module Collected; Hardware Cask 4 docked | 146.6826 | 28.4468
|  | Deploy Pipe Lifter | Logistics | 0.38 | 176.1094 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install LIB Pipe Module | Operation | 4.095 | 180.2044 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Pipe Lifter in Equipment Cask 2 | Logistics | 0.38 | 180.5844 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Connect LIB Pipe Module | Deploy Service Joint System from Equipment Cask 2 | Logistics | 0.38 | 180.9644 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Weld LIB Pipe Module | Operation | 24.0227 | 204.9872 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Service Joint System in Equipment Cask 2 | Logistics | 0.38 | 205.3672 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 | LIB Lower Port Pipe Module installed | N/A | N/A
|  | Deploy Multifunction Manipulator | Logistics | 0.38 | 205.7472 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Connect Multipipe Flange 4 | Operation | 7.83 | 213.5772 | Connect Multipipe Flange & Access Lid | 7.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Multifunction Manipulator in Equipment Cask 2 | Logistics | 0.38 | 213.9572 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Install ROB Pipe Module | Collect ROB Pipe Module from Hardware Cask 2 | Logistics | 0.6 | 214.5572 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 | Hardware Cask 4 Un-Docked; ROB Pipe Module Collected; Hardware Cask 2 docked | 185.5104 | 28.4468
|  | Deploy Pipe Lifter | Logistics | 0.38 | 214.9372 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install ROB Pipe Module | Operation | 4.095 | 219.0322 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Pipe Lifter in Equipment Cask 2 | Logistics | 0.38 | 219.4122 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Connect ROB Pipe Module | Deploy Service Joint System from Equipment Cask 2 | Logistics | 0.38 | 219.7922 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Weld ROB Pipe Module | Operation | 24.0227 | 243.8149 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Service Joint System in Equipment Cask 2 | Logistics | 0.38 | 244.1949 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 | ROB Lower Port Pipe Module installed | N/A | N/A
|  | Deploy Multifunction Manipulator | Logistics | 0.38 | 244.5749 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Connect Multipipe Flange 4 | Operation | 7.83 | 252.4049 | Connect Multipipe Flange & Access Lid | 7.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Multifunction Manipulator in Equipment Cask 2 | Logistics | 0.38 | 252.7849 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Install LOB Pipe Module | Collect LOB Pipe Module from Hardware Cask 4 | Logistics | 0.6 | 253.3849 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 | Hardware Cask 2 Un-Docked; LOB Pipe Module Collected; Hardware Cask 4 docked | 224.3381 | 28.4468
|  | Deploy Pipe Lifter | Logistics | 0.38 | 253.7649 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install LOB Pipe Module | Operation | 4.095 | 257.8599 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Pipe Lifter in Equipment Cask 2 | Logistics | 0.38 | 258.2399 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Connect LOB Pipe Module | Deploy Service Joint System from Equipment Cask 2 | Logistics | 0.38 | 258.6199 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Weld ROB Pipe Module | Operation | 24.0227 | 282.6426 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Service Joint System in Equipment Cask 2 | Logistics | 0.38 | 283.0226 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 | LOB Lower Port Pipe Module installed | N/A | N/A
|  |  | Total |  | 283.0226
Failure of ROB Vertical Port Welds
Assumptions:
|  | TIG welding and laser cutting is the current worst case scenario | [14 empty] | Single Port | DEMO
|  | In-situ surface treatment is not possible, so all hardware must be removed and replaced/reconditioned before it can be re-welded | [13 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
|  | All other positioning, delivery and retrieval operations are of a similar length to nominal operations | [13 empty] | Duration of welding operations (h) | 24.0227 | 432.4092 | 216.2046 | 144.1364 | 120.1137 | 72.0682
|  | Service Joint system is capable of cutting and pipes without tool change | [13 empty] | Estimated number of failures, impacting all RM systems equally | 0.26425 | 4.7565 | 2.3783 | 1.5855 | 1.3213 | 0.79275
|  | No additional blanket modules will need to be removed to access impacted blanket module | [13 empty] | Operational contribution | 44.7502 | 805.5037 | 402.7518 | 268.5012 | 223.751 | 134.2506
[16 empty] | Logistical contribution | 8.456 | 152.208 | 76.104 | 50.736 | 42.28 | 25.368
|  | Failure rate: | 1.1% | [12 empty] | Idle time waiting for dependent operations | 8.2795 | 149.0309 | 74.5154 | 49.677 | 41.3975 | 24.8385
|  | Assuming a weld failure rate of | 0.1% | [12 empty] | Total Duration of Recovery Operations | 61.4857 | 1106.7426 | 553.3713 | 368.9142 | 307.4285 | 184.4571
|  | Assuming a tool failure rate of | 1%
|  | Probability of Secondary Failure/hr or Event | 0.07063%
[6 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies
| Group | Pipe weld failure (Sub Tasks) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack
| Cut Failed Welds | Weld Failure identified at ROB/Pipe Module joint | Operation | 0 | 0 | Hardware Recovery Required | 0 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Cut Failed ROB Pipe Module Weld | Operation | 1.0499 | 1.0499 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| ROB Blanket Pipework Removal | Deploy Pipe Lifter | Logistics | 0.38 | 1.4299 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Extract ROB Pipe Module | Operation | 0.725 | 2.1549 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store ROB Pipe Module In Hardware Cask 4 | Logistics | 0.63 | 2.7849 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | LOB Pipe Module stored; Hardware Cask 4 docked | N/A | N/A
|  | Store Pipe Lifter in Equipment Cask 2 | Logistics | 0.38 | 3.1649 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| LIB Blanket Pipework Disconnection | Deploy Multifunction Manipulator | Logistics | 0.38 | 3.5449 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Disconnect Multipipe Flange 4 | Operation | 6.83 | 10.3749 | Disconnect Multipipe Flange & Access Lid | 6.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Multifunction Manipulator in Equipment Cask 2 | Logistics | 0.38 | 10.7549 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
|  | Deploy Service Joint System | Logistics | 0.38 | 11.1349 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Cut LIB Pipe joint | Operation | 1.0499 | 12.1848 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Service Joint System in Equipment Cask 2 | Logistics | 0.38 | 12.5648 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| LIB Blanket Pipework Removal | Deploy Pipe Lifter | Logistics | 0.38 | 12.9448 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Extract LIB Pipe Module | Operation | 0.725 | 13.6698 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store LIB Pipe Module In Hardware Cask 4 | Logistics | 0.63 | 14.2998 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | ROB Pipe Module stored; Hardware Cask 4 docked | 7.4608 | 6.209
|  | Store Pipe Lifter in Equipment Cask 2 | Logistics | 0.38 | 14.6798 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| RIB Blanket Pipework Disconnection | Deploy Multifunction Manipulator | Logistics | 0.38 | 15.0598 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Disconnect Multipipe Flange 5 | Operation | 6.83 | 21.8898 | Disconnect Multipipe Flange & Access Lid | 6.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Multifunction Manipulator in Equipment Cask 2 | Logistics | 0.38 | 22.2698 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
|  | Deploy Service Joint System | Logistics | 0.38 | 22.6498 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Cut RIB Pipe joint | Operation | 1.0499 | 23.6997 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Service Joint System in Equipment Cask 2 | Logistics | 0.38 | 24.0797 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| RIB Blanket Pipework Removal | Deploy Pipe Lifter | Logistics | 0.38 | 24.4597 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Extract RIB Pipe Module | Operation | 0.725 | 25.1847 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store RIB Pipe Module In Hardware Cask 4 | Logistics | 0.63 | 25.8147 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | LIB Pipe Module stored; Hardware Cask 4 docked | 18.9758 | 6.209
|  | Store Pipe Lifter in Equipment Cask 2 | Logistics | 0.38 | 26.1947 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Equipment Cask 2 | Logistics | 2.54 | 28.7347 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Equipment Cask | 2.54 |  | N/A | N/A
| Blanket Removal | Dock Equipment Cask 3 | Logistics | 1.64 | 32.0492 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Equipment Cask | 1.64 | Equipment Cask 3 collected; Equipment Cask 3 moved to equipment stillage | 30.4092 | -1.6744
|  | Deploy Blanket Transporter | Logistics | 0.38 | 32.4292 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Extract COB Blanket Segment | Operation | 5.74 | 38.1692 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store COB Blanket Segment in Hardware Cask 5 | Logistics | 0.63 | 38.7992 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | RIB Pipe Module stored; Hardware Cask 4 stored; Hardware Cask 5 collected; Hardware Cask 5 docked | 32.034 | 6.1352
|  | Deploy Blanket Transporter | Logistics | 0.5 | 39.2992 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Equipment from Store | 0.5 |  | N/A | N/A
|  | Extract LOB Blanket Segment | Operation | 5.74 | 45.0392 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store LOB Blanket Segment in Hardware Cask 6 | Logistics | 0.63 | 45.6692 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | Equipment Cask 2 stored; Hardware Cask 6 Collected; Hardware Cask 6 docked | 6.9416 | 38.0976
|  | Deploy Blanket Transporter | Logistics | 0.5 | 46.1692 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Equipment from Store | 0.5 |  | N/A | N/A
|  | Extract ROB Blanket Segment | Operation | 5.74 | 51.9092 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store ROB Blanket Segment in Hardware Cask 5 | Logistics | 0.63 | 52.5392 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | COB Blanket Segment stored; Hardware Cask 5 docked | 44.1051 | 7.8041
|  | Deploy Blanket Transporter | Logistics | 0.5 | 53.0392 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Equipment from Store | 0.5 |  | N/A | N/A
|  | Extract LIB Blanket Segment | Operation | 5.74 | 58.7792 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store LIB Blanket Segment in Hardware Cask 6 | Logistics | 0.63 | 59.4092 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | LOB Blanket Segment stored; Hardware Cask 6 docked | 50.9751 | 7.8041
|  | Deploy Blanket Transporter | Logistics | 0.5 | 59.9092 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Equipment from Store | 0.5 |  | N/A | N/A
|  | Extract RIB Blanket Segment | Operation | 5.74 | 65.6492 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store RIB Blanket Segment in Hardware Cask 5 | Logistics | 0.63 | 66.2792 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | ROB Blanket Segment stored; Hardware Cask 5 docked | 57.8451 | 7.8041
|  | Un-Dock Hardware Cask 5 | Logistics | 2.3 | 68.5792 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3 |  | N/A | N/A
| Blanket Installation | Collect Blanket Segment 5 from Hardware Cask 6 | Logistics | 0.6 | 69.1792 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 |  | N/A | N/A
|  | Deploy Blanket Transporter | Logistics | 0.38 | 69.5592 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install RIB Blanket Segment | Operation | 4.33 | 78.6494 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A | RIB Blanket Segment Collected; Hardware Cask 6 docked | 74.3194 | -4.7602
|  | Collect Blanket Segment 4 from Hardware Cask 5 | Logistics | 0.6 | 79.2494 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 |  | N/A | N/A
|  | Deploy Blanket Transporter | Logistics | 0.38 | 79.6294 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install LIB Blanket Segment | Operation | 4.33 | 88.7196 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A | LIB Blanket Segment Collected; Hardware Cask 5 docked | 84.3896 | -4.7602
|  | Collect Blanket Segment 3 from Hardware Cask 6 | Logistics | 0.6 | 89.3196 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 |  | N/A | N/A
|  | Deploy Blanket Transporter | Logistics | 0.38 | 89.6996 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install ROB Blanket Segment | Operation | 4.33 | 98.7897 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A | ROB Blanket Segment Collected; Hardware Cask 6 docked | 94.4597 | -4.7602
|  | Collect Blanket Segment 2 from Hardware Cask 5 | Logistics | 0.6 | 99.3897 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 |  | N/A | N/A
|  | Deploy Blanket Transporter | Logistics | 0.38 | 99.7697 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install LOB Blanket Segment | Operation | 4.33 | 108.8599 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A | LOB Blanket Segment Collected; Hardware Cask 5 docked | 104.5299 | -4.7602
|  | Collect Blanket Segment 1 from Hardware Cask 6 | Logistics | 0.6 | 109.4599 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 |  | N/A | N/A
|  | Deploy Blanket Transporter | Logistics | 0.38 | 109.8399 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install COB Blanket Segment | Operation | 4.33 | 118.9301 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A | COB Blanket Segment Collected; Hardware Cask 6 docked | 114.6001 | -4.7602
| Install RIB Pipe Module | Collect RIB Pipe Module from Hardware Cask 2 | Logistics | 0.6 | 125.3868 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 | Equipment Cask 6 stored; Equipment Cask 2 Collected; Hardware Cask 2 docked; RIB Pipe Module Collected | 124.7868 | -5.8567
|  | Deploy Pipe Lifter | Logistics | 0.38 | 125.7668 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install RIB Pipe Module | Operation | 4.095 | 129.8618 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Pipe Lifter in Equipment Cask 2 | Logistics | 0.38 | 130.2418 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Connect RIB Pipe Module | Deploy Service Joint System from Equipment Cask 2 | Logistics | 0.38 | 130.6218 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Weld RIB Pipe Module | Operation | 24.0227 | 154.6445 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Service Joint System in Equipment Cask 2 | Logistics | 0.38 | 155.0245 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 | RIB Lower Port Pipe Module installed | N/A | N/A
|  | Deploy Multifunction Manipulator | Logistics | 0.38 | 155.4045 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Connect Multipipe Flange 5 | Operation | 7.83 | 163.2345 | Connect Multipipe Flange & Access Lid | 7.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Multifunction Manipulator in Equipment Cask 2 | Logistics | 0.38 | 163.6145 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Install LIB Pipe Module | Collect LIB Pipe Module from Hardware Cask 4 | Logistics | 0.6 | 164.2145 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 | Hardware Cask 2 Un-Docked; LIB Pipe Module Collected; Hardware Cask 4 docked | 135.1677 | 28.4468
|  | Deploy Pipe Lifter | Logistics | 0.38 | 164.5945 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install LIB Pipe Module | Operation | 4.095 | 168.6895 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Pipe Lifter in Equipment Cask 2 | Logistics | 0.38 | 169.0695 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Connect LIB Pipe Module | Deploy Service Joint System from Equipment Cask 2 | Logistics | 0.38 | 169.4495 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Weld LIB Pipe Module | Operation | 24.0227 | 193.4722 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Service Joint System in Equipment Cask 2 | Logistics | 0.38 | 193.8522 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 | LIB Lower Port Pipe Module installed | N/A | N/A
|  | Deploy Multifunction Manipulator | Logistics | 0.38 | 194.2322 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Connect Multipipe Flange 4 | Operation | 7.83 | 202.0622 | Connect Multipipe Flange & Access Lid | 7.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Multifunction Manipulator in Equipment Cask 2 | Logistics | 0.38 | 202.4422 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Install ROB Pipe Module | Collect ROB Pipe Module from Hardware Cask 2 | Logistics | 0.6 | 203.0422 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 | Hardware Cask 4 Un-Docked; ROB Pipe Module Collected; Hardware Cask 2 docked | 173.9954 | 28.4468
|  | Deploy Pipe Lifter | Logistics | 0.38 | 203.4222 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install ROB Pipe Module | Operation | 4.095 | 207.5172 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Pipe Lifter in Equipment Cask 2 | Logistics | 0.38 | 207.8972 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Connect ROB Pipe Module | Deploy Service Joint System from Equipment Cask 2 | Logistics | 0.38 | 208.2772 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Weld ROB Pipe Module | Operation | 24.0227 | 232.3 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Service Joint System in Equipment Cask 2 | Logistics | 0.38 | 232.68 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 | ROB Lower Port Pipe Module installed | N/A | N/A
|  |  | Total |  | 232.68
Failure of LIB Vertical Port Welds
Assumptions:
|  | TIG welding and laser cutting is the current worst case scenario | [14 empty] | Single Port | DEMO
|  | In-situ surface treatment is not possible, so all hardware must be removed and replaced/reconditioned before it can be re-welded | [13 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
|  | All other positioning, delivery and retrieval operations are of a similar length to nominal operations | [13 empty] | Duration of welding operations (h) | 24.0227 | 108 | 54 | 36 | 30 | 18
|  | Service Joint system is capable of cutting and pipes without tool change | [13 empty] | Estimated number of failures, impacting all RM systems equally | 0.26425 | 1.188 | 0.594 | 0.396 | 0.33 | 0.198
|  | No additional blanket modules will need to be removed to access impacted blanket module | [13 empty] | Operational contribution | 35.0594 | 157.6182 | 78.8091 | 52.5394 | 43.7828 | 26.2697
[16 empty] | Logistical contribution | 7.3277 | 32.9432 | 16.4716 | 10.9811 | 9.1509 | 5.4905
|  | Failure rate: | 1.1% | [12 empty] | Idle time waiting for dependent operations | 8.2795 | 37.2225 | 18.6112 | 12.4075 | 10.3396 | 6.2037
|  | Assuming a weld failure rate of | 0.1% | [12 empty] | Total Duration of Recovery Operations | 50.6666 | 227.7839 | 113.8919 | 75.928 | 63.2733 | 37.964
|  | Assuming a tool failure rate of | 1%
|  | Probability of Secondary Failure/hr or Event | 0.07063%
[6 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies
| Group | Pipe weld failure (Sub Tasks) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End
| Cut Failed Welds | Weld Failure identified at LIB/Pipe Module joint | Operation | 0 | 0 | Hardware Recovery Required | 0 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Cut Failed LIB Pipe Module Weld | Operation | 1.0499 | 1.0499 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| LIB Blanket Pipework Disconnection | Deploy Multifunction Manipulator | Logistics | 0.38 | 1.4299 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Disconnect Multipipe Flange 4 | Operation | 6.83 | 8.2599 | Disconnect Multipipe Flange & Access Lid | 6.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Multifunction Manipulator in Equipment Cask 2 | Logistics | 0.38 | 8.6399 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
|  | Deploy Service Joint System | Logistics | 0.38 | 9.0199 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Cut LIB Pipe joint | Operation | 1.0499 | 10.0698 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Service Joint System in Equipment Cask 2 | Logistics | 0.38 | 10.4498 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| LIB Blanket Pipework Removal | Deploy Pipe Lifter | Logistics | 0.38 | 10.8298 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Extract LIB Pipe Module | Operation | 0.725 | 11.5548 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store LIB Pipe Module In Hardware Cask 4 | Logistics | 0.63 | 12.1848 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | ROB Pipe Module stored; Hardware Cask 4 docked | N/A | N/A
|  | Store Pipe Lifter in Equipment Cask 2 | Logistics | 0.38 | 12.5648 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| RIB Blanket Pipework Disconnection | Deploy Multifunction Manipulator | Logistics | 0.38 | 12.9448 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Disconnect Multipipe Flange 5 | Operation | 6.83 | 19.7748 | Disconnect Multipipe Flange & Access Lid | 6.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Multifunction Manipulator in Equipment Cask 2 | Logistics | 0.38 | 20.1548 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
|  | Deploy Service Joint System | Logistics | 0.38 | 20.5348 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Cut RIB Pipe joint | Operation | 1.0499 | 21.5847 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Service Joint System in Equipment Cask 2 | Logistics | 0.38 | 21.9647 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| RIB Blanket Pipework Removal | Deploy Pipe Lifter | Logistics | 0.38 | 22.3447 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Extract RIB Pipe Module | Operation | 0.725 | 23.0697 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store RIB Pipe Module In Hardware Cask 4 | Logistics | 0.63 | 23.6997 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | LIB Pipe Module stored; Hardware Cask 4 docked | 16.8608 | 6.209
|  | Store Pipe Lifter in Equipment Cask 2 | Logistics | 0.38 | 24.0797 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Equipment Cask 2 | Logistics | 2.54 | 26.6197 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Equipment Cask | 2.54 |  | N/A | N/A
| Blanket Removal | Dock Equipment Cask 3 | Logistics | 1.64 | 29.9342 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Equipment Cask | 1.64 | Equipment Cask 3 collected; Equipment Cask 3 moved to equipment stillage | 28.2942 | -1.6744
|  | Deploy Blanket Transporter | Logistics | 0.38 | 30.3142 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Extract COB Blanket Segment | Operation | 5.74 | 36.0542 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store COB Blanket Segment in Hardware Cask 5 | Logistics | 0.63 | 36.6842 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | RIB Pipe Module stored; Hardware Cask 4 stored; Hardware Cask 5 collected; Hardware Cask 5 docked | 29.919 | 6.1352
|  | Deploy Blanket Transporter | Logistics | 0.5 | 37.1842 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Equipment from Store | 0.5 |  | N/A | N/A
|  | Extract LOB Blanket Segment | Operation | 5.74 | 42.9242 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store LOB Blanket Segment in Hardware Cask 6 | Logistics | 0.63 | 43.5542 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | Equipment Cask 2 stored; Hardware Cask 6 Collected; Hardware Cask 6 docked | 29.9335 | 12.9907
|  | Deploy Blanket Transporter | Logistics | 0.5 | 44.0542 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Equipment from Store | 0.5 |  | N/A | N/A
|  | Extract ROB Blanket Segment | Operation | 5.74 | 49.7942 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store ROB Blanket Segment in Hardware Cask 5 | Logistics | 0.63 | 50.4242 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | COB Blanket Segment stored; Hardware Cask 5 docked | 41.9901 | 7.8041
|  | Deploy Blanket Transporter | Logistics | 0.5 | 50.9242 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Equipment from Store | 0.5 |  | N/A | N/A
|  | Extract LIB Blanket Segment | Operation | 5.74 | 56.6642 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store LIB Blanket Segment in Hardware Cask 6 | Logistics | 0.63 | 57.2942 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | LOB Blanket Segment stored; Hardware Cask 6 docked | 48.8601 | 7.8041
|  | Deploy Blanket Transporter | Logistics | 0.5 | 57.7942 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Equipment from Store | 0.5 |  | N/A | N/A
|  | Extract RIB Blanket Segment | Operation | 5.74 | 63.5342 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store RIB Blanket Segment in Hardware Cask 5 | Logistics | 0.63 | 64.1642 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | ROB Blanket Segment stored; Hardware Cask 5 docked | 55.7301 | 7.8041
|  | Un-Dock Hardware Cask 5 | Logistics | 2.3 | 66.4642 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3 |  | N/A | N/A
| Blanket Installation | Collect Blanket Segment 5 from Hardware Cask 6 | Logistics | 0.6 | 67.0642 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 |  | N/A | N/A
|  | Deploy Blanket Transporter | Logistics | 0.38 | 67.4442 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install RIB Blanket Segment | Operation | 4.33 | 76.5344 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A | RIB Blanket Segment Collected; Hardware Cask 6 docked | 72.2044 | -4.7602
|  | Collect Blanket Segment 4 from Hardware Cask 5 | Logistics | 0.6 | 77.1344 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 |  | N/A | N/A
|  | Deploy Blanket Transporter | Logistics | 0.38 | 77.5144 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install LIB Blanket Segment | Operation | 4.33 | 86.6046 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A | LIB Blanket Segment Collected; Hardware Cask 5 docked | 82.2746 | -4.7602
|  | Collect Blanket Segment 3 from Hardware Cask 6 | Logistics | 0.6 | 87.2046 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 |  | N/A | N/A
|  | Deploy Blanket Transporter | Logistics | 0.38 | 87.5846 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install ROB Blanket Segment | Operation | 4.33 | 96.6747 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A | ROB Blanket Segment Collected; Hardware Cask 6 docked | 92.3447 | -4.7602
|  | Collect Blanket Segment 2 from Hardware Cask 5 | Logistics | 0.6 | 97.2747 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 |  | N/A | N/A
|  | Deploy Blanket Transporter | Logistics | 0.38 | 97.6547 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install LOB Blanket Segment | Operation | 4.33 | 106.7449 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A | LOB Blanket Segment Collected; Hardware Cask 5 docked | 102.4149 | -4.7602
|  | Collect Blanket Segment 1 from Hardware Cask 6 | Logistics | 0.6 | 107.3449 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 |  | N/A | N/A
|  | Deploy Blanket Transporter | Logistics | 0.38 | 107.7249 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install COB Blanket Segment | Operation | 4.33 | 116.8151 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A | COB Blanket Segment Collected; Hardware Cask 6 docked | 112.4851 | -4.7602
| Install RIB Pipe Module | Collect RIB Pipe Module from Hardware Cask 2 | Logistics | 0.6 | 123.2718 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 | Equipment Cask 6 stored; Equipment Cask 2 Collected; Hardware Cask 2 docked; RIB Pipe Module Collected | 122.6718 | -5.8567
|  | Deploy Pipe Lifter | Logistics | 0.38 | 123.6518 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install RIB Pipe Module | Operation | 4.095 | 127.7468 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Pipe Lifter in Equipment Cask 2 | Logistics | 0.38 | 128.1268 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Connect RIB Pipe Module | Deploy Service Joint System from Equipment Cask 2 | Logistics | 0.38 | 128.5068 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Weld RIB Pipe Module | Operation | 24.0227 | 152.5295 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Service Joint System in Equipment Cask 2 | Logistics | 0.38 | 152.9095 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 | RIB Lower Port Pipe Module installed | N/A | N/A
|  | Deploy Multifunction Manipulator | Logistics | 0.38 | 153.2895 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Connect Multipipe Flange 5 | Operation | 7.83 | 161.1195 | Connect Multipipe Flange & Access Lid | 7.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Multifunction Manipulator in Equipment Cask 2 | Logistics | 0.38 | 161.4995 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Install LIB Pipe Module | Collect LIB Pipe Module from Hardware Cask 4 | Logistics | 0.6 | 162.0995 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 | Hardware Cask 2 Un-Docked; LIB Pipe Module Collected; Hardware Cask 4 docked | 133.0527 | 28.4468
|  | Deploy Pipe Lifter | Logistics | 0.38 | 162.4795 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install LIB Pipe Module | Operation | 4.095 | 166.5745 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Pipe Lifter in Equipment Cask 2 | Logistics | 0.38 | 166.9545 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Connect LIB Pipe Module | Deploy Service Joint System from Equipment Cask 2 | Logistics | 0.38 | 167.3345 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Weld ROB Pipe Module | Operation | 24.0227 | 191.3572 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Service Joint System in Equipment Cask 2 | Logistics | 0.38 | 191.7372 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 | LIB Lower Port Pipe Module installed | N/A | N/A
|  |  | Total |  | 191.7372
Failure of RIB Vertical Port Welds
Assumptions:
|  | TIG welding and laser cutting is the current worst case scenario | [14 empty] | Single Port | DEMO
|  | In-situ surface treatment is not possible, so all hardware must be removed and replaced/reconditioned before it can be re-welded | [13 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
|  | All other positioning, delivery and retrieval operations are of a similar length to nominal operations | [13 empty] | Duration of welding operations (h) | 24.0227 | 108 | 54 | 36 | 30 | 18
|  | Service Joint system is capable of cutting and pipes without tool change | [13 empty] | Estimated number of failures, impacting all RM systems equally | 0.26425 | 1.188 | 0.594 | 0.396 | 0.33 | 0.198
|  | No additional blanket modules will need to be removed to access impacted blanket module | [13 empty] | Operational contribution | 21.2041 | 95.3283 | 47.6641 | 31.7761 | 26.4801 | 15.888
[16 empty] | Logistical contribution | 5.396 | 24.259 | 12.1295 | 8.0863 | 6.7386 | 4.0432
|  | Failure rate: | 1.1% | [12 empty] | Idle time waiting for dependent operations | 13.8062 | 62.0693 | 31.0346 | 20.6898 | 17.2415 | 10.3449
|  | Assuming a weld failure rate of | 0.1% | [12 empty] | Total Duration of Recovery Operations | 40.4063 | 181.6565 | 90.8283 | 60.5522 | 50.4601 | 30.2761
|  | Assuming a tool failure rate of | 1%
|  | Probability of Secondary Failure/hr or Event | 0.07063%
[6 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies
| Group | Pipe weld failure (Sub Tasks) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End
| Cut Failed Welds | Weld Failure identified at RIB/Pipe Module joint | Operation | 0 | 0 | Hardware Recovery Required | 0 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Cut Failed RIB Pipe Module Weld | Operation | 1.0499 | 1.0499 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| RIB Blanket Pipework Removal | Deploy Pipe Lifter | Logistics | 0.38 | 1.4299 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Extract RIB Pipe Module | Operation | 0.725 | 2.1549 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store RIB Pipe Module In Hardware Cask 4 | Logistics | 0.63 | 17.4908 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | LIB Pipe Module stored; Hardware Cask 4 docked | 16.8608 | -14.7058
|  | Store Pipe Lifter in Equipment Cask 2 | Logistics | 0.38 | 17.8708 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
|  | Un-Dock Equipment Cask 2 | Logistics | 2.54 | 20.4108 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Equipment Cask | 2.54 |  | N/A | N/A
| Blanket Removal | Dock Equipment Cask 3 | Logistics | 1.64 | 29.9342 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Equipment Cask | 1.64 | Equipment Cask 3 collected; Equipment Cask 3 moved to equipment stillage | 28.2942 | -7.8834
|  | Deploy Blanket Transporter | Logistics | 0.38 | 30.3142 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Extract COB Blanket Segment | Operation | 5.74 | 36.0542 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store COB Blanket Segment in Hardware Cask 5 | Logistics | 0.63 | 36.6842 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | RIB Pipe Module stored; Hardware Cask 4 stored; Hardware Cask 5 collected; Hardware Cask 5 docked | 29.919 | 6.1352
|  | Deploy Blanket Transporter | Logistics | 0.5 | 37.1842 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Equipment from Store | 0.5 |  | N/A | N/A
|  | Extract LOB Blanket Segment | Operation | 5.74 | 42.9242 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store LOB Blanket Segment in Hardware Cask 6 | Logistics | 0.63 | 43.5542 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | Equipment Cask 2 stored; Hardware Cask 6 Collected; Hardware Cask 6 docked | 29.9335 | 12.9907
|  | Deploy Blanket Transporter | Logistics | 0.5 | 44.0542 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Equipment from Store | 0.5 |  | N/A | N/A
|  | Extract ROB Blanket Segment | Operation | 5.74 | 49.7942 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store ROB Blanket Segment in Hardware Cask 5 | Logistics | 0.63 | 50.4242 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | COB Blanket Segment stored; Hardware Cask 5 docked | 41.9901 | 7.8041
|  | Deploy Blanket Transporter | Logistics | 0.5 | 50.9242 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Equipment from Store | 0.5 |  | N/A | N/A
|  | Extract LIB Blanket Segment | Operation | 5.74 | 56.6642 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store LIB Blanket Segment in Hardware Cask 6 | Logistics | 0.63 | 57.2942 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | LOB Blanket Segment stored; Hardware Cask 6 docked | 48.8601 | 7.8041
|  | Deploy Blanket Transporter | Logistics | 0.5 | 57.7942 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Equipment from Store | 0.5 |  | N/A | N/A
|  | Extract RIB Blanket Segment | Operation | 5.74 | 63.5342 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store RIB Blanket Segment in Hardware Cask 5 | Logistics | 0.63 | 64.1642 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | ROB Blanket Segment stored; Hardware Cask 5 docked | 55.7301 | 7.8041
|  | Un-Dock Hardware Cask 5 | Logistics | 2.3 | 66.4642 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3 |  | N/A | N/A
| Blanket Installation | Collect Blanket Segment 5 from Hardware Cask 6 | Logistics | 0.6 | 67.0642 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 |  | N/A | N/A
|  | Deploy Blanket Transporter | Logistics | 0.38 | 67.4442 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install RIB Blanket Segment | Operation | 4.33 | 76.5344 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A | RIB Blanket Segment Collected; Hardware Cask 6 docked | 72.2044 | -4.7602
|  | Collect Blanket Segment 4 from Hardware Cask 5 | Logistics | 0.6 | 77.1344 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 |  | N/A | N/A
|  | Deploy Blanket Transporter | Logistics | 0.38 | 77.5144 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install LIB Blanket Segment | Operation | 4.33 | 86.6046 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A | LIB Blanket Segment Collected; Hardware Cask 5 docked | 82.2746 | -4.7602
|  | Collect Blanket Segment 3 from Hardware Cask 6 | Logistics | 0.6 | 87.2046 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 |  | N/A | N/A
|  | Deploy Blanket Transporter | Logistics | 0.38 | 87.5846 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install ROB Blanket Segment | Operation | 4.33 | 96.6747 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A | ROB Blanket Segment Collected; Hardware Cask 6 docked | 92.3447 | -4.7602
|  | Collect Blanket Segment 2 from Hardware Cask 5 | Logistics | 0.6 | 97.2747 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 |  | N/A | N/A
|  | Deploy Blanket Transporter | Logistics | 0.38 | 97.6547 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install LOB Blanket Segment | Operation | 4.33 | 106.7449 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A | LOB Blanket Segment Collected; Hardware Cask 5 docked | 102.4149 | -4.7602
|  | Collect Blanket Segment 1 from Hardware Cask 6 | Logistics | 0.6 | 107.3449 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 |  | N/A | N/A
|  | Deploy Blanket Transporter | Logistics | 0.38 | 107.7249 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install COB Blanket Segment | Operation | 4.33 | 116.8151 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A | COB Blanket Segment Collected; Hardware Cask 6 docked | 112.4851 | -4.7602
| Install RIB Pipe Module | Collect RIB Pipe Module from Hardware Cask 2 | Logistics | 0.6 | 123.2718 |  | N/A |  |  |  | N/A | N/A | N/A | Export Hardware from Hardware Cask | 0.6 | Equipment Cask 6 stored; Equipment Cask 2 Collected; Hardware Cask 2 docked; RIB Pipe Module Collected | 122.6718 | -5.8567
|  | Deploy Pipe Lifter | Logistics | 0.38 | 123.6518 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Install RIB Pipe Module | Operation | 4.095 | 127.7468 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Pipe Lifter in Equipment Cask 2 | Logistics | 0.38 | 128.1268 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 |  | N/A | N/A
| Connect RIB Pipe Module | Deploy Service Joint System from Equipment Cask 2 | Logistics | 0.38 | 128.5068 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Tool From Equipment Cask | 0.38 |  | N/A | N/A
|  | Weld ROB Pipe Module | Operation | 24.0227 | 152.5295 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Store Service Joint System in Equipment Cask 2 | Logistics | 0.38 | 152.9095 |  | N/A |  |  |  | N/A | N/A | N/A | Store Tool In Equipment Cask | 0.38 | RIB Lower Port Pipe Module Installed | N/A | N/A
|  |  | Total |  | 152.9095

## Upper Cask Recovery Scenarios (hidden)
Delay caused by failure and recovery of remote handling equipment
Additional tasks required to recover from failures
General Assumptions:
There are two sorts of process failure considered; failure of a weld and failure of a mechanical connection, both uncovered by failure to pass acceptance criteria
In addition five types of equipment failure are considered; Pipe interface hardware, Overhead Crane, Blanket transporter system, divertor cask system and Multifunction manipulator system
Equipment failure includes tool failure, for example if a weld tool fails during welding
| Single Port | Full DEMO Maintenance
No. Systems | 1 | 1 | 2 | 3 | 4 | 6
Operational contribution | 35.9214 | 646.5855 | 323.2927 | 215.5285 | 179.6071 | 107.7642
Logistical contribution | 63.6897 | 1146.4141 | 573.2071 | 382.138 | 318.4484 | 191.069
Idle time waiting for dependant operations | 0 | 0 | 0 | 0 | 0 | 0
Estimated Delay | 99.6111 | 1792.9996 | 896.4998 | 597.6665 | 498.0555 | 298.8333
Loaded Overhead Crane failure
Assumptions:
Recovery of Blanket Transporter is completed using standard predetermined procedures.
Rare and time consuming special recoveries are not considered
A replacement overhead crane (if required) is available on demand from the AMF
The crane's load is able to be set down in-situ safely, using a rescue system
Failure rate: | 0.1%
Failure rate of Overhead crane per hour | 0.1%
[18 empty] | Loaded Overhead Crane failure | Single Port
[5 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies |  |  | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
RH Cask RHE failure (Sub Tasks) | (Sub Task Notes) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack | Duration of Overhead Crane Tasks per port | 5.3333 | 5.3333 | 5.3333 | 5.3333 | 5.3333 | 5.3333
Move recovery system into the Vertical Port area |  | Movement | 0.069444 | 0.069444 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A | Duration of RM operations (h) | 5.3333 | 96 | 48 | 32 | 26.6667 | 16
Engage the recovery system with the failed hardware |  | Logistics | 1.64 | 1.7094 |  | N/A |  |  |  | N/A | N/A | N/A | Dock equipment cask | 1.64 |  | N/A | N/A | Estimated number of failures, impacting all RM systems equally | 0.0053333 | 0.096 | 0.048 | 0.032 | 0.026667 | 0.016
Recovery system engages crane safety system to lower and detach the suspended load | Assumed to take 4 hours | Operation | 4 | 5.7094 | Recovery Operations | 4 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A | Operational contribution | 0.032 | 0.576 | 0.288 | 0.192 | 0.16 | 0.096
Recovery system moves failed crane to AMF Equipment Receipt for repair | Assumed movement speed at half to speed of the crane | Movement | 0.069444 | 5.7789 |  | N/A | Overhead Crane (Unloaded) | Vertical Port | AMF Equipment Receipt | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A | Logistical contribution | 0.012418 | 0.22352 | 0.11176 | 0.074507 | 0.062089 | 0.037253
Crane is repaired or replaced | Assumed to take 1 hours to identify fault and decide course of action, 1 hour to complete repairs | Operation | 2 | 7.7789 | Recovery Operations | 2 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A | Idle time waiting for dependant operations | 0 | 0 | 0 | 0 | 0 | 0
Crane returned to abandoned payload |  | Movement | 0.069444 | 7.8483 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A | Total Duration of Recovery Operations | 0.044418 | 0.79952 | 0.39976 | 0.26651 | 0.22209 | 0.13325
Abandoned payload is collected |  | Logistics | 0.48 | 8.3283 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48 |  | N/A | N/A
Crane returns to the Vertical Port |  | Movement | 0 | 8.3283 |  | N/A | Overhead Crane (Loaded) | Vertical Port | Vertical Port | 0 | 0.02 | 0 |  | N/A |  | N/A | N/A
|  | Total |  | 8.3283
Cask Transporter failure
Assumptions:
Recovery of Cask Transporter is completed using standard predetermined procedures.
Rare and time consuming special recoveries are not considered
A replacement cask transporter (if required) is available on demand from the AMF
The cask transporter's load is able to be set down in-situ safely, using a rescue system
Failure rate: | 0.0111%
Failure rate of cask transporter crane per hour | 0.0111%
[18 empty] | Cask Transporter failure | Single Port
[5 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies |  |  | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
RH Cask RHE failure (Sub Tasks) | (Sub Task Notes) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack | Duration of Overhead Crane Tasks | 33.1343 | 33.1343 | 33.1343 | 33.1343 | 33.1343 | 33.1343
Move recovery system into the Vertical Port area |  | Movement | 0.069444 | 0.069444 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A | Duration of RM operations (h) | 33.1343 | 596.4167 | 298.2083 | 198.8056 | 165.6713 | 99.4028
Engage the recovery system with the failed cask transporter |  | Logistics | 0.48 | 0.54944 |  | N/A |  |  |  | N/A | N/A | N/A | collect cask | 0.48 |  | N/A | N/A | Estimated number of failures, impacting all RM systems equally | 0.0036779 | 0.066202 | 0.033101 | 0.022067 | 0.01839 | 0.011034
Recovery system engages crane safety system to lower and detach the suspended cask | Assumed to take 4 hours | Operation | 4 | 4.5494 | Recovery Operations | 4 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A | Operational contribution | 0.022067 | 0.39721 | 0.19861 | 0.1324 | 0.11034 | 0.066202
Recovery system moves failed crane to AMF Equipment Receipt for repair | Assumed movement speed at half to speed of the crane | Movement | 0.069444 | 4.6189 |  | N/A | Overhead Crane (Unloaded) | Vertical Port | AMF Equipment Receipt | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A | Logistical contribution | 0.0058295 | 0.10493 | 0.052465 | 0.034977 | 0.029147 | 0.017488
Cask transporter is repaired or replaced | Assumed to take 1 hours to identify fault and decide course of action, 1 hour to complete repairs | Operation | 2 | 6.6189 | Recovery Operations | 2 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A | Idle time waiting for dependant operations | 0 | 0 | 0 | 0 | 0 | 0
cask transporter returned to abandoned cask |  | Movement | 0.069444 | 6.6883 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A | Total Duration of Recovery Operations | 0.027897 | 0.50214 | 0.25107 | 0.16738 | 0.13948 | 0.083691
Abandoned cask is collected |  | Logistics | 0.48 | 7.1683 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48 |  | N/A | N/A
Cask transporter returns to the Vertical Port |  | Movement | 0.41667 | 7.585 |  | N/A | Overhead Crane (Loaded) | bioshield stillage | Vertical Port | 30 | 0.02 | 0.41667 |  | N/A |  | N/A | N/A
|  | Total |  | 7.585
Vertical Maintenance Cask Failure
Assumptions:
Recovery of deployed is completed using standard predetermined procedures.
Rare and time consuming special recoveries are not considered
A replacement overhead crane (if required) is available on demand from the AMF
The crane's load is able to be set down in-situ safely, using a rescue system
Failure rate: | 0.009%
Failure rate of VM Cask per hour | 0.009%
[18 empty] | Vertical Maintenance Cask Failure | Single Port
[5 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies |  |  | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
RH Cask RHE failure (Sub Tasks) | (Sub Task Notes) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack | Duration of Overhead Crane Tasks | 452.451 | 452.451 | 452.451 | 452.451 | 452.451 | 452.451
Move recovery system into the Vertical Port area |  | Movement | 0.069444 | 0.069444 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A | Duration of RM operations (h) | 452.451 | 8144.1183 | 4072.0592 | 2714.7061 | 2262.2551 | 1357.3531
Dock with the VMC |  | Logistics | 1.64 | 1.7094 |  | N/A |  |  |  | N/A | N/A | N/A | Dock equipment cask | 1.64 |  | N/A | N/A | Estimated number of failures, impacting all RM systems equally | 0.040721 | 0.73297 | 0.36649 | 0.24432 | 0.2036 | 0.12216
Commission the RM system and connect to the failed system | Assumed to take 2 hours | Operation | 2 | 3.7094 | Recovery Operations | 2 |  |  |  | N/A | N/A | N/A | collect cask | N/A |  | N/A | N/A | Operational contribution | 0.24432 | 4.3978 | 2.1989 | 1.4659 | 1.2216 | 0.73297
Recovery system engages crane safety system to make the suspended load safe | Assumed to take 4 hours | Operation | 4 | 7.7094 | Recovery Operations | 4 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A | Logistical contribution | 0.45075 | 8.1136 | 4.0568 | 2.7045 | 2.2538 | 1.3523
Recover failed RHE into the failed VMC cask |  | Logistics | 0.38 | 8.0894 |  | N/A |  |  |  | N/A | N/A | N/A | Store tool in equipment cask | 0.38 |  | N/A | N/A | Delay to the Critical Path | 0 | 0 | 0 | 0 | 0 | 0
un-dock the recovery system |  | Logistics | 2.54 | 10.6294 |  | N/A |  |  |  | N/A | N/A | N/A | un-dock equipment cask | 2.54 |  | N/A | N/A | Total Duration of Recovery Operations | 0.69508 | 12.5114 | 6.2557 | 4.1705 | 3.4754 | 2.0852
Un-dock the failed VMC |  | Logistics | 2.54 | 13.1694 |  | N/A |  |  |  | N/A | N/A | N/A | un-dock maintenance cask | 2.54 |  | N/A | N/A
Dock replacement VMC |  | Logistics | 3.9 | 17.0694 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Maintenance Cask | 3.9 | Replacement VMC issued from AMF | 9.2639 | 3.9056
|  | Total |  | 17.0694
Multifunction Manipulator failure
Assumptions:
Recovery of Multifunction Manipulator is completed using standard predetermined procedures.
Rare and time consuming special recoveries are not considered
A replacement Multifunction Manipulator (if required) is available on demand from the AMF
Failure rate: | 2%
Failure rate of Multifunction Manipulator per hour | 2%
[18 empty] | Multifunction Manipulator failure | Single Port
[5 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies |  |  | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
RH Cask RHE failure (Sub Tasks) | (Sub Task Notes) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack | Duration of Multifunction Manipulator Tasks | 181.0417 | 181.0417 | 181.0417 | 181.0417 | 181.0417 | 181.0417
Deploy Recovery System from AMF |  | Movement | 0.069444 | 0.069444 |  | N/A | Overhead crane (unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A | Duration of RM operations (h) | 181.0417 | 3258.75 | 1629.375 | 1086.25 | 905.2083 | 543.125
Dock to failed blanket transporter |  | Logistics | 1.64 | 1.7094 |  | N/A |  |  |  | N/A | N/A | N/A | dock equipment cask | 1.64 |  | N/A | N/A | Estimated number of failures, impacting all RM systems equally | 3.6208 | 65.175 | 32.5875 | 21.725 | 18.1042 | 10.8625
Recover failed MM into the equipment cask |  | Operation | 3 | 4.7094 | Recovery Operations | 3 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A | Operational contribution | 18.1042 | 325.875 | 162.9375 | 108.625 | 90.5208 | 54.3125
Undock recovery system |  | Logistics | 2.54 | 7.2494 |  | N/A |  |  |  | N/A | N/A | N/A | un-dock equipment cask | 2.54 |  | N/A | N/A | Logistical contribution | 31.8975 | 574.1555 | 287.0778 | 191.3852 | 159.4877 | 95.6926
un-dock equipment cask |  | Logistics | 2.54 | 9.7894 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Equipment Cask | 2.54 |  | N/A | N/A | Idle time waiting for dependant operations | 0 | 0 | 0 | 0 | 0 | 0
Replace or repair the Blanket Transporter | Assumed chosen tasks takes 2 hours | Operation | 2 | 11.7894 | Recovery Operations | 2 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A | Total Duration of Recovery Operations | 50.0017 | 900.0305 | 450.0153 | 300.0102 | 250.0085 | 150.0051
dock replacement equipment cask |  | Logistics | 1.64 | 13.4294 |  | N/A |  |  |  | N/A | N/A | N/A | Dock equipment cask | 1.64 | Replacement MM equipment cask issued from AMF | 5.8839 | 5.9056
deploy new MM into port |  | Logistics | 0.38 | 13.8094 |  | N/A |  |  |  | N/A | N/A | N/A | deploy tool from equipment cask | 0.38 |  | N/A | N/A
|  | Total |  | 13.8094
Hardware Cask failure
Assumptions:
Recovery of a cask is completed using standard predetermined procedures.
Rare and time consuming special recoveries are not considered
A new cask and hardware (if required) are available on demand from the AMF
Failure rate: | 0.009%
Failure rate of hardware per hour | 0.009% | [16 empty] | Hardware Cask failure | Single Port
[18 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
[5 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies |  |  | Hardware Cask 1 operating time | 79.0567 | 79.0567 | 79.0567 | 79.0567 | 79.0567 | 79.0567
RH Cask RHE failure (Sub Tasks) | (Sub Task Notes) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack | Hardware cask 2 operating time | 75.8705 | 75.8705 | 75.8705 | 75.8705 | 75.8705 | 75.8705
Deploy Recovery System from AMF |  | Movement | 0.069444 | 0.069444 |  | N/A | Overhead crane (unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A | Hardware cask 3 operating time | 31.8044 | 31.8044 | 31.8044 | 31.8044 | 31.8044 | 31.8044
Dock to failed blanket transporter |  | Logistics | 1.64 | 1.7094 |  | N/A |  |  |  | N/A | N/A | N/A | dock equipment cask | 1.64 |  | N/A | N/A | Hardware cask 4 operating time | 207.4606 | 207.4606 | 207.4606 | 207.4606 | 207.4606 | 207.4606
Recover failed blanket transporter into the equipment cask |  | Operation | 3 | 4.7094 | Recovery Operations | 3 | Overhead crane (unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | N/A | Store tool in equipment cask | N/A |  | N/A | N/A | Hardware cask 5 operating time | 25.88 | 25.88 | 25.88 | 25.88 | 25.88 | 25.88
Dock to failed blanket transporter |  | Logistics | 1.64 | 6.3494 |  | N/A |  |  |  | N/A | N/A | N/A | dock equipment cask | 1.64 |  | N/A | N/A | Hardware cask 6 operating time | 24.36 | 24.36 | 24.36 | 24.36 | 24.36 | 24.36
Recovery RM tools into cask for replacement |  | Movement | 3 | 9.3494 | Recovery Operations | 3 | Overhead crane (unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A | Duration of RM operations (h) | 444.4322 | 7999.7798 | 3999.8899 | 2666.5933 | 2222.1611 | 1333.2966
Undock recovery system |  | Logistics | 2.54 | 11.8894 |  | N/A |  |  |  | N/A | N/A | N/A | un-dock equipment cask | 2.54 |  | N/A | N/A | Estimated number of failures, impacting all RM systems equally | 0.039999 | 0.71998 | 0.35999 | 0.23999 | 0.19999 | 0.12
Un-dock Cask |  | Logistics | 2.54 | 14.4294 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock equipment cask | 2.54 |  | N/A | N/A | Operational contribution | 0.12 | 2.1599 | 1.08 | 0.71998 | 0.59998 | 0.35999
Dock Replacement cask |  | Logistics | 1.64 | 16.0694 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Equipment Cask | 1.64 | Replacement hardware cask issued from AMF | N/A | N/A | Logistical contribution | 0.52276 | 9.4097 | 4.7049 | 3.1366 | 2.6138 | 1.5683
|  | Total |  | 16.0694 | [13 empty] | Idle time waiting for dependant operations | 0 | 0 | 0 | 0 | 0 | 0
[18 empty] | Total Duration of Recovery Operations | 0.64276 | 11.5697 | 5.7848 | 3.8566 | 3.2138 | 1.9283
Equipment Cask failure
Assumptions:
Recovery of cask is completed using standard predetermined procedures.
Rare and time consuming special recoveries are not considered
A new cask and equipment (if required) are available on demand from the AMF
Failure rate: | 0.009%
Failure rate of equipment cask per hour | 0.009% | [16 empty] | Equipment Cask failure | Single Port
[18 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
[5 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies |  |  | Equipment Cask 1 operating time | 188.2511 | 188.2511 | 188.2511 | 188.2511 | 188.2511 | 188.2511
RH Cask RHE failure (Sub Tasks) | (Sub Task Notes) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack | Equipment cask 2 operating time | 261.3332 | 261.3332 | 261.3332 | 261.3332 | 261.3332 | 261.3332
Deploy Recovery System from AMF |  | Movement | 0.069444 | 0.069444 |  | N/A | Overhead crane (unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A | Equipment cask 3 operating time | 64.72 | 64.72 | 64.72 | 64.72 | 64.72 | 64.72
Dock to failed blanket transporter |  | Logistics | 1.64 | 1.7094 |  | N/A |  |  |  | N/A | N/A | N/A | dock equipment cask | 1.64 |  | N/A | N/A | Duration of RM operations (h) | 514.3044 | 9257.4783 | 4628.7392 | 3085.8261 | 2571.5218 | 1542.9131
Recover failed blanket transporter into the equipment cask |  | Operation | 3 | 4.7094 | Recovery Operations | 3 | Overhead crane (unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | N/A | Store tool in equipment cask | N/A |  | N/A | N/A | Estimated number of failures, impacting all RM systems equally | 0.046287 | 0.83317 | 0.41659 | 0.27772 | 0.23144 | 0.13886
Undock recovery system |  | Logistics | 2.54 | 7.2494 |  | N/A |  |  |  | N/A | N/A | N/A | un-dock equipment cask | 2.54 |  | N/A | N/A | Operational contribution | 0.13886 | 2.4995 | 1.2498 | 0.83317 | 0.69431 | 0.41659
Un-dock Cask |  | Logistics | 2.54 | 9.7894 |  | N/A |  |  |  | N/A | N/A | N/A | Un-dock equipment cask | 2.54 |  | N/A | N/A | Logistical contribution | 0.39018 | 7.0232 | 3.5116 | 2.3411 | 1.9509 | 1.1705
Dock Replacement cask |  | Logistics | 1.64 | 11.4294 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Equipment Cask | 1.64 |  | N/A | N/A | Idle time waiting for dependant operations | 0 | 0 | 0 | 0 | 0 | 0
|  | Total |  | 11.4294 | [13 empty] | Total Duration of Recovery Operations | 0.52904 | 9.5227 | 4.7614 | 3.1742 | 2.6452 | 1.5871
Blanket Transporter failure
Assumptions:
Recovery of Blanket Transporter is completed using standard predetermined procedures.
The failed blanket transporter can be recovered and transported without first having to detach any suspended load
Rare and time consuming special recoveries are not considered
A new Blanket Transport and/or replacement blanket module (if required) is available on demand from the AMF
Failure rate: | 5%
Failure rate of Blanket Transporter per hour | 5% | [16 empty] | Blanket Transporter failure
[18 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
[5 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies |  |  | Blanket Removal Duration | 38.17 | 38.17 | 38.17 | 38.17 | 38.17 | 38.17
RH Cask RHE failure (Sub Tasks) | (Sub Task Notes) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack | Blanket Installation Duration | 30.87 | 30.87 | 30.87 | 30.87 | 30.87 | 30.87
Deploy Recovery System from AMF |  | Movement | 0.069444 | 0.069444 |  | N/A | Overhead crane (unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A | Duration of RM operations (h) | 69.04 | 1242.72 | 621.36 | 414.24 | 345.2 | 207.12
Dock to failed blanket transporter |  | Logistics | 1.64 | 1.7094 |  | N/A |  |  |  | N/A | N/A | N/A | dock equipment cask | 1.64 |  | N/A | N/A | Estimated number of failures, impacting all RM systems equally | 3.452 | 62.136 | 31.068 | 20.712 | 17.26 | 10.356
Recover failed MM into the equipment cask |  | Operation | 3 | 4.7094 | Recovery Operations | 3 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A | Operational contribution | 17.26 | 310.68 | 155.34 | 103.56 | 86.3 | 51.78
Undock recovery system |  | Logistics | 2.54 | 7.2494 |  | N/A |  |  |  | N/A | N/A | N/A | un-dock equipment cask | 2.54 |  | N/A | N/A | Logistical contribution | 30.4102 | 547.3836 | 273.6918 | 182.4612 | 152.051 | 91.2306
un-dock equipment cask |  | Logistics | 2.54 | 9.7894 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Equipment Cask | 2.54 |  | N/A | N/A | Idle time waiting for dependant operations | 0 | 0 | 0 | 0 | 0 | 0
Replace or repair the Blanket Transporter | Assumed chosen tasks takes 2 hours | Operation | 2 | 11.7894 | Recovery Operations | 2 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A | Total Duration of Recovery Operations | 47.6702 | 858.0636 | 429.0318 | 286.0212 | 238.351 | 143.0106
dock replacement equipment cask |  | Logistics | 1.64 | 13.4294 |  | N/A |  |  |  | N/A | N/A | N/A | Dock equipment cask | 1.64 | Replacement MM equipment cask issued from AMF | 5.8839 | 5.9056
deploy new MM into port |  | Logistics | 0.38 | 13.8094 |  | N/A |  |  |  | N/A | N/A | N/A | deploy tool from equipment cask | 0.38 |  | N/A | N/A
|  | Total |  | 13.8094
Note on D25: Farquhar, Iain: Uses complex RM systems
Note on N32: Farquhar, Iain: Movement speed halved due to failure
Note on D50: Farquhar, Iain: Uses complex RM systems
Note on N57: Farquhar, Iain: Movement speed halved due to failure
Note on D75: Farquhar, Iain: Uses complex RM systems
Note on D102: Farquhar, Iain: Uses complex RM systems
Note on D183: Farquhar, Iain: Uses complex RM systems

## Upper Cask Recovery Logistics (hidden)
[5 empty] | Operations |  | Movement | [5 empty] | Logistics
Group | Activity | Activity Type | Time (h) | Cumulative | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h)
VMC Failure
Replacement VMC issued from AMF | Recover failed RHE into the failed VMC cask | Trigger | 0 | 8.0894 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Issue replacement VMC from the AMF | Logistics | 0.48 | 8.5694 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48
| Move replacement VMC to Upper Port | Movement | 0.69444 | 9.2639 |  | N/A | Overhead Crane (loaded) | AMF Equipment Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A
| Replacement VMC issued from AMF | Total | 0 | 9.2639 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Blanket Transporter failure
Replacement blanket transporter cask issued from AMF | Recover failed blanket transporter into the equipment cask | Trigger | 0 | 4.7094 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Issue replacement equipment cask from the AMF | Logistics | 0.48 | 5.1894 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48
| Move replacement cask to upper port | Movement | 0.69444 | 5.8839 |  | N/A | Overhead Crane (loaded) | AMF Equipment Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A
| Replacement blanket transporter cask issued from AMF | Total | 0 | 5.8839 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Multifunction Manipulator Failure
Replacement MM equipment cask issued from AMF | Recover failed MM into the equipment cask | Trigger | 0 | 4.7094 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Issue replacement equipment cask from the AMF | Logistics | 0.48 | 5.1894 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48
| Move equipment cask to Upper Port | Movement | 0.69444 | 5.8839 |  | N/A | Overhead Crane (loaded) | AMF Equipment Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A
| Replacement MM equipment cask issued from AMF | Total | 0 | 5.8839 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
COB Weld Failure
Shield Plug & Fixations & Hardware Cask 3 stored; Equipment Cask 2 collected; Equipment cask 2 docked | Weld Failure identified at COB/Pipe Module joint | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter A to AMF Equipment Receipt | Movement | 0.27778 | 0.27778 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | AMF Equipment Receipt | 20 | 0.02 | 0.27778 |  | N/A
| Store Hardware Cask 3 | Logistics | 0.48 | 0.75778 |  | N/A |  |  |  | N/A | N/A | N/A | Store Cask | 0.48
| Move Cask Transporter A to AMF Equipment Issue | Movement | 0.027778 | 0.78556 |  | N/A | Cask Transporter (unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Equipment Cask 2 | Logistics | 0.48 | 1.2656 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48
| Move Cask Transporter A to Equipment Stillage | Movement | 0.69444 | 1.96 |  | N/A | Cask Transporter (loaded) | AMF Equipment Issue | Equipment Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Equipment Cask 2 | Logistics | 1.64 | 3.6 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Equipment Cask | 1.64
| Shield Plug & Fixations & Hardware Cask 3 stored; Equipment Cask 2 collected; Equipment cask 2 docked | Total | 0 | 3.6 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
COB Pipe Module stored; Hardware Cask 4 docked | Extract COB Pipe Module | Trigger | 0 | 2.1549 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 4 | Logistics | 2.3 | 4.4549 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Receipt | Movement | 0.69444 | 5.1494 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store COB Pipe Module | Logistics | 0.68 | 5.8294 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.23148 | 6.0608 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 4 | Logistics | 1.4 | 7.4608 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| COB Pipe Module stored; Hardware Cask 4 docked | Total | 0 | 7.4608 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Pipe Module stored; Hardware Cask 4 docked | Extract LOB Pipe Module | Trigger | 0 | 15.1149 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 4 | Logistics | 2.3 | 17.4149 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Receipt | Movement | 0.69444 | 18.1094 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store LOB Pipe Module | Logistics | 0.68 | 18.7894 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.23148 | 19.0208 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 4 | Logistics | 1.4 | 20.4208 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| LOB Pipe Module stored; Hardware Cask 4 docked | Total | 0 | 20.4208 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Pipe Module stored; Hardware Cask 4 docked | Extract ROB Pipe Module | Trigger | 0 | 26.6298 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 4 | Logistics | 2.3 | 28.9298 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Receipt | Movement | 0.69444 | 29.6243 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store ROB Pipe Module | Logistics | 0.68 | 30.3043 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.23148 | 30.5358 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 4 | Logistics | 1.4 | 31.9358 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| ROB Pipe Module stored; Hardware Cask 4 docked | Total | 0 | 31.9358 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Pipe Module stored; Hardware Cask 4 docked | Extract LIB Pipe Module | Trigger | 0 | 38.1447 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-dock Hardware Cask 4 | Logistics | 2.3 | 40.4447 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Receipt | Movement | 0.69444 | 41.1392 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store LIB Pipe Module | Logistics | 0.68 | 41.8192 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.23148 | 42.0507 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 4 | Logistics | 1.4 | 43.4507 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| LIB Pipe Module stored; Hardware Cask 4 docked | Total | 0 | 43.4507 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Pipe Module stored; Hardware Cask 4 stored; Hardware Cask 5 collected; Hardware Cask 5 docked | Extract RIB Pipe Module | Trigger | 0 | 49.6597 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 4 | Logistics | 2.3 | 51.9597 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Receipt | Movement | 0.69444 | 52.6541 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store ROB Pipe Module | Logistics | 0.68 | 53.3341 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to AMF Equipment Receipt | Movement | 0.092593 | 53.4267 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | AMF Equipment Receipt | 20 | 0.06 | 0.092593 |  | N/A
| Store Hardware Cask 4 | Logistics | 0.48 | 53.9067 |  | N/A |  |  |  | N/A | N/A | N/A | Store Cask | 0.48
| Move to Cask Transporter B to AMF Equipment Issue | Movement | 0.027778 | 53.9345 |  | N/A | Cask Transporter (unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Hardware Cask 5 | Logistics | 0.48 | 54.4145 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48
| Move Cask Transporter B to Hardware Stillage | Movement | 0.69444 | 55.1089 |  | N/A | Cask Transporter (loaded) | AMF Equipment Issue | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 5 | Logistics | 1.4 | 56.5089 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| RIB Pipe Module stored; Hardware Cask 4 stored; Hardware Cask 5 collected; Hardware Cask 5 docked | Total | 0 | 56.5089 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Equipment Cask 3 collected; Equipment Cask 3 moved to equipment stillage | Store Pipe Lifter in Equipment Cask 2 | Trigger | 0 | 4.61 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Deploy Cask Transporter C | Logistics | 0.5 | 5.11 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Equipment from Store | 0.5
| Collect Equipment Cask 3 | Logistics | 0.48 | 5.59 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48
| Move Cask Transporter C to Equipment Stillage | Movement | 0.69444 | 6.2844 |  | N/A | Cask Transporter (loaded) | AMF Equipment Issue | Equipment Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Equipment Cask 3 collected; Equipment Cask 3 moved to equipment stillage | Total | 0 | 6.2844 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Disconnect COB Divertor port pipe module | weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to lower port operations | Operation | 12.603 | 12.603 | Cut Failed COB Pipe Module Weld | 12.603 |  |  |  | N/A | N/A | N/A |  | N/A
| Disconnect COB Divertor port pipe module | Total | 0 | 12.603 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
COB Blanket Segment stored; Hardware Cask 5 docked | Store COB Blanket Segment in Hardware Cask 5 | Trigger | 0 | 61.5997 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 5 | Logistics | 2.3 | 63.8997 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Receipt | Movement | 0.69444 | 64.5941 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store COB Blanket Segment | Logistics | 0.68 | 65.2741 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.23148 | 65.5056 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 5 | Logistics | 1.4 | 66.9056 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| COB Blanket Segment stored; Hardware Cask 5 docked | Total | 0 | 66.9056 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Blanket Segment stored; Hardware Cask 6 docked | Store LOB Blanket Segment in Hardware Cask 6 | Trigger | 0 | 68.4697 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 6 | Logistics | 2.3 | 70.7697 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Receipt | Movement | 0.69444 | 71.4641 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store LOB Blanket Segment | Logistics | 0.68 | 72.1441 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter A to Hardware Stillage | Movement | 0.23148 | 72.3756 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 73.7756 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| LOB Blanket Segment stored; Hardware Cask 6 docked | Total | 0 | 73.7756 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Blanket Segment stored; Hardware Cask 5 docked | Store ROB Blanket Segment in Hardware Cask 5 | Trigger | 0 | 75.3397 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 5 | Logistics | 2.3 | 77.6397 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Receipt | Movement | 0.69444 | 78.3341 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store ROB Blanket Segment | Logistics | 0.68 | 79.0141 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.23148 | 79.2456 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 5 | Logistics | 1.4 | 80.6456 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| ROB Blanket Segment stored; Hardware Cask 5 docked | Total | 0 | 80.6456 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Blanket Segment stored; Hardware Cask 6 docked | Store LIB Blanket Segment in Hardware Cask 6 | Trigger | 0 | 82.2097 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter A to AMF Hardware Receipt | Movement | 0.34722 | 82.5569 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Issue | 25 | 0.02 | 0.34722 |  | N/A
| Store RIB Blanket Segment | Logistics | 0.68 | 83.2369 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter A to Hardware Stillage | Movement | 0.23148 | 83.4684 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 84.8684 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| LIB Blanket Segment stored; Hardware Cask 6 docked | Total | 0 | 84.8684 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Blanket Segment stored; Hardware Cask 5 docked | Un-dock hardware cask 5 | Trigger | 0 | 91.3797 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 5 | Logistics | 2.3 | 93.6797 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Receipt | Movement | 0.69444 | 94.3741 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store RIB Blanket Segment | Logistics | 0.68 | 95.0541 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter A to Hardware Stillage | Movement | 0.23148 | 95.2856 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 96.6856 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| RIB Blanket Segment stored; Hardware Cask 5 docked | Total | 0 | 96.6856 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Equipment Cask 2 stored; Hardware Cask 6 Collected; Hardware Cask 6 docked | Store Pipe Lifter in Equipment Cask 2 | Trigger | 0 | 4.61 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter A to AMF Equipment Receipt | Movement | 0.69444 | 5.3044 |  | N/A | Cask Transporter (loaded) | Equipment Stillage | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Equipment Cask 2 | Logistics | 0.48 | 5.7844 |  | N/A |  |  |  | N/A | N/A | N/A | Store Cask | 0.48
| Move Cask Transporter A to AMF Equipment Issue | Movement | 0.027778 | 5.8122 |  | N/A | Cask Transporter (unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Hardware Cask 6 | Logistics | 0.48 | 6.2922 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48
| Move Cask Transporter A to Hardware Stillage | Movement | 0.69444 | 6.9867 |  | N/A | Cask Transporter (loaded) | AMF Equipment Issue | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 8.3867 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Equipment Cask 2 stored; Hardware Cask 6 Collected; Hardware Cask 6 docked | Total | 0 | 8.3867 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Blanket Segment Collected; Hardware Cask 6 docked | Collect Blanket Segment 5 from Hardware Cask 6 | Trigger | 0 | 91.9797 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 7 | Logistics | 2.3 | 94.2797 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Issue | Movement | 0.11574 | 94.3954 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Issue | 25 | 0.06 | 0.11574 |  | N/A
| Export RIB Blanket Segment | Logistics | 0.63 | 95.0254 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63
| Move Cask Transporter A to Hardware Stillage | Movement | 0.69444 | 95.7198 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 97.1198 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| RIB Blanket Segment Collected; Hardware Cask 6 docked | Total | 0 | 97.1198 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Blanket Segment Collected; Hardware Cask 5 docked | Collect Blanket Segment 4 from Hardware Cask 5 | Trigger | 0 | 102.0498 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 6 | Logistics | 2.3 | 104.3498 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Issue | Movement | 0.11574 | 104.4656 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Issue | 25 | 0.06 | 0.11574 |  | N/A
| Export LIB Blanket Segment | Logistics | 0.63 | 105.0956 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63
| Move Cask Transporter A to Hardware Stillage | Movement | 0.69444 | 105.79 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 107.19 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| LIB Blanket Segment Collected; Hardware Cask 5 docked | Total | 0 | 107.19 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Blanket Segment Collected; Hardware Cask 6 docked | Collect Blanket Segment 3 from Hardware Cask 6 | Trigger | 0 | 112.12 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 5 | Logistics | 2.3 | 114.42 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Issue | Movement | 0.11574 | 114.5358 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Issue | 25 | 0.06 | 0.11574 |  | N/A
| Export ROB Blanket Segment | Logistics | 0.63 | 115.1658 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63
| Move Cask Transporter B to Hardware Stillage | Movement | 0.69444 | 115.8602 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 117.2602 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| ROB Blanket Segment Collected; Hardware Cask 6 docked | Total | 0 | 117.2602 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Blanket Segment Collected; Hardware Cask 5 docked | Collect Blanket Segment 2 from Hardware Cask 5 | Trigger | 0 | 122.1902 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 6 | Logistics | 2.3 | 124.4902 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Issue | Movement | 0.11574 | 124.606 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Issue | 25 | 0.06 | 0.11574 |  | N/A
| Export LOB Blanket Segment | Logistics | 0.63 | 125.236 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63
| Move Cask Transporter A to Hardware Stillage | Movement | 0.69444 | 125.9304 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 127.3304 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| LOB Blanket Segment Collected; Hardware Cask 5 docked | Total | 0 | 127.3304 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
COB Blanket Segment Collected; Hardware Cask 6 docked | Collect Blanket Segment 1 from Hardware Cask 6 | Trigger | 0 | 132.2604 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 5 | Logistics | 2.3 | 134.5604 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Issue | Movement | 0.11574 | 134.6761 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Issue | 25 | 0.06 | 0.11574 |  | N/A
| Export COB Blanket Segment | Logistics | 0.63 | 135.3061 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63
| Move Cask Transporter B to Hardware Stillage | Movement | 0.69444 | 136.0006 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 137.4006 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| COB Blanket Segment Collected; Hardware Cask 6 docked | Total | 0 | 137.4006 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Equipment Cask 6 stored; Equipment Cask 2 Collected; Hardware Cask 2 docked; RIB Pipe Module Collected | Install COB Blanket Segment | Trigger | 0 | 141.7306 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter A to AMF Equipment Receipt | Movement | 0.23148 | 141.9621 |  | N/A | Cask Transporter (empty) | Equipment Stillage | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Equipment Cask 6 | Logistics | 0.48 | 142.4421 |  | N/A |  |  |  | N/A | N/A | N/A | Store Cask | 0.48
| Move Cask Transporter A to AMF Equipment Issue | Movement | 0.027778 | 142.4698 |  | N/A | Cask Transporter (unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Equipment Cask 2 | Logistics | 0.48 | 142.9498 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48
| Move Cask Transporter A to Hardware Stillage | Movement | 0.23148 | 143.1813 |  | N/A | Cask Transporter (empty) | AMF Equipment Issue | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Equipment Cask 2 | Logistics | 1.4 | 144.5813 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Move Cask Transporter B to AMF Hardware Issue | Movement | 0.23148 | 144.8128 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Collect RIB Pipe Module | Logistics | 0.68 | 145.4928 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.69444 | 146.1873 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 4 | Logistics | 1.4 | 147.5873 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Equipment Cask 6 stored; Equipment Cask 2 Collected; Hardware Cask 2 docked; RIB Pipe Module Collected | Total | 0 | 147.5873 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Hardware Cask 2 Un-Docked; LIB Pipe Module Collected; Hardware Cask 4 docked | Install RIB Pipe Module | Trigger | 0 | 152.6623 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-dock Hardware Cask 4 | Logistics | 2.3 | 154.9623 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Issue | Movement | 0.23148 | 155.1937 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Collect LIB Pipe Module | Logistics | 0.68 | 155.8737 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.69444 | 156.5682 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 4 | Logistics | 1.4 | 157.9682 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Hardware Cask 2 Un-Docked; LIB Pipe Module Collected; Hardware Cask 4 docked | Total | 0 | 157.9682 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Hardware Cask 4 Un-Docked; ROB Pipe Module Collected; Hardware Cask 2 docked | Install LIB Pipe Module | Trigger | 0 | 191.49 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-dock Hardware Cask 4 | Logistics | 2.3 | 193.79 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Issue | Movement | 0.23148 | 194.0215 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Collect LIB Pipe Module | Logistics | 0.68 | 194.7015 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter A to Hardware Stillage | Movement | 0.69444 | 195.3959 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 4 | Logistics | 1.4 | 196.7959 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Hardware Cask 4 Un-Docked; ROB Pipe Module Collected; Hardware Cask 2 docked | Total | 0 | 196.7959 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Hardware Cask 2 Un-Docked; LOB Pipe Module Collected; Hardware Cask 4 docked | Install ROB Pipe Module | Trigger | 0 | 230.3177 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-dock Hardware Cask 4 | Logistics | 2.3 | 232.6177 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Issue | Movement | 0.23148 | 232.8492 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Collect LIB Pipe Module | Logistics | 0.68 | 233.5292 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.69444 | 234.2236 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 4 | Logistics | 1.4 | 235.6236 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Hardware Cask 2 Un-Docked; LOB Pipe Module Collected; Hardware Cask 4 docked | Total | 0 | 235.6236 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Hardware Cask 4 Un-Docked; COB Pipe Module Collected; Hardware Cask 2 docked | Install LOB Pipe Module | Trigger | 0 | 269.1455 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-dock Hardware Cask 4 | Logistics | 2.3 | 271.4455 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Issue | Movement | 0.23148 | 271.6769 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Collect LOB Pipe Module | Logistics | 0.68 | 272.3569 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.69444 | 273.0514 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 4 | Logistics | 1.4 | 274.4514 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Hardware Cask 4 Un-Docked; COB Pipe Module Collected; Hardware Cask 2 docked | Total | 0 | 274.4514 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
COB Lower Port Pipe Module installed | weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to lower port operations | Operation | #N/A | #N/A | Install COB blanket pipework module | #N/A |  |  |  | N/A | N/A | N/A |  | N/A
| COB Lower Port Pipe Module installed | Total | 0 | #N/A |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Weld Failure
LOB Pipe Module stored; Hardware Cask 4 docked | Extract LOB Pipe Module | Trigger | 0 | 2.1549 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 4 | Logistics | 2.3 | 4.4549 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Receipt | Movement | 0.69444 | 5.1494 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store LOB Pipe Module | Logistics | 0.68 | 5.8294 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.23148 | 6.0608 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 4 | Logistics | 1.4 | 7.4608 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| LOB Pipe Module stored; Hardware Cask 4 docked | Total | 0 | 7.4608 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Pipe Module stored; Hardware Cask 4 docked | Extract ROB Pipe Module | Trigger | 0 | 13.6698 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 4 | Logistics | 2.3 | 15.9698 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Receipt | Movement | 0.69444 | 16.6643 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store ROB Pipe Module | Logistics | 0.68 | 17.3443 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.23148 | 17.5758 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 4 | Logistics | 1.4 | 18.9758 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| ROB Pipe Module stored; Hardware Cask 4 docked | Total | 0 | 18.9758 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Pipe Module stored; Hardware Cask 4 docked | Extract LIB Pipe Module | Trigger | 0 | 25.1847 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-dock Hardware Cask 4 | Logistics | 2.3 | 27.4847 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Receipt | Movement | 0.69444 | 28.1792 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store LIB Pipe Module | Logistics | 0.68 | 28.8592 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.23148 | 29.0907 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 4 | Logistics | 1.4 | 30.4907 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| LIB Pipe Module stored; Hardware Cask 4 docked | Total | 0 | 30.4907 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Pipe Module stored; Hardware Cask 4 stored; Hardware Cask 5 collected; Hardware Cask 5 docked | Extract RIB Pipe Module | Trigger | 0 | 36.6997 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 4 | Logistics | 2.3 | 38.9997 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Receipt | Movement | 0.69444 | 39.6941 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store ROB Pipe Module | Logistics | 0.68 | 40.3741 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to AMF Equipment Receipt | Movement | 0.092593 | 40.4667 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | AMF Equipment Receipt | 20 | 0.06 | 0.092593 |  | N/A
| Store Hardware Cask 4 | Logistics | 0.48 | 40.9467 |  | N/A |  |  |  | N/A | N/A | N/A | Store Cask | 0.48
| Move to Cask Transporter B to AMF Equipment Issue | Movement | 0.027778 | 40.9745 |  | N/A | Cask Transporter (unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Hardware Cask 5 | Logistics | 0.48 | 41.4545 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48
| Move Cask Transporter B to Hardware Stillage | Movement | 0.69444 | 42.1489 |  | N/A | Cask Transporter (loaded) | AMF Equipment Issue | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 5 | Logistics | 1.4 | 43.5489 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| RIB Pipe Module stored; Hardware Cask 4 stored; Hardware Cask 5 collected; Hardware Cask 5 docked | Total | 0 | 43.5489 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Equipment Cask 3 collected; Equipment Cask 3 moved to equipment stillage | Un-dock equipment cask 2 | Trigger | 0 | 40.2497 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Deploy Cask Transporter C | Logistics | 0.5 | 40.7497 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Equipment from Store | 0.5
| Collect Equipment Cask 3 | Logistics | 0.48 | 41.2297 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48
| Move Cask Transporter C to Equipment Stillage | Movement | 0.69444 | 41.9241 |  | N/A | Cask Transporter (loaded) | AMF Equipment Issue | Equipment Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Equipment Cask 3 collected; Equipment Cask 3 moved to equipment stillage | Total | 0 | 41.9241 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
COB Blanket Segment stored; Hardware Cask 5 docked | Store COB Blanket Segment in Hardware Cask 5 | Trigger | 0 | 50.3141 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 5 | Logistics | 2.3 | 52.6141 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Receipt | Movement | 0.69444 | 53.3086 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store COB Blanket Segment | Logistics | 0.68 | 53.9886 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.23148 | 54.22 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 5 | Logistics | 1.4 | 55.62 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| COB Blanket Segment stored; Hardware Cask 5 docked | Total | 0 | 55.62 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Blanket Segment stored; Hardware Cask 6 docked | Store LOB Blanket Segment in Hardware Cask 6 | Trigger | 0 | 57.1841 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 6 | Logistics | 2.3 | 59.4841 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Receipt | Movement | 0.69444 | 60.1786 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store LOB Blanket Segment | Logistics | 0.68 | 60.8586 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter A to Hardware Stillage | Movement | 0.23148 | 61.09 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 62.49 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| LOB Blanket Segment stored; Hardware Cask 6 docked | Total | 0 | 62.49 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Blanket Segment stored; Hardware Cask 5 docked | Store ROB Blanket Segment in Hardware Cask 5 | Trigger | 0 | 64.0541 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 5 | Logistics | 2.3 | 66.3541 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Receipt | Movement | 0.69444 | 67.0486 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store ROB Blanket Segment | Logistics | 0.68 | 67.7286 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.23148 | 67.96 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 5 | Logistics | 1.4 | 69.36 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| ROB Blanket Segment stored; Hardware Cask 5 docked | Total | 0 | 69.36 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Blanket Segment stored; Hardware Cask 6 docked | Store LIB Blanket Segment in Hardware Cask 6 | Trigger | 0 | 70.9241 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter A to AMF Hardware Receipt | Movement | 0.34722 | 71.2713 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Issue | 25 | 0.02 | 0.34722 |  | N/A
| Store RIB Blanket Segment | Logistics | 0.68 | 71.9513 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter A to Hardware Stillage | Movement | 0.23148 | 72.1828 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 73.5828 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| LIB Blanket Segment stored; Hardware Cask 6 docked | Total | 0 | 73.5828 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Blanket Segment stored; Hardware Cask 5 docked | Un-dock hardware cask 5 | Trigger | 0 | 80.0941 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 5 | Logistics | 2.3 | 82.3941 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Receipt | Movement | 0.69444 | 83.0886 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store RIB Blanket Segment | Logistics | 0.68 | 83.7686 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter A to Hardware Stillage | Movement | 0.23148 | 84 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 85.4 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| RIB Blanket Segment stored; Hardware Cask 5 docked | Total | 0 | 85.4 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Equipment Cask 2 stored; Hardware Cask 6 Collected; Hardware Cask 6 docked | Un-dock equipment cask 2 | Trigger | 0 | 40.2497 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter A to AMF Equipment Receipt | Movement | 0.69444 | 40.9441 |  | N/A | Cask Transporter (loaded) | Equipment Stillage | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Equipment Cask 2 | Logistics | 0.48 | 41.4241 |  | N/A |  |  |  | N/A | N/A | N/A | Store Cask | 0.48
| Move Cask Transporter A to AMF Equipment Issue | Movement | 0.027778 | 41.4519 |  | N/A | Cask Transporter (unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Hardware Cask 6 | Logistics | 0.48 | 41.9319 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48
| Move Cask Transporter A to Hardware Stillage | Movement | 0.69444 | 42.6263 |  | N/A | Cask Transporter (loaded) | AMF Equipment Issue | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 44.0263 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Equipment Cask 2 stored; Hardware Cask 6 Collected; Hardware Cask 6 docked | Total | 0 | 44.0263 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Blanket Segment Collected; Hardware Cask 6 docked | Collect Blanket Segment 5 from Hardware Cask 6 | Trigger | 0 | 80.6941 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 7 | Logistics | 2.3 | 82.9941 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Issue | Movement | 0.11574 | 83.1098 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Issue | 25 | 0.06 | 0.11574 |  | N/A
| Export RIB Blanket Segment | Logistics | 0.63 | 83.7398 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63
| Move Cask Transporter A to Hardware Stillage | Movement | 0.69444 | 84.4343 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 85.8343 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| RIB Blanket Segment Collected; Hardware Cask 6 docked | Total | 0 | 85.8343 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Blanket Segment Collected; Hardware Cask 5 docked | Collect Blanket Segment 4 from Hardware Cask 5 | Trigger | 0 | 90.7643 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 6 | Logistics | 2.3 | 93.0643 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Issue | Movement | 0.11574 | 93.18 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Issue | 25 | 0.06 | 0.11574 |  | N/A
| Export LIB Blanket Segment | Logistics | 0.63 | 93.81 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63
| Move Cask Transporter A to Hardware Stillage | Movement | 0.69444 | 94.5045 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 95.9045 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| LIB Blanket Segment Collected; Hardware Cask 5 docked | Total | 0 | 95.9045 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Blanket Segment Collected; Hardware Cask 6 docked | Collect Blanket Segment 3 from Hardware Cask 6 | Trigger | 0 | 100.8345 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 5 | Logistics | 2.3 | 103.1345 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Issue | Movement | 0.11574 | 103.2502 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Issue | 25 | 0.06 | 0.11574 |  | N/A
| Export ROB Blanket Segment | Logistics | 0.63 | 103.8802 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63
| Move Cask Transporter B to Hardware Stillage | Movement | 0.69444 | 104.5747 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 105.9747 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| ROB Blanket Segment Collected; Hardware Cask 6 docked | Total | 0 | 105.9747 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Blanket Segment Collected; Hardware Cask 5 docked | Collect Blanket Segment 2 from Hardware Cask 5 | Trigger | 0 | 110.9047 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 6 | Logistics | 2.3 | 113.2047 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Issue | Movement | 0.11574 | 113.3204 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Issue | 25 | 0.06 | 0.11574 |  | N/A
| Export LOB Blanket Segment | Logistics | 0.63 | 113.9504 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63 | 515151221
| Move Cask Transporter A to Hardware Stillage | Movement | 0.69444 | 114.6448 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 116.0448 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| LOB Blanket Segment Collected; Hardware Cask 5 docked | Total | 0 | 116.0448 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
COB Blanket Segment Collected; Hardware Cask 6 docked | Collect Blanket Segment 1 from Hardware Cask 6 | Trigger | 0 | 120.9748 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 5 | Logistics | 2.3 | 123.2748 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Issue | Movement | 0.11574 | 123.3906 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Issue | 25 | 0.06 | 0.11574 |  | N/A
| Export COB Blanket Segment | Logistics | 0.63 | 124.0206 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63
| Move Cask Transporter B to Hardware Stillage | Movement | 0.69444 | 124.715 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 126.115 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| COB Blanket Segment Collected; Hardware Cask 6 docked | Total | 0 | 126.115 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Equipment Cask 6 stored; Equipment Cask 2 Collected; Hardware Cask 2 docked; RIB Pipe Module Collected | Install COB Blanket Segment | Trigger | 0 | 130.445 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter A to AMF Equipment Receipt | Movement | 0.23148 | 130.6765 |  | N/A | Cask Transporter (empty) | Equipment Stillage | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Equipment Cask 6 | Logistics | 0.48 | 131.1565 |  | N/A |  |  |  | N/A | N/A | N/A | Store Cask | 0.48
| Move Cask Transporter A to AMF Equipment Issue | Movement | 0.027778 | 131.1843 |  | N/A | Cask Transporter (unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Equipment Cask 2 | Logistics | 0.48 | 131.6643 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48
| Move Cask Transporter A to Hardware Stillage | Movement | 0.23148 | 131.8958 |  | N/A | Cask Transporter (empty) | AMF Equipment Issue | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Equipment Cask 2 | Logistics | 1.4 | 133.2958 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Move Cask Transporter B to AMF Hardware Issue | Movement | 0.23148 | 133.5273 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Collect RIB Pipe Module | Logistics | 0.68 | 134.2073 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.69444 | 134.9017 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 4 | Logistics | 1.4 | 136.3017 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Equipment Cask 6 stored; Equipment Cask 2 Collected; Hardware Cask 2 docked; RIB Pipe Module Collected | Total | 0 | 136.3017 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Hardware Cask 2 Un-Docked; LIB Pipe Module Collected; Hardware Cask 4 docked | Install RIB Pipe Module | Trigger | 0 | 141.3767 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-dock Hardware Cask 4 | Logistics | 2.3 | 143.6767 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Issue | Movement | 0.23148 | 143.9082 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Collect LIB Pipe Module | Logistics | 0.68 | 144.5882 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.69444 | 145.2826 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 4 | Logistics | 1.4 | 146.6826 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Hardware Cask 2 Un-Docked; LIB Pipe Module Collected; Hardware Cask 4 docked | Total | 0 | 146.6826 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Hardware Cask 4 Un-Docked; ROB Pipe Module Collected; Hardware Cask 2 docked | Install LIB Pipe Module | Trigger | 0 | 180.2044 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-dock Hardware Cask 4 | Logistics | 2.3 | 182.5044 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Issue | Movement | 0.23148 | 182.7359 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Collect LIB Pipe Module | Logistics | 0.68 | 183.4159 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter A to Hardware Stillage | Movement | 0.69444 | 184.1104 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 4 | Logistics | 1.4 | 185.5104 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Hardware Cask 4 Un-Docked; ROB Pipe Module Collected; Hardware Cask 2 docked | Total | 0 | 185.5104 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Hardware Cask 2 Un-Docked; LOB Pipe Module Collected; Hardware Cask 4 docked | Install ROB Pipe Module | Trigger | 0 | 219.0322 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-dock Hardware Cask 4 | Logistics | 2.3 | 221.3322 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Issue | Movement | 0.23148 | 221.5636 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Collect LIB Pipe Module | Logistics | 0.68 | 222.2436 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.69444 | 222.9381 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 4 | Logistics | 1.4 | 224.3381 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Hardware Cask 2 Un-Docked; LOB Pipe Module Collected; Hardware Cask 4 docked | Total | 0 | 224.3381 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Lower Port Pipe Module installed | weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to lower port operations | Operation | #REF! | #REF! | Install RIB blanket pipework module | #REF! |  |  |  | N/A | N/A | N/A |  | N/A
| RIB Lower Port Pipe Module installed | Total | 0 | #REF! |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Lower Port Pipe Module installed | weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to lower port operations | Operation | #REF! | #REF! | Install LIB blanket pipework module | #REF! |  |  |  | N/A | N/A | N/A |  | N/A
| LIB Lower Port Pipe Module installed | Total | 0 | #REF! |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Lower Port Pipe Module installed | weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to lower port operations | Operation | #REF! | #REF! | Install ROB blanket pipework module | #REF! |  |  |  | N/A | N/A | N/A |  | N/A
| ROB Lower Port Pipe Module installed | Total | 0 | #REF! |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Lower Port Pipe Module installed | weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to lower port operations | Operation | #REF! | #REF! | Install LOB blanket pipework module | #REF! |  |  |  | N/A | N/A | N/A |  | N/A
| LOB Lower Port Pipe Module installed | Total | 0 | #REF! |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Weld Failure
Shield Plug & Fixations & Hardware Cask 3 stored; Equipment Cask 2 collected; Equipment cask 2 docked | Weld Failure identified at ROB/Pipe Module joint | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter A to AMF Equipment Receipt | Movement | 0.27778 | 0.27778 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | AMF Equipment Receipt | 20 | 0.02 | 0.27778 |  | N/A
| Store Hardware Cask 3 | Logistics | 0.48 | 0.75778 |  | N/A |  |  |  | N/A | N/A | N/A | Store Cask | 0.48
| Move Cask Transporter A to AMF Equipment Issue | Movement | 0.027778 | 0.78556 |  | N/A | Cask Transporter (unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Equipment Cask 2 | Logistics | 0.48 | 1.2656 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48
| Move Cask Transporter A to Equipment Stillage | Movement | 0.69444 | 1.96 |  | N/A | Cask Transporter (loaded) | AMF Equipment Issue | Equipment Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Equipment Cask 2 | Logistics | 1.64 | 3.6 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Equipment Cask | 1.64
| Shield Plug & Fixations & Hardware Cask 3 stored; Equipment Cask 2 collected; Equipment cask 2 docked | Total | 0 | 3.6 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Pipe Module stored; Hardware Cask 4 docked | Extract ROB Pipe Module | Trigger | 0 | 2.1549 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 4 | Logistics | 2.3 | 4.4549 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Receipt | Movement | 0.69444 | 5.1494 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store ROB Pipe Module | Logistics | 0.68 | 5.8294 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.23148 | 6.0608 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 4 | Logistics | 1.4 | 7.4608 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| ROB Pipe Module stored; Hardware Cask 4 docked | Total | 0 | 7.4608 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Pipe Module stored; Hardware Cask 4 docked | Extract LIB Pipe Module | Trigger | 0 | 13.6698 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-dock Hardware Cask 4 | Logistics | 2.3 | 15.9698 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Receipt | Movement | 0.69444 | 16.6643 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store LIB Pipe Module | Logistics | 0.68 | 17.3443 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.23148 | 17.5758 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 4 | Logistics | 1.4 | 18.9758 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| LIB Pipe Module stored; Hardware Cask 4 docked | Total | 0 | 18.9758 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Pipe Module stored; Hardware Cask 4 stored; Hardware Cask 5 collected; Hardware Cask 5 docked | Extract RIB Pipe Module | Trigger | 0 | 25.1847 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 4 | Logistics | 2.3 | 27.4847 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Receipt | Movement | 0.69444 | 28.1792 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store ROB Pipe Module | Logistics | 0.68 | 28.8592 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to AMF Equipment Receipt | Movement | 0.092593 | 28.9518 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | AMF Equipment Receipt | 20 | 0.06 | 0.092593 |  | N/A
| Store Hardware Cask 4 | Logistics | 0.48 | 29.4318 |  | N/A |  |  |  | N/A | N/A | N/A | Store Cask | 0.48
| Move to Cask Transporter B to AMF Equipment Issue | Movement | 0.027778 | 29.4596 |  | N/A | Cask Transporter (unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Hardware Cask 5 | Logistics | 0.48 | 29.9396 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48
| Move Cask Transporter B to Hardware Stillage | Movement | 0.69444 | 30.634 |  | N/A | Cask Transporter (loaded) | AMF Equipment Issue | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 5 | Logistics | 1.4 | 32.034 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| RIB Pipe Module stored; Hardware Cask 4 stored; Hardware Cask 5 collected; Hardware Cask 5 docked | Total | 0 | 32.034 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Equipment Cask 3 collected; Equipment Cask 3 moved to equipment stillage | Un-dock equipment cask 2 | Trigger | 0 | 28.7347 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Deploy Cask Transporter C | Logistics | 0.5 | 29.2347 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Equipment from Store | 0.5
| Collect Equipment Cask 3 | Logistics | 0.48 | 29.7147 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48
| Move Cask Transporter C to Equipment Stillage | Movement | 0.69444 | 30.4092 |  | N/A | Cask Transporter (loaded) | AMF Equipment Issue | Equipment Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Equipment Cask 3 collected; Equipment Cask 3 moved to equipment stillage | Total | 0 | 30.4092 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
COB Blanket Segment stored; Hardware Cask 5 docked | Store COB Blanket Segment in Hardware Cask 5 | Trigger | 0 | 38.7992 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 5 | Logistics | 2.3 | 41.0992 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Receipt | Movement | 0.69444 | 41.7936 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store COB Blanket Segment | Logistics | 0.68 | 42.4736 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.23148 | 42.7051 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 5 | Logistics | 1.4 | 44.1051 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| COB Blanket Segment stored; Hardware Cask 5 docked | Total | 0 | 44.1051 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Blanket Segment stored; Hardware Cask 6 docked | Store LOB Blanket Segment in Hardware Cask 6 | Trigger | 0 | 45.6692 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 6 | Logistics | 2.3 | 47.9692 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Receipt | Movement | 0.69444 | 48.6636 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store LOB Blanket Segment | Logistics | 0.68 | 49.3436 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter A to Hardware Stillage | Movement | 0.23148 | 49.5751 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 50.9751 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| LOB Blanket Segment stored; Hardware Cask 6 docked | Total | 0 | 50.9751 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Blanket Segment stored; Hardware Cask 5 docked | Store ROB Blanket Segment in Hardware Cask 5 | Trigger | 0 | 52.5392 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 5 | Logistics | 2.3 | 54.8392 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Receipt | Movement | 0.69444 | 55.5336 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store ROB Blanket Segment | Logistics | 0.68 | 56.2136 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.23148 | 56.4451 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 5 | Logistics | 1.4 | 57.8451 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| ROB Blanket Segment stored; Hardware Cask 5 docked | Total | 0 | 57.8451 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Blanket Segment stored; Hardware Cask 6 docked | Store LIB Blanket Segment in Hardware Cask 6 | Trigger | 0 | 59.4092 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter A to AMF Hardware Receipt | Movement | 0.34722 | 59.7564 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Issue | 25 | 0.02 | 0.34722 |  | N/A
| Store RIB Blanket Segment | Logistics | 0.68 | 60.4364 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter A to Hardware Stillage | Movement | 0.23148 | 60.6679 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 62.0679 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| LIB Blanket Segment stored; Hardware Cask 6 docked | Total | 0 | 62.0679 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Blanket Segment stored; Hardware Cask 5 docked | Un-dock hardware cask 5 | Trigger | 0 | 68.5792 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter A to AMF Hardware Receipt | Movement | 0.69444 | 69.2736 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store RIB Blanket Segment | Logistics | 0.68 | 69.9536 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter A to Hardware Stillage | Movement | 0.23148 | 70.1851 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 71.5851 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| RIB Blanket Segment stored; Hardware Cask 5 docked | Total | 0 | 71.5851 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Equipment Cask 2 stored; Hardware Cask 6 Collected; Hardware Cask 6 docked | Store Pipe Lifter in Equipment Cask 2 | Trigger | 0 | 3.1649 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter A to AMF Equipment Receipt | Movement | 0.69444 | 3.8594 |  | N/A | Cask Transporter (loaded) | Equipment Stillage | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Equipment Cask 2 | Logistics | 0.48 | 4.3394 |  | N/A |  |  |  | N/A | N/A | N/A | Store Cask | 0.48
| Move Cask Transporter A to AMF Equipment Issue | Movement | 0.027778 | 4.3671 |  | N/A | Cask Transporter (unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Hardware Cask 6 | Logistics | 0.48 | 4.8471 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48
| Move Cask Transporter A to Hardware Stillage | Movement | 0.69444 | 5.5416 |  | N/A | Cask Transporter (loaded) | AMF Equipment Issue | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 6.9416 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Equipment Cask 2 stored; Hardware Cask 6 Collected; Hardware Cask 6 docked | Total | 0 | 6.9416 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Blanket Segment Collected; Hardware Cask 6 docked | Collect Blanket Segment 5 from Hardware Cask 6 | Trigger | 0 | 69.1792 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 7 | Logistics | 2.3 | 71.4792 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Issue | Movement | 0.11574 | 71.5949 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Issue | 25 | 0.06 | 0.11574 |  | N/A
| Export RIB Blanket Segment | Logistics | 0.63 | 72.2249 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63
| Move Cask Transporter A to Hardware Stillage | Movement | 0.69444 | 72.9194 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 74.3194 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| RIB Blanket Segment Collected; Hardware Cask 6 docked | Total | 0 | 74.3194 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Blanket Segment Collected; Hardware Cask 5 docked | Collect Blanket Segment 4 from Hardware Cask 5 | Trigger | 0 | 79.2494 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 6 | Logistics | 2.3 | 81.5494 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Issue | Movement | 0.11574 | 81.6651 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Issue | 25 | 0.06 | 0.11574 |  | N/A
| Export LIB Blanket Segment | Logistics | 0.63 | 82.2951 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63
| Move Cask Transporter A to Hardware Stillage | Movement | 0.69444 | 82.9896 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 84.3896 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| LIB Blanket Segment Collected; Hardware Cask 5 docked | Total | 0 | 84.3896 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Blanket Segment Collected; Hardware Cask 6 docked | Collect Blanket Segment 3 from Hardware Cask 6 | Trigger | 0 | 89.3196 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 5 | Logistics | 2.3 | 91.6196 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Issue | Movement | 0.11574 | 91.7353 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Issue | 25 | 0.06 | 0.11574 |  | N/A
| Export ROB Blanket Segment | Logistics | 0.63 | 92.3653 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63
| Move Cask Transporter B to Hardware Stillage | Movement | 0.69444 | 93.0597 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 94.4597 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| ROB Blanket Segment Collected; Hardware Cask 6 docked | Total | 0 | 94.4597 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Blanket Segment Collected; Hardware Cask 5 docked | Collect Blanket Segment 2 from Hardware Cask 5 | Trigger | 0 | 99.3897 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 6 | Logistics | 2.3 | 101.6897 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Issue | Movement | 0.11574 | 101.8055 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Issue | 25 | 0.06 | 0.11574 |  | N/A
| Export LOB Blanket Segment | Logistics | 0.63 | 102.4355 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63
| Move Cask Transporter A to Hardware Stillage | Movement | 0.69444 | 103.1299 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 104.5299 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| LOB Blanket Segment Collected; Hardware Cask 5 docked | Total | 0 | 104.5299 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
COB Blanket Segment Collected; Hardware Cask 6 docked | Collect Blanket Segment 1 from Hardware Cask 6 | Trigger | 0 | 109.4599 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 5 | Logistics | 2.3 | 111.7599 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Issue | Movement | 0.11574 | 111.8757 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Issue | 25 | 0.06 | 0.11574 |  | N/A
| Export COB Blanket Segment | Logistics | 0.63 | 112.5057 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63
| Move Cask Transporter B to Hardware Stillage | Movement | 0.69444 | 113.2001 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 114.6001 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| COB Blanket Segment Collected; Hardware Cask 6 docked | Total | 0 | 114.6001 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Equipment Cask 6 stored; Equipment Cask 2 Collected; Hardware Cask 2 docked; RIB Pipe Module Collected | Install COB Blanket Segment | Trigger | 0 | 118.9301 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter A to AMF Equipment Receipt | Movement | 0.23148 | 119.1616 |  | N/A | Cask Transporter (empty) | Equipment Stillage | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Equipment Cask 6 | Logistics | 0.48 | 119.6416 |  | N/A |  |  |  | N/A | N/A | N/A | Store Cask | 0.48
| Move Cask Transporter A to AMF Equipment Issue | Movement | 0.027778 | 119.6694 |  | N/A | Cask Transporter (unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Equipment Cask 2 | Logistics | 0.48 | 120.1494 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48
| Move Cask Transporter A to Hardware Stillage | Movement | 0.23148 | 120.3809 |  | N/A | Cask Transporter (empty) | AMF Equipment Issue | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Equipment Cask 2 | Logistics | 1.4 | 121.7809 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Move Cask Transporter B to AMF Hardware Issue | Movement | 0.23148 | 122.0123 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Collect RIB Pipe Module | Logistics | 0.68 | 122.6923 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.69444 | 123.3868 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 4 | Logistics | 1.4 | 124.7868 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Equipment Cask 6 stored; Equipment Cask 2 Collected; Hardware Cask 2 docked; RIB Pipe Module Collected | Total | 0 | 124.7868 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Hardware Cask 2 Un-Docked; LIB Pipe Module Collected; Hardware Cask 4 docked | Install RIB Pipe Module | Trigger | 0 | 129.8618 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-dock Hardware Cask 4 | Logistics | 2.3 | 132.1618 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Issue | Movement | 0.23148 | 132.3933 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Collect LIB Pipe Module | Logistics | 0.68 | 133.0733 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.69444 | 133.7677 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 4 | Logistics | 1.4 | 135.1677 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Hardware Cask 2 Un-Docked; LIB Pipe Module Collected; Hardware Cask 4 docked | Total | 0 | 135.1677 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Hardware Cask 4 Un-Docked; ROB Pipe Module Collected; Hardware Cask 2 docked | Install LIB Pipe Module | Trigger | 0 | 168.6895 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-dock Hardware Cask 4 | Logistics | 2.3 | 170.9895 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Issue | Movement | 0.23148 | 171.221 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Collect LIB Pipe Module | Logistics | 0.68 | 171.901 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter A to Hardware Stillage | Movement | 0.69444 | 172.5954 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 4 | Logistics | 1.4 | 173.9954 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Hardware Cask 4 Un-Docked; ROB Pipe Module Collected; Hardware Cask 2 docked | Total | 0 | 173.9954 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Lower Port Pipe Module installed | weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to lower port operations | Operation | #REF! | #REF! | Install RIB blanket pipework module | #REF! |  |  |  | N/A | N/A | N/A |  | N/A
| RIB Lower Port Pipe Module installed | Total | 0 | #REF! |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Lower Port Pipe Module installed | weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to lower port operations | Operation | #REF! | #REF! | Install LIB blanket pipework module | #REF! |  |  |  | N/A | N/A | N/A |  | N/A
| LIB Lower Port Pipe Module installed | Total | 0 | #REF! |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Lower Port Pipe Module installed | weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to lower port operations | Operation | #REF! | #REF! | Install ROB blanket pipework module | #REF! |  |  |  | N/A | N/A | N/A |  | N/A
| ROB Lower Port Pipe Module installed | Total | 0 | #REF! |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Weld Failure
LIB Pipe Module stored; Hardware Cask 4 docked | Extract LIB Pipe Module | Trigger | 0 | 11.5548 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-dock Hardware Cask 4 | Logistics | 2.3 | 13.8548 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Receipt | Movement | 0.69444 | 14.5493 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store LIB Pipe Module | Logistics | 0.68 | 15.2293 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.23148 | 15.4608 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 4 | Logistics | 1.4 | 16.8608 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| LIB Pipe Module stored; Hardware Cask 4 docked | Total | 0 | 16.8608 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Pipe Module stored; Hardware Cask 4 stored; Hardware Cask 5 collected; Hardware Cask 5 docked | Extract RIB Pipe Module | Trigger | 0 | 23.0697 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 4 | Logistics | 2.3 | 25.3697 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Receipt | Movement | 0.69444 | 26.0642 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store ROB Pipe Module | Logistics | 0.68 | 26.7442 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to AMF Equipment Receipt | Movement | 0.092593 | 26.8368 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | AMF Equipment Receipt | 20 | 0.06 | 0.092593 |  | N/A
| Store Hardware Cask 4 | Logistics | 0.48 | 27.3168 |  | N/A |  |  |  | N/A | N/A | N/A | Store Cask | 0.48
| Move to Cask Transporter B to AMF Equipment Issue | Movement | 0.027778 | 27.3446 |  | N/A | Cask Transporter (unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Hardware Cask 5 | Logistics | 0.48 | 27.8246 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48
| Move Cask Transporter B to Hardware Stillage | Movement | 0.69444 | 28.519 |  | N/A | Cask Transporter (loaded) | AMF Equipment Issue | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 5 | Logistics | 1.4 | 29.919 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| RIB Pipe Module stored; Hardware Cask 4 stored; Hardware Cask 5 collected; Hardware Cask 5 docked | Total | 0 | 29.919 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Equipment Cask 3 collected; Equipment Cask 3 moved to equipment stillage | Un-dock equipment cask 2 | Trigger | 0 | 26.6197 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Deploy Cask Transporter C | Logistics | 0.5 | 27.1197 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Equipment from Store | 0.5
| Collect Equipment Cask 3 | Logistics | 0.48 | 27.5997 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48
| Move Cask Transporter C to Equipment Stillage | Movement | 0.69444 | 28.2942 |  | N/A | Cask Transporter (loaded) | AMF Equipment Issue | Equipment Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Equipment Cask 3 collected; Equipment Cask 3 moved to equipment stillage | Total | 0 | 28.2942 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
COB Blanket Segment stored; Hardware Cask 5 docked | Store COB Blanket Segment in Hardware Cask 5 | Trigger | 0 | 36.6842 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 5 | Logistics | 2.3 | 38.9842 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Receipt | Movement | 0.69444 | 39.6786 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store COB Blanket Segment | Logistics | 0.68 | 40.3586 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.23148 | 40.5901 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 5 | Logistics | 1.4 | 41.9901 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| COB Blanket Segment stored; Hardware Cask 5 docked | Total | 0 | 41.9901 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Blanket Segment stored; Hardware Cask 6 docked | Store LOB Blanket Segment in Hardware Cask 6 | Trigger | 0 | 43.5542 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 6 | Logistics | 2.3 | 45.8542 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Receipt | Movement | 0.69444 | 46.5486 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store LOB Blanket Segment | Logistics | 0.68 | 47.2286 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter A to Hardware Stillage | Movement | 0.23148 | 47.4601 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 48.8601 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| LOB Blanket Segment stored; Hardware Cask 6 docked | Total | 0 | 48.8601 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Blanket Segment stored; Hardware Cask 5 docked | Store ROB Blanket Segment in Hardware Cask 5 | Trigger | 0 | 50.4242 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 5 | Logistics | 2.3 | 52.7242 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Receipt | Movement | 0.69444 | 53.4186 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store ROB Blanket Segment | Logistics | 0.68 | 54.0986 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.23148 | 54.3301 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 5 | Logistics | 1.4 | 55.7301 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| ROB Blanket Segment stored; Hardware Cask 5 docked | Total | 0 | 55.7301 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Blanket Segment stored; Hardware Cask 6 docked | Store LIB Blanket Segment in Hardware Cask 6 | Trigger | 0 | 57.2942 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter A to AMF Hardware Receipt | Movement | 0.34722 | 57.6414 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Issue | 25 | 0.02 | 0.34722 |  | N/A
| Store RIB Blanket Segment | Logistics | 0.68 | 58.3214 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter A to Hardware Stillage | Movement | 0.23148 | 58.5529 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 59.9529 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| LIB Blanket Segment stored; Hardware Cask 6 docked | Total | 0 | 59.9529 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Blanket Segment stored; Hardware Cask 5 docked | Un-dock hardware cask 5 | Trigger | 0 | 66.4642 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 5 | Logistics | 2.3 | 68.7642 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Receipt | Movement | 0.69444 | 69.4586 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store RIB Blanket Segment | Logistics | 0.68 | 70.1386 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter A to Hardware Stillage | Movement | 0.23148 | 70.3701 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 71.7701 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| RIB Blanket Segment stored; Hardware Cask 5 docked | Total | 0 | 71.7701 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Equipment Cask 2 stored; Hardware Cask 6 Collected; Hardware Cask 6 docked | Un-dock equipment cask 2 | Trigger | 0 | 26.6197 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter A to AMF Equipment Receipt | Movement | 0.69444 | 27.3142 |  | N/A | Cask Transporter (loaded) | Equipment Stillage | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Equipment Cask 2 | Logistics | 0.48 | 27.7942 |  | N/A |  |  |  | N/A | N/A | N/A | Store Cask | 0.48
| Move Cask Transporter A to AMF Equipment Issue | Movement | 0.027778 | 27.822 |  | N/A | Cask Transporter (unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Hardware Cask 6 | Logistics | 0.48 | 28.302 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48
| Move Cask Transporter A to Hardware Stillage | Movement | 0.23148 | 28.5335 |  | N/A | Cask Transporter (empty) | AMF Equipment Issue | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 29.9335 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Equipment Cask 2 stored; Hardware Cask 6 Collected; Hardware Cask 6 docked | Total | 0 | 29.9335 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Blanket Segment Collected; Hardware Cask 6 docked | Collect Blanket Segment 5 from Hardware Cask 6 | Trigger | 0 | 67.0642 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 7 | Logistics | 2.3 | 69.3642 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Issue | Movement | 0.11574 | 69.4799 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Issue | 25 | 0.06 | 0.11574 |  | N/A
| Export RIB Blanket Segment | Logistics | 0.63 | 70.1099 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63
| Move Cask Transporter A to Hardware Stillage | Movement | 0.69444 | 70.8044 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 72.2044 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| RIB Blanket Segment Collected; Hardware Cask 6 docked | Total | 0 | 72.2044 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Blanket Segment Collected; Hardware Cask 5 docked | Collect Blanket Segment 4 from Hardware Cask 5 | Trigger | 0 | 77.1344 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 6 | Logistics | 2.3 | 79.4344 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Issue | Movement | 0.11574 | 79.5501 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Issue | 25 | 0.06 | 0.11574 |  | N/A
| Export LIB Blanket Segment | Logistics | 0.63 | 80.1801 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63
| Move Cask Transporter A to Hardware Stillage | Movement | 0.69444 | 80.8746 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 82.2746 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| LIB Blanket Segment Collected; Hardware Cask 5 docked | Total | 0 | 82.2746 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Blanket Segment Collected; Hardware Cask 6 docked | Collect Blanket Segment 3 from Hardware Cask 6 | Trigger | 0 | 87.2046 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 5 | Logistics | 2.3 | 89.5046 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Issue | Movement | 0.11574 | 89.6203 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Issue | 25 | 0.06 | 0.11574 |  | N/A
| Export ROB Blanket Segment | Logistics | 0.63 | 90.2503 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63
| Move Cask Transporter B to Hardware Stillage | Movement | 0.69444 | 90.9447 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 92.3447 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| ROB Blanket Segment Collected; Hardware Cask 6 docked | Total | 0 | 92.3447 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Blanket Segment Collected; Hardware Cask 5 docked | Collect Blanket Segment 2 from Hardware Cask 5 | Trigger | 0 | 97.2747 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 6 | Logistics | 2.3 | 99.5747 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Issue | Movement | 0.11574 | 99.6905 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Issue | 25 | 0.06 | 0.11574 |  | N/A
| Export LOB Blanket Segment | Logistics | 0.63 | 100.3205 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63
| Move Cask Transporter A to Hardware Stillage | Movement | 0.69444 | 101.0149 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 102.4149 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| LOB Blanket Segment Collected; Hardware Cask 5 docked | Total | 0 | 102.4149 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
COB Blanket Segment Collected; Hardware Cask 6 docked | Collect Blanket Segment 1 from Hardware Cask 6 | Trigger | 0 | 107.3449 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 5 | Logistics | 2.3 | 109.6449 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Issue | Movement | 0.11574 | 109.7607 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Issue | 25 | 0.06 | 0.11574 |  | N/A
| Export COB Blanket Segment | Logistics | 0.63 | 110.3907 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63
| Move Cask Transporter B to Hardware Stillage | Movement | 0.69444 | 111.0851 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 112.4851 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| COB Blanket Segment Collected; Hardware Cask 6 docked | Total | 0 | 112.4851 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Equipment Cask 6 stored; Equipment Cask 2 Collected; Hardware Cask 2 docked; RIB Pipe Module Collected | Install COB Blanket Segment | Trigger | 0 | 116.8151 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter A to AMF Equipment Receipt | Movement | 0.23148 | 117.0466 |  | N/A | Cask Transporter (empty) | Equipment Stillage | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Equipment Cask 6 | Logistics | 0.48 | 117.5266 |  | N/A |  |  |  | N/A | N/A | N/A | Store Cask | 0.48
| Move Cask Transporter A to AMF Equipment Issue | Movement | 0.027778 | 117.5544 |  | N/A | Cask Transporter (unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Equipment Cask 2 | Logistics | 0.48 | 118.0344 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48
| Move Cask Transporter A to Hardware Stillage | Movement | 0.23148 | 118.2659 |  | N/A | Cask Transporter (empty) | AMF Equipment Issue | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Equipment Cask 2 | Logistics | 1.4 | 119.6659 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Move Cask Transporter B to AMF Hardware Issue | Movement | 0.23148 | 119.8973 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Collect RIB Pipe Module | Logistics | 0.68 | 120.5773 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.69444 | 121.2718 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 4 | Logistics | 1.4 | 122.6718 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Equipment Cask 6 stored; Equipment Cask 2 Collected; Hardware Cask 2 docked; RIB Pipe Module Collected | Total | 0 | 122.6718 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Hardware Cask 2 Un-Docked; LIB Pipe Module Collected; Hardware Cask 4 docked | Install RIB Pipe Module | Trigger | 0 | 127.7468 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-dock Hardware Cask 4 | Logistics | 2.3 | 130.0468 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Issue | Movement | 0.23148 | 130.2783 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Collect LIB Pipe Module | Logistics | 0.68 | 130.9583 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.69444 | 131.6527 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 4 | Logistics | 1.4 | 133.0527 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Hardware Cask 2 Un-Docked; LIB Pipe Module Collected; Hardware Cask 4 docked | Total | 0 | 133.0527 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Lower Port Pipe Module installed | weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to lower port operations | Operation | #REF! | #REF! | Install RIB blanket pipework module | #REF! |  |  |  | N/A | N/A | N/A |  | N/A
| RIB Lower Port Pipe Module installed | Total | 0 | #REF! |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Lower Port Pipe Module installed | weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to lower port operations | Operation | #REF! | #REF! | Install LIB blanket pipework module | #REF! |  |  |  | N/A | N/A | N/A |  | N/A
| LIB Lower Port Pipe Module installed | Total | 0 | #REF! |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Weld Failure
RIB Pipe Module stored; Hardware Cask 4 stored; Hardware Cask 5 collected; Hardware Cask 5 docked | Extract RIB Pipe Module | Trigger | 0 | 2.1549 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 4 | Logistics | 2.3 | 4.4549 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Receipt | Movement | 0.69444 | 5.1494 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store ROB Pipe Module | Logistics | 0.68 | 5.8294 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to AMF Equipment Receipt | Movement | 0.092593 | 5.922 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | AMF Equipment Receipt | 20 | 0.06 | 0.092593 |  | N/A
| Store Hardware Cask 4 | Logistics | 0.48 | 6.402 |  | N/A |  |  |  | N/A | N/A | N/A | Store Cask | 0.48
| Move to Cask Transporter B to AMF Equipment Issue | Movement | 0.027778 | 6.4297 |  | N/A | Cask Transporter (unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Hardware Cask 5 | Logistics | 0.48 | 6.9097 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48
| Move Cask Transporter B to Hardware Stillage | Movement | 0.69444 | 7.6042 |  | N/A | Cask Transporter (loaded) | AMF Equipment Issue | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 5 | Logistics | 1.4 | 9.0042 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| RIB Pipe Module stored; Hardware Cask 4 stored; Hardware Cask 5 collected; Hardware Cask 5 docked | Total | 0 | 9.0042 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Equipment Cask 3 collected; Equipment Cask 3 moved to equipment stillage | Un-dock equipment cask 2 | Trigger | 0 | 20.4108 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Deploy Cask Transporter C | Logistics | 0.5 | 20.9108 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy Equipment from Store | 0.5
| Collect Equipment Cask 3 | Logistics | 0.48 | 21.3908 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48
| Move Cask Transporter C to Equipment Stillage | Movement | 0.69444 | 22.0852 |  | N/A | Cask Transporter (loaded) | AMF Equipment Issue | Equipment Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Equipment Cask 3 collected; Equipment Cask 3 moved to equipment stillage | Total | 0 | 22.0852 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
COB Blanket Segment stored; Hardware Cask 5 docked | Store COB Blanket Segment in Hardware Cask 5 | Trigger | 0 | 36.6842 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 5 | Logistics | 2.3 | 38.9842 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Receipt | Movement | 0.69444 | 39.6786 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store COB Blanket Segment | Logistics | 0.68 | 40.3586 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.23148 | 40.5901 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 5 | Logistics | 1.4 | 41.9901 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| COB Blanket Segment stored; Hardware Cask 5 docked | Total | 0 | 41.9901 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Blanket Segment stored; Hardware Cask 6 docked | Store LOB Blanket Segment in Hardware Cask 6 | Trigger | 0 | 43.5542 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 6 | Logistics | 2.3 | 45.8542 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Receipt | Movement | 0.69444 | 46.5486 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store LOB Blanket Segment | Logistics | 0.68 | 47.2286 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter A to Hardware Stillage | Movement | 0.23148 | 47.4601 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 48.8601 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| LOB Blanket Segment stored; Hardware Cask 6 docked | Total | 0 | 48.8601 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Blanket Segment stored; Hardware Cask 5 docked | Store ROB Blanket Segment in Hardware Cask 5 | Trigger | 0 | 50.4242 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 5 | Logistics | 2.3 | 52.7242 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Receipt | Movement | 0.69444 | 53.4186 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store ROB Blanket Segment | Logistics | 0.68 | 54.0986 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.23148 | 54.3301 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 5 | Logistics | 1.4 | 55.7301 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| ROB Blanket Segment stored; Hardware Cask 5 docked | Total | 0 | 55.7301 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Blanket Segment stored; Hardware Cask 6 docked | Store LIB Blanket Segment in Hardware Cask 6 | Trigger | 0 | 57.2942 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter A to AMF Hardware Receipt | Movement | 0.34722 | 57.6414 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Issue | 25 | 0.02 | 0.34722 |  | N/A
| Store RIB Blanket Segment | Logistics | 0.68 | 58.3214 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter A to Hardware Stillage | Movement | 0.23148 | 58.5529 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 59.9529 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| LIB Blanket Segment stored; Hardware Cask 6 docked | Total | 0 | 59.9529 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Blanket Segment stored; Hardware Cask 5 docked | Un-dock hardware cask 5 | Trigger | 0 | 66.4642 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 5 | Logistics | 2.3 | 68.7642 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Receipt | Movement | 0.69444 | 69.4586 |  | N/A | Cask Transporter (loaded) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store RIB Blanket Segment | Logistics | 0.68 | 70.1386 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter A to Hardware Stillage | Movement | 0.23148 | 70.3701 |  | N/A | Cask Transporter (empty) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 71.7701 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| RIB Blanket Segment stored; Hardware Cask 5 docked | Total | 0 | 71.7701 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Equipment Cask 2 stored; Hardware Cask 6 Collected; Hardware Cask 6 docked | Un-dock equipment cask 2 | Trigger | 0 | 20.4108 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter A to AMF Equipment Receipt | Movement | 0.69444 | 21.1052 |  | N/A | Cask Transporter (loaded) | Equipment Stillage | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Equipment Cask 2 | Logistics | 0.48 | 21.5852 |  | N/A |  |  |  | N/A | N/A | N/A | Store Cask | 0.48
| Move Cask Transporter A to AMF Equipment Issue | Movement | 0.027778 | 21.613 |  | N/A | Cask Transporter (unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Hardware Cask 6 | Logistics | 0.48 | 22.093 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48
| Move Cask Transporter A to Hardware Stillage | Movement | 0.69444 | 22.7874 |  | N/A | Cask Transporter (loaded) | AMF Equipment Issue | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 24.1874 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Equipment Cask 2 stored; Hardware Cask 6 Collected; Hardware Cask 6 docked | Total | 0 | 24.1874 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Blanket Segment Collected; Hardware Cask 6 docked | Collect Blanket Segment 5 from Hardware Cask 6 | Trigger | 0 | 67.0642 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 7 | Logistics | 2.3 | 69.3642 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Issue | Movement | 0.11574 | 69.4799 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Issue | 25 | 0.06 | 0.11574 |  | N/A
| Export RIB Blanket Segment | Logistics | 0.63 | 70.1099 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63
| Move Cask Transporter A to Hardware Stillage | Movement | 0.69444 | 70.8044 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 72.2044 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| RIB Blanket Segment Collected; Hardware Cask 6 docked | Total | 0 | 72.2044 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Blanket Segment Collected; Hardware Cask 5 docked | Collect Blanket Segment 4 from Hardware Cask 5 | Trigger | 0 | 77.1344 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 6 | Logistics | 2.3 | 79.4344 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Issue | Movement | 0.11574 | 79.5501 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Issue | 25 | 0.06 | 0.11574 |  | N/A
| Export LIB Blanket Segment | Logistics | 0.63 | 80.1801 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63
| Move Cask Transporter A to Hardware Stillage | Movement | 0.69444 | 80.8746 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 82.2746 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| LIB Blanket Segment Collected; Hardware Cask 5 docked | Total | 0 | 82.2746 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Blanket Segment Collected; Hardware Cask 6 docked | Collect Blanket Segment 3 from Hardware Cask 6 | Trigger | 0 | 87.2046 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 5 | Logistics | 2.3 | 89.5046 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Issue | Movement | 0.11574 | 89.6203 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Issue | 25 | 0.06 | 0.11574 |  | N/A
| Export ROB Blanket Segment | Logistics | 0.63 | 90.2503 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63
| Move Cask Transporter B to Hardware Stillage | Movement | 0.69444 | 90.9447 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 92.3447 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| ROB Blanket Segment Collected; Hardware Cask 6 docked | Total | 0 | 92.3447 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Blanket Segment Collected; Hardware Cask 5 docked | Collect Blanket Segment 2 from Hardware Cask 5 | Trigger | 0 | 97.2747 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 6 | Logistics | 2.3 | 99.5747 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter A to AMF Hardware Issue | Movement | 0.11574 | 99.6905 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Issue | 25 | 0.06 | 0.11574 |  | N/A
| Export LOB Blanket Segment | Logistics | 0.63 | 100.3205 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63
| Move Cask Transporter A to Hardware Stillage | Movement | 0.69444 | 101.0149 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 102.4149 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| LOB Blanket Segment Collected; Hardware Cask 5 docked | Total | 0 | 102.4149 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
COB Blanket Segment Collected; Hardware Cask 6 docked | Collect Blanket Segment 1 from Hardware Cask 6 | Trigger | 0 | 107.3449 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Un-Dock Hardware Cask 5 | Logistics | 2.3 | 109.6449 |  | N/A |  |  |  | N/A | N/A | N/A | Un-Dock Hardware Cask | 2.3
| Move Cask Transporter B to AMF Hardware Issue | Movement | 0.11574 | 109.7607 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Issue | 25 | 0.06 | 0.11574 |  | N/A
| Export COB Blanket Segment | Logistics | 0.63 | 110.3907 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Hardware Cask | 0.63
| Move Cask Transporter B to Hardware Stillage | Movement | 0.69444 | 111.0851 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 6 | Logistics | 1.4 | 112.4851 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| COB Blanket Segment Collected; Hardware Cask 6 docked | Total | 0 | 112.4851 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Equipment Cask 6 stored; Equipment Cask 2 Collected; Hardware Cask 2 docked; RIB Pipe Module Collected | Install COB Blanket Segment | Trigger | 0 | 116.8151 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Cask Transporter A to AMF Equipment Receipt | Movement | 0.23148 | 117.0466 |  | N/A | Cask Transporter (empty) | Equipment Stillage | AMF Equipment Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Store Equipment Cask 6 | Logistics | 0.48 | 117.5266 |  | N/A |  |  |  | N/A | N/A | N/A | Store Cask | 0.48
| Move Cask Transporter A to AMF Equipment Issue | Movement | 0.027778 | 117.5544 |  | N/A | Cask Transporter (unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Equipment Cask 2 | Logistics | 0.48 | 118.0344 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Cask | 0.48
| Move Cask Transporter A to Hardware Stillage | Movement | 0.23148 | 118.2659 |  | N/A | Cask Transporter (empty) | AMF Equipment Issue | Hardware Stillage | 50 | 0.06 | 0.23148 |  | N/A
| Dock Equipment Cask 2 | Logistics | 1.4 | 119.6659 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Move Cask Transporter B to AMF Hardware Issue | Movement | 0.23148 | 119.8973 |  | N/A | Cask Transporter (empty) | Hardware Stillage | AMF Hardware Receipt | 50 | 0.06 | 0.23148 |  | N/A
| Collect RIB Pipe Module | Logistics | 0.68 | 120.5773 |  | N/A |  |  |  | N/A | N/A | N/A | Store Hardware in Storage Location | 0.68
| Move Cask Transporter B to Hardware Stillage | Movement | 0.69444 | 121.2718 |  | N/A | Cask Transporter (loaded) | AMF Hardware Receipt | Hardware Stillage | 50 | 0.02 | 0.69444 |  | N/A
| Dock Hardware Cask 4 | Logistics | 1.4 | 122.6718 |  | N/A |  |  |  | N/A | N/A | N/A | Dock Hardware Cask | 1.4
| Equipment Cask 6 stored; Equipment Cask 2 Collected; Hardware Cask 2 docked; RIB Pipe Module Collected | Total | 0 | 122.6718 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Lower Port Pipe Module installed | weld failure identified | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to lower port operations | Operation | #REF! | #REF! | Install RIB blanket pipework module | #REF! |  |  |  | N/A | N/A | N/A |  | N/A
| RIB Lower Port Pipe Module installed | Total | 0 | #REF! |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A

## Upper Hot Cell Summary
|  |  | Hot Cell Vertical Port Long Maintenance Interval |  |  |  |  | Time Taken to complete | Estimated Duration of
|  |  | Blanket Maintenance |  | Failures |  | Total
|  |  | Blanket Removal | Blanket Installation | RM Equipment | Welding Operations | Maintenance Cycle | Lower Port Hot Cell Ops | Maintenace Campaign
Single Port | Operations | hrs | 154.919 | 290.1264 | 38.9013 | 241.8747 | 725.8215 | 906.8095
|  | %age | 75.05% | 93.87% | 52.55% | 81.36% | 81.85% | 77.97%
| Logistics | hrs | 21.0233 | 17.8044 | 27.4455 | 7.8575 | 74.1307 | 134.4096
|  | %age | 10.18% | 5.76% | 37.08% | 2.643% | 8.359% | 11.56%
|  | Idle time | 30.4865 | 1.1494 | 7.674 | 47.5405 | 86.8504 | 121.8332
|  | %age | 14.77% | 0.3719% | 10.37% | 15.99% | 9.794% | 10.48%
| Total Time | hrs | 206.4288 | 309.0803 | 74.0208 | 297.2727 | 886.8027 | 1163.0523 | 1163.0523
|  | days | 8.6012 | 12.8783 | 3.0842 | 12.3864 | 36.9501 | 48.4605 | 48.4605
| Elapsed Time | hrs | 340.6075 | 509.9825 | 122.1344 | 490.4999 | 1463.2244 | 1919.0363 | 1919.0363
|  | Days | 14.192 | 21.2493 | 5.0889 | 20.4375 | 60.9677 | 79.9598 | 79.9598
|  | Months | 0.47307 | 0.70831 | 0.16963 | 0.68125 | 2.0323 | 2.6653 | 2.6653
|  | % | 23.28% | 34.85% | 8.347% | 33.52% | 100% | 100% | 100%
All 18 Ports in series | Operations | hrs | 2788.5424 | 5222.2759 | 700.2241 | 4353.745 | 13064.7874 | 11513.0551
|  | days | 116.1893 | 217.5948 | 29.176 | 181.406 | 544.3661 | 479.7106
| Logistics | hrs | 378.42 | 320.48 | 494.0189 | 141.4346 | 1334.3535 | 1829.9472
|  | days | 15.7675 | 13.3533 | 20.5841 | 5.8931 | 55.5981 | 76.2478
|  | Idle time | 548.7562 | 20.69 | 138.1321 | 855.7286 | 1563.3069 | 200.8735
| Total Time | hrs | 3715.7186 | 5563.4459 | 1332.3751 | 5350.9082 | 15962.4478 | 13543.8758 | 15962.4478
|  | days | 154.8216 | 231.8102 | 55.5156 | 222.9545 | 665.102 | 564.3282 | 665.102
| Elapsed Time | hrs | 6130.9356 | 9179.6858 | 2198.4189 | 8828.9985 | 26338.0388 | 22347.3951 | 26338.0388
|  | Days | 255.4557 | 382.4869 | 91.6008 | 367.8749 | 1097.4183 | 931.1415 | 1097.4183
|  | Months | 8.5152 | 12.7496 | 3.0534 | 12.2625 | 36.5806 | 31.038 | 36.5806
|  | % | 23.28% | 34.85% | 8.347% | 33.52% | 100% | 100% | 100%
All 18 Ports with 2 Systems | Operations | hrs | 1394.2712 | 2611.138 | 350.112 | 2176.8725 | 6532.3937 | 8161.2854
|  | days | 58.0946 | 108.7974 | 14.588 | 90.703 | 272.1831 | 340.0536
| Logistics | hrs | 189.21 | 160.24 | 247.0095 | 70.7173 | 667.1767 | 1209.6863
|  | days | 7.8838 | 6.6767 | 10.2921 | 2.9466 | 27.799 | 50.4036
|  | Idle time | 274.3781 | 10.345 | 69.066 | 427.8643 | 781.6534 | 1096.499
| Total Time | hrs | 1857.8593 | 2781.723 | 666.1875 | 2675.4541 | 7981.2239 | 10467.4708 | 10467.4708
|  | days | 77.4108 | 115.9051 | 27.7578 | 111.4773 | 332.551 | 436.1446 | 436.1446
| Elapsed Time | hrs | 3065.4678 | 4589.8429 | 1099.2095 | 4414.4993 | 13169.0194 | 17271.3268 | 17271.3268
|  | Days | 127.7278 | 191.2435 | 45.8004 | 183.9375 | 548.7091 | 719.6386 | 719.6386
|  | Months | 4.2576 | 6.3748 | 1.5267 | 6.1312 | 18.2903 | 23.988 | 23.988
|  | % | 34.92% | 52.28% | 12.52% | 50.28% | 150% | 100% | 150%
All 18 Ports with 3 Systems | Operations | hrs | 929.5141 | 1740.7586 | 233.408 | 1451.2483 | 4354.9291 | 5440.8569
|  | days | 38.7298 | 72.5316 | 9.7253 | 60.4687 | 181.4554 | 181.2389
| Logistics | hrs | 126.14 | 106.8267 | 164.673 | 47.1449 | 444.7845 | 806.4575
|  | days | 5.2558 | 4.4511 | 6.8614 | 1.9644 | 18.5327 | 27.3014
|  | Idle time | 182.9187 | 6.8967 | 46.044 | 285.2429 | 521.1023 | 730.9994
| Total Time | hrs | 1238.5729 | 1854.482 | 444.125 | 1783.6361 | 5320.8159 | 6978.3138 | 6978.3138
|  | days | 51.6072 | 77.2701 | 18.5052 | 74.3182 | 221.7007 | 238.7161 | 238.7161
| Elapsed Time | hrs | 2043.6452 | 3059.8953 | 732.8063 | 2942.9995 | 8779.3463 | 11514.2178 | 11514.2178
|  | Days | 85.1519 | 127.4956 | 30.5336 | 122.625 | 365.8061 | 479.7591 | 479.7591
|  | Months | 2.8384 | 4.2499 | 1.0178 | 4.0875 | 12.1935 | 15.992 | 15.992
|  | % | 23.28% | 34.85% | 8.347% | 33.52% | 100% | 100% | 100%
All 18 Ports with 4 Systems | Operations | hrs | 774.5951 | 1450.6322 | 194.4113 | 1209.3736 | 3629.0122 | 4534.0474
|  | days | 32.2748 | 60.443 | 8.1005 | 50.3906 | 151.2088 | 130.3673
| Logistics | hrs | 105.1167 | 89.0222 | 137.157 | 39.2874 | 370.5832 | 672.048
|  | days | 4.3799 | 3.7093 | 5.7149 | 1.637 | 15.441 | 19.887
|  | Idle time | 152.4323 | 5.7472 | 38.37 | 237.7024 | 434.2519 | 609.1661
| Total Time | hrs | 1032.144 | 1545.4016 | 369.9383 | 1486.3634 | 4433.8474 | 5815.2615 | 5815.2615
|  | days | 43.006 | 64.3917 | 15.4141 | 61.9318 | 184.7436 | 175.2724 | 184.7436
| Elapsed Time | hrs | 1703.0377 | 2549.9127 | 610.3982 | 2452.4996 | 7315.8482 | 9595.1815 | 9595.1815
|  | Days | 70.9599 | 106.2464 | 25.4333 | 102.1875 | 304.827 | 399.7992 | 399.7992
|  | Months | 2.3653 | 3.5415 | 0.84778 | 3.4062 | 10.1609 | 13.3266 | 13.3266
|  | % | 19.4% | 29.04% | 6.953% | 27.93% | 83.33% | 100% | 100%
All 18 Ports with 6 Systems | Operations | hrs | 464.7571 | 870.3793 | 116.704 | 725.6242 | 2177.4646 | 2720.4285
|  | days | 19.3649 | 36.2658 | 4.8627 | 30.2343 | 90.7277 | 65.0463
| Logistics | hrs | 63.07 | 53.4133 | 82.3365 | 23.5724 | 222.3922 | 403.2288
|  | days | 2.6279 | 2.2256 | 0.37078 | 0.026432 | 9.2663 | 10.1063
|  | Idle time | 91.4594 | 3.4483 | 23.022 | 142.6214 | 260.5511 | 365.4997
| Total Time | hrs | 619.2864 | 927.241 | 222.0625 | 891.818 | 2660.408 | 3489.1569 | 3489.1569
|  | days | 25.8036 | 38.635 | 9.2526 | 37.1591 | 110.8503 | 90.0816 | 110.8503
| Elapsed Time | hrs | 1021.8226 | 1529.9476 | 366.4032 | 1471.4998 | 4389.6731 | 5757.1089 | 5757.1089
|  | Days | 42.5759 | 63.7478 | 15.2668 | 61.3125 | 182.903 | 239.8795 | 239.8795
|  | Months | 1.4192 | 2.1249 | 0.50889 | 2.0437 | 6.0968 | 7.996 | 7.996
|  | % | 23.28% | 34.85% | 8.347% | 33.52% | 100% | 100% | 100%
Note on C13: Farquhar, Iain: Calculated by factoring a efficiently factor of 0.67, as well as an allowance for both un-planned maintenance and logistics tasks, equal to an additional 10%.
Note on C25: Farquhar, Iain: Calculated by factoring a efficiently factor of 0.67, as well as an allowance for both un-planned maintenance and logistics tasks equal to an additional 10%.
Note on C37: Farquhar, Iain: Calculated by factoring a efficiently factor of 0.67, as well as an allowance for both un-planned maintenance and logistics tasks equal to an additional 10%.
Note on C49: Farquhar, Iain: Calculated by factoring a efficiently factor of 0.67, as well as an allowance for both un-planned maintenance and logistics tasks equal to an additional 10%.
Note on C61: Farquhar, Iain: Calculated by factoring a efficiently factor of 0.67, as well as an allowance for both un-planned maintenance and logistics tasks equal to an additional 10%.
Note on C73: Farquhar, Iain: Calculated by factoring a efficiently factor of 0.67, as well as an allowance for both un-planned maintenance and logistics tasks equal to an additional 10%.

## Upper Hot Cell Critical Path (hidden)
[5 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies
Group | Activity | Activity Type | Time (h) | Cumulative Time (h) | Type | N/A | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack
Open Bioshield | Blanket Removal Required | Operation | 0 | 0 | Blanket Removal Required | 0 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Deploy Crane A | Logistics | 1.08 | 1.08 |  | N/A |  |  |  | N/A | N/A | N/A | collect RM equipment | 1.08 |  | N/A | N/A
| Collect Bioshield interface hardware | Logistics | 0.58 | 1.66 |  | N/A |  |  |  | N/A | N/A | N/A | Collect interface hardware | 0.58 |  | N/A | N/A
| Move Crane A to Upper Port | Movement | 0.069444 | 1.7294 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A
| Open Bioshield | Operation | 0.56667 | 2.2961 | Open Bioshield | 0.56667 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move bioshield to bioshield storage area | Movement | 0.41667 | 2.7128 |  | N/A | Overhead Crane (Loaded) | Vertical Port | Hardware Stillage | 30 | 0.02 | 0.41667 |  | N/A |  | N/A | N/A
Carry Out health physics checks | Deploy health physics hardware | Logistics | 1.28 | 3.9928 |  | N/A | [5 empty] | N/A | Deploy RM system into the port | 1.28 | Port Inspection System collected | 1.7744 | 0.93833
| Perform Health Physics Checks | Operation | 6.7722 | 10.765 | Perform Health Physics Checks | 6.7722 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract health physics hardware | Logistics | 1.1 | 11.865 |  | N/A |  |  |  | N/A | N/A | N/A | Recovery RM system from the port | 1.1 |  | N/A | N/A
Install Contamination Control system | Move Crane A to Vertical Port | Movement | 0.69444 | 12.5594 |  | N/A | Overhead Crane (loaded) | AMF Equipment Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A | Bioshield Attachment stored & CCS Attachment collected | 4.65 | 7.215
| Install contamination control system | Operation | 0.5 | 13.0594 | Install Contamination Control System | 0.5 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Commission Contamination Control System | Operation | 2.2 | 15.2594 | Commission Contamination Control System | 2.2 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
Perform engineering survey | Deploy Port Inspection Hardware | Logistics | 1.28 | 16.5394 |  | N/A | [5 empty] | N/A | Deploy RM system into the port | 1.28 |  | N/A | N/A
| Perform engineering checks | Operation | 5.7722 | 22.3117 | Perform engineering checks | 5.7722 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract Port Inspection System | Logistics | 1.1 | 23.4117 |  | N/A |  |  |  | N/A | N/A | N/A | Recovery RM system from the port | 1.1 |  | N/A | N/A
ECH Removal | Move Multifunction Manipulator to Upper Port | Movement | 0.69444 | 24.1061 |  | N/A | Multifunction Manipulator | AMF Equipment Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A
| Disconnect ECH using Multifunction Manipulator | Operation | 9.425 | 33.5311 | Disconnect ECH | 9.425 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move Crane A to Upper Port | Movement | 0.069444 | 33.6006 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A
| Extract ECH | Operation | 2.175 | 35.7756 | Extract ECH | 2.175 |  |  |  | N/A | N/A | N/A |  | N/A | CCS Attachment stored & ECH Lifting Attachment collected | 17.5133 | 16.0872
Carry Out health physics checks | Deploy health physics hardware | Logistics | 1.28 | 37.0556 |  | N/A | [5 empty] | N/A | Deploy RM system into the port | 1.28 |  | N/A | N/A
| Perform Health Physics Checks | Operation | 6.7722 | 43.8278 | Perform Health Physics Checks | 6.7722 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract health physics hardware | Logistics | 1.1 | 44.9278 |  | N/A |  |  |  | N/A | N/A | N/A | Recovery RM system from the port | 1.1 |  | N/A | N/A
Perform engineering survey | Deploy Port Inspection Hardware | Logistics | 1.28 | 46.2078 |  | N/A | [5 empty] | N/A | Deploy RM system into the port | 1.28 |  | N/A | N/A
| Perform engineering checks | Operation | 5.7722 | 51.98 | Perform engineering checks | 5.7722 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract Port Inspection System | Logistics | 1.1 | 53.08 |  | N/A |  |  |  | N/A | N/A | N/A | Recovery RM system from the port | 1.1 |  | N/A | N/A
Closure Plate Removal | Move Closure Plate Disconnection Equipment to Upper Port | Movement | 0.69444 | 53.7744 |  | N/A | Closure Plate Disconnection Equipment | AMF Equipment Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A
| Move Multifunction Manipulator to Upper Port | Movement | 0.20833 | 53.9828 |  | N/A | Multifunction Manipulator | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A |  | N/A | N/A
| Deploy multifunction manipulator into the port | Logistics | 1.28 | 55.2628 |  | N/A |  |  |  | N/A | N/A | N/A | Deploy RM system into the port | 1.28 |  | N/A | N/A
| Disconnect Port Closure Plate using Multifunction Manipulator | Operation | 29.3333 | 84.5961 | Disconnect Port Closure Plate | 29.3333 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Recovery multifunction manipulator from the port | Logistics | 1.1 | 85.6961 |  | N/A |  |  |  | N/A | N/A | N/A | Recovery RM system from the port | 1.1 |  | N/A | N/A
| Move Crane B to Upper Port | Movement | 0.069444 | 85.7656 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A
| Extract Port Closure Plate | Operation | 0.375 | 86.1406 | Extract Port Closure Plate | 0.375 |  |  |  | N/A | N/A | N/A |  | N/A | Port Inspection System stored and Port Closure plate lifting hardware collected | 18.3133 | 67.4522
Shield Plug & Fixations Removal | Move Multifunction Manipulator to Upper Port | Movement | 0.20833 | 86.3489 |  | N/A | Multifunction Manipulator | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A |  | N/A | N/A
| Disconnect Shield Plug Pipe Flange using Multifunction Manipulator | Operation | 3.8333 | 90.1822 | Disconnect Shield Plug Pipe Flange | 3.8333 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move Crane A to Upper Port | Movement | 0.069444 | 90.2517 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | ECH & ECH Attachment stored & Shield Plug Equip collected | 38.8656 | 51.3167
| Disconnect & extract Shield Plug and Fixations | Operation | 3.925 | 94.1767 | Disconnect & extract Shield Plug and Fixations | 3.925 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
Carry Out Engineering survey | Deploy Port Inspection Hardware | Logistics | 1.28 | 95.4567 |  | N/A | [5 empty] | N/A | Deploy RM system into the port | 1.28 |  | N/A | N/A
| Perform engineering checks | Operation | 5.7722 | 101.2289 | Perform engineering checks | 5.7722 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract Port Inspection System | Logistics | 1.1 | 102.3289 |  | N/A |  |  |  | N/A | N/A | N/A | Recovery RM system from the port | 1.1 |  | N/A | N/A
COB Blanket Pipework Disconnection | Move Multifunction Manipulator to Upper Port | Movement | 0.20833 | 102.5372 |  | N/A | Multifunction Manipulator | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A |  | N/A | N/A
| Disconnect Multipipe Flange 1 using Multifunction Manipulator | Operation | 6.83 | 109.3672 | Disconnect Multipipe Flange & Access Lid | 6.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move Crane B to Upper Port | Movement | 0.069444 | 109.4367 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | Closure plate & Closure Attachment Stored & Service Joint System collected | 89.2306 | 20.1367
| Cut COB Pipe joint using SJS | Operation | 1.0499 | 110.4866 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
COB Blanket Pipework Removal | Move pipe module lifting attachment to Upper Port | Movement | 0.069444 | 110.556 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | Shield Plug & Shield Plug Equip stored & Pipe Lifter collected | 97.3667 | 13.1199
| Extract COB Pipe Module | Operation | 0.725 | 111.281 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
LOB Blanket Pipework Disconnection | Move Multifunction Manipulator to Upper Port | Movement | 0.20833 | 111.4894 |  | N/A | Multifunction Manipulator | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A |  | N/A | N/A
| Disconnect Multipipe Flange 2 using Multifunction Manipulator | Operation | 6.83 | 118.3194 | Disconnect Multipipe Flange & Access Lid | 6.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move Crane B to Upper Port | Movement | 0.020833 | 118.3402 |  | N/A | Overhead Crane (Unloaded) | Equipment Stillage | Vertical Port | 15 | 0.2 | 0.020833 |  | N/A |  | N/A | N/A
| Cut LOB Pipe joint using SJS | Operation | 1.0499 | 119.3901 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
LOB Blanket Pipework Removal | Move pipe module lifting attachment to Upper Port | Movement | 0.069444 | 119.4596 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | Pipe Module 1 Stored | 112.5555 | 6.8346
| Extract LOB Pipe Module | Operation | 0.725 | 120.1846 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
ROB Blanket Pipework Disconnection | Move Multifunction Manipulator to Upper Port | Movement | 0.20833 | 120.3929 |  | N/A | Multifunction Manipulator | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A |  | N/A | N/A
| Disconnect Multipipe Flange 3 using Multifunction Manipulator | Operation | 6.83 | 127.2229 | Disconnect Multipipe Flange & Access Lid | 6.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move Crane B to Upper Port | Movement | 0.020833 | 127.2437 |  | N/A | Overhead Crane (Unloaded) | Equipment Stillage | Vertical Port | 15 | 0.2 | 0.020833 |  | N/A |  | N/A | N/A
| Cut ROB Pipe joint using SJS | Operation | 1.0499 | 128.2936 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
ROB Blanket Pipework Removal | Move pipe module lifting attachment to Upper Port | Movement | 0.069444 | 128.3631 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | Pipe Module 2 Stored | 121.459 | 6.8346
| Extract ROB Pipe Module | Operation | 0.725 | 129.0881 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
LIB Blanket Pipework Disconnection | Move Multifunction Manipulator to Upper Port | Movement | 0.20833 | 129.2964 |  | N/A | Multifunction Manipulator | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A |  | N/A | N/A
| Disconnect Multipipe Flange 4 using Multifunction Manipulator | Operation | 6.83 | 136.1264 | Disconnect Multipipe Flange & Access Lid | 6.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move Crane B to Upper Port | Movement | 0.020833 | 136.1472 |  | N/A | Overhead Crane (Unloaded) | Equipment Stillage | Vertical Port | 15 | 0.2 | 0.020833 |  | N/A |  | N/A | N/A
| Cut LIB Pipe joint using SJS | Operation | 1.0499 | 137.1972 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
LIB Blanket Pipework Removal | Move pipe module lifting attachment to Upper Port | Movement | 0.069444 | 137.2666 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | Pipe Module 3 Stored | 130.3625 | 6.8346
| Extract LIB Pipe Module | Operation | 0.725 | 137.9916 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
RIB Blanket Pipework Disconnection | Move Multifunction Manipulator to Upper Port | Movement | 0.20833 | 138.1999 |  | N/A | Multifunction Manipulator | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A |  | N/A | N/A
| Disconnect Multipipe Flange 5 using Multifunction Manipulator | Operation | 6.83 | 145.0299 | Disconnect Multipipe Flange & Access Lid | 6.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move Crane B to Upper Port | Movement | 0.020833 | 145.0508 |  | N/A | Overhead Crane (Unloaded) | Equipment Stillage | Vertical Port | 15 | 0.2 | 0.020833 |  | N/A |  | N/A | N/A
| Cut RIB Pipe joint using SJS | Operation | 1.0499 | 146.1007 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
RIB Blanket Pipework Removal | Move pipe module lifting attachment to Upper Port | Movement | 0.069444 | 146.1701 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | Pipe Module 4 Stored | 139.2661 | 6.8346
| Extract RIB Pipe Module | Operation | 0.725 | 146.8951 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
Blanket Removal | Move Crane B to Upper Port | Movement | 0.069444 | 148.1274 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | Service Joint System stored & Blanket Transporter collected | 148.0579 | -1.1628
| Extract COB Blanket Segment | Operation | 5.74 | 178.9105 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A | Lower Port COB Pipe Module Removed | 173.1705 | -25.0431
| Move Crane A to Upper Port | Movement | 0.069444 | 178.9799 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | Pipe Module 5 & Pipe Lifter Stored & Blanket Transporter collected | 150.0851 | 28.8253
| Extract LOB Blanket Segment | Operation | 5.74 | 189.0005 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A | Lower Port LOB Pipe Module Removed | 183.2605 | -4.2806
| Move Crane B to Upper Port | Movement | 0.069444 | 189.0699 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | COB Blanket Segment Stored | 180.1849 | 8.8156
| Extract ROB Blanket Segment | Operation | 5.74 | 194.8099 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A | Lower Port ROB Pipe Module Removed | 184.9305 | 4.1394
| Move Crane A to Upper Port | Movement | 0.069444 | 194.8794 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | LOB Blanket Segment Stored | 190.2749 | 4.535
| Extract LIB Blanket Segment | Operation | 5.74 | 200.6194 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A | Lower Port LIB Pipe Module Removed | 191.0305 | 3.8488
| Move Crane B to Upper Port | Movement | 0.069444 | 200.6888 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | ROB Blanket Segment Stored | 196.0844 | 4.535
| Extract RIB Blanket Segment | Operation | 5.74 | 206.4288 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A | Lower Port RIB Pipe Module Removed | 192.7005 | 7.9883
Removal Complete | End Time |  | 206.4288
| Operational Time |  | 154.919 |  |  | 75.05%
| Logistical Time |  | 15.94 |  |  | 7.722% | [9 empty] | Delays | -30.4865
| Movement Time |  | 5.0833 |  |  | 2.463%
Inspect and re-condition Lower Port | Blanket Installation Required | Operation | 0 | 0 | Blanket Removal Required | 0 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Deploy inspection system | Movement | 0.69444 | 1.8439 |  | N/A | Overhead Crane (loaded) | AMF Equipment Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A | Deploy inspection and repair hardware to upper port | 1.1494 | -1.1494
| Inspect the port | Operation | 8.5 | 10.3439 | Inspect the port | 8.5 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Re-condition IVC hardware/fixations | Operation | 8.5 | 18.8439 | Clean/re-condition port hardware | 8.5 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
Install Blanket Segments | Move Crane A to Upper Port | Movement | 0.69444 | 19.5383 |  | N/A | Overhead Crane (Loaded) | AMF Hardware Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A | Blanket Transporter collected; RIB Blanket Segment Exported | 0.84944 | 17.9944
| Install RIB Blanket Segment | Operation | 4.33 | 23.8683 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move Segment 4 (Crane B) to Upper Port | Movement | 0.69444 | 24.5628 |  | N/A | Overhead Crane (Loaded) | AMF Hardware Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A | Inspection and repair hardware stored; Blanket Transporter collected; LIB Blanket Segment Exported | 20.3183 | 3.55
| Install LIB Blanket Segment | Operation | 4.33 | 28.8928 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move Segment 3 (Crane A) to Upper Port | Movement | 0.69444 | 29.5872 |  | N/A | Overhead Crane (Loaded) | AMF Hardware Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A | ROB Blanket Segment Exported | 25.3428 | 3.55
| Install ROB Blanket Segment | Operation | 4.33 | 33.9172 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move Segment 2 (Crane B) to Upper Port | Movement | 0.69444 | 34.6117 |  | N/A | Overhead Crane (Loaded) | AMF Hardware Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A | LOB Blanket Segment Exported | 30.3672 | 3.55
| Install LOB Blanket Segment | Operation | 4.33 | 38.9417 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move Segment 1 (Crane A) to Upper Port | Movement | 0.69444 | 39.6361 |  | N/A | Overhead Crane (Loaded) | AMF Hardware Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A | COB Blanket Segment Exported | 35.3917 | 3.55
| Install COB Blanket Segment | Operation | 4.33 | 43.9661 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
Install RIB Pipe Module | Move pipe module lifting attachment to Upper Port | Movement | 0.069444 | 44.0356 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | Blanket Transporter stored & Pipe Module interface hardware Collected & RIB Pipe Module Collected | N/A | N/A
| Install RIB Pipe Module | Operation | 4.095 | 48.1306 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
Connect RIB Blanket Pipe Module | Move Crane B to Upper Port | Movement | 0.69444 | 48.825 |  | N/A | Overhead Crane (Loaded) | AMF Hardware Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A
| Weld RIB Joint using SJS | Operation | 24.0227 | 72.8477 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A | Blanket Transporter stored & Service Joint System Collected | 46.5344 | 2.2906
| Move Multifunction Manipulator to Upper Port | Movement | 0.20833 | 73.0561 |  | N/A | Multifunction Manipulator | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A |  | N/A | N/A
| Connect Multipipe Flange 5 using Multifunction Manipulator | Operation | 7.83 | 80.8861 | Connect Multipipe Flange & Access Lid | 7.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
LIB Blanket Pipework Installation | Move pipe module lifting attachment to Upper Port | Movement | 0.069444 | 80.9555 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | LIB Pipe Module Exported | N/A | N/A
| Install LIB Pipe Module | Operation | 4.095 | 85.0505 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
LIB Blanket Pipework Connection | Move Crane B to Upper Port | Movement | 0.69444 | 85.745 |  | N/A | Overhead Crane (Loaded) | AMF Hardware Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A
| Weld LIB Joint using SJS | Operation | 24.0227 | 109.7677 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move Multifunction Manipulator to Upper Port | Movement | 0.20833 | 109.976 |  | N/A | Multifunction Manipulator | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A |  | N/A | N/A
| Connect Multipipe Flange 4 using Multifunction Manipulator | Operation | 7.83 | 117.806 | Connect Multipipe Flange & Access Lid | 7.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
ROB Blanket Pipework Installation | Move pipe module lifting attachment to Upper Port | Movement | 0.069444 | 117.8755 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | ROB Pipe Module Exported | N/A | N/A
| Install ROB Pipe Module | Operation | 4.095 | 121.9705 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
ROB Blanket Pipework Connection | Move Crane B to Upper Port | Movement | 0.69444 | 122.6649 |  | N/A | Overhead Crane (Loaded) | AMF Hardware Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A
| Weld ROB Joint using SJS | Operation | 24.0227 | 146.6876 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move Multifunction Manipulator to Upper Port | Movement | 0.20833 | 146.896 |  | N/A | Multifunction Manipulator | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A |  | N/A | N/A
| Connect Multipipe Flange 3 using Multifunction Manipulator | Operation | 7.83 | 154.726 | Connect Multipipe Flange & Access Lid | 7.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
LOB Blanket Pipework Installation | Move pipe module lifting attachment to Upper Port | Movement | 0.069444 | 154.7954 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | LOB Pipe Module Exported | N/A | N/A
| Install LOB Pipe Module | Operation | 4.095 | 158.8904 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
LOB Blanket Pipework Connection | Move Crane B to Upper Port | Movement | 0.69444 | 159.5849 |  | N/A | Overhead Crane (Loaded) | AMF Hardware Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A
| Weld LOB Joint using SJS | Operation | 24.0227 | 183.6076 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move Multifunction Manipulator to Upper Port | Movement | 0.20833 | 183.8159 |  | N/A | Multifunction Manipulator | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A |  | N/A | N/A
| Connect Multipipe Flange 2 using Multifunction Manipulator | Operation | 7.83 | 191.6459 | Connect Multipipe Flange & Access Lid | 7.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
COB Blanket Pipework Installation | Move pipe module lifting attachment to Upper Port | Movement | 0.069444 | 191.7154 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | COB Pipe Module Exported | N/A | N/A
| Install COB Pipe Module | Operation | 4.095 | 195.8104 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
COB Blanket Pipework Connection | Move Crane B to Upper Port | Movement | 0.69444 | 196.5048 |  | N/A | Overhead Crane (Loaded) | AMF Hardware Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A
| Weld COB Joint using SJS | Operation | 24.0227 | 220.5276 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move Multifunction Manipulator to Upper Port | Movement | 0.20833 | 220.7359 |  | N/A | Multifunction Manipulator | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A |  | N/A | N/A
| Connect Multipipe Flange 1 using Multifunction Manipulator | Operation | 7.83 | 228.5659 | Connect Multipipe Flange & Access Lid | 7.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
Shield Plug & Fixations Installed | Move pipe module lifting attachment to Upper Port | Movement | 0.20833 | 228.7742 |  | N/A | Overhead Crane (Loaded) | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A | Pipe Module interface hardware Stored & Shield Plug & Fixations Equipment Collected | 197.7676 | 30.7983
| Install and Connect Shield Plug & Fixations | Operation | 3.695 | 232.4692 | Insert and Connect Shield Plug and Fixations | 3.695 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move Multifunction Manipulator to Upper Port | Movement | 0.069444 | 232.5387 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A
| Connect Shield Plug Pipe Flange using Multifunction Manipulator | Operation | 4.105 | 236.6437 | Connect Shield Plug Pipe Flange | 4.105 |  |  |  | N/A | N/A | N/A |  | N/A | Service Joint System Stored & Closure Plate interface hardware Collected | 223.4176 | 9.1211
Install Closure Plate | Move Crane A to Upper Port | Movement | 0.69444 | 237.3381 |  | N/A | Overhead Crane (Loaded) | AMF Hardware Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A
| Install Port Closure Plate | Operation | 0.375 | 237.7131 | Insert Port Closure Plate | 0.375 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move Closure Plate Disconnection Equipment to Upper Port | Movement | 0 | 237.7131 |  | N/A | Closure Plate Connection Equipment | AMF Equipment Issue | Vertical Port | 50 | N/A | Error |  | N/A |  | N/A | N/A
| Move Multifunction Manipulator to Upper Port | Movement | 0.20833 | 237.9214 |  | N/A | Multifunction Manipulator | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A |  | N/A | N/A
| Connect Port Closure Plate using Multifunction Manipulator | Operation | 34.32 | 272.2414 | Connect Port Closure Plate | 34.32 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
Install ECH | Move Crane A to Upper Port | Movement | 0.69444 | 272.9359 |  | N/A | Overhead Crane (Loaded) | AMF Hardware Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A
| Install ECH | Operation | 0.16667 | 273.1026 | Insert ECH | 0.16667 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move Multifunction Manipulator to Upper Port | Movement | 0.20833 | 273.3109 |  | N/A | Multifunction Manipulator | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A |  | N/A | N/A
| Connect ECH Services using Multifunction Manipulator | Operation | 14.565 | 287.8759 | Connect ECH | 14.565 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
Carry Out Engineering survey | Deploy Port Inspection Hardware | Logistics | 1.28 | 289.1559 |  | N/A | [5 empty] | N/A | Deploy RM system into the port | 1.28 |  | N/A | N/A
| Perform engineering checks | Operation | 5.7722 | 294.9281 | Perform engineering checks | 5.7722 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract Port Inspection System | Logistics | 1.1 | 296.0281 |  | N/A |  |  |  | N/A | N/A | N/A | Recovery RM system from the port | 1.1 |  | N/A | N/A
Install CCD and Seal Bioshield | Move Crane A to Upper Port | Movement | 0.41667 | 296.4448 |  | N/A | Overhead Crane (Loaded) | Hardware Stillage | Vertical Port | 30 | 0.02 | 0.41667 |  | N/A |  | N/A | N/A
| Disconnect CCS Services | Operation | 0.86667 | 297.3114 | Disconnect CCS Services | 0.86667 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Recover CCS from port area | Logistics | 1.1 | 298.4114 |  | N/A |  |  |  | N/A | N/A | N/A | Recovery RM system from the port | 1.1 |  | N/A | N/A
| Move Crane B to Upper Port | Movement | 0.41667 | 298.8281 |  | N/A | Overhead Crane (Loaded) | Hardware Stillage | Vertical Port | 30 | 0.02 | 0.41667 |  | N/A |  | N/A | N/A
| Seal Bioshield | Operation | 1.1 | 299.9281 | Seal Bioshield | 1.1 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
Carry Out health physics checks | Deploy health physics hardware | Logistics | 1.28 | 301.2081 |  | N/A | [5 empty] | N/A | Deploy RM system into the port | 1.28 | Port Inspection System collected | 1.7744 | 298.1537
| Perform Health Physics Checks | Operation | 6.7722 | 307.9803 | Perform Health Physics Checks | 6.7722 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Retract health physics hardware | Logistics | 1.1 | 309.0803 |  | N/A |  |  |  | N/A | N/A | N/A | Recovery RM system from the port | 1.1 |  | N/A | N/A
Installation Complete | End Time |  | 309.0803 | 310.2298
| Operational Time |  | 290.1264 |  |  | 93.87%
| Logistical Time |  | 5.86 |  |  | 1.896% | [7 empty] | Delays |  | Delays | -1.1494
| Movement Time |  | 11.9444 |  |  | 3.865%
Maintenance Cycle Complete | End Time |  | 309.0803
| Operational Time |  | 290.1264 |  |  | 93.87%
| Logistical Time |  | 5.86 |  |  | 1.896% | [7 empty] | Delays |  | Delays | -31.6359
| Movement Time |  | 11.9444 |  |  | 3.865%

## Upper Hot Cell Dependencies (hidden)
[5 empty] | Operations |  | Movement | [5 empty] | Logistics
Group | Activity | Activity Type | Time (h) | Cumulative | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h)
Port Inspection System collected | Blanket Removal Required | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Collect Port Inspection System hardware | Logistics | 1.08 | 1.08 |  | N/A |  |  |  | N/A | N/A | N/A | Collect RM Equipment | 1.08
| Move to Vertical Port | Movement | 0.69444 | 1.7744 |  | N/A | Overhead Crane (loaded) | AMF Equipment Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A
| Port Inspection System collected | Total | 0 | 1.7744 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Bioshield Attachment stored & CCS Attachment collected | Open Bioshield | Trigger | 0 | 2.2961 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to Hardware Stillage | Movement | 0.41667 | 2.7128 |  | N/A | Overhead Crane (Loaded) | Vertical Port | Hardware Stillage | 30 | 0.02 | 0.41667 |  | N/A
| Store Bioshield | Logistics | 0.58 | 3.2928 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| Move Crane A to AMF Equipment Receipt | Movement | 0.069444 | 3.3622 |  | N/A | Overhead Crane (Unloaded) | Hardware Stillage | AMF Equipment Receipt | 50 | 0.2 | 0.069444 |  | N/A
| Store Bioshield Attachment | Logistics | 0.68 | 4.0422 |  | N/A |  |  |  | N/A | N/A | N/A | Store Interface hardware | 0.68
| Move Crane A to AMF Equipment Issue | Movement | 0.027778 | 4.07 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect ECH interface hardware | Logistics | 0.58 | 4.65 |  | N/A |  |  |  | N/A | N/A | N/A | Collect interface hardware | 0.58
| Bioshield Attachment stored & CCS Attachment collected | Total | 0 | 4.65 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Port Inspection System stored and Port Closure plate lifting hardware collected | Deploy Port Inspection Hardware | Trigger | 0 | 16.5394 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF equipment reciept | Movement | 0.41667 | 16.9561 |  | N/A | Overhead Crane (Loaded) | Vertical Port | Hardware Stillage | 30 | 0.02 | 0.41667 |  | N/A
| Store port inspection system | Logistics | 0.58 | 17.5361 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| Move Crane A to AMF Equipment issue | Movement | 0.069444 | 17.6056 |  | N/A | Overhead Crane (Unloaded) | Hardware Stillage | AMF Equipment Receipt | 50 | 0.2 | 0.069444 |  | N/A
| Store port closure plate lifting attachment | Logistics | 0.68 | 18.2856 |  | N/A |  |  |  | N/A | N/A | N/A | Store Interface hardware | 0.68
| Move Crane A to vertical port | Movement | 0.027778 | 18.3133 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Port Inspection System stored and Port Closure plate lifting hardware collected | Total | 0 | 18.3133 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
CCS Attachment stored & ECH Lifting Attachment collected | Commission Contamination Control System | Trigger | 0 | 15.2594 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to Hardware Stillage | Movement | 0.41667 | 15.6761 |  | N/A | Overhead Crane (Loaded) | Vertical Port | Hardware Stillage | 30 | 0.02 | 0.41667 |  | N/A
| Store CCD | Logistics | 0.58 | 16.2561 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| Move Crane B to AMF Equipment Receipt | Movement | 0.069444 | 16.3256 |  | N/A | Overhead Crane (Unloaded) | Hardware Stillage | AMF Equipment Receipt | 50 | 0.2 | 0.069444 |  | N/A
| Store CCD Attachment | Logistics | 0.58 | 16.9056 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| Move Crane B to AMF Equipment Issue | Movement | 0.027778 | 16.9333 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Closure interface hardware | Logistics | 0.58 | 17.5133 |  | N/A |  |  |  | N/A | N/A | N/A | Collect interface hardware | 0.58
| CCS Attachment stored & ECH Lifting Attachment collected | Total | 0 | 17.5133 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ECH & ECH Attachment stored & Shield Plug Equip collected | Extract ECH | Trigger | 0 | 35.7756 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Hardware Receipt | Movement | 0.69444 | 36.47 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store ECH | Logistics | 0.58 | 37.05 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| Move Crane A to AMF Equipment Receipt | Movement | 0.027778 | 37.0778 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | AMF Equipment Receipt | 20 | 0.2 | 0.027778 |  | N/A
| Store ECH Attachment | Logistics | 0.68 | 37.7578 |  | N/A |  |  |  | N/A | N/A | N/A | Store Interface hardware | 0.68
| Move Crane A to AMF Equipment Issue | Movement | 0.027778 | 37.7856 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Shield Plug Equip. | Logistics | 1.08 | 38.8656 |  | N/A |  |  |  | N/A | N/A | N/A | Collect RM Equipment | 1.08
| ECH & ECH Attachment stored & Shield Plug Equip collected | Total | 0 | 38.8656 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Closure plate & Closure Attachment Stored & Service Joint System collected | Extract Port Closure Plate | Trigger | 0 | 86.1406 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Receipt | Movement | 0.69444 | 86.835 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Closure Plate | Logistics | 0.58 | 87.415 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| Move Crane B to AMF Equipment Receipt | Movement | 0.027778 | 87.4428 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | AMF Equipment Receipt | 20 | 0.2 | 0.027778 |  | N/A
| Store Closure Plate Attachment | Logistics | 0.68 | 88.1228 |  | N/A |  |  |  | N/A | N/A | N/A | Store Interface hardware | 0.68
| Move Crane B to AMF Equipment Issue | Movement | 0.027778 | 88.1506 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Service Joint System | Logistics | 1.08 | 89.2306 |  | N/A |  |  |  | N/A | N/A | N/A | Collect RM Equipment | 1.08
| Closure plate & Closure Attachment Stored & Service Joint System collected | Total | 0 | 89.2306 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Shield Plug & Shield Plug Equip stored & Pipe Lifter collected | Disconnect & extract Shield Plug and Fixations | Trigger | 0 | 94.1767 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Hardware Receipt | Movement | 0.69444 | 94.8711 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Shield Plug | Logistics | 0.58 | 95.4511 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| Move Crane A to AMF Equipment Receipt | Movement | 0.027778 | 95.4789 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | AMF Equipment Receipt | 20 | 0.2 | 0.027778 |  | N/A
| Store Shield Plug Attachment | Logistics | 0.78 | 96.2589 |  | N/A |  |  |  | N/A | N/A | N/A | Store RM Equipment | 0.78
| Move Crane A to AMF Equipment Issue | Movement | 0.027778 | 96.2867 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Pipe Lifter | Logistics | 1.08 | 97.3667 |  | N/A |  |  |  | N/A | N/A | N/A | Collect RM Equipment | 1.08
| Shield Plug & Shield Plug Equip stored & Pipe Lifter collected | Total | 0 | 97.3667 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Pipe Module 1 Stored | Extract COB Pipe Module | Trigger | 0 | 111.281 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Hardware Receipt | Movement | 0.69444 | 111.9755 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Pipe Module | Logistics | 0.58 | 112.5555 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| Pipe Module 1 Stored | Total | 0 | 112.5555 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Pipe Module 2 Stored | Extract LOB Pipe Module | Trigger | 0 | 120.1846 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Hardware Receipt | Movement | 0.69444 | 120.879 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Pipe Module | Logistics | 0.58 | 121.459 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| Pipe Module 2 Stored | Total | 0 | 121.459 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Pipe Module 3 Stored | Extract ROB Pipe Module | Trigger | 0 | 129.0881 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Hardware Receipt | Movement | 0.69444 | 129.7825 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Pipe Module | Logistics | 0.58 | 130.3625 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| Pipe Module 3 Stored | Total | 0 | 130.3625 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Pipe Module 4 Stored | Extract LIB Pipe Module | Trigger | 0 | 137.9916 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Hardware Receipt | Movement | 0.69444 | 138.6861 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Pipe Module | Logistics | 0.58 | 139.2661 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| Pipe Module 4 Stored | Total | 0 | 139.2661 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Lower Port COB Pipe Module Removed | Blanket Removal Required | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Lower Port COB pipework joint cut and pipework removed | Operation | 173.1705 | 173.1705 | Remove COB blanket pipework module | 173.1705 |  |  |  | N/A | N/A | N/A |  | N/A
| Lower Port COB Pipe Module Removed | Total | 0 | 173.1705 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Lower Port LOB Pipe Module Removed | Blanket Removal Required | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Lower Port LOB pipework joint cut and pipework removed | Operation | 183.2605 | 183.2605 | Remove LOB blanket pipework module | 183.2605 |  |  |  | N/A | N/A | N/A |  | N/A
| Lower Port LOB Pipe Module Removed | Total | 0 | 183.2605 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Lower Port ROB Pipe Module Removed | Blanket Removal Required | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Lower Port ROB pipework joint cut and pipework removed | Operation | 184.9305 | 184.9305 | Remove ROB blanket pipework module | 184.9305 |  |  |  | N/A | N/A | N/A |  | N/A
| Lower Port ROB Pipe Module Removed | Total | 0 | 184.9305 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Lower Port LIB Pipe Module Removed | Blanket Removal Required | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Lower Port LIB pipework joint cut and pipework removed | Operation | 191.0305 | 191.0305 | Remove LIB blanket pipework module | 191.0305 |  |  |  | N/A | N/A | N/A |  | N/A
| Lower Port LIB Pipe Module Removed | Total | 0 | 191.0305 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Lower Port RIB Pipe Module Removed | Blanket Removal Required | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Lower Port RIB pipework joint cut and pipework removed | Operation | 192.7005 | 192.7005 | Remove RIB blanket pipework module | 192.7005 |  |  |  | N/A | N/A | N/A |  | N/A
| Lower Port RIB Pipe Module Removed | Total | 0 | 192.7005 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Service Joint System stored & Blanket Transporter collected | Cut RIB Pipe joint using SJS | Trigger | 0 | 146.1007 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Equipment Receipt | Movement | 0.069444 | 146.1701 |  | N/A | Overhead Crane (Unloaded) | Vertical Port | AMF Equipment Receipt | 50 | 0.2 | 0.069444 |  | N/A
| Store Service Joint System | Logistics | 0.78 | 146.9501 |  | N/A |  |  |  | N/A | N/A | N/A | Store RM Equipment | 0.78
| Move Crane B to AMF Equipment Issue | Movement | 0.027778 | 146.9779 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Blanket Transporter | Logistics | 1.08 | 148.0579 |  | N/A |  |  |  | N/A | N/A | N/A | Collect RM Equipment | 1.08
| Service Joint System stored & Blanket Transporter collected | Total | 0 | 148.0579 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Pipe Module 5 & Pipe Lifter Stored & Blanket Transporter collected | Extract RIB Pipe Module | Trigger | 0 | 146.8951 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Hardware Receipt | Movement | 0.69444 | 147.5896 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Pipe Module | Logistics | 0.58 | 148.1696 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| Move Crane A to AMF Equipment Receipt | Movement | 0.027778 | 148.1974 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | AMF Equipment Receipt | 20 | 0.2 | 0.027778 |  | N/A
| Store Pipe Lifter | Logistics | 0.78 | 148.9774 |  | N/A |  |  |  | N/A | N/A | N/A | Store RM Equipment | 0.78
| Move Crane A to AMF Equipment Issue | Movement | 0.027778 | 149.0051 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Blanket Transporter | Logistics | 1.08 | 150.0851 |  | N/A |  |  |  | N/A | N/A | N/A | Collect RM Equipment | 1.08
| Pipe Module 5 & Pipe Lifter Stored & Blanket Transporter collected | Total | 0 | 150.0851 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
COB Blanket Segment Stored | Extract COB Blanket Segment | Trigger | 0 | 178.9105 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Receipt | Movement | 0.69444 | 179.6049 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Segment | Logistics | 0.58 | 180.1849 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| COB Blanket Segment Stored | Total | 0 | 180.1849 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Blanket Segment Stored | Extract LOB Blanket Segment | Trigger | 0 | 189.0005 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Hardware Receipt | Movement | 0.69444 | 189.6949 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Segment | Logistics | 0.58 | 190.2749 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| LOB Blanket Segment Stored | Total | 0 | 190.2749 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Blanket Segment Stored | Extract ROB Blanket Segment | Trigger | 0 | 194.8099 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Receipt | Movement | 0.69444 | 195.5044 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Segment | Logistics | 0.58 | 196.0844 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| ROB Blanket Segment Stored | Total | 0 | 196.0844 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Blanket Segment Stored | Extract LIB Blanket Segment | Trigger | 0 | 200.6194 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Receipt | Movement | 0.69444 | 201.3138 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Segment | Logistics | 0.58 | 201.8938 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| LIB Blanket Segment Stored | Total | 0 | 201.8938 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Blanket Segment Stored | Extract RIB Blanket Segment | Trigger | 0 | 206.4288 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Receipt | Movement | 0.69444 | 207.1233 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Segment | Logistics | 0.58 | 207.7033 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| RIB Blanket Segment Stored | Total | 0 | 207.7033 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Blankets Removal Complete
| Movement Operations |  |  | 7.8472
| Logistical Operations |  |  | 22.56
Deploy inspection and repair hardware to upper port | Blanket Installation Required | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Issue | Movement | 0.069444 | 0.069444 |  | N/A | Overhead Crane (Unloaded) | Vertical Port | AMF Hardware Issue | 50 | 0.2 | 0.069444 |  | N/A
| Collect Inspection and repair equipment | Logistics | 1.08 | 1.1494 |  | N/A |  |  |  | N/A | N/A | N/A | Collect RM Equipment | 1.08
| Deploy inspection and repair hardware to upper port | Total | 0 | 1.1494 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Blanket Transporter collected; RIB Blanket Segment Exported | Blanket Installation Required | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Issue | Movement | 0.069444 | 0.069444 |  | N/A | Overhead Crane (Unloaded) | Vertical Port | AMF Hardware Issue | 50 | 0.2 | 0.069444 |  | N/A
| Collect Segment | Logistics | 0.78 | 0.84944 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP Hardware | 0.78
| Blanket Transporter collected; RIB Blanket Segment Exported | Total | 0 | 0.84944 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Inspection and repair hardware stored; Blanket Transporter collected; LIB Blanket Segment Exported | Re-condition IVC hardware/fixations | Trigger | 0 | 18.8439 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Issue | Movement | 0.69444 | 19.5383 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Issue | 50 | 0.02 | 0.69444 |  | N/A
| Collect Segment | Logistics | 0.78 | 20.3183 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP Hardware | 0.78
| Inspection and repair hardware stored; Blanket Transporter collected; LIB Blanket Segment Exported | Total | 0 | 20.3183 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Blanket Segment Exported | Install RIB Blanket Segment | Trigger | 0 | 23.8683 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Issue | Movement | 0.69444 | 24.5628 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Issue | 50 | 0.02 | 0.69444 |  | N/A
| Collect Segment | Logistics | 0.78 | 25.3428 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP Hardware | 0.78
| ROB Blanket Segment Exported | Total | 0 | 25.3428 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Blanket Segment Exported | Install LIB Blanket Segment | Trigger | 0 | 28.8928 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Issue | Movement | 0.69444 | 29.5872 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Issue | 50 | 0.02 | 0.69444 |  | N/A
| Collect Segment | Logistics | 0.78 | 30.3672 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP Hardware | 0.78
| LOB Blanket Segment Exported | Total | 0 | 30.3672 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
COB Blanket Segment Exported | Install ROB Blanket Segment | Trigger | 0 | 33.9172 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Issue | Movement | 0.69444 | 34.6117 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Issue | 50 | 0.02 | 0.69444 |  | N/A
| Collect Segment | Logistics | 0.78 | 35.3917 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP Hardware | 0.78
| COB Blanket Segment Exported | Total | 0 | 35.3917 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Blanket Transporter stored & Pipe Module interface hardware Collected & Pipe Module 5 Collected | Install LOB Blanket Segment | Trigger | 0 | 38.9417 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Equipment Receipt | Movement | 0.69444 | 39.6361 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Blanket Transporter | Logistics | 0.78 | 40.4161 |  | N/A |  |  |  | N/A | N/A | N/A | Store RM Equipment | 0.78
| Move Crane B to AMF Hardware Issue | Movement | 0.013889 | 40.43 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | AMF Hardware Issue | 10 | 0.2 | 0.013889 |  | N/A
| Collect Shield Plug Lifting Equipment | Logistics | 1.08 | 41.51 |  | N/A |  |  |  | N/A | N/A | N/A | Collect RM Equipment | 1.08
| Move Crane B to AMF Hardware Issue | Movement | 0.027778 | 41.5378 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | AMF Hardware Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Pipe Module 5 | Logistics | 0.78 | 42.3178 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP Hardware | 0.78
| Blanket Transporter stored & Pipe Module interface hardware Collected & Pipe Module 5 Collected | Total | 0 | 42.3178 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Blanket Transporter stored & Service Joint System Collected | Install COB Blanket Segment | Trigger | 0 | 43.9661 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Equipment Receipt | Movement | 0.69444 | 44.6606 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Blanket Transporter | Logistics | 0.78 | 45.4406 |  | N/A |  |  |  | N/A | N/A | N/A | Store RM Equipment | 0.78
| Move Crane A to AMF Hardware Issue | Movement | 0.013889 | 45.4544 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | AMF Hardware Issue | 10 | 0.2 | 0.013889 |  | N/A
| Collect Service Joint System | Logistics | 1.08 | 46.5344 |  | N/A |  |  |  | N/A | N/A | N/A | Collect RM Equipment | 1.08
| Blanket Transporter stored & Service Joint System Collected | Total | 0 | 46.5344 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Pipe Module 4 Exported | Install RIB Pipe Module | Trigger | 0 | 48.1306 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Issue | Movement | 0.069444 | 48.2 |  | N/A | Overhead Crane (Unloaded) | Vertical Port | AMF Hardware Issue | 50 | 0.2 | 0.069444 |  | N/A
| Collect Pipe Module | Logistics | 0.78 | 48.98 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP Hardware | 0.78
| Pipe Module 4 Exported | Total | 0 | 48.98 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Pipe Module 3 Exported | Install LIB Pipe Module | Trigger | 0 | 85.0505 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Issue | Movement | 0.069444 | 85.12 |  | N/A | Overhead Crane (Unloaded) | Vertical Port | AMF Hardware Issue | 50 | 0.2 | 0.069444 |  | N/A
| Collect Pipe Module | Logistics | 0.78 | 85.9 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP Hardware | 0.78
| Pipe Module 3 Exported | Total | 0 | 85.9 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Pipe Module 2 Exported | Install ROB Pipe Module | Trigger | 0 | 121.9705 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Issue | Movement | 0.069444 | 122.0399 |  | N/A | Overhead Crane (Unloaded) | Vertical Port | AMF Hardware Issue | 50 | 0.2 | 0.069444 |  | N/A
| Collect Pipe Module | Logistics | 0.78 | 122.8199 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP Hardware | 0.78
| Pipe Module 2 Exported | Total | 0 | 122.8199 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Pipe Module 1 Exported | Install LOB Pipe Module | Trigger | 0 | 158.8904 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Issue | Movement | 0.069444 | 158.9599 |  | N/A | Overhead Crane (Unloaded) | Vertical Port | AMF Hardware Issue | 50 | 0.2 | 0.069444 |  | N/A
| Collect Pipr Module | Logistics | 0.78 | 159.7399 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP Hardware | 0.78
| Pipe Module 1 Exported | Total | 0 | 159.7399 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Pipe Module interface hardware Stored & Shield Plug & Fixations Equipment Collected | Install COB Pipe Module | Trigger | 0 | 195.8104 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Equipment Receipt | Movement | 0.069444 | 195.8798 |  | N/A | Overhead Crane (Unloaded) | Vertical Port | AMF Equipment Receipt | 50 | 0.2 | 0.069444 |  | N/A
| Store Pipe Module interface hardware | Logistics | 0.78 | 196.6598 |  | N/A |  |  |  | N/A | N/A | N/A | Store RM Equipment | 0.78
| Move Crane B to AMF Equipment Issue | Movement | 0.027778 | 196.6876 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Shield Plug & Fixations Equipment | Logistics | 1.08 | 197.7676 |  | N/A |  |  |  | N/A | N/A | N/A | Collect RM Equipment | 1.08
| Pipe Module interface hardware Stored & Shield Plug & Fixations Equipment Collected | Total | 0 | 197.7676 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Service Joint System Stored & Closure Plate interface hardware Collected | Weld COB Joint using SJS | Trigger | 0 | 220.5276 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Equipment Receipt | Movement | 0.69444 | 221.222 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Service Joint System | Logistics | 0.78 | 222.002 |  | N/A |  |  |  | N/A | N/A | N/A | Store RM Equipment | 0.78
| Move Crane A to AMF Equipment Issue | Movement | 0.027778 | 222.0298 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Closure Plate interface hardware | Logistics | 0.58 | 222.6098 |  | N/A |  |  |  | N/A | N/A | N/A | Collect interface hardware | 0.58
| Move Crane A to AMF Equipment Issue | Movement | 0.027778 | 222.6376 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | AMF Hardware Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Closure Plate | Logistics | 0.78 | 223.4176 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP Hardware | 0.78
| Service Joint System Stored & Closure Plate interface hardware Collected | Total | 0 | 223.4176 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Shield Plug & Fixations Equipment Stored & ECH Lifting Equipment & ECH Collected | Install COB Pipe Module | Trigger | 0 | 195.8104 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Equipment Receipt | Movement | 0.69444 | 196.5048 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Shield Plug & Fixations Equipment | Logistics | 0.58 | 197.0848 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| Move Crane A to AMF Equipment Issue | Movement | 0.069444 | 197.1543 |  | N/A | Overhead Crane (Unloaded) | Hardware Stillage | AMF Equipment Issue | 50 | 0.2 | 0.069444 |  | N/A
| Collect ECH interface hardware | Logistics | 0.58 | 197.7343 |  | N/A |  |  |  | N/A | N/A | N/A | Collect interface hardware | 0.58
| Move Crane A to AMF Hardware Issue | Movement | 0.027778 | 197.762 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | AMF Hardware Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect ECH | Logistics | 0.78 | 198.542 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP Hardware | 0.78
| Shield Plug & Fixations Equipment Stored & ECH Lifting Equipment & ECH Collected | Total | 0 | 198.542 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Store Closure Plate interface hardware & Collect CCD interface hardware & CCD | Install Port Closure Plate | Trigger | 0 | 237.7131 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to Equipment Receipt | Movement | 0.69444 | 238.4076 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Closure Plate interface hardware | Logistics | 0.78 | 239.1876 |  | N/A |  |  |  | N/A | N/A | N/A | Store RM Equipment | 0.78
| Move Crane A to AMF Equipment Issue | Movement | 0.027778 | 239.2153 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect CCD interface hardware | Logistics | 0.58 | 239.7953 |  | N/A |  |  |  | N/A | N/A | N/A | Collect interface hardware | 0.58
| Move Crane A to Hardware Stillage | Movement | 0.069444 | 239.8648 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Hardware Stillage | 50 | 0.2 | 0.069444 |  | N/A
| Collect CCD | Logistics | 0.78 | 240.6448 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP Hardware | 0.78
| Store Closure Plate interface hardware & Collect CCD interface hardware & CCD | Total | 0 | 240.6448 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ECH interface hardware Stored & Bioshield interface hardware Collected | Install ECH | Trigger | 0 | 273.1026 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Equipment Receipt | Movement | 0.069444 | 273.172 |  | N/A | Overhead Crane (Unloaded) | Vertical Port | AMF Equipment Receipt | 50 | 0.2 | 0.069444 |  | N/A
| Store ECH interface hardware | Logistics | 0.68 | 273.852 |  | N/A |  |  |  | N/A | N/A | N/A | Store Interface hardware | 0.68
| Move Crane B to Hardware Stillage | Movement | 0.069444 | 273.9214 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Receipt | Hardware Stillage | 50 | 0.2 | 0.069444 |  | N/A
| Collect Bioshield Plug | Logistics | 0.78 | 274.7014 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP Hardware | 0.78
| ECH interface hardware Stored & Bioshield interface hardware Collected | Total | 0 | 274.7014 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Store Bioshield interface hardware & Store Crane B | Seal Bioshield | Trigger | 0 | 299.9281 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Equipment Receipt | Movement | 0.069444 | 299.9976 |  | N/A | Overhead Crane (Unloaded) | Vertical Port | AMF Equipment Receipt | 50 | 0.2 | 0.069444 |  | N/A
| Store Bioshield interface hardware | Logistics | 0.68 | 300.6776 |  | N/A |  |  |  | N/A | N/A | N/A | Store Interface hardware | 0.68
| Move Crane B to Hardware Stillage | Movement | 0.069444 | 300.747 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Receipt | Hardware Stillage | 50 | 0.2 | 0.069444 |  | N/A
| Store Bioshield interface hardware & Store Crane B | Total | 0 | 300.747 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Store CCD interface hardware & Store Crane A | Seal Bioshield | Trigger | 0 | 299.9281 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Equipment Receipt | Movement | 0.069444 | 299.9976 |  | N/A | Overhead Crane (Unloaded) | Vertical Port | AMF Equipment Receipt | 50 | 0.2 | 0.069444 |  | N/A
| Store CCD interface hardware | Logistics | 0.68 | 300.6776 |  | N/A |  |  |  | N/A | N/A | N/A | Store Interface hardware | 0.68
| Move Crane A to Hardware Stillage | Movement | 0.069444 | 300.747 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Receipt | Hardware Stillage | 50 | 0.2 | 0.069444 |  | N/A
| Store CCD interface hardware & Store Crane A | Total | 0 | 300.6776 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Blankets Installation Complete
| Movement Operations |  |  | 7.4167
| Logistical Operations |  |  | 22.42

## Upper Hot Cell Logistics (hidden)
Logistical Activities |  |  | Equipment Speed
Activity | Sub activity | Time | Equipment | Speed (m/s)
Deploy Equipment | Deploy Equipment | 0 | Overhead Crane (Loaded) | 0.02
Collect interface hardware | Position | 0.28 | Overhead Crane (Unloaded) | 0.2
| Lower onto storage location | 0.2 | Hardware Transporter (Loaded) | 0.02
| Make Connections/Commission | 0.1 | Hardware Transporter (Unloaded) | 0.2
| Collect interface hardware | 0.58 | Hardware Transporter (empty Stillage) | 0.06
Collect RM Equipment | Position | 0.28 | Multifunction Manipulator | 0.02
| Lower onto storage location | 0.2 | Closure Plate Disconnection Equipment | 0.02
| Engage fastenings | 0.3 | Closure Plate Connection Equipment | 0.02
| Connect Services | 0.1
| Check hardware | 0.2
| Collect RM Equipment | 1.08
Deploy RM system into the port | Position | 0.28
| Lower onto Vertical Port Flange | 0.2
| Engage fastenings | 0.3
| Connect Services | 0.1
| Commission and check software | 0.2
| Confirm hardware status | 0.2
| Deploy RM system into the port | 1.28
Recovery RM system from the port | Disconnect services | 0.1
| Remove mechanical fastenings | 0.2
| Confirm hardware status | 0.2
| Lift RM hardware out of the port | 0.5
| Confirm hardware has been removed | 0.1
| Recovery RM system from the port | 1.1
Store RM Equipment | Position | 0.28
| Lower onto storage location | 0.2
| Disconnect fastenings | 0.2
| Disconnect Services | 0.1
| Store RM Equipment | 0.78
Store Interface hardware | Position | 0.28 | Distance Table
| Lower onto storage location | 0.2 | To: From : | Equipment Stillage | Vertical Port | Hardware Stillage | AMF Equipment Issue | AMF Equipment Receipt | AMF Hardware Receipt | AMF Hardware Issue
| Release crane | 0.2 | Equipment Stillage |  | 15 | 10 | 50 | 50 | 50 | 50
| Store Interface hardware | 0.68 | Vertical Port | 15 |  | 30 | 50 | 50 | 50 | 50
Store PP Hardware | Position | 0.28 | Hardware Stillage | 10 | 30 |  | 50 | 50 | 50 | 50
| Lower onto storage location | 0.2 | AMF Equipment Issue | 50 | 50 | 50 |  | 20 | 20 | 20
| Release Connections/Commission | 0.1 | AMF Equipment Receipt | 50 | 50 | 50 | 20 |  | 20 | 20
| Store PP Hardware | 0.58 | AMF Hardware Receipt | 50 | 50 | 50 | 20 | 20 |  | 10
Collect PP Hardware | Position | 0.28 | AMF Hardware Issue | 50 | 50 | 50 | 20 | 20 | 10
| Attach crane | 0.3
| Lift from storage location | 0.2
| Collect PP Hardware | 0.78
Engage recovery system | Secure recovery system to failed hardware | 0.5
| Connect Services | 0.1
| Inspect failed hardware | 2
| Deploy remote handling system | 0.5
| Engage recovery system | 3.1
Logistical Activity List
Deploy Equipment
Collect interface hardware
Store Interface hardware
Store PP Hardware
Collect PP Hardware

## Upper Hot Cell Welding failures (hidden)
Delay caused by failure and recovery from failed welding operations
Welding Assumptions | [15 empty] | Estimated Delay
Operations Assumptions
TIG welding and laser cutting is the current worst case scenario
In-situ surface treatment is not possible, so all hardware must be removed and replaced/reconditioned before it can be re-welded
All other positioning, delivery and retrieval operations are of a similar length to nominal operations
Service Joint system is capable of cutting and pipes without tool change
No additional blanket modules will need to be removed to access impacted blanket module
RM Tooling is able to cut and weld all pipes within a pipe module simultaneously
No logistical bottlenecks occur during recovery operations
Both upper and lower port welding operations are carried out simultaneously for each blanket, to prevent unnecessary cutting of welds
Design Assumptions
Each upper port pipe module contains 5 pipes
Each lower port pipe module contains 3 pipes
All other positioning, delivery and retrieval operations are of a similar length to nominal operations
Service Joint system is capable of cutting and pipes without tool change
|  | Single Port | Full DEMO Maintenance
| No. Systems | 1 | 1 | 2 | 3 | 4 | 6
| Upper Port Maintenance | 1 Port | 18 Ports | 9 Ports | 6 Ports | 5 Ports | 3 Ports
| Operational contribution | 241.8747 | 4353.745 | 2176.8725 | 1451.2483 | 1209.3736 | 725.6242
| Logistical contribution | 7.8575 | 141.4346 | 70.7173 | 47.1449 | 39.2874 | 23.5724
| Idle time waiting for dependent operations | 47.5405 | 855.7286 | 427.8643 | 285.2429 | 237.7024 | 142.6214
| Estimated Delay (h) | 315.3153 | 5675.6746 | 2837.8373 | 1891.8915 | 1576.5763 | 945.9458
Estimated Operational Durations (taken from Hotcell Critical Path)
Failure of COB Upper Port Welds
Assumptions:
|  | TIG welding and laser cutting is the current worst case scenario | [15 empty] | Single Port | Full DEMO Maintnance
|  | In-situ surface treatment is not possible, so all hardware must be removed and replaced/reconditioned before it can be re-welded | [14 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
|  | All other positioning, delivery and retrieval operations are of a similar length to nominal operations | [14 empty] | Duration of welding operations (h) | 24.0227 | 432.4092 | 216.2046 | 144.1364 | 120.1137 | 72.0682
|  | Service Joint system is capable of cutting and pipes without tool change | [14 empty] | Estimated number of failures, impacting all RM systems equally | 0.26425 | 4.7565 | 2.3783 | 1.5855 | 1.3213 | 0.79275
|  | No additional blanket modules will need to be removed to access impacted blanket module | [14 empty] | Operational contribution | 75.1629 | 1352.9328 | 676.4664 | 450.9776 | 375.8147 | 225.4888
[17 empty] | Logistical contribution | 3.3469 | 60.2437 | 30.1219 | 20.0812 | 16.7344 | 10.0406
|  | Failure rate: | 1.1% | [13 empty] | Idle time waiting for dependent operations | 17.6813 | 318.2631 | 159.1316 | 106.0877 | 88.4064 | 53.0439
|  | Assuming a weld failure rate of | 0.1% | [13 empty] | Total Duration of Recovery Operations | 96.1911 | 1731.4397 | 865.7198 | 577.1466 | 480.9555 | 288.5733
|  | Assuming a tool failure rate of | 1%
|  | Probability of Secondary Failure/hr or Event | 0.07063%
[7 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies
| Group | Pipe weld failure (Sub Tasks) | (Sub Task Notes) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack
| Cut Failed Welds | Weld Failure identified at COB/Pipe Module joint |  | Operation | 0 | 0 | Hardware Recovery Required | 0 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Cut Failed COB Pipe Module Weld |  | Operation | 3.45 | 3.45 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove COB Pipework Module | Move Crane A to Upper Port |  | Movement | 0.2 | 3.65 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | Shield Plug & Fixations Equipment Stored, Pipe Module interface hardware Collected and moved to port | 1.4267 | 2.0233
|  | Extract COB Pipe Module |  | Operation | 0 | 3.65 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Disconnect LOB Pipe Module | Move Multifunction Manipulator to Upper Port |  | Movement | 0.20833 | 3.8583 |  | N/A | Multifunction Manipulator | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A |  | N/A | N/A
|  | Disconnect Multipipe Flange 2 |  | Operation | 6.66 | 10.5183 | Disconnect Multipipe Flange & Access Lid | 6.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Crane B to Upper Port |  | Movement | 0.20833 | 10.7267 |  | N/A | Overhead Crane (Unloaded) | Equipment Stillage | Vertical Port | 15 | 0.2 | 0.020833 |  | N/A |  | N/A | N/A
|  | Cut Pipes 2 |  | Operation | 3.45 | 14.1767 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove LOB Pipe Module | Move Crane A to Upper Port |  | Movement | 0.69444 | 14.8711 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A
|  | Extract LOB Pipe Module |  | Operation | 1.91 | 16.7811 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Disconnect ROB Pipe Module | Move Multifunction Manipulator to Upper Port |  | Movement | 0.20833 | 16.9894 |  | N/A | Multifunction Manipulator | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A |  | N/A | N/A
|  | Disconnect Multipipe Flange 3 |  | Operation | 6.66 | 23.6494 | Disconnect Multipipe Flange & Access Lid | 6.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Crane B to Upper Port |  | Movement | 0.20833 | 23.8578 |  | N/A | Overhead Crane (Unloaded) | Equipment Stillage | Vertical Port | 15 | 0.2 | 0.020833 |  | N/A |  | N/A | N/A
|  | Cut Pipes 3 |  | Operation | 3.45 | 27.3078 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove ROB Pipe Module | Move Crane A to Upper Port |  | Movement | 0.69444 | 28.0022 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A
|  | Extract ROB Pipe Module |  | Operation | 1.91 | 29.9122 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Disconnect LIB Pipe Module | Move Multifunction Manipulator to Upper Port |  | Movement | 0.20833 | 30.1206 |  | N/A | Multifunction Manipulator | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A |  | N/A | N/A
|  | Disconnect Multipipe Flange 4 |  | Operation | 6.66 | 36.7806 | Disconnect Multipipe Flange & Access Lid | 6.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Crane B to Upper Port |  | Movement | 0.20833 | 36.9889 |  | N/A | Overhead Crane (Unloaded) | Equipment Stillage | Vertical Port | 15 | 0.2 | 0.020833 |  | N/A |  | N/A | N/A
|  | Cut Pipes 4 |  | Operation | 3.45 | 40.4389 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove LIB Pipe Module | Move Crane A to Upper Port |  | Movement | 0.69444 | 41.1333 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A
|  | Extract LIB Pipe Module |  | Operation | 1.91 | 43.0433 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Disconnect RIB Pipe Module | Move Multifunction Manipulator to Upper Port |  | Movement | 0.20833 | 43.2517 |  | N/A | Multifunction Manipulator | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A |  | N/A | N/A
|  | Disconnect Multipipe Flange 5 |  | Operation | 6.66 | 49.9117 | Disconnect Multipipe Flange & Access Lid | 6.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Crane B to Upper Port |  | Movement | 0.20833 | 50.12 |  | N/A | Overhead Crane (Unloaded) | Equipment Stillage | Vertical Port | 15 | 0.2 | 0.020833 |  | N/A |  | N/A | N/A
|  | Cut Pipes 5 |  | Operation | 3.45 | 53.57 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove RIB Pipe Module | Move Crane A to Upper Port |  | Movement | 0.69444 | 54.2644 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A
|  | Extract RIB Pipe Module |  | Operation | 1.91 | 56.1744 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Removed Failed COB Blanket | Move Blanket Transporter to Upper Port |  | Movement | 1.91 | 58.0844 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | Service Joint System Stored & Blanket Transporter Collected | 55.5383 | 0.63611
|  | Extract COB Blanket Segment |  | Operation | 5.74 | 63.8244 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove Other Blanket Modules | Move Crane A to Upper Port |  | Movement | 0.069444 | 63.8939 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | RIB Pipe Module Stored; Pipe Module interface hardware Stored; Blanket Transporter Collected | 58.7339 | 5.0906
|  | Extract LOB Blanket Segment |  | Operation | 5.74 | 69.6339 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Crane B to Upper Port |  | Movement | 0.069444 | 69.7033 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | COB Blanket Segment Stored | 65.0989 | 4.535
|  | Extract ROB Blanket Segment |  | Operation | 5.74 | 75.4433 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Crane A to Upper Port |  | Movement | 0.069444 | 75.5128 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | LOB Blanket Segment Stored | 70.9083 | 4.535
|  | Extract LIB Blanket Segment |  | Operation | 5.74 | 81.2528 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Crane B to Upper Port |  | Movement | 0.069444 | 81.3222 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | ROB Blanket Segment Stored | 76.7178 | 4.535
|  | Extract RIB Blanket Segment |  | Operation | 5.74 | 87.0622 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Install New Blanket Modules | Move Crane A to Upper Port |  | Movement | 0.069444 | 87.1317 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | LIB Blanket Segment Stored; Replacement RIB Blanket Segment collected | 82.5272 | 4.535
|  | Install RIB Blanket Segment |  | Operation | 4.33 | 91.4617 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Segment 4 (Crane B) to Upper Port |  | Movement | 0.069444 | 91.5311 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | RIB Blanket Segment Stored; Replacement LIB Blanket Segment collected | 89.1306 | 2.3311
|  | Install LIB Blanket Segment |  | Operation | 4.33 | 95.8611 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Segment 3 (Crane A) to Upper Port |  | Movement | 0.069444 | 95.9306 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | ROB Blanket Segment Exported | 92.7361 | 3.125
|  | Install ROB Blanket Segment |  | Operation | 4.33 | 100.2606 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Segment 2 (Crane B) to Upper Port |  | Movement | 0.069444 | 100.33 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | LOB Blanket Segment Exported | 97.3356 | 2.925
|  | Install LOB Blanket Segment |  | Operation | 5.74 | 106.07 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Segment 1 (Crane A) to Upper Port |  | Movement | 0.069444 | 106.1394 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | COB Blanket Segment Exported | 101.735 | 4.335
|  | Install COB Blanket Segment |  | Operation | 5.74 | 111.8794 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Install RIB Pipe Module | Move Pipe interface hardware to Upper Port |  | Movement | 0.69444 | 112.5739 |  | N/A | Overhead Crane (Loaded) | AMF Hardware Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A | Blanket Transporter stored & Pipe Module interface hardware Collected & RIB Pipe Module Exported | 108.8461 | 3.0333
|  | Insert RIB Pipe Module |  | Operation | 4.095 | 116.6689 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Connect RIB Pipe Module | Move Crane B to Upper Port |  | Movement | 0.69444 | 117.3633 |  | N/A | Overhead Crane (Loaded) | AMF Hardware Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A | Blanket Transporter stored & Service Joint System Collected | N/A | N/A
|  | Weld RIB Pipe Module |  | Operation | 24.0227 | 141.3861 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Multifunction Manipulator to Upper Port |  | Movement | 0.20833 | 156.5206 |  | N/A | Multifunction Manipulator | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A | RIB Lower Port Pipe Module installed | 156.3123 | -14.9262
|  | Connect Multipipe Flange 5 |  | Operation | 7.83 | 164.3506 | Connect Multipipe Flange & Access Lid | 7.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Install LIB Pipe Module | Move Crane A to Upper Port |  | Movement | 0.069444 | 164.42 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | LIB Pipe Module Exported | 117.5183 | 46.8323
|  | Insert LIB Pipe Module |  | Operation | 4.095 | 168.515 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Connect LIB Pipe Module | Move Crane B to Upper Port |  | Movement | 0.69444 | 169.2095 |  | N/A | Overhead Crane (Loaded) | AMF Hardware Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A
|  | Weld LIB Pipe Module |  | Operation | 24.0227 | 193.2322 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Multifunction Manipulator to Upper Port |  | Movement | 0.20833 | 228.4789 |  | N/A | Multifunction Manipulator | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A | LIB Lower Port Pipe Module installed | 228.2705 | -35.0383
|  | Connect Multipipe Flange 4 |  | Operation | 7.83 | 236.3089 | Connect Multipipe Flange & Access Lid | 7.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Install ROB Pipe Module | Move Crane A to Upper Port |  | Movement | 0.069444 | 236.3783 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | ROB Pipe Module Exported | 169.1645 | 67.1444
|  | Insert ROB Pipe Module |  | Operation | 4.095 | 240.4733 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Connect ROB Pipe Module | Move Crane B to Upper Port |  | Movement | 0.69444 | 241.1678 |  | N/A | Overhead Crane (Loaded) | AMF Hardware Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A
|  | Weld ROB Pipe Module |  | Operation | 24.0227 | 265.1905 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Multifunction Manipulator to Upper Port |  | Movement | 0.20833 | 265.3988 |  | N/A | Multifunction Manipulator | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A | ROB Lower Port Pipe Module installed | 233.9677 | 31.2228
|  | Connect Multipipe Flange 3 |  | Operation | 7.83 | 273.2288 | Connect Multipipe Flange & Access Lid | 7.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Install LOB Pipe Module | Move Crane A to Upper Port |  | Movement | 0.069444 | 273.2983 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | LOB Pipe Module Exported | 241.1228 | 32.1061
|  | Insert LOB Pipe Module |  | Operation | 4.095 | 277.3933 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Connect LOB Pipe Module | Move Crane B to Upper Port |  | Movement | 0.69444 | 278.0877 |  | N/A | Overhead Crane (Loaded) | AMF Hardware Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A
|  | Weld LOB Pipe Module |  | Operation | 24.0227 | 302.1105 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Multifunction Manipulator to Upper Port |  | Movement | 0.20833 | 319.2655 |  | N/A | Multifunction Manipulator | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A | LOB Lower Port Pipe Module installed | 319.0571 | -16.9467
|  | Connect Multipipe Flange 2 |  | Operation | 7.83 | 327.0955 | Connect Multipipe Flange & Access Lid | 7.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Install COB Pipe Module | Move Crane A to Upper Port |  | Movement | 0.069444 | 327.1649 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | COB Pipe Module Exported | 278.0427 | 49.0527
|  | Insert COB Pipe Module |  | Operation | 4.095 | 331.2599 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Connect COB Pipe Module | Move Crane B to Upper Port |  | Movement | 0.69444 | 331.9543 |  | N/A | Overhead Crane (Loaded) | AMF Hardware Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A
|  | Weld COB Pipe Module |  | Operation | 24.0227 | 355.9771 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Multifunction Manipulator to Upper Port |  | Movement | 0.20833 | 356.1854 |  | N/A | Multifunction Manipulator | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A | COB Lower Port Pipe Module installed | 311.6232 | 44.3539
|  | Connect Multipipe Flange 1 |  | Operation | 7.83 | 364.0154 | Connect Multipipe Flange & Access Lid | 7.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  |  |  | Total |  | 364.0154
Failure of LOB Upper Port Welds
Assumptions:
|  | TIG welding and laser cutting is the current worst case scenario | [14 empty] | Bore Pipe Welds | Single Port | Full DEMO Maintnance
|  | In-situ surface treatment is not possible, so all hardware must be removed and replaced/reconditioned before it can be re-welded | [14 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
|  | All other positioning, delivery and retrieval operations are of a similar length to nominal operations | [14 empty] | Duration of welding operations (h) | 24.0227 | 432.4092 | 216.2046 | 144.1364 | 120.1137 | 72.0682
|  | Service Joint system is capable of cutting and pipes without tool change | [14 empty] | Estimated number of failures, impacting all RM systems equally | 0.26425 | 4.7565 | 2.3783 | 1.5855 | 1.3213 | 0.79275
|  | No additional blanket modules will need to be removed to access impacted blanket module | [14 empty] | Operational contribution | 59.3375 | 1068.0751 | 534.0376 | 356.025 | 296.6875 | 178.0125
[17 empty] | Logistical contribution | 1.6314 | 29.3648 | 14.6824 | 9.7883 | 8.1569 | 4.8941
|  | Failure rate: | 1.1% | [13 empty] | Idle time waiting for dependent operations | 18.0426 | 324.7664 | 162.3832 | 108.2555 | 90.2129 | 54.1277
|  | Assuming a weld failure rate of | 0.1% | [13 empty] | Total Duration of Recovery Operations | 97.054 | 1746.9727 | 873.4864 | 582.3242 | 485.2702 | 291.1621
|  | Assuming a tool failure rate of | 1%
|  | Probability of Secondary Failure/hr or Event | 0.07063%
[7 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies
| Group | Pipe weld failure (Sub Tasks) | (Sub Task Notes) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack
| Cut Failed Welds | Weld Failure identified at LOB/Pipe Module joint |  | Operation | 0 | 0 | Hardware Recovery Required | 0 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Cut Failed LOB Pipe Module Weld |  | Operation | 1.0499 | 1.0499 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove LOB Pipework Module | Move Crane A to Upper Port |  | Movement | 0.069444 | 1.4961 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | Shield Plug & Fixations Equipment Stored, Pipe Module interface hardware Collected and moved to port | 1.4267 | -0.37675
|  | Extract LOB Pipe Module |  | Operation | 0.725 | 2.2211 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Disconnect ROB Pipe Module | Move Multifunction Manipulator to Upper Port |  | Movement | 0.20833 | 2.4294 |  | N/A | Multifunction Manipulator | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A |  | N/A | N/A
|  | Disconnect Multipipe Flange 3 |  | Operation | 6.83 | 9.2594 | Disconnect Multipipe Flange & Access Lid | 6.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Crane B to Upper Port |  | Movement | 0.020833 | 9.2803 |  | N/A | Overhead Crane (Unloaded) | Equipment Stillage | Vertical Port | 15 | 0.2 | 0.020833 |  | N/A |  | N/A | N/A
|  | Cut Pipes 3 |  | Operation | 1.0499 | 10.3302 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove ROB Pipe Module | Move Crane A to Upper Port |  | Movement | 0.069444 | 10.3996 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | LOB Pipe Module Stored and Transporter Returned to Upper Port | N/A | N/A
|  | Extract ROB Pipe Module |  | Operation | 0.725 | 11.1246 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Disconnect LIB Pipe Module | Move Multifunction Manipulator to Upper Port |  | Movement | 0.20833 | 11.333 |  | N/A | Multifunction Manipulator | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A |  | N/A | N/A
|  | Disconnect Multipipe Flange 4 |  | Operation | 6.83 | 18.163 | Disconnect Multipipe Flange & Access Lid | 6.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Crane B to Upper Port |  | Movement | 0.020833 | 18.1838 |  | N/A | Overhead Crane (Unloaded) | Equipment Stillage | Vertical Port | 15 | 0.2 | 0.020833 |  | N/A |  | N/A | N/A
|  | Cut Pipes 4 |  | Operation | 1.0499 | 19.2337 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove LIB Pipe Module | Move Crane A to Upper Port |  | Movement | 0.069444 | 19.3032 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | ROB Pipe Module Stored and Transporter Returned to Upper Port | N/A | N/A
|  | Extract LIB Pipe Module |  | Operation | 0.725 | 20.0282 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Disconnect RIB Pipe Module | Move Multifunction Manipulator to Upper Port |  | Movement | 0.20833 | 20.2365 |  | N/A | Multifunction Manipulator | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A |  | N/A | N/A
|  | Disconnect Multipipe Flange 5 |  | Operation | 6.83 | 27.0665 | Disconnect Multipipe Flange & Access Lid | 6.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Crane B to Upper Port |  | Movement | 0.020833 | 27.0873 |  | N/A | Overhead Crane (Unloaded) | Equipment Stillage | Vertical Port | 15 | 0.2 | 0.020833 |  | N/A |  | N/A | N/A
|  | Cut Pipes 5 |  | Operation | 1.0499 | 28.1372 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove RIB Pipe Module | Move Crane A to Upper Port |  | Movement | 0.069444 | 28.2067 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | LIB Pipe Module Stored and Transporter Returned to Upper Port | N/A | N/A
|  | Extract RIB Pipe Module |  | Operation | 0.725 | 28.9317 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove Blanket Modules | Move Blanket Transporter to Upper Port |  | Movement | 0.069444 | 30.275 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | Service Joint System Stored & Blanket Transporter Collected | 30.2056 | -1.2739
|  | Extract COB Blanket Segment |  | Operation | 5.74 | 36.015 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Crane A to Upper Port |  | Movement | 0.069444 | 36.0845 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | RIB Pipe Module Stored; Pipe Module interface hardware Stored; Blanket Transporter Collected | 31.5911 | 4.4239
|  | Extract LOB Blanket Segment |  | Operation | 5.74 | 41.8245 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Crane B to Upper Port |  | Movement | 0.069444 | 41.8939 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | COB Blanket Segment Stored | 37.2895 | 4.535
|  | Extract ROB Blanket Segment |  | Operation | 5.74 | 47.6339 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Crane A to Upper Port |  | Movement | 0.069444 | 47.7034 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | LOB Blanket Segment Stored | 43.0989 | 4.535
|  | Extract LIB Blanket Segment |  | Operation | 5.74 | 53.4434 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Crane B to Upper Port |  | Movement | 0.069444 | 53.5128 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | ROB Blanket Segment Stored | 48.9084 | 4.535
|  | Extract RIB Blanket Segment |  | Operation | 5.74 | 59.2528 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Install New Blanket Modules | Move Crane A to Upper Port |  | Movement | 0.069444 | 59.3222 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | LIB Blanket Segment Stored; Replacement RIB Blanket Segment collected | 54.7178 | 4.535
|  | Install RIB Blanket Segment |  | Operation | 4.33 | 63.6522 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Segment 4 (Crane B) to Upper Port |  | Movement | 0.069444 | 63.7217 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | RIB Blanket Segment Stored; Replacement LIB Blanket Segment collected | 61.3211 | 2.3311
|  | Install LIB Blanket Segment |  | Operation | 4.33 | 68.0517 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Segment 3 (Crane A) to Upper Port |  | Movement | 0.069444 | 68.1211 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | ROB Blanket Segment Exported | 64.9267 | 3.125
|  | Install ROB Blanket Segment |  | Operation | 4.33 | 72.4511 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Segment 2 (Crane B) to Upper Port |  | Movement | 0.069444 | 72.5206 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | LOB Blanket Segment Exported | 69.5261 | 2.925
|  | Install LOB Blanket Segment |  | Operation | 5.74 | 78.2606 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Segment 1 (Crane A) to Upper Port |  | Movement | 0.069444 | 78.33 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | COB Blanket Segment Exported | 73.7256 | 4.535
|  | Install COB Blanket Segment |  | Operation | 5.74 | 84.07 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Install RIB Pipe Module | Move Pipe interface hardware to Upper Port |  | Movement | 0.69444 | 84.7645 |  | N/A | Overhead Crane (Loaded) | AMF Hardware Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A | Blanket Transporter stored & Pipe Module interface hardware Collected & RIB Pipe Module Exported | 81.0367 | 3.0333
|  | Insert RIB Pipe Module |  | Operation | 4.095 | 88.8595 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Connect RIB Pipe Module | Move Crane B to Upper Port |  | Movement | 0.69444 | 89.5539 |  | N/A | Overhead Crane (Loaded) | AMF Hardware Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A | Blanket Transporter stored & Service Joint System Collected | 86.5384 | 2.3211
|  | Weld RIB Pipe Module |  | Operation | 24.0227 | 113.5766 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Multifunction Manipulator to Upper Port |  | Movement | 0.20833 | 180.4128 |  | N/A | Multifunction Manipulator | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A | LIB Lower Port Pipe Module installed | 180.2044 | -66.6278
|  | Connect Multipipe Flange 5 |  | Operation | 7.83 | 188.2428 | Connect Multipipe Flange & Access Lid | 7.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Install LIB Pipe Module | Move Crane A to Upper Port |  | Movement | 0.069444 | 188.3122 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | LIB Pipe Module Exported | 89.7089 | 98.5339
|  | Insert LIB Pipe Module |  | Operation | 4.095 | 192.4072 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Connect LIB Pipe Module | Move Crane B to Upper Port |  | Movement | 0.69444 | 193.1017 |  | N/A | Overhead Crane (Loaded) | AMF Hardware Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A
|  | Weld LIB Pipe Module |  | Operation | 24.0227 | 217.1244 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Multifunction Manipulator to Upper Port |  | Movement | 0.20833 | 217.3327 |  | N/A | Multifunction Manipulator | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A | LIB Lower Port Pipe Module installed | 180.2044 | 36.92
|  | Connect Multipipe Flange 4 |  | Operation | 7.83 | 225.1627 | Connect Multipipe Flange & Access Lid | 7.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Install ROB Pipe Module | Move Crane A to Upper Port |  | Movement | 0.069444 | 225.2322 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | ROB Pipe Module Exported | 193.2567 | 31.9061
|  | Insert ROB Pipe Module |  | Operation | 4.095 | 229.3272 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Connect ROB Pipe Module | Move Crane B to Upper Port |  | Movement | 0.69444 | 230.0216 |  | N/A | Overhead Crane (Loaded) | AMF Hardware Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A
|  | Weld ROB Pipe Module |  | Operation | 24.0227 | 254.0443 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Multifunction Manipulator to Upper Port |  | Movement | 0.20833 | 254.2527 |  | N/A | Multifunction Manipulator | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A | ROB Lower Port Pipe Module installed | 219.0322 | 35.0122
|  | Connect Multipipe Flange 3 |  | Operation | 7.83 | 262.0827 | Connect Multipipe Flange & Access Lid | 7.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Install LOB Pipe Module | Move Crane A to Upper Port |  | Movement | 0.069444 | 262.1521 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | LOB Pipe Module Exported | 230.1766 | 31.9061
|  | Insert LOB Pipe Module |  | Operation | 4.095 | 266.2471 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Connect LOB Pipe Module | Move Crane B to Upper Port |  | Movement | 0.69444 | 266.9416 |  | N/A | Overhead Crane (Loaded) | AMF Hardware Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A
|  | Weld LOB Pipe Module |  | Operation | 24.0227 | 290.9643 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Multifunction Manipulator to Upper Port |  | Movement | 0.20833 | 291.1726 |  | N/A | Multifunction Manipulator | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A | LOB Lower Port Pipe Module installed | 257.8599 | 33.1044
|  | Connect Multipipe Flange 2 |  | Operation | 7.83 | 299.0026 | Connect Multipipe Flange & Access Lid | 7.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  |  |  | Total |  | 367.2811
Failure of ROB Upper Port Welds
Assumptions:
|  | TIG welding and laser cutting is the current worst case scenario | [15 empty] | Single Port | Full DEMO Maintnance
|  | In-situ surface treatment is not possible, so all hardware must be removed and replaced/reconditioned before it can be re-welded | [14 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
|  | All other positioning, delivery and retrieval operations are of a similar length to nominal operations | [14 empty] | Duration of welding operations (h) | 24.0227 | 432.4092 | 216.2046 | 144.1364 | 120.1137 | 72.0682
|  | Service Joint system is capable of cutting and pipes without tool change | [14 empty] | Estimated number of failures, impacting all RM systems equally | 0.26425 | 4.7565 | 2.3783 | 1.5855 | 1.3213 | 0.79275
|  | No additional blanket modules will need to be removed to access impacted blanket module | [14 empty] | Operational contribution | 47.5645 | 856.1604 | 428.0802 | 285.3868 | 237.8223 | 142.6934
[17 empty] | Logistical contribution | 1.2956 | 23.3201 | 11.66 | 7.7734 | 6.4778 | 3.8867
|  | Failure rate: | 1.1% | [13 empty] | Idle time waiting for dependent operations | 11.1434 | 200.5806 | 100.2903 | 66.8602 | 55.7168 | 33.4301
|  | Assuming a weld failure rate of | 0.1% | [13 empty] | Total Duration of Recovery Operations | 60.0034 | 1080.0611 | 540.0305 | 360.0204 | 300.017 | 180.0102
|  | Assuming a tool failure rate of | 1%
|  | Probability of Secondary Failure/hr or Event | 0.07063%
[7 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies
| Group | Pipe weld failure (Sub Tasks) | (Sub Task Notes) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack
| Cut Failed Welds | Weld Failure identified at ROB/Pipe Module joint |  | Operation | 0 | 0 | Hardware Recovery Required | 0 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Cut Failed ROB Pipe Module Weld |  | Operation | 1.0499 | 1.0499 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove LOB Pipework Module | Move Crane A to Upper Port |  | Movement | 0.069444 | 1.4961 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | Shield Plug & Fixations Equipment Stored, Pipe Module interface hardware Collected and moved to port | 1.4267 | -0.37675
|  | Extract ROB Pipe Module |  | Operation | 0.725 | 2.2211 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Disconnect LIB Pipe Module | Move Multifunction Manipulator to Upper Port |  | Movement | 0.20833 | 2.4294 |  | N/A | Multifunction Manipulator | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A |  | N/A | N/A
|  | Disconnect Multipipe Flange 4 |  | Operation | 6.83 | 9.2594 | Disconnect Multipipe Flange & Access Lid | 6.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Crane B to Upper Port |  | Movement | 0.020833 | 9.2803 |  | N/A | Overhead Crane (Unloaded) | Equipment Stillage | Vertical Port | 15 | 0.2 | 0.020833 |  | N/A |  | N/A | N/A
|  | Cut Pipes 4 |  | Operation | 1.0499 | 10.3302 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove LIB Pipe Module | Move Crane A to Upper Port |  | Movement | 0.069444 | 10.3996 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | ROB Pipe Module Stored | N/A | N/A
|  | Extract LIB Pipe Module |  | Operation | 0.725 | 11.1246 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Disconnect RIB Pipe Module | Move Multifunction Manipulator to Upper Port |  | Movement | 0.20833 | 11.333 |  | N/A | Multifunction Manipulator | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A |  | N/A | N/A
|  | Disconnect Multipipe Flange 5 |  | Operation | 6.83 | 18.163 | Disconnect Multipipe Flange & Access Lid | 6.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Crane B to Upper Port |  | Movement | 0.020833 | 18.1838 |  | N/A | Overhead Crane (Unloaded) | Equipment Stillage | Vertical Port | 15 | 0.2 | 0.020833 |  | N/A |  | N/A | N/A
|  | Cut Pipes 5 |  | Operation | 1.0499 | 19.2337 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove RIB Pipe Module | Move Crane A to Upper Port |  | Movement | 0.069444 | 19.3032 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | LIB Pipe Module Stored | N/A | N/A
|  | Extract RIB Pipe Module |  | Operation | 0.725 | 20.0282 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove Blanket Modules | Move Blanket Transporter to Upper Port |  | Movement | 0.069444 | 21.3715 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | Service Joint System Stored & Blanket Transporter Collected | 21.3021 | -1.2739
|  | Extract COB Blanket Segment |  | Operation | 5.74 | 27.1115 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Crane A to Upper Port |  | Movement | 0.069444 | 27.1809 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | RIB Pipe Module Stored; Pipe Module interface hardware Stored; Blanket Transporter Collected | 22.6876 | 4.4239
|  | Extract LOB Blanket Segment |  | Operation | 5.74 | 32.9209 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Crane B to Upper Port |  | Movement | 0.069444 | 32.9904 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | COB Blanket Segment Stored | 28.3859 | 4.535
|  | Extract ROB Blanket Segment |  | Operation | 5.74 | 38.7304 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Crane A to Upper Port |  | Movement | 0.069444 | 38.7998 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | LOB Blanket Segment Stored | 34.1954 | 4.535
|  | Extract LIB Blanket Segment |  | Operation | 5.74 | 44.5398 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Crane B to Upper Port |  | Movement | 0.069444 | 44.6093 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | ROB Blanket Segment Stored | 40.0048 | 4.535
|  | Extract RIB Blanket Segment |  | Operation | 5.74 | 50.3493 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Install New Blanket Modules | Move Crane A to Upper Port |  | Movement | 0.069444 | 50.4187 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | LIB Blanket Segment Stored; Replacement RIB Blanket Segment collected | 45.8143 | 4.535
|  | Install RIB Blanket Segment |  | Operation | 4.33 | 54.7487 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Segment 4 (Crane B) to Upper Port |  | Movement | 0.069444 | 54.8182 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | RIB Blanket Segment Stored; Replacement LIB Blanket Segment collected | 52.4176 | 2.3311
|  | Install LIB Blanket Segment |  | Operation | 4.33 | 59.1482 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Segment 3 (Crane A) to Upper Port |  | Movement | 0.069444 | 59.2176 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | ROB Blanket Segment Exported | 56.0232 | 3.125
|  | Install ROB Blanket Segment |  | Operation | 4.33 | 63.5476 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Segment 2 (Crane B) to Upper Port |  | Movement | 0.069444 | 63.6171 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | LOB Blanket Segment Exported | 60.6226 | 2.925
|  | Install LOB Blanket Segment |  | Operation | 5.74 | 69.3571 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Segment 1 (Crane A) to Upper Port |  | Movement | 0.069444 | 69.4265 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | COB Blanket Segment Exported | 64.8221 | 4.535
|  | Install COB Blanket Segment |  | Operation | 5.74 | 75.1665 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Install RIB Pipe Module | Move Pipe interface hardware to Upper Port |  | Movement | 0.69444 | 75.8609 |  | N/A | Overhead Crane (Loaded) | AMF Hardware Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A | Blanket Transporter stored & Pipe Module interface hardware Collected & RIB Pipe Module Exported | 72.1332 | 3.0333
|  | Insert RIB Pipe Module |  | Operation | 4.095 | 79.9559 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Connect RIB Pipe Module | Move Crane B to Upper Port |  | Movement | 0.69444 | 80.6504 |  | N/A | Overhead Crane (Loaded) | AMF Hardware Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A | Blanket Transporter stored & Service Joint System Collected | 77.6348 | 2.3211
|  | Weld RIB Pipe Module |  | Operation | 24.0227 | 104.6731 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Multifunction Manipulator to Upper Port |  | Movement | 0.20833 | 141.585 |  | N/A | Multifunction Manipulator | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A | RIB Lower Port Pipe Module installed | 141.3767 | -36.7036
|  | Connect Multipipe Flange 5 |  | Operation | 7.83 | 149.415 | Connect Multipipe Flange & Access Lid | 7.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Install LIB Pipe Module | Move Crane A to Upper Port |  | Movement | 0.069444 | 149.4845 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | LIB Pipe Module Exported | 80.8054 | 68.6096
|  | Insert LIB Pipe Module |  | Operation | 4.095 | 153.5795 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Connect LIB Pipe Module | Move Crane B to Upper Port |  | Movement | 0.69444 | 154.2739 |  | N/A | Overhead Crane (Loaded) | AMF Hardware Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A
|  | Weld LIB Pipe Module |  | Operation | 24.0227 | 178.2967 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Multifunction Manipulator to Upper Port |  | Movement | 0.20833 | 180.4128 |  | N/A | Multifunction Manipulator | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A | LIB Lower Port Pipe Module installed | 180.2044 | -1.9078
|  | Connect Multipipe Flange 4 |  | Operation | 7.83 | 188.2428 | Connect Multipipe Flange & Access Lid | 7.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Install ROB Pipe Module | Move Crane A to Upper Port |  | Movement | 0.069444 | 188.3122 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | ROB Pipe Module Exported | 154.4289 | 33.8138
|  | Insert ROB Pipe Module |  | Operation | 4.095 | 192.4072 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Connect ROB Pipe Module | Move Crane B to Upper Port |  | Movement | 0.69444 | 193.1017 |  | N/A | Overhead Crane (Loaded) | AMF Hardware Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A
|  | Weld ROB Pipe Module |  | Operation | 24.0227 | 217.1244 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Multifunction Manipulator to Upper Port |  | Movement | 0.20833 | 219.2405 |  | N/A | Multifunction Manipulator | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A | ROB Lower Port Pipe Module installed | 219.0322 | -1.9078
|  | Connect Multipipe Flange 3 |  | Operation | 7.83 | 227.0705 | Connect Multipipe Flange & Access Lid | 7.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  |  |  | Total |  | 227.0705
Failure of LIB Upper Port Welds
Assumptions:
|  | TIG welding and laser cutting is the current worst case scenario | [15 empty] | Single Port | Full DEMO Maintnance
|  | In-situ surface treatment is not possible, so all hardware must be removed and replaced/reconditioned before it can be re-welded | [14 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
|  | All other positioning, delivery and retrieval operations are of a similar length to nominal operations | [14 empty] | Duration of welding operations (h) | 24.0227 | 432.4092 | 216.2046 | 144.1364 | 120.1137 | 72.0682
|  | Service Joint system is capable of cutting and pipes without tool change | [14 empty] | Estimated number of failures, impacting all RM systems equally | 0.26425 | 4.7565 | 2.3783 | 1.5855 | 1.3213 | 0.79275
|  | No additional blanket modules will need to be removed to access impacted blanket module | [14 empty] | Operational contribution | 35.7914 | 644.2457 | 322.1228 | 214.7486 | 178.9571 | 107.3743
[17 empty] | Logistical contribution | 0.95974 | 17.2753 | 8.6377 | 5.7584 | 4.7987 | 2.8792
|  | Failure rate: | 1.1% | [13 empty] | Idle time waiting for dependent operations | 0.33663 | 6.0593 | 3.0296 | 2.0198 | 1.6831 | 1.0099
|  | Assuming a weld failure rate of | 0.1% | [13 empty] | Total Duration of Recovery Operations | 37.0878 | 667.5803 | 333.7901 | 222.5268 | 185.439 | 111.2634
|  | Assuming a tool failure rate of | 1%
|  | Probability of Secondary Failure/hr or Event | 0.07063%
[7 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies
| Group | Pipe weld failure (Sub Tasks) | (Sub Task Notes) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack
| Cut Failed Welds | Weld Failure identified at LIB/Pipe Module joint |  | Operation | 0 | 0 | Hardware Recovery Required | 0 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Cut Failed LIB Pipe Module Weld |  | Operation | 1.0499 | 1.0499 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove LIB Pipe Module | Move Crane A to Upper Port |  | Movement | 0.069444 | 1.1194 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | ROB Pipe Module Stored | N/A | N/A
|  | Extract LIB Pipe Module |  | Operation | 0.725 | 1.8444 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Disconnect RIB Pipe Module | Move Multifunction Manipulator to Upper Port |  | Movement | 0.20833 | 2.0527 |  | N/A | Multifunction Manipulator | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A |  | N/A | N/A
|  | Disconnect Multipipe Flange 5 |  | Operation | 6.83 | 8.8827 | Disconnect Multipipe Flange & Access Lid | 6.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Crane B to Upper Port |  | Movement | 0.020833 | 8.9035 |  | N/A | Overhead Crane (Unloaded) | Equipment Stillage | Vertical Port | 15 | 0.2 | 0.020833 |  | N/A |  | N/A | N/A
|  | Cut Pipes 5 |  | Operation | 1.0499 | 9.9534 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove RIB Pipe Module | Move Crane A to Upper Port |  | Movement | 0.069444 | 10.0229 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | LIB Pipe Module Stored | N/A | N/A
|  | Extract RIB Pipe Module |  | Operation | 0.725 | 10.7479 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove Blanket Modules | Move Blanket Transporter to Upper Port |  | Movement | 0.069444 | 12.0912 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | Service Joint System Stored & Blanket Transporter Collected | 12.0218 | -1.2739
|  | Extract COB Blanket Segment |  | Operation | 5.74 | 17.8312 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Crane A to Upper Port |  | Movement | 0.069444 | 17.9007 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | RIB Pipe Module Stored; Pipe Module interface hardware Stored; Blanket Transporter Collected | 13.4073 | 4.4239
|  | Extract LOB Blanket Segment |  | Operation | 5.74 | 23.6407 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Crane B to Upper Port |  | Movement | 0.069444 | 23.7101 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | COB Blanket Segment Stored | 19.1057 | 4.535
|  | Extract ROB Blanket Segment |  | Operation | 5.74 | 29.4501 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Crane A to Upper Port |  | Movement | 0.069444 | 29.5196 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | LOB Blanket Segment Stored | 24.9151 | 4.535
|  | Extract LIB Blanket Segment |  | Operation | 5.74 | 35.2596 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Crane B to Upper Port |  | Movement | 0.069444 | 35.329 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | ROB Blanket Segment Stored | 30.7246 | 4.535
|  | Extract RIB Blanket Segment |  | Operation | 5.74 | 41.069 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Install New Blanket Modules | Move Crane A to Upper Port |  | Movement | 0.069444 | 41.1384 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | LIB Blanket Segment Stored; Replacement RIB Blanket Segment collected | 36.534 | 4.535
|  | Install RIB Blanket Segment |  | Operation | 4.33 | 45.4684 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Segment 4 (Crane B) to Upper Port |  | Movement | 0.069444 | 45.5379 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | RIB Blanket Segment Stored; Replacement LIB Blanket Segment collected | 43.1373 | 2.3311
|  | Install LIB Blanket Segment |  | Operation | 4.33 | 49.8679 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Segment 3 (Crane A) to Upper Port |  | Movement | 0.069444 | 49.9373 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | ROB Blanket Segment Exported | 46.7429 | 3.125
|  | Install ROB Blanket Segment |  | Operation | 4.33 | 54.2673 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Segment 2 (Crane B) to Upper Port |  | Movement | 0.069444 | 54.3368 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | LOB Blanket Segment Exported | 51.3423 | 2.925
|  | Install LOB Blanket Segment |  | Operation | 5.74 | 60.0768 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Segment 1 (Crane A) to Upper Port |  | Movement | 0.069444 | 60.1462 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | COB Blanket Segment Exported | 55.7418 | 4.335
|  | Install COB Blanket Segment |  | Operation | 5.74 | 65.8862 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Install RIB Pipe Module | Move Pipe interface hardware to Upper Port |  | Movement | 0.69444 | 66.5807 |  | N/A | Overhead Crane (Loaded) | AMF Hardware Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A | Blanket Transporter stored & Pipe Module interface hardware Collected & RIB Pipe Module Exported | 62.8529 | 3.0333
|  | Insert RIB Pipe Module |  | Operation | 4.095 | 70.6757 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Connect RIB Pipe Module | Move Crane B to Upper Port |  | Movement | 0.69444 | 71.3701 |  | N/A | Overhead Crane (Loaded) | AMF Hardware Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A | Blanket Transporter stored & Service Joint System Collected | 68.3546 | 2.3211
|  | Weld RIB Pipe Module |  | Operation | 24.0227 | 95.3928 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Multifunction Manipulator to Upper Port |  | Movement | 0.20833 | 95.6012 |  | N/A | Multifunction Manipulator | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A |  | N/A | N/A
|  | Connect Multipipe Flange 5 |  | Operation | 7.83 | 103.4312 | Connect Multipipe Flange & Access Lid | 7.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Install LIB Pipe Module | Move Crane A to Upper Port |  | Movement | 0.069444 | 103.5006 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | LIB Pipe Module Exported | 71.5251 | 31.9061
|  | Insert LIB Pipe Module |  | Operation | 4.095 | 107.5956 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A | LIB Lower Port Pipe Module installed | N/A | N/A
| Connect LIB Pipe Module | Move Crane B to Upper Port |  | Movement | 0.69444 | 108.2901 |  | N/A | Overhead Crane (Loaded) | AMF Hardware Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A
|  | Weld LIB Pipe Module |  | Operation | 24.0227 | 132.3128 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Multifunction Manipulator to Upper Port |  | Movement | 0.20833 | 132.5211 |  | N/A | Multifunction Manipulator | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A |  | N/A | N/A
|  | Connect Multipipe Flange 4 |  | Operation | 7.83 | 140.3511 | Connect Multipipe Flange & Access Lid | 7.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  |  |  | Total |  | 140.3511
Failure of RIB Upper Port Welds
Assumptions:
|  | TIG welding and laser cutting is the current worst case scenario | [15 empty] | Single Port | Full DEMO Maintnance
|  | In-situ surface treatment is not possible, so all hardware must be removed and replaced/reconditioned before it can be re-welded | [14 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
|  | All other positioning, delivery and retrieval operations are of a similar length to nominal operations | [14 empty] | Duration of welding operations (h) | 24.0227 | 432.4092 | 216.2046 | 144.1364 | 120.1137 | 72.0682
|  | Service Joint system is capable of cutting and pipes without tool change | [14 empty] | Estimated number of failures, impacting all RM systems equally | 0.26425 | 4.7565 | 2.3783 | 1.5855 | 1.3213 | 0.79275
|  | No additional blanket modules will need to be removed to access impacted blanket module | [14 empty] | Operational contribution | 24.0184 | 432.331 | 216.1655 | 144.1103 | 120.0919 | 72.0552
[17 empty] | Logistical contribution | 0.62392 | 11.2306 | 5.6153 | 3.7435 | 3.1196 | 1.8718
|  | Failure rate: | 1.1% | [13 empty] | Idle time waiting for dependent operations | 0.33663 | 6.0593 | 3.0296 | 2.0198 | 1.6831 | 1.0099
|  | Assuming a weld failure rate of | 0.1% | [13 empty] | Total Duration of Recovery Operations | 24.9789 | 449.6209 | 224.8104 | 149.8736 | 124.8947 | 74.9368
|  | Assuming a tool failure rate of | 1%
|  | Probability of Secondary Failure/hr or Event | 0.07063%
[7 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies
| Group | Pipe weld failure (Sub Tasks) | (Sub Task Notes) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack
| Cut Failed Welds | Weld Failure identified at RIB/Pipe Module joint |  | Operation | 0 | 0 | Hardware Recovery Required | 0 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Cut Failed RIB Pipe Module Weld |  | Operation | 1.0499 | 1.0499 | Disconnect Vertical Port Pipework | 1.0499 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove RIB Pipe Module | Move Crane A to Upper Port |  | Movement | 0.069444 | 1.1194 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | LIB Pipe Module Stored | N/A | N/A
|  | Extract RIB Pipe Module |  | Operation | 0.725 | 1.8444 | Extract Pipe Module | 0.725 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove Blanket Modules | Move Blanket Transporter to Upper Port |  | Movement | 0.069444 | 3.1877 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | Service Joint System Stored & Blanket Transporter Collected | 3.1182 | -1.2739
|  | Extract COB Blanket Segment |  | Operation | 5.74 | 8.9277 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Crane A to Upper Port |  | Movement | 0.069444 | 8.9971 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | RIB Pipe Module Stored; Pipe Module interface hardware Stored; Blanket Transporter Collected | 4.5038 | 4.4239
|  | Extract LOB Blanket Segment |  | Operation | 5.74 | 14.7371 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Crane B to Upper Port |  | Movement | 0.069444 | 14.8066 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | COB Blanket Segment Stored | 10.2021 | 4.535
|  | Extract ROB Blanket Segment |  | Operation | 5.74 | 20.5466 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Crane A to Upper Port |  | Movement | 0.069444 | 20.616 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | LOB Blanket Segment Stored | 16.0116 | 4.535
|  | Extract LIB Blanket Segment |  | Operation | 5.74 | 26.356 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Crane B to Upper Port |  | Movement | 0.069444 | 26.4255 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | ROB Blanket Segment Stored | 21.821 | 4.535
|  | Extract RIB Blanket Segment |  | Operation | 5.74 | 32.1655 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Install New Blanket Modules | Move Crane A to Upper Port |  | Movement | 0.069444 | 32.2349 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | LIB Blanket Segment Stored; Replacement RIB Blanket Segment collected | 27.6305 | 4.535
|  | Install RIB Blanket Segment |  | Operation | 4.33 | 36.5649 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Segment 4 (Crane B) to Upper Port |  | Movement | 0.069444 | 36.6344 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | RIB Blanket Segment Stored; Replacement LIB Blanket Segment collected | 34.2338 | 2.3311
|  | Install LIB Blanket Segment |  | Operation | 4.33 | 40.9644 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Segment 3 (Crane A) to Upper Port |  | Movement | 0.069444 | 41.0338 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | ROB Blanket Segment Exported | 37.8394 | 3.125
|  | Install ROB Blanket Segment |  | Operation | 4.33 | 45.3638 | Install Blanket Segment | 4.33 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Segment 2 (Crane B) to Upper Port |  | Movement | 0.069444 | 45.4332 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | LOB Blanket Segment Exported | 42.4388 | 2.925
|  | Install LOB Blanket Segment |  | Operation | 5.74 | 51.1732 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Segment 1 (Crane A) to Upper Port |  | Movement | 0.069444 | 51.2427 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A | COB Blanket Segment Exported | 46.6382 | 4.535
|  | Install COB Blanket Segment |  | Operation | 5.74 | 56.9827 | Extract Blanket Segment | 5.74 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Install RIB Pipe Module | Move Pipe interface hardware to Upper Port |  | Movement | 0.69444 | 57.6771 |  | N/A | Overhead Crane (Loaded) | AMF Hardware Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A | Blanket Transporter stored & Pipe Module interface hardware Collected & RIB Pipe Module Exported | 53.9494 | 3.0333
|  | Insert RIB Pipe Module |  | Operation | 4.095 | 61.7721 | Install Pipe Module | 4.095 |  |  |  | N/A | N/A | N/A |  | N/A | RIB Lower Port Pipe Module installed | N/A | N/A
| Connect RIB Pipe Module | Move Crane B to Upper Port |  | Movement | 0.69444 | 62.4666 |  | N/A | Overhead Crane (Loaded) | AMF Hardware Issue | Vertical Port | 50 | 0.02 | 0.69444 |  | N/A | Blanket Transporter stored & Service Joint System Collected | 59.451 | 2.3211
|  | Weld RIB Pipe Module |  | Operation | 24.0227 | 86.4893 | Connect Vertical Port Pipework | 24.0227 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  | Move Multifunction Manipulator to Upper Port |  | Movement | 0.20833 | 86.6976 |  | N/A | Multifunction Manipulator | Equipment Stillage | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A |  | N/A | N/A
|  | Connect Multipipe Flange 5 |  | Operation | 7.83 | 94.5276 | Connect Multipipe Flange & Access Lid | 7.83 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
|  |  |  | Total |  | 94.5276

## Upper HotCell HardwareRecovery (hidden)
Delay caused by failure and recovery of remote handling equipment
Additional tasks required to recover from failures
General Assumptions:
There are two sorts of process failure considered; failure of a weld and failure of a mechanical connection, both uncovered by failure to pass acceptance criteria
In addition five types of equipment failure are considered; Pipe interface hardware, Overhead Crane, Blanket transporter system, divertor cask system and Multifunction manipulator system
Equipment failure includes tool failure, for example if a weld tool fails during welding
| Single Port | Full DEMO Maintenance
No. Systems | 1 | 1 | 2 | 3 | 4 | 6
Operational contribution | 38.9013 | 700.2241 | 350.112 | 233.408 | 194.4113 | 116.704
Logitical contribution | 27.4455 | 494.0189 | 247.0095 | 164.673 | 137.157 | 82.3365
Idle time due to waiting for dependant operations | 7.674 | 138.1321 | 69.066 | 46.044 | 38.37 | 23.022
Estimated Delay (h) | 52.8045 | 950.4805 | 475.2403 | 316.8268 | 263.8565 | 158.4134
Loaded Overhead Crane failure
Assumptions:
Recovery of Blanket Transporter is completed using standard predetermined procedures.
Rare and time consuming special recoveries are not considered
A replacement overhead crane (if required) is available on demand from the AMF
The crane's load is able to be set down in-situ safely, using a rescue system
Failure rate: | 0.1%
Failure rate of Overhead crane per hour | 0.1%
[18 empty] | Loaded Overhead Crane failure | Single Port | Full Maintenance of DEMO
[5 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies |  |  | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
RH Cask RHE failure (Sub Tasks) | (Sub Task Notes) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack | Duration of Overhead Crane Tasks | 31.7917 | 31.7917 | 31.7917 | 31.7917 | 31.7917 | 31.7917
Move recovery system into the upper port area |  | Movement | 0.069444 | 0.069444 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A | Duration of RM operations (h) | 31.7917 | 572.25 | 286.125 | 190.75 | 143.0625 | 95.375
Engage the recovery system with the failed hardware |  | Logistics | 3.1 | 3.1694 |  | N/A |  |  |  | N/A | N/A | N/A | Engage recovery system | 3.1 |  | N/A | N/A | Estimated number of failures, impacting all RM systems equally | 0.031792 | 0.57225 | 0.28612 | 0.19075 | 0.14306 | 0.095375
Recovery system engages crane safety system to lower and detach the suspended load | Assumed to take 4 hours | Operation | 4 | 7.1694 | Recovery Operations | 4 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A | Operational contribution | 0.19075 | 3.4335 | 1.7167 | 1.1445 | 0.85837 | 0.57225
Recovery system moves failed crane to AMF Equipment Receipt for repair | Assumed movement speed at half to speed of the crane | Movement | 0.13889 | 7.3083 |  | N/A | Overhead Crane (Unloaded) | Vertical Port | AMF Equipment Receipt | 50 | 0.1 | 0.13889 |  | N/A |  | N/A | N/A | Logitical contribution | 0.14101 | 2.5382 | 1.2691 | 0.84608 | 0.63456 | 0.42304
Crane is repaired or replaced | Assumed to take 1 hours to identify fault and decide course of action, 1 hour to complete repairs | Operation | 2 | 9.3083 | Recovery Operations | 2 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A | Idle time due to waiting for dependant operations | 0 | 0 | 0 | 0 | 0 | 0
Crane returned to abandoned payload |  | Movement | 0.13889 | 9.4472 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Receipt | Vertical Port | 50 | 0.1 | 0.13889 |  | N/A |  | N/A | N/A | Total Duration of Recovery Tasks | 0.33176 | 5.9717 | 2.9859 | 1.9906 | 1.4929 | 0.99529
Abandoned payload is collected |  | Logistics | 0.78 | 10.2272 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP Hardware | 0.78 |  | N/A | N/A
Crane returns to the Upper Port |  | Movement | 0.20833 | 10.4356 |  | N/A | Overhead Crane (Loaded) | Vertical Port | Vertical Port | 15 | 0.02 | 0.20833 |  | N/A |  | N/A | N/A
|  | Total |  | 10.4356
Multifunction Manipulator failure
Assumptions:
Recovery of Multifunction Manipulator is completed using standard predetermined procedures.
Rare and time consuming special recoveries are not considered
A replacement Multifunction Manipulator (if required) is available on demand from the AMF
Failure rate: | 2%
Failure rate of Multifunction Manipulator per hour | 2%
[18 empty] | Multifunction Manipulator failure | Single Port | Full Maintenance of DEMO
[5 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies |  |  | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
RH Cask RHE failure (Sub Tasks) | (Sub Task Notes) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack | Duration of Multifunction Manipulator Tasks | 174.9422 | 174.9422 | 174.9422 | 174.9422 | 174.9422 | 174.9422
Move recovery system into the upper port area |  | Movement | 0.069444 | 0.069444 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A | Duration of RM operations (h) | 174.9422 | 3148.96 | 1574.48 | 1049.6533 | 874.7111 | 524.8267
Engage the recovery system with the failed hardware |  | Logistics | 3.1 | 3.1694 |  | N/A |  |  |  | N/A | N/A | N/A | Engage recovery system | 3.1 |  | N/A | N/A | Estimated number of recoveries required | 3.4988 | 62.9792 | 31.4896 | 20.9931 | 17.4942 | 10.4965
Recover Multifunction Manipulator into hotcell | Assumed recovery takes 3 hours | Operation | 3 | 6.1694 | Recovery Operations | 3 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A | Operational contribution | 17.4942 | 314.896 | 157.448 | 104.9653 | 87.4711 | 52.4827
Move to AMF Hardware Receipt |  | Movement | 0.69444 | 6.8639 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A | Logitical contribution | 13.7621 | 247.7182 | 123.8591 | 82.5727 | 68.8106 | 41.2864
Replace or repair the Multifunction Manipulator Transporter | Assumed chosen tasks takes 2 hours | Operation | 2 | 8.8639 | Recovery Operations | 2 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A | Idle time due to waiting for dependant operations | 0 | 0 | 0 | 0 | 0 | 0
Return to the Upper Port |  | Movement | 0.069444 | 8.9333 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A | Total Duration of Recovery Tasks | 31.2563 | 562.6142 | 281.3071 | 187.5381 | 156.2817 | 93.769
|  | Total |  | 8.9333
Blanket Transporter failure
Assumptions:
Recovery of Blanket Transporter is completed using standard predetermined procedures.
The failed blanket transporter can be recovered and transported without first having to detach any suspended load
Rare and time consuming special recoveries are not considered
A new Blanket Transport and/or replacement blanket module (if required) is available on demand from the AMF
Failure rate: | 5% | [16 empty] | Blanket Transporter failure | Single Port | Full Maintenance of DEMO
Failure rate of Blanket Transporter per hour | 5% | [16 empty] | Number of systems operating in parallel | 1 | 1 | 2 | 3 | 4 | 6
[18 empty] | Blanket Removal Duration | 29.0472 | 29.0472 | 29.0472 | 29.0472 | 29.0472 | 29.0472
[5 empty] | Operations |  | Movement | [5 empty] | Logistics |  | Dependencies |  |  | Blanket Installation Duration | 25.1222 | 25.1222 | 25.1222 | 25.1222 | 25.1222 | 25.1222
RH Cask RHE failure (Sub Tasks) | (Sub Task Notes) | Activity Type | Time (h) | Cumulative Time (h) | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack | Duration of RM operations (h) | 54.1694 | 975.05 | 487.525 | 325.0167 | 270.8472 | 162.5083
Deploy Recovery System from AMF |  | Movement | 0.069444 | 0.069444 |  | N/A | Overhead crane (unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A | Estimated number of recoveries required | 2.7085 | 48.7525 | 24.3762 | 16.2508 | 13.5424 | 8.1254
Dock to failed blanket transporter |  | Logistics | 2 | 2.0694 |  | N/A |  |  |  | N/A | N/A | N/A | Engage recovery system | 2 |  | N/A | N/A | Estimated Delay (h) | 21.2164 | 381.8946 | 190.9473 | 127.2982 | 106.0818 | 63.6491
Recover Blanket Transporter into hotcell | Assumed recovery takes 3 hours | Operation | 3 | 5.0694 | Recovery Operations | 3 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A | Operational contribution | 13.5424 | 243.7625 | 121.8812 | 81.2542 | 67.7118 | 40.6271
Move to AMF Hardware Receipt |  | Movement | 0.69444 | 5.7639 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A |  | N/A | N/A | Logitical contribution | 7.674 | 138.1321 | 69.066 | 46.044 | 38.37 | 23.022
Replace or repair the Blanket Transporter | Assumed chosen tasks takes 2 hours | Operation | 2 | 7.7639 | Recovery Operations | 2 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A | Idle time due to waiting for dependant operations | 21.2164 | 381.8946 | 190.9473 | 127.2982 | 106.0818 | 63.6491
Return to the Upper Port |  | Movement | 0.069444 | 7.8333 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A |  | N/A | N/A
|  | Total |  | 7.8333
Note on D25: Farquhar, Iain: Uses complex RM systems
Note on N32: Farquhar, Iain: Movement speed halved due to failure
Note on D48: Farquhar, Iain: Uses complex RM systems
Note on D71: Farquhar, Iain: Uses complex RM systems

## Upper HotCell RecoveryLogisitcs (hidden)
[5 empty] | Operations |  | Movement | [5 empty] | Logistics
Group | Activity | Activity Type | Time (h) | Cumulative | Type | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h)
COB Weld Failure
Shield Plug & Fixations Equipment Stored, Pipe Module interface hardware Collected and moved to port | Weld Failure identified at COB/Pipe Module joint | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Equipment Receipt | Movement | 0.069444 | 0.069444 |  | N/A | Overhead Crane (Unloaded) | Vertical Port | AMF Equipment Receipt | 50 | 0.2 | 0.069444 |  | N/A
| Store Shield Plug & Fixations Equipment | Logistics | 0.68 | 0.74944 |  | N/A |  |  |  | N/A | N/A | N/A | Store Interface hardware | 0.68
| Move Crane B to AMF Equipment Issue | Movement | 0.027778 | 0.77722 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Pipe Module Lifting Equipment | Logistics | 0.58 | 1.3572 |  | N/A |  |  |  | N/A | N/A | N/A | Collect interface hardware | 0.58
| Move Pipe Module interface hardware to Vertical Port | Movement | 0.069444 | 1.4267 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A
| Shield Plug & Fixations Equipment Stored, Pipe Module interface hardware Collected and moved to port | Total | 0 | 1.4267 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
COB Pipe Module Stored and Transporter Returned to Vertical Port | Extract COB Pipe Module | Trigger | 0 | 3.65 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Hardware Receipt | Movement | 0.69444 | 4.3444 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Pipe Module | Logistics | 0.58 | 4.9244 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| Move Crane A to Vertical Port | Movement | 0.069444 | 4.9939 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A
| COB Pipe Module Stored and Transporter Returned to Vertical Port | Total | 0 | 4.9939 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Pipe Module Stored and Transporter Returned to Vertical Port | Extract LOB Pipe Module | Trigger | 0 | 16.7811 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Hardware Receipt | Movement | 0.69444 | 17.4756 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Pipe Module | Logistics | 0.58 | 18.0556 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| Move Crane A to Vertical Port | Movement | 0.069444 | 18.125 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A
| LOB Pipe Module Stored and Transporter Returned to Vertical Port | Total | 0 | 18.125 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Pipe Module Stored and Transporter Returned to Vertical Port | Extract ROB Pipe Module | Trigger | 0 | 29.9122 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Hardware Receipt | Movement | 0.69444 | 30.6067 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Pipe Module | Logistics | 0.58 | 31.1867 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| Move Crane A to Vertical Port | Movement | 0.069444 | 31.2561 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A
| ROB Pipe Module Stored and Transporter Returned to Vertical Port | Total | 0 | 31.2561 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Pipe Module Stored and Transporter Returned to Vertical Port | Extract LIB Pipe Module | Trigger | 0 | 43.0433 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Hardware Receipt | Movement | 0.69444 | 43.7378 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Pipe Module | Logistics | 0.58 | 44.3178 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| Move Crane A to Vertical Port | Movement | 0.069444 | 44.3872 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A
| LIB Pipe Module Stored and Transporter Returned to Vertical Port | Total | 0 | 44.3872 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Service Joint System Stored & Blanket Transporter Collected | Cut Pipes 5 | Trigger | 0 | 53.57 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Equipment Receipt | Movement | 0.69444 | 54.2644 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Service Joint System | Logistics | 0.68 | 54.9444 |  | N/A |  |  |  | N/A | N/A | N/A | Store Interface hardware | 0.68
| Move Crane A to AMF Hardware Issue | Movement | 0.013889 | 54.9583 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | AMF Hardware Issue | 10 | 0.2 | 0.013889 |  | N/A
| Collect Blanket Transporter | Logistics | 0.58 | 55.5383 |  | N/A |  |  |  | N/A | N/A | N/A | Collect interface hardware | 0.58
| Service Joint System Stored & Blanket Transporter Collected | Total | 0 | 55.5383 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Pipe Module Stored; Pipe Module interface hardware Stored; Blanket Transporter Collected | Extract RIB Pipe Module | Trigger | 0 | 56.1744 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Hardware Receipt | Movement | 0.69444 | 56.8689 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Pipe Module | Logistics | 0.58 | 57.4489 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| Move Crane A to AMF Equipment Receipt | Movement | 0.027778 | 57.4767 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | AMF Equipment Receipt | 20 | 0.2 | 0.027778 |  | N/A
| Store Pipe Module interface hardware | Logistics | 0.58 | 58.0567 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| Move Crane A to AMF Equipment Issue | Movement | 0.027778 | 58.0844 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Blanket Transporter | Logistics | 0.58 | 58.6644 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Interface hardware | 0.58
| Move Blanket Transporter to Vertical Port | Movement | 0.069444 | 58.7339 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A
| RIB Pipe Module Stored; Pipe Module interface hardware Stored; Blanket Transporter Collected | Total | 0 | 58.7339 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
COB Blanket Segment Stored | Extract COB Blanket Segment | Trigger | 0 | 63.8244 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Receipt | Movement | 0.69444 | 64.5189 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Segment | Logistics | 0.58 | 65.0989 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| COB Blanket Segment Stored | Total | 0 | 65.0989 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Blanket Segment Stored | Extract LOB Blanket Segment | Trigger | 0 | 69.6339 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Hardware Receipt | Movement | 0.69444 | 70.3283 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Segment | Logistics | 0.58 | 70.9083 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| LOB Blanket Segment Stored | Total | 0 | 70.9083 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Blanket Segment Stored | Extract ROB Blanket Segment | Trigger | 0 | 75.4433 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Receipt | Movement | 0.69444 | 76.1378 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Segment | Logistics | 0.58 | 76.7178 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| ROB Blanket Segment Stored | Total | 0 | 76.7178 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Blanket Segment Stored; Replacement RIB Blanket Segment collected | Extract LIB Blanket Segment | Trigger | 0 | 81.2528 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Receipt | Movement | 0.69444 | 81.9472 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Segment | Logistics | 0.58 | 82.5272 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| LIB Blanket Segment Stored; Replacement RIB Blanket Segment collected | Total | 0 | 82.5272 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Blanket Segment Stored; Replacement LIB Blanket Segment collected | Extract RIB Blanket Segment | Trigger | 0 | 87.0622 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Receipt | Movement | 0.69444 | 87.7567 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Segment | Logistics | 0.58 | 88.3367 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| Move to AMF Hardware Issue | Movement | 0.013889 | 88.3506 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | AMF Hardware Issue | 10 | 0.2 | 0.013889 |  | N/A
| Collect RIB Blanket Segment | Logistics | 0.78 | 89.1306 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware | 0.78
| RIB Blanket Segment Stored; Replacement LIB Blanket Segment collected | Total | 0 | 89.1306 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Blanket Segment Exported | Install RIB Blanket Segment | Trigger | 0 | 91.4617 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Hardware Receipt | Movement | 0.69444 | 92.1561 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Issue | 50 | 0.02 | 0.69444 |  | N/A
| Collect Segment | Logistics | 0.58 | 92.7361 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| ROB Blanket Segment Exported | Total | 0 | 92.7361 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Blanket Segment Exported | Install LIB Blanket Segment | Trigger | 0 | 95.8611 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Receipt | Movement | 0.69444 | 96.5556 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Issue | 50 | 0.02 | 0.69444 |  | N/A
| Collect Segment | Logistics | 0.78 | 97.3356 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware | 0.78
| LOB Blanket Segment Exported | Total | 0 | 97.3356 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
COB Blanket Segment Exported | Install ROB Blanket Segment | Trigger | 0 | 100.2606 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Hardware Receipt | Movement | 0.69444 | 100.955 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Issue | 50 | 0.02 | 0.69444 |  | N/A
| Collect Segment | Logistics | 0.78 | 101.735 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware | 0.78
| COB Blanket Segment Exported | Total | 0 | 101.735 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Blanket Transporter stored & Pipe Module interface hardware Collected & RIB Pipe Module Exported | Install LOB Blanket Segment | Trigger | 0 | 106.07 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Equipment Receipt | Movement | 0.69444 | 106.7644 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Blanket Transporter | Logistics | 0.68 | 107.4444 |  | N/A |  |  |  | N/A | N/A | N/A | Store Interface hardware | 0.68
| Move Crane B to AMF Hardware Issue | Movement | 0.013889 | 107.4583 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | AMF Hardware Issue | 10 | 0.2 | 0.013889 |  | N/A
| Collect Shield Plug Lifting Equipment | Logistics | 0.58 | 108.0383 |  | N/A |  |  |  | N/A | N/A | N/A | Collect interface hardware | 0.58
| Move Crane B to AMF Hardware Issue | Movement | 0.027778 | 108.0661 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | AMF Hardware Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Pipe Module 5 | Logistics | 0.78 | 108.8461 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware | 0.78
| Blanket Transporter stored & Pipe Module interface hardware Collected & RIB Pipe Module Exported | Total | 0 | 108.8461 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Blanket Tranporter stored & Service Joint System Collected | Install COB Blanket Segment | Trigger | 0 | 111.8794 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF AMF Equipment Receipt | Movement | 0.69444 | 112.5739 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Blanket Transporter | Logistics | 0.68 | 113.2539 |  | N/A |  |  |  | N/A | N/A | N/A | Store Interface hardware | 0.68
| Move Crane A to AMF AMF Hardware Issue | Movement | 0.013889 | 113.2678 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | AMF Hardware Issue | 10 | 0.2 | 0.013889 |  | N/A
| Collect Service Joint System | Logistics | 1.08 | 114.3478 |  | N/A |  |  |  | N/A | N/A | N/A | Collect RM equipment | 1.08
| Blanket Tranporter stored & Service Joint System Collected | Total | 0 | 114.3478 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Pipe Module Exported | Insert RIB Pipe Module | Trigger | 0 | 116.6689 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF AMF Hardware Issue | Movement | 0.069444 | 116.7383 |  | N/A | Overhead Crane (Unloaded) | Vertical Port | AMF Hardware Issue | 50 | 0.2 | 0.069444 |  | N/A
| Collect Pipe Module | Logistics | 0.78 | 117.5183 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware | 0.78
| LIB Pipe Module Exported | Total | 0 | 117.5183 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Pipe Module Exported | Insert LIB Pipe Module | Trigger | 0 | 168.515 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF AMF Hardware Issue | Movement | 0.069444 | 168.5845 |  | N/A | Overhead Crane (Unloaded) | Vertical Port | AMF Hardware Issue | 50 | 0.2 | 0.069444 |  | N/A
| Store Pipe Module | Logistics | 0.58 | 169.1645 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| ROB Pipe Module Exported | Total | 0 | 169.1645 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Pipe Module Exported | Insert ROB Pipe Module | Trigger | 0 | 240.4733 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF AMF Hardware Issue | Movement | 0.069444 | 240.5428 |  | N/A | Overhead Crane (Unloaded) | Vertical Port | AMF Hardware Issue | 50 | 0.2 | 0.069444 |  | N/A
| Store Pipe Module | Logistics | 0.58 | 241.1228 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| LOB Pipe Module Exported | Total | 0 | 241.1228 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
COB Pipe Module Exported | Insert LOB Pipe Module | Trigger | 0 | 277.3933 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF AMF Hardware Issue | Movement | 0.069444 | 277.4627 |  | N/A | Overhead Crane (Unloaded) | Vertical Port | AMF Hardware Issue | 50 | 0.2 | 0.069444 |  | N/A
| Store Pipe Module | Logistics | 0.58 | 278.0427 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| COB Pipe Module Exported | Total | 0 | 278.0427 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Lower Port Pipe Module installed | Move Crane A to Upper Port | Trigger | 0 | 3.65 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to lower port operations | Operation | 152.6623 | 156.3123 | Install RIB Pipe Module | 152.6623 |  |  |  | N/A | N/A | N/A |  | N/A
| RIB Lower Port Pipe Module installed | Total | 0 | 156.3123 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Lower Port Pipe Module installed | Disconnect Multipipe Flange 4 | Trigger | 0 | 36.7806 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to lower port operations | Operation | 191.49 | 228.2705 | Install LIB Pipe Module | 191.49 |  |  |  | N/A | N/A | N/A |  | N/A
| LIB Lower Port Pipe Module installed | Total | 0 | 228.2705 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Lower Port Pipe Module installed | Move Crane A to Upper Port | Trigger | 0 | 3.65 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to lower port operations | Operation | 230.3177 | 233.9677 | Install ROB Pipe Module | 230.3177 |  |  |  | N/A | N/A | N/A |  | N/A
| ROB Lower Port Pipe Module installed | Total | 0 | 233.9677 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Lower Port Pipe Module installed | Disconnect Multipipe Flange 5 | Trigger | 0 | 49.9117 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to lower port operations | Operation | 269.1455 | 319.0571 | Install LOB Pipe Module | 269.1455 |  |  |  | N/A | N/A | N/A |  | N/A
| LOB Lower Port Pipe Module installed | Total | 0 | 319.0571 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
COB Lower Port Pipe Module installed | Move Crane A to Upper Port | Trigger | 0 | 3.65 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to lower port operations | Operation | 307.9732 | 311.6232 | Install COB Pipe Module | 307.9732 |  |  |  | N/A | N/A | N/A |  | N/A
| COB Lower Port Pipe Module installed | Total | 0 | 311.6232 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Weld Failure
Shield Plug & Fixations Equipment Stored, Pipe Module interface hardware Collected and moved to port | Weld Failure identified at LOB/Pipe Module joint | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF AMF Equipment Receipt | Movement | 0.069444 | 0.069444 |  | N/A | Overhead Crane (Unloaded) | Vertical Port | AMF Equipment Receipt | 50 | 0.2 | 0.069444 |  | N/A
| Store Shield Plug & Fixations Equipment | Logistics | 0.68 | 0.74944 |  | N/A |  |  |  | N/A | N/A | N/A | Store interface hardware | 0.68
| Move Crane B to AMF AMF Equipment Issue | Movement | 0.027778 | 0.77722 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Pipe Module Lifting Equipment | Logistics | 0.58 | 1.3572 |  | N/A |  |  |  | N/A | N/A | N/A | Collect interface hardware | 0.58
| Move Pipe Module interface hardware to Vertical Port | Movement | 0.069444 | 1.4267 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A
| Shield Plug & Fixations Equipment Stored, Pipe Module interface hardware Collected and moved to port | Total | 0 | 1.4267 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Pipe Module Stored and Transporter Returned to Vertical Port | Extract LOB Pipe Module | Trigger | 0 | 2.2211 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF AMF Hardware Receipt | Movement | 0.69444 | 2.9156 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Pipe Module | Logistics | 0.58 | 3.4956 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| Move Crane A to Vertical Port | Movement | 0.069444 | 3.565 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A
| LOB Pipe Module Stored and Transporter Returned to Vertical Port | Total | 0 | 3.565 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Pipe Module Stored and Transporter Returned to Vertical Port | Extract ROB Pipe Module | Trigger | 0 | 11.1246 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF AMF Hardware Receipt | Movement | 0.69444 | 11.8191 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Pipe Module | Logistics | 0.58 | 12.3991 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| Move Crane A to Vertical Port | Movement | 0.069444 | 12.4685 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A
| ROB Pipe Module Stored and Transporter Returned to Vertical Port | Total | 0 | 12.4685 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Pipe Module Stored and Transporter Returned to Vertical Port | Extract LIB Pipe Module | Trigger | 0 | 20.0282 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF AMF Hardware Receipt | Movement | 0.69444 | 20.7226 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Pipe Module | Logistics | 0.58 | 21.3026 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| Move Crane A to Vertical Port | Movement | 0.069444 | 21.3721 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A
| LIB Pipe Module Stored and Transporter Returned to Vertical Port | Total | 0 | 21.3721 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Service Joint System Stored & Blanket Transporter Collected | Cut Pipes 5 | Trigger | 0 | 28.1372 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF AMF Equipment Receipt | Movement | 0.69444 | 28.8317 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Service Joint System | Logistics | 0.78 | 29.6117 |  | N/A |  |  |  | N/A | N/A | N/A | Store RM equipment | 0.78
| Move Crane A to AMF AMF Hardware Issue | Movement | 0.013889 | 29.6256 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | AMF Hardware Issue | 10 | 0.2 | 0.013889 |  | N/A
| Collect Blanket Transporter | Logistics | 0.58 | 30.2056 |  | N/A |  |  |  | N/A | N/A | N/A | Collect interface hardware | 0.58
| Service Joint System Stored & Blanket Transporter Collected | Total | 0 | 30.2056 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Pipe Module Stored; Pipe Module interface hardware Stored; Blanket Transporter Collected | Extract RIB Pipe Module | Trigger | 0 | 28.9317 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF AMF Hardware Receipt | Movement | 0.69444 | 29.6261 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Pipe Module | Logistics | 0.58 | 30.2061 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| Move Crane A to AMF Equipment Receipt | Movement | 0.027778 | 30.2339 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | AMF Equipment Receipt | 20 | 0.2 | 0.027778 |  | N/A
| Store Pipe Module interface hardware | Logistics | 0.68 | 30.9139 |  | N/A |  |  |  | N/A | N/A | N/A | Store interface hardware | 0.68
| Move Crane A to AMF Equipment Issue | Movement | 0.027778 | 30.9417 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Blanket Transporter | Logistics | 0.58 | 31.5217 |  | N/A |  |  |  | N/A | N/A | N/A | Collect interface hardware | 0.58
| Move Blanket Transporter to Vertical Port | Movement | 0.069444 | 31.5911 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A
| RIB Pipe Module Stored; Pipe Module interface hardware Stored; Blanket Transporter Collected | Total | 0 | 31.5911 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
COB Blanket Segment Stored | Extract COB Blanket Segment | Trigger | 0 | 36.015 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF AMF Hardware Receipt | Movement | 0.69444 | 36.7095 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Segment | Logistics | 0.58 | 37.2895 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| COB Blanket Segment Stored | Total | 0 | 37.2895 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Blanket Segment Stored | Extract LOB Blanket Segment | Trigger | 0 | 41.8245 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF AMF Hardware Receipt | Movement | 0.69444 | 42.5189 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Segment | Logistics | 0.58 | 43.0989 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| LOB Blanket Segment Stored | Total | 0 | 43.0989 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Blanket Segment Stored | Extract ROB Blanket Segment | Trigger | 0 | 47.6339 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Receipt | Movement | 0.69444 | 48.3284 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Segment | Logistics | 0.58 | 48.9084 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| ROB Blanket Segment Stored | Total | 0 | 48.9084 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Blanket Segment Stored; Replacement RIB Blanket Segment collected | Extract LIB Blanket Segment | Trigger | 0 | 53.4434 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Receipt | Movement | 0.69444 | 54.1378 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Segment | Logistics | 0.58 | 54.7178 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| LIB Blanket Segment Stored; Replacement RIB Blanket Segment collected | Total | 0 | 54.7178 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Blanket Segment Stored; Replacement LIB Blanket Segment collected | Extract RIB Blanket Segment | Trigger | 0 | 59.2528 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Receipt | Movement | 0.69444 | 59.9472 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Segment | Logistics | 0.58 | 60.5272 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| Move to AMF Hardware Issue | Movement | 0.013889 | 60.5411 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | AMF Hardware Issue | 10 | 0.2 | 0.013889 |  | N/A
| Collect RIB Blanket Segment | Logistics | 0.78 | 61.3211 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware | 0.78
| RIB Blanket Segment Stored; Replacement LIB Blanket Segment collected | Total | 0 | 61.3211 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Blanket Segment Exported | Install RIB Blanket Segment | Trigger | 0 | 63.6522 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Hardware Receipt | Movement | 0.69444 | 64.3467 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Issue | 50 | 0.02 | 0.69444 |  | N/A
| Collect Segment | Logistics | 0.58 | 64.9267 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| ROB Blanket Segment Exported | Total | 0 | 64.9267 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Blanket Segment Exported | Install LIB Blanket Segment | Trigger | 0 | 68.0517 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Receipt | Movement | 0.69444 | 68.7461 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Issue | 50 | 0.02 | 0.69444 |  | N/A
| Collect Segment | Logistics | 0.78 | 69.5261 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware | 0.78
| LOB Blanket Segment Exported | Total | 0 | 69.5261 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
COB Blanket Segment Exported | Install ROB Blanket Segment | Trigger | 0 | 72.4511 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Hardware Receipt | Movement | 0.69444 | 73.1456 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Issue | 50 | 0.02 | 0.69444 |  | N/A
| Collect Segment | Logistics | 0.58 | 73.7256 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| COB Blanket Segment Exported | Total | 0 | 73.7256 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Blanket Transporter stored & Pipe Module interface hardware Collected & RIB Pipe Module Exported | Install LOB Blanket Segment | Trigger | 0 | 78.2606 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Equipment Receipt | Movement | 0.69444 | 78.955 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Blanket Transporter | Logistics | 0.68 | 79.635 |  | N/A |  |  |  | N/A | N/A | N/A | Store interface hardware | 0.68
| Move Crane B to AMF Hardware Issue | Movement | 0.013889 | 79.6489 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | AMF Hardware Issue | 10 | 0.2 | 0.013889 |  | N/A
| Collect Shield Plug Lifting Equipment | Logistics | 0.58 | 80.2289 |  | N/A |  |  |  | N/A | N/A | N/A | Collect interface hardware | 0.58
| Move Crane B to AMF Hardware Issue | Movement | 0.027778 | 80.2567 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | AMF Hardware Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Pipe Module 5 | Logistics | 0.78 | 81.0367 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware | 0.78
| Blanket Transporter stored & Pipe Module interface hardware Collected & RIB Pipe Module Exported | Total | 0 | 81.0367 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Blanket Transporter stored & Service Joint System Collected | Install COB Blanket Segment | Trigger | 0 | 84.07 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Equipment Receipt | Movement | 0.69444 | 84.7645 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Blanket Transporter | Logistics | 0.68 | 85.4445 |  | N/A |  |  |  | N/A | N/A | N/A | Store interface hardware | 0.68
| Move Crane A to AMF Hardware Issue | Movement | 0.013889 | 85.4584 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | AMF Hardware Issue | 10 | 0.2 | 0.013889 |  | N/A
| Collect Service Joint System | Logistics | 1.08 | 86.5384 |  | N/A |  |  |  | N/A | N/A | N/A | Collect RM equipment | 1.08
| Blanket Transporter stored & Service Joint System Collected | Total | 0 | 86.5384 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Pipe Module Exported | Insert RIB Pipe Module | Trigger | 0 | 88.8595 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Issue | Movement | 0.069444 | 88.9289 |  | N/A | Overhead Crane (Unloaded) | Vertical Port | AMF Hardware Issue | 50 | 0.2 | 0.069444 |  | N/A
| Collect Pipe Module | Logistics | 0.78 | 89.7089 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware | 0.78
| LIB Pipe Module Exported | Total | 0 | 89.7089 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Pipe Module Exported | Insert LIB Pipe Module | Trigger | 0 | 192.4072 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Issue | Movement | 0.069444 | 192.4767 |  | N/A | Overhead Crane (Unloaded) | Vertical Port | AMF Hardware Issue | 50 | 0.2 | 0.069444 |  | N/A
| Store Pipe Module | Logistics | 0.78 | 193.2567 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware | 0.78
| ROB Pipe Module Exported | Total | 0 | 193.2567 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Pipe Module Exported | Insert ROB Pipe Module | Trigger | 0 | 229.3272 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Issue | Movement | 0.069444 | 229.3966 |  | N/A | Overhead Crane (Unloaded) | Vertical Port | AMF Hardware Issue | 50 | 0.2 | 0.069444 |  | N/A
| Store Pipe Module | Logistics | 0.78 | 230.1766 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware | 0.78
| LOB Pipe Module Exported | Total | 0 | 230.1766 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Lower Port Pipe Module installed | Weld Failure identified at LOB/Pipe Module joint | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to lower port operations | Operation | 219.0322 | 219.0322 | Install ROB Pipe Module | 219.0322 |  |  |  | N/A | N/A | N/A |  | N/A
| ROB Lower Port Pipe Module installed | Total | 0 | 219.0322 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Lower Port Pipe Module installed | Weld Failure identified at LOB/Pipe Module joint | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to lower port operations | Operation | 180.2044 | 180.2044 | Install LIB Pipe Module | 180.2044 |  |  |  | N/A | N/A | N/A |  | N/A
| LIB Lower Port Pipe Module installed | Total | 0 | 180.2044 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Lower Port Pipe Module installed | Weld Failure identified at LOB/Pipe Module joint | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to lower port operations | Operation | 141.3767 | 141.3767 | Install RIB Pipe Module | 141.3767 |  |  |  | N/A | N/A | N/A |  | N/A
| RIB Lower Port Pipe Module installed | Total | 0 | 141.3767 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Lower Port Pipe Module installed | Weld Failure identified at LOB/Pipe Module joint | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to lower port operations | Operation | 257.8599 | 257.8599 | Install LOB Pipe Module | 257.8599 |  |  |  | N/A | N/A | N/A |  | N/A
| LOB Lower Port Pipe Module installed | Total | 0 | 257.8599 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Weld Failure
Shield Plug & Fixations Equipment Stored, Pipe Module interface hardware Collected and moved to port | Weld Failure identified at ROB/Pipe Module joint | Trigger | 0 | 0 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Equipment Receipt | Movement | 0.069444 | 0.069444 |  | N/A | Overhead Crane (Unloaded) | Vertical Port | AMF Equipment Receipt | 50 | 0.2 | 0.069444 |  | N/A
| Store Shield Plug & Fixations Equipment | Logistics | 0.68 | 0.74944 |  | N/A |  |  |  | N/A | N/A | N/A | Store interface hardware | 0.68
| Move Crane B to AMF Equipment Issue | Movement | 0.027778 | 0.77722 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Pipe Module Lifting Equipment | Logistics | 0.58 | 1.3572 |  | N/A |  |  |  | N/A | N/A | N/A | Collect interface hardware | 0.58
| Move Pipe Module interface hardware to Vertical Port | Movement | 0.069444 | 1.4267 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A
| Shield Plug & Fixations Equipment Stored, Pipe Module interface hardware Collected and moved to port | Total | 0 | 1.4267 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Pipe Module Stored and Transporter Returned to Vertical Port | Extract ROB Pipe Module | Trigger | 0 | 2.2211 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Hardware Receipt | Movement | 0.69444 | 2.9156 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Pipe Module | Logistics | 0.58 | 3.4956 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| Move Crane A to Vertical Port | Movement | 0.069444 | 3.565 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A
| ROB Pipe Module Stored and Transporter Returned to Vertical Port | Total | 0 | 3.565 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Pipe Module Stored and Transporter Returned to Vertical Port | Extract LIB Pipe Module | Trigger | 0 | 11.1246 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Hardware Receipt | Movement | 0.69444 | 11.8191 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Pipe Module | Logistics | 0.58 | 12.3991 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| Move Crane A to Vertical Port | Movement | 0.069444 | 12.4685 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A
| LIB Pipe Module Stored and Transporter Returned to Vertical Port | Total | 0 | 12.4685 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Service Joint System Stored & Blanket Transporter Collected | Cut Pipes 5 | Trigger | 0 | 19.2337 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Equipment Receipt | Movement | 0.69444 | 19.9282 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Service Joint System | Logistics | 0.78 | 20.7082 |  | N/A |  |  |  | N/A | N/A | N/A | Store RM equipment | 0.78
| Move Crane A to AMF Hardware Issue | Movement | 0.013889 | 20.7221 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | AMF Hardware Issue | 10 | 0.2 | 0.013889 |  | N/A
| Collect Blanket Transporter | Logistics | 0.58 | 21.3021 |  | N/A |  |  |  | N/A | N/A | N/A | Collect interface hardware | 0.58
| Service Joint System Stored & Blanket Transporter Collected | Total | 0 | 21.3021 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Pipe Module Stored; Pipe Module interface hardware Stored; Blanket Transporter Collected | Extract RIB Pipe Module | Trigger | 0 | 20.0282 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Hardware Receipt | Movement | 0.69444 | 20.7226 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Pipe Module | Logistics | 0.58 | 21.3026 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| Move Crane A to AMF Equipment Receipt | Movement | 0.027778 | 21.3304 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | AMF Equipment Receipt | 20 | 0.2 | 0.027778 |  | N/A
| Store Pipe Module interface hardware | Logistics | 0.68 | 22.0104 |  | N/A |  |  |  | N/A | N/A | N/A | Store interface hardware | 0.68
| Move Crane A to AMF Equipment Issue | Movement | 0.027778 | 22.0382 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Blanket Transporter | Logistics | 0.58 | 22.6182 |  | N/A |  |  |  | N/A | N/A | N/A | Collect interface hardware | 0.58
| Move Blanket Transporter to Vertical Port | Movement | 0.069444 | 22.6876 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A
| RIB Pipe Module Stored; Pipe Module interface hardware Stored; Blanket Transporter Collected | Total | 0 | 22.6876 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
COB Blanket Segment Stored | Extract COB Blanket Segment | Trigger | 0 | 27.1115 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Receipt | Movement | 0.69444 | 27.8059 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Segment | Logistics | 0.58 | 28.3859 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| COB Blanket Segment Stored | Total | 0 | 28.3859 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Blanket Segment Stored | Extract LOB Blanket Segment | Trigger | 0 | 32.9209 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Hardware Receipt | Movement | 0.69444 | 33.6154 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Segment | Logistics | 0.58 | 34.1954 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| LOB Blanket Segment Stored | Total | 0 | 34.1954 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Blanket Segment Stored | Extract ROB Blanket Segment | Trigger | 0 | 38.7304 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Receipt | Movement | 0.69444 | 39.4248 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Segment | Logistics | 0.58 | 40.0048 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| ROB Blanket Segment Stored | Total | 0 | 40.0048 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Blanket Segment Stored; Replacement RIB Blanket Segment collected | Extract LIB Blanket Segment | Trigger | 0 | 44.5398 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Receipt | Movement | 0.69444 | 45.2343 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Segment | Logistics | 0.58 | 45.8143 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| LIB Blanket Segment Stored; Replacement RIB Blanket Segment collected | Total | 0 | 45.8143 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Blanket Segment Stored; Replacement LIB Blanket Segment collected | Extract RIB Blanket Segment | Trigger | 0 | 50.3493 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Receipt | Movement | 0.69444 | 51.0437 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Segment | Logistics | 0.58 | 51.6237 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| Move to AMF Hardware Issue | Movement | 0.013889 | 51.6376 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | AMF Hardware Issue | 10 | 0.2 | 0.013889 |  | N/A
| Collect RIB Blanket Segment | Logistics | 0.78 | 52.4176 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware | 0.78
| RIB Blanket Segment Stored; Replacement LIB Blanket Segment collected | Total | 0 | 52.4176 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Blanket Segment Exported | Install RIB Blanket Segment | Trigger | 0 | 54.7487 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Hardware Receipt | Movement | 0.69444 | 55.4432 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Issue | 50 | 0.02 | 0.69444 |  | N/A
| Collect Segment | Logistics | 0.58 | 56.0232 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| ROB Blanket Segment Exported | Total | 0 | 56.0232 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Blanket Segment Exported | Install LIB Blanket Segment | Trigger | 0 | 59.1482 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Receipt | Movement | 0.69444 | 59.8426 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Issue | 50 | 0.02 | 0.69444 |  | N/A
| Collect Segment | Logistics | 0.78 | 60.6226 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware | 0.78
| LOB Blanket Segment Exported | Total | 0 | 60.6226 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
COB Blanket Segment Exported | Install ROB Blanket Segment | Trigger | 0 | 63.5476 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Hardware Receipt | Movement | 0.69444 | 64.2421 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Issue | 50 | 0.02 | 0.69444 |  | N/A
| Collect Segment | Logistics | 0.58 | 64.8221 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| COB Blanket Segment Exported | Total | 0 | 64.8221 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Blanket Transporter stored & Pipe Module interface hardware Collected & RIB Pipe Module Exported | Install LOB Blanket Segment | Trigger | 0 | 69.3571 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Equipment Receipt | Movement | 0.69444 | 70.0515 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Blanket Transporter | Logistics | 0.68 | 70.7315 |  | N/A |  |  |  | N/A | N/A | N/A | Store interface hardware | 0.68
| Move Crane B to AMF Hardware Issue | Movement | 0.013889 | 70.7454 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | AMF Hardware Issue | 10 | 0.2 | 0.013889 |  | N/A
| Collect Shield Plug Lifting Equipment | Logistics | 0.58 | 71.3254 |  | N/A |  |  |  | N/A | N/A | N/A | Collect interface hardware | 0.58
| Move Crane B to AMF Hardware Issue | Movement | 0.027778 | 71.3532 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | AMF Hardware Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Pipe Module 5 | Logistics | 0.78 | 72.1332 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware | 0.78
| Blanket Transporter stored & Pipe Module interface hardware Collected & RIB Pipe Module Exported | Total | 0 | 72.1332 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Blanket Transporter stored & Service Joint System Collected | Install COB Blanket Segment | Trigger | 0 | 75.1665 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Equipment Receipt | Movement | 0.69444 | 75.8609 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Blanket Transporter | Logistics | 0.68 | 76.5409 |  | N/A |  |  |  | N/A | N/A | N/A | Store interface hardware | 0.68
| Move Crane A to AMF Hardware Issue | Movement | 0.013889 | 76.5548 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | AMF Hardware Issue | 10 | 0.2 | 0.013889 |  | N/A
| Collect Service Joint System | Logistics | 1.08 | 77.6348 |  | N/A |  |  |  | N/A | N/A | N/A | Collect RM equipment | 1.08
| Blanket Transporter stored & Service Joint System Collected | Total | 0 | 77.6348 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Pipe Module Exported | Insert RIB Pipe Module | Trigger | 0 | 79.9559 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Issue | Movement | 0.069444 | 80.0254 |  | N/A | Overhead Crane (Unloaded) | Vertical Port | AMF Hardware Issue | 50 | 0.2 | 0.069444 |  | N/A
| Collect Pipe Module | Logistics | 0.78 | 80.8054 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware | 0.78
| LIB Pipe Module Exported | Total | 0 | 80.8054 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Pipe Module Exported | Insert LIB Pipe Module | Trigger | 0 | 153.5795 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Issue | Movement | 0.069444 | 153.6489 |  | N/A | Overhead Crane (Unloaded) | Vertical Port | AMF Hardware Issue | 50 | 0.2 | 0.069444 |  | N/A
| Collect Pipe Module | Logistics | 0.78 | 154.4289 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware | 0.78
| ROB Pipe Module Exported | Total | 0 | 154.4289 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Pipe Module Exported | Insert ROB Pipe Module | Trigger | 0 | 192.4072 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Issue | Movement | 0.069444 | 192.4767 |  | N/A | Overhead Crane (Unloaded) | Vertical Port | AMF Hardware Issue | 50 | 0.2 | 0.069444 |  | N/A
| Collect Pipe Module | Logistics | 0.78 | 193.2567 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware | 0.78
| LOB Pipe Module Exported | Total | 0 | 193.2567 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Lower Port Pipe Module installed | weld failure identified | Trigger | 0 | #REF! |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to lower port operations | Operation | #REF! | #REF! | Install ROB blanket pipework module | #REF! |  |  |  | N/A | N/A | N/A |  | N/A
| ROB Lower Port Pipe Module installed | Total | 0 | #REF! |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Weld Failure
LIB Pipe Module Stored and Transporter Returned to Vertical Port | Extract LIB Pipe Module | Trigger | 0 | 1.8444 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Hardware Receipt | Movement | 0.69444 | 2.5388 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Pipe Module | Logistics | 0.58 | 3.1188 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| Move Crane A to Vertical Port | Movement | 0.069444 | 3.1882 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A
| LIB Pipe Module Stored and Transporter Returned to Vertical Port | Total | 0 | 3.1882 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Service Joint System Stored & Blanket Transporter Collected | Cut Pipes 5 | Trigger | 0 | 9.9534 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Equipment Receipt | Movement | 0.69444 | 10.6479 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Service Joint System | Logistics | 0.78 | 11.4279 |  | N/A |  |  |  | N/A | N/A | N/A | Store RM equipment | 0.78
| Move Crane A to AMF Hardware Issue | Movement | 0.013889 | 11.4418 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | AMF Hardware Issue | 10 | 0.2 | 0.013889 |  | N/A
| Collect Blanket Transporter | Logistics | 0.58 | 12.0218 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Interface hardware | 0.58
| Service Joint System Stored & Blanket Transporter Collected | Total | 0 | 12.0218 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Pipe Module Stored; Pipe Module interface hardware Stored; Blanket Transporter Collected | Extract RIB Pipe Module | Trigger | 0 | 10.7479 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Hardware Receipt | Movement | 0.69444 | 11.4423 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Pipe Module | Logistics | 0.58 | 12.0223 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| Move Crane A to AMF Equipment Receipt | Movement | 0.027778 | 12.0501 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | AMF Equipment Receipt | 20 | 0.2 | 0.027778 |  | N/A
| Store Pipe Module interface hardware | Logistics | 0.68 | 12.7301 |  | N/A |  |  |  | N/A | N/A | N/A | Store Interface hardware | 0.68
| Move Crane A to AMF Equipment Issue | Movement | 0.027778 | 12.7579 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Blanket Transporter | Logistics | 0.58 | 13.3379 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Interface hardware | 0.58
| Move Blanket Transporter to Vertical Port | Movement | 0.069444 | 13.4073 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A
| RIB Pipe Module Stored; Pipe Module interface hardware Stored; Blanket Transporter Collected | Total | 0 | 13.4073 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
COB Blanket Segment Stored | Extract COB Blanket Segment | Trigger | 0 | 17.8312 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Receipt | Movement | 0.69444 | 18.5257 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Segment | Logistics | 0.58 | 19.1057 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| COB Blanket Segment Stored | Total | 0 | 19.1057 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Blanket Segment Stored | Extract LOB Blanket Segment | Trigger | 0 | 23.6407 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Hardware Receipt | Movement | 0.69444 | 24.3351 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Segment | Logistics | 0.58 | 24.9151 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| LOB Blanket Segment Stored | Total | 0 | 24.9151 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Blanket Segment Stored | Extract ROB Blanket Segment | Trigger | 0 | 29.4501 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Receipt | Movement | 0.69444 | 30.1446 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Segment | Logistics | 0.58 | 30.7246 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| ROB Blanket Segment Stored | Total | 0 | 30.7246 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Blanket Segment Stored; Replacement RIB Blanket Segment collected | Extract LIB Blanket Segment | Trigger | 0 | 35.2596 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Receipt | Movement | 0.69444 | 35.954 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Segment | Logistics | 0.58 | 36.534 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| LIB Blanket Segment Stored; Replacement RIB Blanket Segment collected | Total | 0 | 36.534 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Blanket Segment Stored; Replacement LIB Blanket Segment collected | Extract RIB Blanket Segment | Trigger | 0 | 41.069 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Receipt | Movement | 0.69444 | 41.7634 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Segment | Logistics | 0.58 | 42.3434 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| Move to AMF Hardware Issue | Movement | 0.013889 | 42.3573 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | AMF Hardware Issue | 10 | 0.2 | 0.013889 |  | N/A
| Collect RIB Blanket Segment | Logistics | 0.78 | 43.1373 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware | 0.78
| RIB Blanket Segment Stored; Replacement LIB Blanket Segment collected | Total | 0 | 43.1373 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Blanket Segment Exported | Install RIB Blanket Segment | Trigger | 0 | 45.4684 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Hardware Receipt | Movement | 0.69444 | 46.1629 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Issue | 50 | 0.02 | 0.69444 |  | N/A
| Collect Segment | Logistics | 0.58 | 46.7429 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| ROB Blanket Segment Exported | Total | 0 | 46.7429 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Blanket Segment Exported | Install LIB Blanket Segment | Trigger | 0 | 49.8679 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Receipt | Movement | 0.69444 | 50.5623 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Issue | 50 | 0.02 | 0.69444 |  | N/A
| Collect Segment | Logistics | 0.78 | 51.3423 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware | 0.78
| LOB Blanket Segment Exported | Total | 0 | 51.3423 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
COB Blanket Segment Exported | Install ROB Blanket Segment | Trigger | 0 | 54.2673 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Hardware Receipt | Movement | 0.69444 | 54.9618 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Issue | 50 | 0.02 | 0.69444 |  | N/A
| Collect Segment | Logistics | 0.78 | 55.7418 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware | 0.78
| COB Blanket Segment Exported | Total | 0 | 55.7418 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Blanket Transporter stored & Pipe Module interface hardware Collected & RIB Pipe Module Exported | Install LOB Blanket Segment | Trigger | 0 | 60.0768 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Equipment Receipt | Movement | 0.69444 | 60.7712 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Blanket Transporter | Logistics | 0.68 | 61.4512 |  | N/A |  |  |  | N/A | N/A | N/A | Store Interface hardware | 0.68
| Move Crane B to AMF Hardware Issue | Movement | 0.013889 | 61.4651 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | AMF Hardware Issue | 10 | 0.2 | 0.013889 |  | N/A
| Collect Shield Plug Lifting Equipment | Logistics | 0.58 | 62.0451 |  | N/A |  |  |  | N/A | N/A | N/A | Collect Interface hardware | 0.58
| Move Crane B to AMF Hardware Issue | Movement | 0.027778 | 62.0729 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | AMF Hardware Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect shield plug | Logistics | 0.78 | 62.8529 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware | 0.78
| Blanket Transporter stored & Pipe Module interface hardware Collected & RIB Pipe Module Exported | Total | 0 | 62.8529 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Blanket Transporter stored & Service Joint System Collected | Install COB Blanket Segment | Trigger | 0 | 65.8862 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Equipment Receipt | Movement | 0.69444 | 66.5807 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Blanket Transporter | Logistics | 0.68 | 67.2607 |  | N/A |  |  |  | N/A | N/A | N/A | Store Interface hardware | 0.68
| Move Crane A to AMF Hardware Issue | Movement | 0.013889 | 67.2746 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | AMF Hardware Issue | 10 | 0.2 | 0.013889 |  | N/A
| Collect Service Joint System | Logistics | 1.08 | 68.3546 |  | N/A |  |  |  | N/A | N/A | N/A | Collect RM equipment | 1.08
| Blanket Transporter stored & Service Joint System Collected | Total | 0 | 68.3546 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Pipe Module Exported | Insert RIB Pipe Module | Trigger | 0 | 70.6757 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Issue | Movement | 0.069444 | 70.7451 |  | N/A | Overhead Crane (Unloaded) | Vertical Port | AMF Hardware Issue | 50 | 0.2 | 0.069444 |  | N/A
| Collect Pipe Module | Logistics | 0.78 | 71.5251 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware | 0.78
| LIB Pipe Module Exported | Total | 0 | 71.5251 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Inner Port Pipe Module installed | weld failure identified | Trigger | 0 | #REF! |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to lower port operations | Operation | #REF! | #REF! | Install LIB inner port pipework module | #REF! |  |  |  | N/A | N/A | N/A |  | N/A
| LIB Inner Port Pipe Module installed | Total | 0 | #REF! |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Lower Port Pipe Module installed | weld failure identified | Trigger | 0 | #REF! |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to lower port operations | Operation | #REF! | #REF! | Install LIB blanket pipework module | #REF! |  |  |  | N/A | N/A | N/A |  | N/A
| LIB Lower Port Pipe Module installed | Total | 0 | #REF! |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Weld Failure
Service Joint System Stored & Blanket Transporter Collected | Cut Failed RIB Pipe Module Weld | Trigger | 0 | 1.0499 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Equipment Receipt | Movement | 0.69444 | 1.7444 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Service Joint System | Logistics | 0.78 | 2.5244 |  | N/A |  |  |  | N/A | N/A | N/A | Store RM equipment | 0.78
| Move Crane A to AMF Hardware Issue | Movement | 0.013889 | 2.5382 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | AMF Hardware Issue | 10 | 0.2 | 0.013889 |  | N/A
| Collect Blanket Transporter | Logistics | 0.58 | 3.1182 |  | N/A |  |  |  | N/A | N/A | N/A | Collect interface hardware | 0.58
| Service Joint System Stored & Blanket Transporter Collected | Total | 0 | 3.1182 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Pipe Module Stored; Pipe Module interface hardware Stored; Blanket Transporter Collected | Extract RIB Pipe Module | Trigger | 0 | 1.8444 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Hardware Receipt | Movement | 0.69444 | 2.5388 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Pipe Module | Logistics | 0.58 | 3.1188 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP hardware | 0.58
| Move Crane A to AMF Equipment Receipt | Movement | 0.027778 | 3.1466 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | AMF Equipment Receipt | 20 | 0.2 | 0.027778 |  | N/A
| Store Pipe Module interface hardware | Logistics | 0.68 | 3.8266 |  | N/A |  |  |  | N/A | N/A | N/A | Store interface hardware | 0.68
| Move Crane A to AMF Equipment Issue | Movement | 0.027778 | 3.8544 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Receipt | AMF Equipment Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect Blanket Transporter | Logistics | 0.58 | 4.4344 |  | N/A |  |  |  | N/A | N/A | N/A | Collect interface hardware | 0.58
| Move Blanket Transporter to Vertical Port | Movement | 0.069444 | 4.5038 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | Vertical Port | 50 | 0.2 | 0.069444 |  | N/A
| RIB Pipe Module Stored; Pipe Module interface hardware Stored; Blanket Transporter Collected | Total | 0 | 4.5038 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
COB Blanket Segment Stored | Extract COB Blanket Segment | Trigger | 0 | 8.9277 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Receipt | Movement | 0.69444 | 9.6221 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Segment | Logistics | 0.58 | 10.2021 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| COB Blanket Segment Stored | Total | 0 | 10.2021 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Blanket Segment Stored | Extract LOB Blanket Segment | Trigger | 0 | 14.7371 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Hardware Receipt | Movement | 0.69444 | 15.4316 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Segment | Logistics | 0.58 | 16.0116 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| LOB Blanket Segment Stored | Total | 0 | 16.0116 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Blanket Segment Stored | Extract ROB Blanket Segment | Trigger | 0 | 20.5466 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Receipt | Movement | 0.69444 | 21.241 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Segment | Logistics | 0.58 | 21.821 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| ROB Blanket Segment Stored | Total | 0 | 21.821 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LIB Blanket Segment Stored; Replacement RIB Blanket Segment collected | Extract LIB Blanket Segment | Trigger | 0 | 26.356 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Receipt | Movement | 0.69444 | 27.0505 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Segment | Logistics | 0.58 | 27.6305 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| LIB Blanket Segment Stored; Replacement RIB Blanket Segment collected | Total | 0 | 27.6305 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Blanket Segment Stored; Replacement LIB Blanket Segment collected | Extract RIB Blanket Segment | Trigger | 0 | 32.1655 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Receipt | Movement | 0.69444 | 32.8599 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Segment | Logistics | 0.58 | 33.4399 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| Move to AMF Hardware Issue | Movement | 0.013889 | 33.4538 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | AMF Hardware Issue | 10 | 0.2 | 0.013889 |  | N/A
| Collect RIB Blanket Segment | Logistics | 0.78 | 34.2338 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware | 0.78
| RIB Blanket Segment Stored; Replacement LIB Blanket Segment collected | Total | 0 | 34.2338 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
ROB Blanket Segment Exported | Install RIB Blanket Segment | Trigger | 0 | 36.5649 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Hardware Receipt | Movement | 0.69444 | 37.2594 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Issue | 50 | 0.02 | 0.69444 |  | N/A
| Collect Segment | Logistics | 0.58 | 37.8394 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| ROB Blanket Segment Exported | Total | 0 | 37.8394 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
LOB Blanket Segment Exported | Install LIB Blanket Segment | Trigger | 0 | 40.9644 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Hardware Receipt | Movement | 0.69444 | 41.6588 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Issue | 50 | 0.02 | 0.69444 |  | N/A
| Collect Segment | Logistics | 0.78 | 42.4388 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware | 0.78
| LOB Blanket Segment Exported | Total | 0 | 42.4388 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
COB Blanket Segment Exported | Install ROB Blanket Segment | Trigger | 0 | 45.3638 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Hardware Receipt | Movement | 0.69444 | 46.0582 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Hardware Issue | 50 | 0.02 | 0.69444 |  | N/A
| Collect Segment | Logistics | 0.58 | 46.6382 |  | N/A |  |  |  | N/A | N/A | N/A | Store PP Hardware | 0.58
| COB Blanket Segment Exported | Total | 0 | 46.6382 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Blanket Transporter stored & Pipe Module interface hardware Collected & RIB Pipe Module Exported | Install LOB Blanket Segment | Trigger | 0 | 51.1732 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane B to AMF Equipment Receipt | Movement | 0.69444 | 51.8677 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Blanket Transporter | Logistics | 0.68 | 52.5477 |  | N/A |  |  |  | N/A | N/A | N/A | Store interface hardware | 0.68
| Move Crane B to AMF Hardware Issue | Movement | 0.013889 | 52.5616 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | AMF Hardware Issue | 10 | 0.2 | 0.013889 |  | N/A
| Collect Shield Plug Lifting Equipment | Logistics | 0.58 | 53.1416 |  | N/A |  |  |  | N/A | N/A | N/A | Collect interface hardware | 0.58
| Move Crane B to AMF Hardware Issue | Movement | 0.027778 | 53.1694 |  | N/A | Overhead Crane (Unloaded) | AMF Equipment Issue | AMF Hardware Issue | 20 | 0.2 | 0.027778 |  | N/A
| Collect shield plug | Logistics | 0.78 | 53.9494 |  | N/A |  |  |  | N/A | N/A | N/A | Collect PP hardware | 0.78
| Blanket Transporter stored & Pipe Module interface hardware Collected & RIB Pipe Module Exported | Total | 0 | 53.9494 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
Blanket Transporter stored & Service Joint System Collected | Install COB Blanket Segment | Trigger | 0 | 56.9827 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Move Crane A to AMF Equipment Receipt | Movement | 0.69444 | 57.6771 |  | N/A | Overhead Crane (Loaded) | Vertical Port | AMF Equipment Receipt | 50 | 0.02 | 0.69444 |  | N/A
| Store Blanket Transporter | Logistics | 0.68 | 58.3571 |  | N/A |  |  |  | N/A | N/A | N/A | Store interface hardware | 0.68
| Move Crane A to AMF Hardware Issue | Movement | 0.013889 | 58.371 |  | N/A | Overhead Crane (Unloaded) | AMF Hardware Receipt | AMF Hardware Issue | 10 | 0.2 | 0.013889 |  | N/A
| Collect Service Joint System | Logistics | 1.08 | 59.451 |  | N/A |  |  |  | N/A | N/A | N/A | Collect RM equipment | 1.08
| Blanket Transporter stored & Service Joint System Collected | Total | 0 | 59.451 |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Inner Port Pipe Module installed | weld failure identified | Trigger | 0 | #REF! |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to lower port operations | Operation | #REF! | #REF! | Install RIB inner port pipework module | #REF! |  |  |  | N/A | N/A | N/A |  | N/A
| RIB Inner Port Pipe Module installed | Total | 0 | #REF! |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
RIB Lower Port Pipe Module installed | weld failure identified | Trigger | 0 | #REF! |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A
| Delay due to lower port operations | Operation | #REF! | #REF! | Install RIB blanket pipework module | #REF! |  |  |  | N/A | N/A | N/A |  | N/A
| RIB Lower Port Pipe Module installed | Total | 0 | #REF! |  | N/A |  |  |  | N/A | N/A | N/A |  | N/A

## Radiation Dose Rates
Installed IVC dose rates
Time | Location | Biological Dose (Sv/h) | Silicon (Gy/h) | Eurofer (Gy/h) | SS316L(N)-IG (Gy/h) | Aluminium (Gy/h) | Steel ASTM A709 Grade 50 (Gy/h) | Average Gy/h
4 Weeks | Point A | 1300 | 1310 | 1420 | 1410 | 1270 | 1410 | 1364
| Point B | 0.00632 | 0.00629 | 0.00693 | 0.00683 | 0.0061 | 0.0068 | 0.00659
| Point C | 0.00453 | 0.00451 | 0.00493 | 0.00487 | 0.00437 | 0.00485 | 0.004706
| Point D | 0.00314 | 0.00313 | 0.00346 | 0.00341 | 0.00303 | 0.00339 | 0.003284
| Point E | 27.06 | 27.188 | 30.82 | 30.429 | 26.315 | 30.226 | 28.9956
| Point F | 16.682 | 16.741 | 18.912 | 18.686 | 16.209 | 18.551 | 17.8198
| Point G | 20.051 | 20.099 | 22.412 | 22.145 | 19.466 | 22.027 | 21.2298
8 Weeks | Point A | 1180 | 1190 | 1280 | 1270 | 1150 | 1270 | 1232
| Point B | 0.00593 | 0.0059 | 0.00647 | 0.00638 | 0.00572 | 0.00636 | 0.006166
| Point C | 0.00427 | 0.00426 | 0.00464 | 0.00458 | 0.00413 | 0.00456 | 0.004434
| Point D | 0.00298 | 0.00297 | 0.00326 | 0.00322 | 0.00288 | 0.0032 | 0.003106
| Point E | 23.633 | 23.74 | 26.848 | 26.509 | 22.98 | 26.338 | 25.283
| Point F | 14.658 | 14.707 | 16.557 | 16.36 | 14.24 | 16.246 | 15.622
| Point G | 17.732 | 17.774 | 19.737 | 19.505 | 17.215 | 19.406 | 18.7274
6 Months | Point A | 807 | 811 | 869 | 864 | 785 | 864 | 838.6
| Point B | 0.00494 | 0.00492 | 0.00534 | 0.00527 | 0.00477 | 0.00525 | 0.00511
| Point C | 0.00361 | 0.0036 | 0.00388 | 0.00383 | 0.00349 | 0.00382 | 0.003724
| Point D | 0.00256 | 0.00255 | 0.00277 | 0.00273 | 0.00247 | 0.00272 | 0.002648
| Point E | 14.084 | 14.123 | 15.811 | 15.613 | 13.675 | 15.525 | 14.9494
| Point F | 9.029 | 9.045 | 10.037 | 9.92 | 8.761 | 9.862 | 9.525
| Point G | 11.465 | 11.499 | 12.606 | 12.465 | 11.136 | 12.402 | 12.0216
1 Year | Point A | 505 | 507 | 538 | 535 | 490 | 535 | 521
| Point B | 0.00427 | 0.00425 | 0.00458 | 0.00452 | 0.00412 | 0.00451 | 0.004396
| Point C | 0.00314 | 0.00313 | 0.00335 | 0.00331 | 0.00303 | 0.0033 | 0.003224
| Point D | 0.00225 | 0.00224 | 0.00242 | 0.00239 | 0.00218 | 0.00238 | 0.002322
| Point E | 8.476 | 8.488 | 9.353 | 9.238 | 8.221 | 9.195 | 8.899
| Point F | 5.723 | 5.715 | 6.219 | 6.145 | 5.539 | 6.122 | 5.948
| Point G | 7.724 | 7.739 | 8.334 | 8.243 | 7.496 | 8.207 | 8.0038
Divertor cassettes Removed dose rates
Decay time | Location | Biological Dose (Sv/h) | Silicon (Gy/h) | Eurofer (Gy/h) | SS316L(N)-IG (Gy/h) | Aluminium (Gy/h) | Steel ASTM A709 Grade 50 (Gy/h) | Average Gy/h
8 Weeks | Point A | 1100 | 1110 | 1200 | 1190 | 1070 | 1190 | 1152
| Point B | 0.00593 | 0.0059 | 0.00647 | 0.00638 | 0.00572 | 0.00636 | 0.006166
| Point C | 0.00427 | 0.00426 | 0.00464 | 0.00458 | 0.00413 | 0.00456 | 0.004434
| Point D | 0.00298 | 0.00297 | 0.00326 | 0.00322 | 0.00288 | 0.0032 | 0.003106
| Point E | 168 | 170 | 195 | 193 | 164 | 191 | 182.6
| Point F | 166 | 166 | 183 | 182 | 161 | 181 | 174.6
| Point G | 121 | 121 | 136 | 134 | 117 | 134 | 128.4
6 Months | Point A | 760 | 764 | 822 | 817 | 740 | 817 | 792
| Point B | 0.00494 | 0.00492 | 0.00534 | 0.00527 | 0.00477 | 0.00525 | 0.00511
| Point C | 0.00361 | 0.0036 | 0.00388 | 0.00383 | 0.00349 | 0.00382 | 0.003724
| Point D | 0.00256 | 0.00255 | 0.00277 | 0.00273 | 0.00247 | 0.00272 | 0.002648
| Point E | 114 | 116 | 132 | 131 | 112 | 129 | 124
| Point F | 113 | 112 | 124 | 122 | 109 | 122 | 117.8
| Point G | 83.2 | 83.1 | 92.9 | 91.8 | 80.4 | 91.4 | 87.92
1 Year | Point A | 479 | 481 | 513 | 510 | 465 | 510 | 495.8
| Point B | 0.00427 | 0.00425 | 0.00458 | 0.00452 | 0.00412 | 0.00451 | 0.004396
| Point C | 0.00314 | 0.00313 | 0.00335 | 0.00331 | 0.00303 | 0.0033 | 0.003224
| Point D | 0.00225 | 0.00224 | 0.00242 | 0.00239 | 0.00218 | 0.00238 | 0.002322
| Point E | 72.2 | 72.9 | 82.8 | 81.9 | 70.4 | 81.3 | 77.86
| Point F | 71 | 70.7 | 77.5 | 76.7 | 68.5 | 76.4 | 73.96
| Point G | 54.2 | 54 | 60 | 59.3 | 52.3 | 59 | 56.92
Shield Plug Removed dose rates
Decay Time |  | Biological Dose (Sv/h) | Silicon (Gy/h) | Eurofer (Gy/h) | SS316L(N)-IG (Gy/h) | Aluminium (Gy/h) | Steel ASTM A709 Grade 50 (Gy/h) | Average Gy/h
4 Weeks | Point A | 1300 | 1310 | 1420 | 1410 | 1270 | 1410 | 1364
| Point B | 15.2 | 15.3 | 16.8 | 16.6 | 14.8 | 16.6 | 16.02
| Point C | 15.2 | 15.3 | 16.8 | 16.6 | 14.8 | 16.6 | 16.02
| Point D | 20.2 | 20.4 | 22.1 | 21.9 | 19.7 | 21.8 | 21.18
| Point E | 27.1 | 27.2 | 30.8 | 30.4 | 26.3 | 30.2 | 28.98
| Point F | 16.7 | 16.7 | 18.9 | 18.7 | 16.2 | 18.6 | 17.82
| Point G | 20.1 | 20.1 | 22.4 | 22.2 | 19.5 | 22 | 21.24
Shield Plug and single blanket removed dose rates
Decay Time |  | Biological Dose (Sv/h) | Silicon (Gy/h) | Eurofer (Gy/h) | SS316L(N)-IG (Gy/h) | Aluminium (Gy/h) | Steel ASTM A709 Grade 50 (Gy/h) | Average Gy/h
4 Weeks | Point A | 1080 | 1090 | 1170 | 1160 | 1050 | 1160 | 1126
| Point B | 15.8 | 15.8 | 18.4 | 18.1 | 15.3 | 18 | 17.12
| Point C | 66.9 | 67.1 | 75 | 74.4 | 65 | 74 | 71.1
| Point D | 85 | 85.8 | 96.7 | 95.8 | 83 | 95.2 | 91.3
| Point E | 27.3 | 27.4 | 31.1 | 30.7 | 26.6 | 30.5 | 29.26
| Point F | 17.7 | 17.7 | 20.4 | 20.1 | 17.2 | 20 | 19.08
| Point G | 45.3 | 45.4 | 50.6 | 50.1 | 43.9 | 49.8 | 47.96